## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Closed By | Closed Date | Closing Status
| 2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18472 | 17.Jul.2026 22:00 | 0.10139 | 23.Jul.2026 15:22 | 0.16181 |  | 0.51042 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | OPS/LK, OPS/LK |  |  |  | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) |  | 2 / 2 | [] |  |  | MET.32712972 | 13008286 | 2026-07-26 | Performed
| 3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB (32712946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:45 | 0.12708 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712946 | 13008286 | 2026-07-23 | Performed
| 4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:47 | 0.12569 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) |  | 1 / 1 | [] |  |  | MET.32712992 | 13008286 | 2026-07-23 | Performed
| 5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB (32712973) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 21.Jul.2026 10:27 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712973 | 13003390 | 2026-07-21 | Performed
| 6 | 200121-01-1 | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 01.Aug.2026 16:31 | 0.084028 |  | 0.5 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | TC/P, TC/P |  |  |  | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) |  | 2 / 2 | [] |  |  | MET.32712986 | 40000930 | 2026-08-02 | Performed
| 7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 24.Jul.2026 07:52 | 0.0625 |  | 0.125 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) |  | 1 / 1 | [] |  |  | MET.32712948 | 13008286 | 2026-07-26 | Performed
| 8 | 200121-04-1 | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.052778 | 17.Jul.2026 22:00 | 0.045833 | 30.Jul.2026 16:03 | 0.083333 |  | 0.16667 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) |  | 1 / 1 | [] |  |  | MET.32712952 | 13008286 | 2026-08-02 | Performed
| 9 | 200125-01-1 | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 30.Jul.2026 06:06 | 0.25 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) |  | 1 / 1 | [] |  |  | MET.32712957 | 40000930 | 2026-08-02 | Performed
| 10 | 200125-05-1 | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP (32712921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.4125 | 17.Jul.2026 22:00 | 0.4125 | 19.Jul.2026 07:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 6 |  | 1 / 1 | [] |  |  | MET.32712921 | 13008286 | 2026-07-20 | Performed
| 12 | 200127-02-1 | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 01.Aug.2026 16:29 | 0.083333 |  | 0.25 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) |  | 1 / 1 | [] |  |  | MET.32712975 | 40000930 | 2026-08-02 | Performed
| 13 | 200127-05-1 | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION (32712929) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 26.Jul.2026 17:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | TC/P |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712929 | 13008286 | 2026-07-27 | Performed
| 14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34792 | 17.Jul.2026 22:00 | 0.34792 | 22.Jul.2026 12:42 | 0.041667 |  | 0.041667 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | INSPECTION |  |  |  | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) |  | 1 / 1 | [] |  |  | MET.32712935 | 13008286 | 2026-07-23 | Performed
| 17 | 200137-01-1 | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:04 | 17.Jul.2026 22:00 | 1899-12-31 11:24 | 24.Jul.2026 19:00 | 1900-01-02 11:59 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) |  | 3 / 3 | [] |  |  | MET.32712985 | 40000930 | 2026-07-28 | Performed
| 21 | 200161-01-1 | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 09:26 | 17.Jul.2026 22:00 | 1899-12-31 00:31 | 24.Jul.2026 17:39 | 1900-01-02 13:21 |  | 0.625 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) |  | 3 / 3 | [] |  |  | MET.25336758 | 40000930 | 2026-07-28 | Performed
| 22 | 200191-01-1 | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING (28325963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 30.Jul.2026 08:08 | 0.16736 |  | 0.33333 | Closed | 0 | T: 16; O: 0; C: 16 | 24-92 |  | [] | PWR-OFF |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.28325963 | 40000930 | 2026-08-02 | Performed
| 23 | 200211-02-1 | 200211-02-1 (01) / COCKPIT WIRING CLEANING | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23819 | 17.Jul.2026 22:00 | 0.11875 | 02.Aug.2026 06:54 | 0.16736 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | PWR-OFF |  |  |  | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) |  | 1 / 1 | [] |  |  | MET.25336264 | 40000929 | 2026-08-03 | Performed
| 24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.15486 | 21.Jul.2026 12:38 | 0.92361 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) |  | 3 / 3 | [] |  |  | MET.32712990 | 13003390 | 2026-07-22 | Performed
| 27 | 200315-01-1 | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 11:11 | 0.020833 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | INSPECTION |  |  |  | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) |  | 1 / 1 | [] |  |  | MET.32712977 | 13003390 | 2026-07-20 | Performed
| 28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 15:27 | 1899-12-31 15:16 |  | 0.23958 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) |  | 3 / 3 | [] |  |  | MET.25335922 | 13009981 | 2026-07-23 | Performed
| 29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:51 | 1899-12-31 15:54 |  | 0.097222 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) |  | 3 / 3 | [] |  |  | MET.25336676 | 13009981 | 2026-07-23 | Performed
| 30 | 212100-03-1 | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 02.Aug.2026 04:34 | 0.11667 |  | 0.375 | Closed | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) |  | 3 / 3 | [] |  |  | MET.32450171 | 13008286 | 2026-08-02 | Performed
| 31 | 212600-09-1 | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 28.Jul.2026 14:17 | 0.16736 |  | 0.33333 | Closed | 0 | T: 2; O: 0; C: 2 | 21-26 |  | [] | CLEAN-UP |  |  |  | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) |  | 1 / 1 | [] |  |  | MET.32712967 | 13008286 | 2026-07-29 | Performed
| 37 | 256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP (32712971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 | 20.Jul.2026 08:31 | 0.11597 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 1 / 1 |  | 5 / 5 | [] |  |  | MET.32712971 | 13003390 | 2026-07-20 | Performed
| 38 | 262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:18 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) |  | 1 / 1 | [] |  |  | MET.32712927 | 13008286 | 2026-07-20 | Performed
| 39 | 272100-13-1 | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 31.Jul.2026 13:07 | 1899-12-31 19:22 |  | 0.16667 | Closed | 0 | T: 4; O: 0; C: 4 | 27 |  | [] |  |  |  |  | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) |  | 3 / 3 | [] |  |  | MET.32450169 | 13008286 | 2026-08-02 | Performed
| 40 | 281800-02-1 | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 06:04 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 28-18 |  | [] | INSPECTION |  |  |  | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) |  | 1 / 1 | [] |  |  | MET.32712944 | 13003390 | 2026-07-20 | Performed
| 41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP (32712932) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 08:02 | 0.11458 |  | 0.1875 | Closed | 0 | T: 3; O: 0; C: 3 | 28-18 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712932 | 13003390 | 2026-07-21 | Performed
| 47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0069444 | 23.Jul.2026 13:22 | 0.27153 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) |  | 3 / 3 | [] |  |  | MET.32712942 | 13008286 | 2026-07-26 | Performed
| 48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 13:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) |  | 3 / 3 | [] |  |  | MET.32712978 | 13003390 | 2026-07-23 | Performed
| 49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 08:00 | 0.93194 |  | 0.11111 | Closed | 0 | T: 4; O: 0; C: 4 | 52-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) |  | 3 / 3 | [] |  |  | MET.32712931 | 13009981 | 2026-07-23 | Performed
| 50 | 530000-01-1 | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 25.Jul.2026 19:12 | 1900-01-07 12:19 |  | 0.40625 | Closed | 0 | T: 0; O: 0; C: 0 | 53-00 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) |  | 3 / 3 | [] |  |  | MET.32712941 | 13003390 | 2026-08-03 | Performed
| 51 | 531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP (32712625) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 26.Jul.2026 04:38 | 1900-01-02 02:27 |  | 0.10486 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | CLEAN-UP, INSPECTION, INSPECTION |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712625 | 13003390 | 2026-07-29 | Performed
| 58 | 532137-03-1 | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION (32712609) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.066667 | 17.Jul.2026 22:00 | 0.054861 | 24.Jul.2026 05:30 | 1899-12-31 10:23 |  | 0.1875 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | JOB-SETUP, INSPECTION, CLOSE-UP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712609 | 13008286 | 2026-07-26 | Performed
| 60 | 534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS (32712709) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.03125 | 26.Jul.2026 04:29 | 1900-01-02 00:17 |  | 0.09375 | Closed | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712709 | 40000929 | 2026-07-30 | Performed
| 64 | 534159-02-1 | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 20.Jul.2026 18:52 | 1900-01-02 15:20 |  | 0.3125 | Closed | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) |  | 3 / 3 | [] |  |  | MET.32712636 | 13008286 | 2026-07-26 | Performed
| 65 | 534171-02-1 | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 24.Jul.2026 07:05 | 0.52361 |  | 0.14653 | Closed | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) |  | 3 / 3 | [] |  |  | MET.32712610 | 13008286 | 2026-07-26 | Performed
| 67 | 534301-01-1 | 534301-01-1 (0) / REAR FUSELAGE | 534301-01-1 (0) / REAR FUSELAGE (32450153) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 06:51 | 1899-12-31 09:03 |  | 0.22986 | Closed | 0 | T: 3; O: 0; C: 3 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534301-01-1 (0) / REAR FUSELAGE (32450153) |  | 4 / 4 | [] |  |  | MET.32450153 | 13008286 | 2026-07-26 | Performed
| 82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 21.Jul.2026 17:28 | 0.69722 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) |  | 3 / 3 | [] |  |  | MET.25335733 | 13009981 | 2026-07-23 | Performed
| 83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.011806 | 21.Jul.2026 17:29 | 0.67431 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) |  | 3 / 3 | [] |  |  | MET.25336621 | 13009981 | 2026-07-23 | Performed
| 86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 17:25 | 0.67847 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) |  | 4 / 4 | [] |  |  | MET.32712633 | 13009981 | 2026-07-23 | Performed
| 87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 17:27 | 0.67639 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) |  | 4 / 4 | [] |  |  | MET.32712611 | 13009981 | 2026-07-23 | Performed
| 90 | 572651-01-2-001 | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:44 | 1899-12-31 05:07 |  | 0.072917 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) |  | 4 / 4 | [] |  |  | MET.32712646 | 13008286 | 2026-07-26 | Performed
| 91 | 572651-01-2-002 | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 13:05 | 1899-12-31 06:49 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) |  | 4 / 4 | [] |  |  | MET.32712601 | 13008286 | 2026-07-26 | Performed
| 92 | 574206-01-1 | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:22 | 1899-12-31 20:41 |  | 0.052778 | Closed | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] |  |  |  |  | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) |  | 3 / 3 | [] |  |  | MET.32712600 | 13003390 | 2026-07-26 | Performed
| 93 | 574306-01-1-001 | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 16:05 | 1899-12-31 16:20 |  | 0.10417 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) |  | 3 / 3 | [] |  |  | MET.28326012 | 13003390 | 2026-07-26 | Performed
| 94 | 574306-01-1-002 | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 14:12 | 1899-12-31 19:04 |  | 0.048611 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) |  | 3 / 3 | [] |  |  | MET.28326010 | 13003390 | 2026-07-26 | Performed
| 95 | 574406-01-1 | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:57 | 1899-12-31 21:02 |  | 0.14931 | Closed | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) |  | 3 / 3 | [] |  |  | MET.32712904 | 13003390 | 2026-07-26 | Performed
| 96 | 574506-01-1-001 | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 16:06 | 1899-12-31 16:18 |  | 0.14583 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) |  | 3 / 3 | [] |  |  | MET.32712655 | 13003390 | 2026-07-26 | Performed
| 97 | 574506-01-1-002 | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 14:09 | 1899-12-31 21:07 |  | 0.15972 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) |  | 3 / 3 | [] |  |  | MET.32713057 | 13003390 | 2026-07-26 | Performed
| 98 | 574606-01-1 | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:44 | 1899-12-31 20:17 |  | 0.024306 | Closed | 0 | T: 4; O: 0; C: 4 | 57-46 |  | [] |  |  |  |  | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) |  | 3 / 3 | [] |  |  | MET.32712994 | 13003390 | 2026-07-26 | Performed
| 102 | 783210-01-1 | 783210-01-1 (0) / THRUST REVERSER STRUCTURE | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:32 | 1899-12-31 16:23 |  | 0.14583 | Closed | 0 | T: 12; O: 0; C: 12 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) |  | 3 / 3 | [] |  |  | MET.32450145 | 13008286 | 2026-07-26 | Performed
| 103 | ZL-110-01-1 | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 05:57 | 0.040972 |  | 0.040972 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) |  | 1 / 1 | [] |  |  | MET.32712939 | 13003390 | 2026-07-20 | Performed
| 104 | ZL-121-02-1 | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 | 24.Jul.2026 08:23 | 0.041667 |  | 0.083333 | Closed | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) |  | 1 / 1 | [] |  |  | MET.32712623 | 13008286 | 2026-07-26 | Performed
| 106 | ZL-127-02-2 | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP (32712599) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 | 25.Jul.2026 13:15 | 1900-01-02 20:47 |  | 0.22917 | Closed | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | INSPECTION |  |  |  | 2 / 3 |  | 1 / 1 | [] |  |  | MET.32712599 | 13003390 | 2026-07-29 | Performed
| 107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION (28325941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:18 | 17.Jul.2026 22:00 | 1899-12-31 14:18 | 21.Jul.2026 08:01 | 0.50694 |  | 0.16667 | Closed | 0 | T: 12; O: 0; C: 12 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.28325941 | 13008286 | 2026-07-22 | Performed
| 110 | ZL-147-03-1 | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP (32712657) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:27 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | INSPECTION |  |  |  | 2 / 3 |  | 1 / 1 | [] |  |  | MET.32712657 | 13003390 | 2026-07-20 | Performed
| 113 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.30069 | 17.Jul.2026 22:00 | 0.30069 | 24.Jul.2026 15:32 | 0.16875 |  | 0.084028 | Closed | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) |  | 4 / 4 | [] |  |  | MET.28325926 | 13008286 | 2026-07-26 | Performed
| 115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP (28325987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 05:00 | 17.Jul.2026 22:00 | 1900-01-02 05:00 | 21.Jul.2026 13:54 | 1899-12-31 23:41 |  | 0.10417 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.28325987 | 13003390 | 2026-07-23 | Performed
| 116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 18:22 | 0.077778 |  | 0.10417 | Closed | 0 | T: 23; O: 0; C: 23 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) |  | 1 / 1 | [] |  |  | MET.28325991 | 13008286 | 2026-07-22 | Performed
| 118 | ZL-195-01-1 | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP (32712964) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 07:54 | 0.027778 |  | 0.027778 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 3 / 8 |  | 1 / 1 | [] |  |  | MET.32712964 | 13003390 | 2026-07-20 | Performed
| 119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION (25336636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 21.Jul.2026 08:02 | 0.11736 |  | 0.22917 | Closed | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336636 | 13003390 | 2026-07-21 | Performed
| 120 | ZL-200-02-1 | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI (32712963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.76944 | 17.Jul.2026 22:00 | 0.76944 | 18.Jul.2026 15:30 | 0.10139 |  | 0.097222 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 2 / 9 |  | 1 / 1 | [] |  |  | MET.32712963 | 13008286 | 2026-07-20 | Performed
| 121 | ZL-200-04-1 | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE (32450172) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.525 | 17.Jul.2026 22:00 | 0.525 | 25.Jul.2026 13:10 | 0.27083 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32450172 | 40000930 | 2026-07-28 | Performed
| 122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 05:08 | 1899-12-31 06:23 |  | 0.875 | Closed | 0 | T: 15; O: 0; C: 15 | 05-22 |  | [] | INSPECTION |  |  |  | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) |  | 1 / 1 | [] |  |  | MET.32712928 | 13003390 | 2026-07-23 | Performed
| 123 | ZL-311-01-1 | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP (32712943) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:41 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.32712943 | 13003390 | 2026-07-20 | Performed
| 124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP (32712980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:43 | 0.37639 |  | 0.625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712980 | 13008286 | 2026-07-21 | Performed
| 125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP (32712954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 12:42 | 0.29375 |  | 0.32639 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712954 | 13008286 | 2026-07-21 | Performed
| 126 | ZL-325-01-1 | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP (32712961) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 16:23 | 1900-01-03 23:20 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.32712961 | 13008286 | 2026-07-27 | Performed
| 127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION (32712645) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 18:07 | 0.068056 |  | 0.076389 | Closed | 0 | T: 24; O: 0; C: 24 | 05-23 |  | [] | PRE INSP |  |  |  | 3 / 6 |  | 1 / 1 | [] |  |  | MET.32712645 | 13008286 | 2026-07-21 | Performed
| 128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 15:39 | 0.17153 |  | 0.34722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) |  | 1 / 1 | [] |  |  | MET.28325802 | 13008286 | 2026-07-21 | Performed
| 129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 19:25 | 0.024306 |  | 0.034722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) |  | 1 / 1 | [] |  |  | MET.28325897 | 13008286 | 2026-07-21 | Performed
| 130 | ZL-433-01-1-001 | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP (32712604) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 06:37 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712604 | 13008286 | 2026-07-20 | Performed
| 131 | ZL-433-01-1-002 | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP (32712607) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 09:54 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712607 | 13008286 | 2026-07-20 | Performed
| 132 | ZL-500-03-1-001 | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP (32712936) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 15:50 | 0.095833 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 4 / 9 |  | 1 / 1 | [] |  |  | MET.32712936 | 13008286 | 2026-07-20 | Performed
| 133 | ZL-500-03-1-002 | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 16:10 | 0.082639 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) |  | 1 / 1 | [] |  |  | MET.32712966 | 13008286 | 2026-07-20 | Performed
| 134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 08:06 | 0.035417 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) |  | 1 / 1 | [] |  |  | MET.32712947 | 13003390 | 2026-07-21 | Performed
| 135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP (32712934) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:21 | 1900-01-01 09:48 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712934 | 13008286 | 2026-07-23 | Performed
| 136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP (28325993) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:20 | 1899-12-31 01:32 |  | 0.15625 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 4 |  | 1 / 1 | [] |  |  | MET.28325993 | 13003390 | 2026-07-21 | Performed
| 137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 07:59 | 0.12014 |  | 0.125 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) |  | 1 / 1 | [] |  |  | MET.28325992 | 13003390 | 2026-07-21 | Performed
| 138 | ZL-531-02-1-001 | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP (25335895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:28 | 1900-01-01 08:16 |  | 0.083333 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.25335895 | 13008286 | 2026-07-23 | Performed
| 139 | ZL-531-02-1-002 | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING (25336980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.25336980 | 13008286 | 2026-07-23 | Performed
| 140 | ZL-532-01-1-001 | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 10:06 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) |  | 1 / 1 | [] |  |  | MET.32712924 | 13003390 | 2026-07-20 | Performed
| 141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP (32712979) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712979 | 13008286 | 2026-07-23 | Performed
| 142 | ZL-532-02-1-001 | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING (25336005) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 10:05 | 0.041667 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336005 | 13003390 | 2026-07-20 | Performed
| 143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 11:29 | 1900-01-01 08:17 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) |  | 1 / 1 | [] |  |  | MET.25336989 | 13008286 | 2026-07-23 | Performed
| 144 | ZL-533-01-1-001 | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP (32712922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 08:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.32712922 | 13008286 | 2026-07-20 | Performed
| 145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP (32712970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:30 | 1900-01-01 08:15 |  | 0.0625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712970 | 13008286 | 2026-07-23 | Performed
| 146 | ZL-571-02-1-001 | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP (32712933) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:22 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 5 |  | 1 / 1 | [] |  |  | MET.32712933 | 13008286 | 2026-07-20 | Performed
| 147 | ZL-571-02-1-002 | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP (32712988) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 2 / 4 |  | 1 / 1 | [] |  |  | MET.32712988 | 13008286 | 2026-07-20 | Performed
| 148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 22.Jul.2026 08:38 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) |  | 1 / 1 | [] |  |  | MET.32712940 | 13003390 | 2026-07-22 | Performed
| 149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP (32712969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 20.Jul.2026 09:20 | 1900-01-01 10:23 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712969 | 13008286 | 2026-07-23 | Performed
| 150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 15:21 | 0.66806 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) |  | 2 / 2 | [] |  |  | MET.32712956 | 13009981 | 2026-07-23 | Performed
| 151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP (32712918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 14:54 | 0.68611 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | 1 / 1 |  | 2 / 2 | [] |  |  | MET.32712918 | 13009981 | 2026-07-23 | Performed
| 152 | ZL-590-01-1-001 | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:13 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) |  | 1 / 1 | [] |  |  | MET.32712955 | 13008286 | 2026-07-20 | Performed
| 153 | ZL-590-01-1-002 | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) |  | 1 / 1 | [] |  |  | MET.32712923 | 13008286 | 2026-07-20 | Performed
| 154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP (32712974) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:41 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712974 | 13008286 | 2026-07-23 | Performed
| 155 | ZL-812-01-1 | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) |  | 1 / 1 | [] |  |  | MET.32712950 | 13008286 | 2026-07-20 | Performed
| 156 | ZL-824-01-1 | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP (32712976) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712976 | 13008286 | 2026-07-20 | Performed
| 161 | 21-SVA-01 | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 01:19 | 0.25139 |  | 0.75 | Closed | 0 | T: 2; O: 0; C: 2 | 21-61 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) |  | 3 / 3 | [] |  |  | MET.32163662 | 40000930 | 2026-07-28 | Performed
| 162 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 08:56 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-23 |  | [] | TC/P, TC/P |  |  |  | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) |  | 2 / 2 | [] |  |  | MET.32807066 | 13008286 | 2026-07-20 | Performed
| 164 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:33 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-41 |  | [] | OPS/LK |  |  |  | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) |  | 1 / 1 | [] |  |  | MET.32807106 | 13008286 | 2026-07-26 | Performed
| 166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 06:45 | 0.11597 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-28 |  | [] | OPS/LK |  |  |  | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) |  | 1 / 1 | [] |  |  | MET.32807105 | 13008286 | 2026-07-22 | Performed
| 167 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 26.Jul.2026 05:42 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-38 |  | [] | OPS/LK |  |  |  | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) |  | 1 / 1 | [] |  |  | MET.32807109 | 40000929 | 2026-07-26 | Performed
| 179 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:19 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] | PRE INSP |  |  |  | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) |  | 1 / 1 | [] |  |  | MET.29295194 | 13008286 | 2026-07-20 | Performed
| 180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29295141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:26 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.29295141 | 40000929 | 2026-07-21 | Performed
| 181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32807056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 19.Jul.2026 06:36 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  | As per requested by CONF ENGG in T/Q CONF ENGG 805450. | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807056 | 40000929 | 2026-07-21 | Performed
| 184 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP (32807080) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 01:14 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 1 / 8 |  | 1 / 1 | [] |  |  | MET.32807080 | 13008286 | 2026-07-20 | Performed
| 185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32807093) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32807093 | 13003390 | 2026-07-22 | Performed
| 186 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 05:08 | 0.22222 |  | 0.41667 | Closed | 0 | T: 4; O: 0; C: 4 | 25-62 |  | [] | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK |  |  |  | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) |  | 4 / 4 | [] |  |  | MET.32807073 | 13008286 | 2026-07-26 | Performed
| 187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:36 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 26-12 |  | [] | OPS/LK |  |  |  | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) |  | 1 / 1 | [] |  |  | MET.32807063 | 13008286 | 2026-07-23 | Performed
| 188 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 25.Jul.2026 11:20 | 0.041667 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) |  | 3 / 3 | [] |  |  | MET.32450147 | 13008286 | 2026-07-26 | Performed
| 189 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 27.Jul.2026 11:03 | 0.043056 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) |  | 3 / 3 | [] |  |  | MET.32450157 | 13008286 | 2026-07-28 | Performed
| 192 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 02.Aug.2026 16:53 | 0.041667 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 12-22 |  | [] | TC/P |  |  |  | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) |  | 1 / 1 | [] |  |  | MET.32807100 | 13008286 | 2026-08-03 | Performed
| 195 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) |  | 2 / 2 | [] |  |  | MET.32807110 | 13008286 | 2026-08-03 | Performed
| 196 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 | 02.Aug.2026 16:58 | 0.041667 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) |  | 2 / 2 | [] |  |  | MET.32807091 | 40000930 | 2026-08-03 | Performed
| 197 | 278468-01-1-002 | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 02.Aug.2026 17:01 | 0.041667 |  | 0.083333 | Closed | 0 | T: 12; O: 0; C: 12 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) |  | 3 / 3 | [] |  |  | MET.32807108 | 40000930 | 2026-08-03 | Performed
| 198 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 | 27.Jul.2026 04:24 | 0.12569 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | OPS/LK |  |  |  | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) |  | 1 / 1 | [] |  |  | MET.32807069 | 13003390 | 2026-07-27 | Performed
| 203 | 282800-09-1 | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.014583 | 19.Jul.2026 01:45 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 28-28 |  | [] | PRE INSP |  |  |  | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) |  | 1 / 1 | [] |  |  | MET.29295144 | 13008286 | 2026-07-20 | Performed
| 204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 15:46 | 0.046528 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | TC/P |  |  |  | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) |  | 1 / 1 | [] |  |  | MET.32807081 | 13008286 | 2026-07-23 | Performed
| 205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 15:46 | 0.17639 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 29-27 |  | [] | TC/P |  |  |  | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) |  | 1 / 1 | [] |  |  | MET.32807098 | 13008286 | 2026-07-23 | Performed
| 208 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 08:00 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-30 |  | [] | PRE HGR |  |  |  | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) |  | 1 / 1 | [] |  |  | MET.32807112 | 13008286 | 2026-07-26 | Performed
| 210 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 18.Jul.2026 21:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) |  | 1 / 1 | [] |  |  | MET.32807092 | 13008286 | 2026-07-20 | Performed
| 211 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 01:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32807075 | 13008286 | 2026-07-20 | Performed
| 212 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807099) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 00:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32807099 | 13008286 | 2026-07-20 | Performed
| 213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 23.Jul.2026 04:34 | 0.084028 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 32-44 |  | [] | TC/P |  |  |  | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) |  | 1 / 1 | [] |  |  | MET.32807113 | 13009981 | 2026-07-23 | Performed
| 214 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.020833 | 29.Jul.2026 03:26 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | CLEAN-UP |  |  |  | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) |  | 1 / 1 | [] |  |  | MET.32796720 | 13008286 | 2026-07-29 | Performed
| 215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 05:00 | 0.21528 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) |  | 3 / 3 | [] |  |  | MET.32796726 | 13003390 | 2026-07-21 | Performed
| 216 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 353000-05-1 (5) / CABIN PBE INSP (32796732) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:54 | 0.15764 |  | 0.11458 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 353000-05-1 (5) / CABIN PBE INSP (32796732) |  | 3 / 3 | [] |  |  | MET.32796732 | 13003390 | 2026-07-19 | Performed
| 217 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 | 21.Jul.2026 15:58 | 1900-01-05 00:07 |  | 0.86458 | Closed | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) |  | 7 / 7 | [] |  |  | MET.29294877 | 13003390 | 2026-07-28 | Performed
| 218 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 | 21.Jul.2026 14:09 | 1900-01-05 01:56 |  | 0.46181 | Closed | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) |  | 7 / 7 | [] |  |  | MET.29295132 | 13003390 | 2026-07-28 | Performed
| 220 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 | 27.Jul.2026 01:43 | 0.38472 |  | 1899-12-31 03:00 | Closed | 0 | T: 2; O: 0; C: 2 | 20-00 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) |  | 3 / 3 | [] |  |  | MET.31784910 | 13003390 | 2026-07-27 | Performed
| 227 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29295131) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 03:30 | 1900-01-04 14:06 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 4 / 9 |  | 4 / 4 | [] |  |  | MET.29295131 | 40000010 | 2026-07-26 | Performed
| 232 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29295096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23611 | 17.Jul.2026 22:00 | 0.097222 | 29.Jul.2026 12:57 | 0.29583 |  | 0.87847 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.29295096 | 13008286 | 2026-07-30 | Performed
| 236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32712874) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 17:47 | 0.72222 |  | 0.625 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712874 | 13003390 | 2026-07-21 | Performed
| 237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:59 | 0.67431 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28390064 | 13003390 | 2026-07-22 | Performed
| 238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.0375 | 21.Jul.2026 13:41 | 0.21736 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 3 / 3 | [] |  |  | MET.28349854 | 13003390 | 2026-07-21 | Performed
| 239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:57 | 1899-12-31 16:08 |  | 0.125 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) |  | 3 / 3 | [] |  |  | MET.32712959 | 13009981 | 2026-07-23 | Performed
| 240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022222 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 13:45 | 1899-12-31 17:12 |  | 0.14583 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) |  | 3 / 3 | [] |  |  | MET.32712991 | 13009981 | 2026-07-23 | Performed
| 241 | 212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 13:51 | 0.23819 |  | 0.0625 | Closed | 0 | T: 2; O: 0; C: 2 | 21-21 |  | [] | TC/P |  |  |  | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) |  | 1 / 1 | [] |  |  | MET.32712900 | 13008286 | 2026-07-26 | Performed
| 242 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 08:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) |  | 1 / 1 | [] |  |  | MET.32712724 | 13008286 | 2026-07-26 | Performed
| 243 | 212600-04-1 | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 16:04 | 0.042361 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) |  | 3 / 3 | [] |  |  | MET.32712870 | 13008286 | 2026-07-26 | Performed
| 244 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 25.Jul.2026 19:03 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) |  | 1 / 1 | [] |  |  | MET.32712746 | 13008286 | 2026-07-26 | Performed
| 247 | 213100-03-1 | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 17:28 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) |  | 1 / 1 | [] |  |  | MET.32712856 | 13008286 | 2026-07-26 | Performed
| 249 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 20.Jul.2026 02:40 | 0.36736 |  | 1899-12-31 16:00 | Closed | 0 | T: 0; O: 0; C: 0 | 21-61 |  | [] | PRE HGR |  |  |  | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) |  | 1 / 1 | [] |  |  | MET.32712787 | 13003390 | 2026-07-20 | Performed
| 250 | 215000-08-1 | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 31.Jul.2026 12:02 | 1899-12-31 21:03 |  | 0.125 | Closed | 0 | T: 5; O: 0; C: 5 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) |  | 3 / 3 | [] |  |  | MET.32450151 | 13003390 | 2026-08-02 | Performed
| 251 | 215000-09-1 | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 23.Jul.2026 13:46 | 0.25069 |  | 0.13542 | Closed | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32450144 | 13008286 | 2026-07-26 | Performed
| 256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 08:44 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 22-10 |  | [] | OPS/LK |  |  |  | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) |  | 1 / 1 | [] |  |  | MET.32712839 | 40000929 | 2026-07-23 | Performed
| 257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 22:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 23-73 |  | [] | OPS/LK |  |  |  | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) |  | 1 / 1 | [] |  |  | MET.19873618 | 13008286 | 2026-07-22 | Performed
| 258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 22:08 | 0.086111 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 23-33 |  | [] | OPS/LK |  |  |  | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) |  | 1 / 1 | [] |  |  | MET.32712733 | 13008286 | 2026-07-22 | Performed
| 259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:14 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 23-51 |  | [] | OPS/LK, OPS/LK |  |  |  | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) |  | 2 / 2 | [] |  |  | MET.25336141 | 13008286 | 2026-07-23 | Performed
| 260 | 237100-02-1 | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 24.Jul.2026 08:02 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] | OPS/LK |  |  |  | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) |  | 1 / 1 | [] |  |  | MET.25336248 | 13008286 | 2026-07-26 | Performed
| 261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.011806 | 23.Jul.2026 13:29 | 0.1 |  | 0.375 | Closed | 0 | T: 1; O: 0; C: 1 | 23-71 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) |  | 3 / 3 | [] |  |  | MET.32712774 | 13003390 | 2026-07-23 | Performed
| 262 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 14:57 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-22 |  | [] | OPS/LK |  |  |  | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) |  | 1 / 1 | [] |  |  | MET.32712665 | 13008286 | 2026-07-26 | Performed
| 263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:38 | 0.083333 |  | 0.16667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) |  | 1 / 1 | [] |  |  | MET.32712832 | 13008286 | 2026-07-23 | Performed
| 264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:36 | 0.083333 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 24-25 |  | [] | OPS/LK |  |  |  | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) |  | 1 / 1 | [] |  |  | MET.32712691 | 13008286 | 2026-07-23 | Performed
| 265 | 242600-02-1 | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 08:01 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-26 |  | [] | OPS/LK |  |  |  | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) |  | 1 / 1 | [] |  |  | MET.32712676 | 13008286 | 2026-07-26 | Performed
| 266 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 243000-13-1 (01) / DC GENERATION (32712892) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.044444 | 28.Jul.2026 17:20 | 0.043056 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-13-1 (01) / DC GENERATION (32712892) |  | 3 / 3 | [] |  |  | MET.32712892 | 13008286 | 2026-07-29 | Performed
| 267 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 243000-14-1 (01) / DC GENERATION (32712858) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0020833 | 17.Jul.2026 22:00 | 0.043056 | 28.Jul.2026 17:24 | 0.043056 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24-30 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-14-1 (01) / DC GENERATION (32712858) |  | 3 / 3 | [] |  |  | MET.32712858 | 13008286 | 2026-07-29 | Performed
| 268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 09:39 | 0.042361 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 24-32 |  | [] | OPS/LK |  |  |  | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) |  | 1 / 1 | [] |  |  | MET.32712840 | 13008286 | 2026-07-23 | Performed
| 269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 24-34 |  | [] | OPS/LK |  |  |  | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) |  | 1 / 1 | [] |  |  | MET.32712850 | 13008286 | 2026-07-23 | Performed
| 270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 08:31 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) |  | 1 / 1 | [] |  |  | MET.32712666 | 13008286 | 2026-07-23 | Performed
| 271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 07:51 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) |  | 1 / 1 | [] |  |  | MET.32712707 | 13008286 | 2026-07-23 | Performed
| 293 | 252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00069444 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:56 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | PRE INSP |  |  |  | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) |  | 1 / 1 | [] |  |  | MET.32712731 | 13008286 | 2026-07-20 | Performed
| 294 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 19.Jul.2026 06:58 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | PRE INSP |  |  |  | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) |  | 1 / 1 | [] |  |  | MET.32712700 | 13008286 | 2026-07-20 | Performed
| 295 | 255000-08-1 | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:30 | 17.Jul.2026 22:00 | 0.80208 | 29.Jul.2026 15:35 | 1899-12-31 03:53 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | INSPECTION |  |  |  | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) |  | 1 / 1 | [] |  |  | MET.25336966 | 40000010 | 2026-07-30 | Performed
| 297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 07:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | OPS/LK |  |  |  | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) |  | 1 / 1 | [] |  |  | MET.31498183 | 13003390 | 2026-07-22 | Performed
| 301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:46 | 0.12222 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) |  | 1 / 1 | [] |  |  | MET.32712831 | 13008286 | 2026-07-23 | Performed
| 302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:48 | 0.12153 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) |  | 1 / 1 | [] |  |  | MET.32712838 | 13008286 | 2026-07-23 | Performed
| 303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:11 | 0.079861 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) |  | 3 / 3 | [] |  |  | MET.32712878 | 13003390 | 2026-07-21 | Performed
| 304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:14 | 0.077083 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) |  | 3 / 3 | [] |  |  | MET.32712803 | 13003390 | 2026-07-21 | Performed
| 306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.020139 | 21.Jul.2026 15:51 | 0.090972 |  | 0.35417 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) |  | 4 / 4 | [] |  |  | MET.32712698 | 13003390 | 2026-07-21 | Performed
| 307 | 262200-04-1 | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:52 | 0.034722 |  | 0.034722 | Closed | 0 | T: 2; O: 0; C: 2 | 26-22 |  | [] | INSPECTION |  |  |  | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) |  | 1 / 1 | [] |  |  | MET.32712842 | 13003390 | 2026-07-20 | Performed
| 308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 13:39 | 0.088889 |  | 0.27083 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) |  | 3 / 3 | [] |  |  | MET.32712744 | 13008286 | 2026-07-23 | Performed
| 309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 19.Jul.2026 06:46 | 0.11667 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) |  | 1 / 1 | [] |  |  | MET.32712716 | 13008286 | 2026-07-22 | Performed
| 310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.036806 | 21.Jul.2026 14:33 | 0.14306 |  | 0.45833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) |  | 4 / 4 | [] |  |  | MET.32712799 | 13003390 | 2026-07-21 | Performed
| 312 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 06:59 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) |  | 1 / 1 | [] |  |  | MET.32712705 | 13008286 | 2026-07-20 | Performed
| 313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 16:40 | 0.063194 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 27-14 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) |  | 3 / 3 | [] |  |  | MET.32712730 | 13003390 | 2026-07-23 | Performed
| 314 | 271400-02-2-001 | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 02:46 | 1900-01-04 19:44 |  | 0.54861 | Closed | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) |  | 4 / 4 | [] |  |  | MET.32712702 | 13008286 | 2026-07-26 | Performed
| 315 | 271400-02-2-002 | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 05:20 | 1900-01-04 17:20 |  | 0.31944 | Closed | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) |  | 4 / 4 | [] |  |  | MET.32712756 | 40000930 | 2026-07-26 | Performed
| 321 | 272100-07-1 | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE (31498738) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 13:17 | 1900-01-05 04:25 |  | 1899-12-31 13:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.31498738 | 13008286 | 2026-07-27 | Performed
| 324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28325998) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.05 | 21.Jul.2026 04:00 | 0.30833 |  | 1899-12-31 16:35 | Closed | 0 | T: 4; O: 0; C: 4 | 27-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 0 / 1 |  | 8 / 8 | [] |  |  | MET.28325998 | 13003390 | 2026-07-21 | Performed
| 325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:10 | 0.38472 |  | 1899-12-31 12:45 | Closed | 0 | T: 9; O: 0; C: 9 | 27-34 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) |  | 4 / 4 | [] |  |  | MET.31481303 | 13003390 | 2026-07-21 | Performed
| 327 | 274000-04-1 | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 02:44 | 0.36458 |  | 0.875 | Closed | 0 | T: 1; O: 0; C: 1 | 27-96 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) |  | 3 / 3 | [] |  |  | MET.32712668 | 13003390 | 2026-07-20 | Performed
| 333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 21.Jul.2026 10:23 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | PRE INSP |  |  |  | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) |  | 1 / 1 | [] |  |  | MET.32712769 | 13003390 | 2026-07-21 | Performed
| 336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.014583 | 22.Jul.2026 15:44 | 0.17986 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK |  |  |  | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) |  | 1 / 1 | [] |  |  | MET.32712861 | 13008286 | 2026-07-23 | Performed
| 337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 22.Jul.2026 11:21 | 0.16875 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) |  | 3 / 3 | [] |  |  | MET.32712713 | 13008286 | 2026-07-23 | Performed
| 338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712880) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:04 | 1899-12-31 13:47 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712880 | 13003390 | 2026-07-23 | Performed
| 339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:00 | 1899-12-31 13:50 |  | 0.61458 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) |  | 3 / 3 | [] |  |  | MET.32712843 | 13003390 | 2026-07-23 | Performed
| 340 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 14:33 | 1900-01-01 04:35 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) |  | 3 / 3 | [] |  |  | MET.32712898 | 13008286 | 2026-07-27 | Performed
| 341 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 14:20 | 1899-12-31 18:47 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) |  | 3 / 3 | [] |  |  | MET.32712723 | 13003390 | 2026-07-26 | Performed
| 342 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 | 22.Jul.2026 00:06 | 1899-12-31 13:43 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) |  | 4 / 4 | [] |  |  | MET.32712748 | 13008286 | 2026-07-26 | Performed
| 343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 | 22.Jul.2026 00:08 | 1899-12-31 13:43 |  | 0.44792 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) |  | 4 / 4 | [] |  |  | MET.32712877 | 13003390 | 2026-07-23 | Performed
| 344 | 275400-01-1-001 | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 | 27.Jul.2026 07:14 | 0.10833 |  | 0.375 | Closed | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) |  | 1 / 1 | [] |  |  | MET.32712660 | 13003390 | 2026-07-27 | Performed
| 345 | 275400-01-1-002 | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 | 27.Jul.2026 06:13 | 0.13889 |  | 0.54167 | Closed | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) |  | 1 / 1 | [] |  |  | MET.32712871 | 13003390 | 2026-07-27 | Performed
| 351 | 276400-02-1-001 | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25972 | 17.Jul.2026 22:00 | 0.12986 | 25.Jul.2026 08:25 | 0.57292 |  | 0.44444 | Closed | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) |  | 7 / 7 | [] |  |  | MET.32712686 | 13008286 | 2026-07-26 | Performed
| 352 | 276400-02-1-002 | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25972 | 17.Jul.2026 22:00 | 0.14097 | 25.Jul.2026 08:36 | 0.57222 |  | 0.36111 | Closed | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) |  | 7 / 7 | [] |  |  | MET.32712857 | 13008286 | 2026-07-26 | Performed
| 354 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 15:18 | 1899-12-31 17:59 |  | 0.125 | Closed | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) |  | 3 / 3 | [] |  |  | MET.32712848 | 13003390 | 2026-07-26 | Performed
| 355 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:00 | 1899-12-31 19:17 |  | 0.076389 | Closed | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) |  | 3 / 3 | [] |  |  | MET.32712711 | 13003390 | 2026-07-26 | Performed
| 361 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:07 | 0.038194 |  | 0.038194 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) |  | 1 / 1 | [] |  |  | MET.32712890 | 13008286 | 2026-07-20 | Performed
| 362 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:03 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) |  | 1 / 1 | [] |  |  | MET.32712804 | 13008286 | 2026-07-20 | Performed
| 367 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP (32712865) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:15 | 0.16042 |  | 0.25 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712865 | 40000010 | 2026-07-19 | Performed
| 368 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:16 | 0.15972 |  | 0.20833 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) |  | 3 / 3 | [] |  |  | MET.32712800 | 40000010 | 2026-07-19 | Performed
| 369 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 17:07 | 0.125 |  | 0.41667 | Closed | 0 | T: 1; O: 0; C: 1 | 28-23 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) |  | 3 / 3 | [] |  |  | MET.28325816 | 40000010 | 2026-07-19 | Performed
| 370 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32712829) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 11:30 | 0.34236 |  | 0.10417 | Closed | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712829 | 13008286 | 2026-07-26 | Performed
| 371 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32712767) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 11:30 | 0.33958 |  | 0.17708 | Closed | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712767 | 13008286 | 2026-07-26 | Performed
| 373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:58 | 0.12569 |  | 0.25 | Closed | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | OPS/LK |  |  |  | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) |  | 1 / 1 | [] |  |  | MET.28325959 | 13003390 | 2026-07-22 | Performed
| 374 | 282800-06-1 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.015278 | 30.Jul.2026 13:35 | 0.2 |  | 0.3125 | Closed | 0 | T: 2; O: 0; C: 2 | 28-28 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  | as req in T/Q: 764919 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) |  | 4 / 4 | [] |  |  | MET.25336404 | 40000010 | 2026-07-30 | Performed
| 377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 14:03 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) |  | 1 / 1 | [] |  |  | MET.32712779 | 13003390 | 2026-07-22 | Performed
| 378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 14:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) |  | 1 / 1 | [] |  |  | MET.32712688 | 13003390 | 2026-07-22 | Performed
| 380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.06875 | 17.Jul.2026 22:00 | 0.034028 | 18.Jul.2026 14:06 | 0.084028 |  | 0.33333 | Closed | 0 | T: 3; O: 0; C: 3 | 29-23 |  | [] | OPS/LK, OPS/LK |  |  |  | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) |  | 2 / 2 | [] |  |  | MET.32712867 | 13003390 | 2026-07-22 | Performed
| 386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 14:55 | 0.67778 |  | 0.10417 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) |  | 3 / 3 | [] |  |  | MET.26225037 | 13003390 | 2026-07-22 | Performed
| 387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (26290689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 13:17 | 0.23403 |  | 0.27083 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290689 | 13003390 | 2026-07-21 | Performed
| 388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.01875 | 23.Jul.2026 12:17 | 0.086111 |  | 0.375 | Closed | 0 | T: 2; O: 0; C: 2 | 30-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) |  | 3 / 3 | [] |  |  | MET.32712674 | 13003390 | 2026-07-23 | Performed
| 389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 23.Jul.2026 13:26 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) |  | 1 / 1 | [] |  |  | MET.32712808 | 13003390 | 2026-07-23 | Performed
| 391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:15 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-50 |  | [] | OPS/LK |  |  |  | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) |  | 1 / 1 | [] |  |  | MET.32712854 | 40000929 | 2026-07-23 | Performed
| 392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 15:09 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) |  | 2 / 2 | [] |  |  | MET.32712781 | 13003390 | 2026-07-22 | Performed
| 393 | 315000-04-1 | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 06:39 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) |  | 2 / 2 | [] |  |  | MET.32712888 | 40000929 | 2026-07-26 | Performed
| 394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 22.Jul.2026 18:15 | 0.063194 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) |  | 3 / 3 | [] |  |  | MET.25336785 | 13008286 | 2026-07-23 | Performed
| 395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 19.Jul.2026 19:10 | 1900-01-02 00:43 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) |  | 3 / 3 | [] |  |  | MET.25336733 | 13008286 | 2026-07-23 | Performed
| 396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 12:02 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) |  | 1 / 1 | [] |  |  | MET.32712855 | 13008286 | 2026-07-23 | Performed
| 397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 18:01 | 0.083333 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) |  | 1 / 1 | [] |  |  | MET.32712715 | 13008286 | 2026-07-23 | Performed
| 400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 18:26 | 0.043056 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 12-12 |  | [] | OPS/LK |  |  |  | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) |  | 1 / 1 | [] |  |  | MET.32712797 | 13008286 | 2026-07-23 | Performed
| 401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.0083333 | 19.Jul.2026 06:43 | 0.11667 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) |  | 1 / 1 | [] |  |  | MET.32712851 | 13008286 | 2026-07-22 | Performed
| 403 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 18.Jul.2026 21:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 32-30 |  | [] | PRE INSP |  |  |  | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) |  | 1 / 1 | [] |  |  | MET.32712809 | 13008286 | 2026-07-20 | Performed
| 411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 07:49 | 0.125 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) |  | 3 / 3 | [] |  |  | MET.32712725 | 13008286 | 2026-07-22 | Performed
| 412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 23.Jul.2026 03:30 | 0.12569 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-45 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) |  | 2 / 2 | [] |  |  | MET.32712873 | 13009981 | 2026-07-23 | Performed
| 413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 21:07 | 0.12847 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 33-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) |  | 3 / 3 | [] |  |  | MET.32712675 | 13008286 | 2026-07-22 | Performed
| 414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.03125 | 21.Jul.2026 15:25 | 0.10833 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 34-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) |  | 3 / 3 | [] |  |  | MET.32712755 | 13003390 | 2026-07-21 | Performed
| 415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 09:45 | 0.042361 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) |  | 4 / 4 | [] |  |  | MET.32712762 | 40000929 | 2026-07-23 | Performed
| 416 | 341300-02-1 | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 15:59 | 0.043056 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) |  | 3 / 3 | [] |  |  | MET.32712811 | 13008286 | 2026-07-26 | Performed
| 417 | 341300-03-1 | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 16:43 | 0.042361 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) |  | 4 / 4 | [] |  |  | MET.32712846 | 40000010 | 2026-07-26 | Performed
| 418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) |  | 1 / 1 | [] |  |  | MET.32712719 | 40000929 | 2026-07-23 | Performed
| 419 | 341300-09-1 | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 08:01 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) |  | 1 / 1 | [] |  |  | MET.32712704 | 13008286 | 2026-07-26 | Performed
| 420 | 342000-03-1 | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 23.Jul.2026 08:36 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-20 |  | [] | OPS/LK |  |  |  | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) |  | 1 / 1 | [] |  |  | MET.32712766 | 13008286 | 2026-07-26 | Performed
| 421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 | 19.Jul.2026 08:08 | 0.056944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) |  | 4 / 4 | [] |  |  | MET.32712695 | 13008286 | 2026-07-22 | Performed
| 422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 | 23.Jul.2026 05:11 | 0.090278 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) |  | 3 / 3 | [] |  |  | MET.32712749 | 13009981 | 2026-07-23 | Performed
| 423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-48 |  | [] | TC/P |  |  |  | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) |  | 1 / 1 | [] |  |  | MET.28325742 | 13008286 | 2026-07-23 | Performed
| 424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.00625 | 21.Jul.2026 09:41 | 0.042361 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) |  | 4 / 4 | [] |  |  | MET.32712786 | 13008286 | 2026-07-23 | Performed
| 426 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32712806) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:08 | 0.18194 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712806 | 40000930 | 2026-07-20 | Performed
| 429 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.09375 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:17 | 0.06875 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25-64 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | as per MGR Mial ear @Jinoy Jose, Thanks for the email. As discussed further, the referenced task cards will be revised to change the replacement interval from 6 months to 02 months prior to expiry. Dear @Mohammed A Albukhari, Refer email below. As discussed, please revised the text for following tasks to change the replacement interval from 6 months to 2 month prior to expiry. Remaining instructions (2 & 3 ) will be deleted from the task as well. MP Task Number Title PBE replacement interval 333 353250-01-1-SVA CABIN ATTENDANTS PORTABLE BREATHING EQUIPMENT (PBE) PERIODIC CHECK FOR EXPIRATION 6 Months 773 25-180-00-SVA PROTECTIVE BREATHING EQUIPMENT (PBE) EXPIRATION DATE CHECK 6 Months 787 25-060-00-01-SVA SMOK HOODS PERIODIC CHECK FOR EXPIRATION 6 Months 32S 353000-06-1-SVA PROTECT. BREATHING EQPT (CKPT & CABIN) PERIODIC CHECK FOR EXPIRATION 6 Months Regards, Muhammad Noor Manager, Maintenance Program E-mail: MONOOR@saudia.com Office: +966126867409 Maintenance Program, JED, SA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) |  | 3 / 3 | [] |  |  | MET.28326058 | 13008286 | 2026-07-20 | Performed
| 430 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32712894) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 07:27 | 0.13611 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712894 | 13003390 | 2026-07-19 | Performed
| 431 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 | 31.Jul.2026 06:20 | 0.2 |  | 0.39583 | Closed | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) |  | 3 / 3 | [] |  |  | MET.25336420 | 13008286 | 2026-08-02 | Performed
| 432 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 | 31.Jul.2026 06:17 | 0.19861 |  | 0.39583 | Closed | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) |  | 3 / 3 | [] |  |  | MET.25336437 | 13008286 | 2026-08-02 | Performed
| 436 | 361200-02-1 | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED (32712883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.091667 | 18.Jul.2026 13:20 | 0.92778 |  | 1899-12-31 18:40 | Closed | 0 | T: 10; O: 0; C: 10 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712883 | 40000010 | 2026-07-19 | Performed
| 437 | 361200-03-1 | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 | 18.Jul.2026 15:16 | 0.84722 |  | 1899-12-31 17:20 | Closed | 0 | T: 2; O: 0; C: 2 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) |  | 3 / 3 | [] |  |  | MET.32712718 | 40000010 | 2026-07-19 | Performed
| 441 | 384241-01-1 | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 27.Jul.2026 08:27 | 0.12569 |  | 0.625 | Closed | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) |  | 3 / 3 | [] |  |  | MET.28325945 | 13003390 | 2026-07-27 | Performed
| 443 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31498553) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.12986 | 17.Jul.2026 22:00 | 0.12986 | 24.Jul.2026 07:11 | 1899-12-31 12:44 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 49-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.31498553 | 13008286 | 2026-07-26 | Performed
| 444 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.011806 | 17.Jul.2026 22:00 | 0.011806 | 24.Jul.2026 05:55 | 1899-12-31 10:00 |  | 0.25 | Closed | 0 | T: 3; O: 0; C: 3 | 49-16 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) |  | 3 / 3 | [] |  |  | MET.31498028 | 13008286 | 2026-07-26 | Performed
| 445 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:51 | 0.020833 |  | 0.020833 | Closed | 0 | T: 3; O: 0; C: 3 | 49-81 |  | [] | INSPECTION |  |  |  | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) |  | 1 / 1 | [] |  |  | MET.32712864 | 13003390 | 2026-07-20 | Performed
| 455 | 521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 | 25.Jul.2026 07:28 | 0.10417 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) |  | 4 / 4 | [] |  |  | MET.32712813 | 13008286 | 2026-07-26 | Performed
| 456 | 521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.044444 | 25.Jul.2026 06:37 | 0.14306 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) |  | 4 / 4 | [] |  |  | MET.32712763 | 13008286 | 2026-07-26 | Performed
| 459 | 521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 | 25.Jul.2026 06:09 | 0.16111 |  | 0.47917 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) |  | 4 / 4 | [] |  |  | MET.32712737 | 13008286 | 2026-07-26 | Performed
| 460 | 521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 24.Jul.2026 06:12 | 0.19097 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) |  | 4 / 4 | [] |  |  | MET.32712783 | 13008286 | 2026-07-26 | Performed
| 461 | 521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 24.Jul.2026 05:14 | 0.22361 |  | 0.33333 | Closed | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) |  | 4 / 4 | [] |  |  | MET.32712823 | 13008286 | 2026-07-26 | Performed
| 463 | 521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.010417 | 24.Jul.2026 08:05 | 1899-12-31 23:00 |  | 0.66667 | Closed | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) |  | 4 / 4 | [] |  |  | MET.32712801 | 40000929 | 2026-07-26 | Performed
| 464 | 521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.15347 | 17.Jul.2026 22:00 | 0.086806 | 24.Jul.2026 07:40 | 1899-12-31 23:27 |  | 0.52083 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) |  | 3 / 3 | [] |  |  | MET.32712671 | 13003390 | 2026-07-26 | Performed
| 465 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 02.Aug.2026 01:34 | 0.16667 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) |  | 4 / 4 | [] |  |  | MET.32712732 | 13008286 | 2026-08-02 | Performed
| 472 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 17:04 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) |  | 1 / 1 | [] |  |  | MET.32712822 | 40000930 | 2026-08-03 | Performed
| 473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP (32712736) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 04:30 | 0.16111 |  | 0.32292 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712736 | 13003390 | 2026-07-21 | Performed
| 474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.0069444 | 21.Jul.2026 03:47 | 0.125 |  | 0.19792 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) |  | 1 / 1 | [] |  |  | MET.32712895 | 13008286 | 2026-07-22 | Performed
| 475 | 525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 05:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) |  | 1 / 1 | [] |  |  | MET.32712807 | 40000929 | 2026-07-26 | Performed
| 476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0027778 | 21.Jul.2026 03:44 | 0.12917 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) |  | 1 / 1 | [] |  |  | MET.32712771 | 13008286 | 2026-07-22 | Performed
| 477 | 525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 25.Jul.2026 10:24 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) |  | 1 / 1 | [] |  |  | MET.32712727 | 13008286 | 2026-07-26 | Performed
| 478 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 25.Jul.2026 09:25 | 0.12569 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 52-71 |  | [] | OPS/LK |  |  |  | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) |  | 1 / 1 | [] |  |  | MET.32712814 | 13008286 | 2026-07-26 | Performed
| 480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 | 23.Jul.2026 03:05 | 0.17639 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK |  |  |  | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) |  | 1 / 1 | [] |  |  | MET.32712706 | 13009981 | 2026-07-23 | Performed
| 481 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 26.Jul.2026 04:30 | 1900-01-02 00:12 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] |  |  |  |  | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) |  | 3 / 3 | [] |  |  | MET.32712794 | 40000929 | 2026-07-30 | Performed
| 482 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 | 23.Jul.2026 12:30 | 0.30208 |  | 0.09375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) |  | 3 / 3 | [] |  |  | MET.32712815 | 13008286 | 2026-07-26 | Performed
| 483 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 29.Jul.2026 04:07 | 1899-12-31 02:10 |  | 0.50139 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) |  | 3 / 3 | [] |  |  | MET.32712862 | 13008286 | 2026-07-30 | Performed
| 486 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 24.Jul.2026 07:37 | 0.10833 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) |  | 3 / 3 | [] |  |  | MET.32712789 | 13008286 | 2026-07-26 | Performed
| 487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.034028 | 21.Jul.2026 14:20 | 0.24514 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP |  |  |  | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) |  | 2 / 2 | [] |  |  | MET.32712835 | 13008286 | 2026-07-22 | Performed
| 488 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16806 | 17.Jul.2026 22:00 | 0.16806 | 24.Jul.2026 05:54 | 1899-12-31 10:00 |  | 0.10486 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) |  | 3 / 3 | [] |  |  | MET.32450143 | 13008286 | 2026-07-26 | Performed
| 489 | 532181-02-1 | 532181-02-1 (0) / FORWARD FUSELAGE | 532181-02-1 (0) / FORWARD FUSELAGE (32450165) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 05:47 | 1900-01-02 05:04 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 0 / 2 |  | 3 / 3 | [] |  |  | MET.32450165 | 13003390 | 2026-07-27 | Performed
| 491 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 26.Jul.2026 04:31 | 1900-01-02 00:14 |  | 0.11111 | Closed | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) |  | 3 / 3 | [] |  |  | MET.32712868 | 40000929 | 2026-07-30 | Performed
| 493 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 534307-03-1 (0) / REAR FUSELAGE (32450173) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 24.Jul.2026 07:17 | 0.51458 |  | 0.14653 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534307-03-1 (0) / REAR FUSELAGE (32450173) |  | 3 / 3 | [] |  |  | MET.32450173 | 13008286 | 2026-07-26 | Performed
| 494 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 534308-02-1 (0) / REAR FUSELAGE (32450166) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 13:31 | 17.Jul.2026 22:00 | 1899-12-31 13:31 | 24.Jul.2026 06:49 | 0.53194 |  | 0.20903 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534308-02-1 (0) / REAR FUSELAGE (32450166) |  | 4 / 4 | [] |  |  | MET.32450166 | 13008286 | 2026-07-26 | Performed
| 497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 15:11 | 1899-12-31 17:42 |  | 0.17361 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) |  | 3 / 3 | [] |  |  | MET.26224706 | 13009981 | 2026-07-23 | Performed
| 498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (26224854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 14:30 | 1899-12-31 16:39 |  | 0.13542 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26224854 | 13009981 | 2026-07-23 | Performed
| 499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 15:24 | 1899-12-31 15:46 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) |  | 3 / 3 | [] |  |  | MET.26224971 | 13009981 | 2026-07-23 | Performed
| 500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 14:26 | 1899-12-31 16:45 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) |  | 3 / 3 | [] |  |  | MET.26225034 | 13009981 | 2026-07-23 | Performed
| 503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 15:18 | 1899-12-31 15:56 |  | 0.23264 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) |  | 3 / 3 | [] |  |  | MET.19876877 | 13009981 | 2026-07-23 | Performed
| 504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 14:42 | 1899-12-31 16:33 |  | 0.097222 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) |  | 3 / 3 | [] |  |  | MET.19876887 | 13009981 | 2026-07-23 | Performed
| 505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:07 | 1899-12-31 16:09 |  | 0.25 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) |  | 3 / 3 | [] |  |  | MET.25336918 | 13009981 | 2026-07-23 | Performed
| 506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:19 | 1899-12-31 16:59 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) |  | 3 / 3 | [] |  |  | MET.25335813 | 13009981 | 2026-07-23 | Performed
| 514 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:34 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) |  | 1 / 1 | [] |  |  | MET.26290633 | 13008286 | 2026-07-20 | Performed
| 515 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:35 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) |  | 1 / 1 | [] |  |  | MET.19875138 | 13008286 | 2026-07-20 | Performed
| 516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 15:06 | 0.66806 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | OPEN-UP, INSPECTION, CLOSE-UP |  |  |  | 1 / 8 |  | 3 / 3 | [] |  |  | MET.28325730 | 13003390 | 2026-07-22 | Performed
| 517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 14:21 | 0.19167 |  | 0.24306 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 5 |  | 3 / 3 | [] |  |  | MET.28325833 | 13003390 | 2026-07-21 | Performed
| 518 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 | 26.Jul.2026 14:34 | 0.125 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) |  | 3 / 3 | [] |  |  | MET.26224780 | 13008286 | 2026-07-27 | Performed
| 519 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 | 26.Jul.2026 14:35 | 0.125 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) |  | 3 / 3 | [] |  |  | MET.19875152 | 13008286 | 2026-07-27 | Performed
| 520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28325843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:50 | 0.67917 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.28325843 | 13003390 | 2026-07-22 | Performed
| 521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28325855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:04 | 0.14653 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.28325855 | 13003390 | 2026-07-21 | Performed
| 522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 15:02 | 0.67153 |  | 0.076389 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) |  | 3 / 3 | [] |  |  | MET.26224711 | 13003390 | 2026-07-22 | Performed
| 523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 14:07 | 0.2 |  | 0.27083 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) |  | 3 / 3 | [] |  |  | MET.26224781 | 13003390 | 2026-07-21 | Performed
| 524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627239) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 11:01 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.23627239 | 40000930 | 2026-07-21 | Performed
| 527 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 | 27.Jul.2026 15:46 | 0.18056 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) |  | 3 / 3 | [] |  |  | MET.28326014 | 13008286 | 2026-07-28 | Performed
| 528 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28326013) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 | 28.Jul.2026 14:10 | 0.19861 |  | 0.70833 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326013 | 13008286 | 2026-07-29 | Performed
| 529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28326019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:59 | 1899-12-31 17:11 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326019 | 13009981 | 2026-07-23 | Performed
| 530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28326018) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:31 | 1899-12-31 17:32 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326018 | 13009981 | 2026-07-23 | Performed
| 531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) |  | 1 / 1 | [] |  |  | MET.28326017 | 40000930 | 2026-07-21 | Performed
| 532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) |  | 1 / 1 | [] |  |  | MET.28326023 | 40000930 | 2026-07-21 | Performed
| 533 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 | 27.Jul.2026 15:46 | 0.18056 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) |  | 3 / 3 | [] |  |  | MET.26290668 | 13008286 | 2026-07-28 | Performed
| 534 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 | 28.Jul.2026 14:10 | 0.19792 |  | 0.875 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) |  | 3 / 3 | [] |  |  | MET.26290572 | 13008286 | 2026-07-29 | Performed
| 535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (26290680) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 15:17 | 1899-12-31 16:53 |  | 0.059028 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290680 | 13009981 | 2026-07-23 | Performed
| 536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (26290654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 14:54 | 1899-12-31 17:10 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290654 | 13009981 | 2026-07-23 | Performed
| 539 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:00 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) |  | 1 / 1 | [] |  |  | MET.28326050 | 40000010 | 2026-07-19 | Performed
| 540 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:01 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) |  | 1 / 1 | [] |  |  | MET.28325746 | 40000010 | 2026-07-19 | Performed
| 545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:04 | 0.66667 |  | 0.16667 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) |  | 3 / 3 | [] |  |  | MET.26224712 | 13003390 | 2026-07-22 | Performed
| 546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:35 | 0.18264 |  | 0.43056 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) |  | 3 / 3 | [] |  |  | MET.26224783 | 13003390 | 2026-07-21 | Performed
| 547 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 26.Jul.2026 14:18 | 0.24861 |  | 0.60417 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) |  | 3 / 3 | [] |  |  | MET.26290667 | 13008286 | 2026-07-27 | Performed
| 548 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 26.Jul.2026 14:18 | 0.24861 |  | 0.60417 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) |  | 3 / 3 | [] |  |  | MET.19875078 | 13008286 | 2026-07-27 | Performed
| 554 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP (32712743) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.51944 | 17.Jul.2026 22:00 | 0.51944 | 18.Jul.2026 13:45 | 0.041667 |  | 0.055556 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712743 | 13008286 | 2026-07-20 | Performed
| 555 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP (32712816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 21:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 5 / 6 |  | 1 / 1 | [] |  |  | MET.32712816 | 13008286 | 2026-07-20 | Performed
| 556 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 01:26 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) |  | 1 / 1 | [] |  |  | MET.32712791 | 13008286 | 2026-07-20 | Performed
| 557 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP (32712684) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.32712684 | 13008286 | 2026-07-20 | Performed
| 558 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:11 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) |  | 1 / 1 | [] |  |  | MET.32712661 | 13008286 | 2026-07-20 | Performed
| 559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 03:43 | 17.Jul.2026 22:00 | 1900-01-02 03:43 | 23.Jul.2026 13:06 | 0.020833 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) |  | 1 / 1 | [] |  |  | MET.31498481 | 13003390 | 2026-07-23 | Performed
| 560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP (28326031) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 08:02 | 0.71389 |  | 0.34722 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.28326031 | 13008286 | 2026-07-22 | Performed
| 561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 05:47 | 1900-01-01 01:43 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) |  | 1 / 1 | [] |  |  | MET.32712776 | 40000930 | 2026-07-21 | Performed
| 562 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) (32712792) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 10:05 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | INSPECTION |  |  |  | 3 / 5 |  | 1 / 1 | [] |  |  | MET.32712792 | 13003390 | 2026-07-20 | Performed
| 563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 14:55 | 0.21667 |  | 1899-12-31 22:50 | Closed | 0 | T: 8; O: 0; C: 8 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) |  | 1 / 1 | [] |  |  | MET.32712826 | 13008286 | 2026-07-21 | Performed
| 564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32712836) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.042361 |  | 0.076389 | Closed | 0 | T: 9; O: 0; C: 9 | 05-24 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712836 | 13008286 | 2026-07-21 | Performed
| 565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32712703) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.044444 |  | 0.083333 | Closed | 0 | T: 16; O: 0; C: 16 | 05-24 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712703 | 13008286 | 2026-07-21 | Performed
| 566 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:10 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) |  | 1 / 1 | [] |  |  | MET.32712987 | 13008286 | 2026-07-20 | Performed
| 567 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE (32712965) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:11 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712965 | 13008286 | 2026-07-20 | Performed
| 568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28325878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:20 | 1900-01-01 14:44 |  | 0.3125 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 4 |  | 3 / 3 | [] |  |  | MET.28325878 | 40000929 | 2026-07-23 | Performed
| 569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28325791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.030556 | 19.Jul.2026 16:20 | 1900-01-01 02:35 |  | 0.5 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 7 |  | 3 / 3 | [] |  |  | MET.28325791 | 13003390 | 2026-07-21 | Performed
| 570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32712853) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:09 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | 2 / 4 |  | 1 / 1 | [] |  |  | MET.32712853 | 40000930 | 2026-07-21 | Performed
| 571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) |  | 1 / 1 | [] |  |  | MET.32712760 | 40000930 | 2026-07-21 | Performed
| 572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:24 | 0.025 |  | 0.034722 | Closed | 0 | T: 12; O: 0; C: 12 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) |  | 1 / 1 | [] |  |  | MET.32712742 | 13008286 | 2026-07-21 | Performed
| 573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:00 | 0.040972 |  | 0.048611 | Closed | 0 | T: 10; O: 0; C: 10 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) |  | 1 / 1 | [] |  |  | MET.32712778 | 13008286 | 2026-07-21 | Performed
| 574 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP (32712761) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:22 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 10 |  | 1 / 1 | [] |  |  | MET.32712761 | 13008286 | 2026-07-20 | Performed
| 575 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP (32712690) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:20 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 6 |  | 1 / 1 | [] |  |  | MET.32712690 | 13008286 | 2026-07-20 | Performed
| 576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32712777) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 20.Jul.2026 07:31 | 1900-01-01 01:55 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712777 | 13003390 | 2026-07-22 | Performed
| 577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32712872) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 22.Jul.2026 17:23 | 0.097917 |  | 0.0625 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 5 |  | 1 / 1 | [] |  |  | MET.32712872 | 13008286 | 2026-07-23 | Performed
| 578 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION (32712687) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 22:32 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP, PRE INSP |  |  |  | 2 / 2 |  | 2 / 2 | [] |  |  | MET.32712687 | 13008286 | 2026-07-20 | Performed
| 579 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP (32712925) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 01:46 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 3 / 8 |  | 1 / 1 | [] |  |  | MET.32712925 | 13008286 | 2026-07-20 | Performed
| 580 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP (32712945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 02:21 | 0.027083 |  | 0.027083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 2 / 3 |  | 1 / 1 | [] |  |  | MET.32712945 | 13008286 | 2026-07-20 | Performed
| 581 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP (32712796) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:15 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712796 | 13008286 | 2026-07-20 | Performed
| 593 | 494000-B2-1 | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 24.Jul.2026 07:06 | 1899-12-31 08:46 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 49-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) |  | 3 / 3 | [] |  |  | MET.32712910 | 13008286 | 2026-07-26 | Performed
| 594 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 03:22 | 0.084028 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) |  | 1 / 1 | [] |  |  | MET.32807087 | 13008286 | 2026-08-02 | Performed
| 595 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 03:25 | 0.083333 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) |  | 1 / 1 | [] |  |  | MET.32807086 | 13008286 | 2026-08-02 | Performed
| 596 | 532178-01-1 | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00625 | 17.Jul.2026 22:00 | 0.00625 | 29.Jul.2026 03:08 | 0.22431 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) |  | 3 / 3 | [] |  |  | MET.32450175 | 13008286 | 2026-07-29 | Performed
| 600 | 572610-02-2 | 572610-02-2 (0) / OUTER WING | 572610-02-2 (0) / OUTER WING (32450162) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 24.Jul.2026 14:05 | 1900-01-01 05:18 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-2 (0) / OUTER WING (32450162) |  | 4 / 4 | [] |  |  | MET.32450162 | 13008286 | 2026-07-27 | Performed
| 601 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP (32807084) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:02 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807084 | 13003390 | 2026-07-20 | Performed
| 602 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR (32807085) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 11:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 2 / 2 | [] |  |  | MET.32807085 | 13008286 | 2026-07-20 | Performed
| 605 | 12-21-11-03-0-SVA | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) | On Demand Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 04:30 | 17.Jul.2026 22:00 | 0.32292 | 17.Jul.2026 17:00 | 1900-01-12 02:36 |  | 1900-01-04 17:30 | Closed | 0 | T: 0; O: 0; C: 0 | 12-21 |  | [] | WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH |  |  |  | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) |  | 25 / 25 | [] |  |  | MET.23560156 | 13003390 | 2026-08-03 | Performed
| 607 | 321000-01-1 | 321000-01-1 (5) / MLG AND DOORS LUBRICATION | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) |  | 3 / 3 | [] |  |  | MET.32807082 | 40000930 | 2026-08-03 | Performed
| 609 | 521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 27.Jul.2026 04:20 | 0.021528 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) |  | 1 / 1 | [] |  |  | MET.32713053 | 13008286 | 2026-07-27 | Performed
| 618 | 531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.2625 | 17.Jul.2026 22:00 | 0.22083 | 27.Jul.2026 14:35 | 1900-01-01 20:53 |  | 0.60417 | Closed | 0 | T: 1; O: 0; C: 1 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) |  | 6 / 6 | [] |  |  | MET.32712875 | 13008286 | 2026-08-02 | Performed
| 622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.023611 | 21.Jul.2026 13:16 | 0.11458 |  | 0.5625 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) |  | 3 / 3 | [] |  |  | MET.32712995 | 13003390 | 2026-07-21 | Performed
| 624 | 532180-04-2 | 532180-04-2 (0) / FORWARD FUSELAGE | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 06:21 | 1899-12-31 09:32 |  | 0.12639 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] |  |  |  |  | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) |  | 3 / 3 | [] |  |  | MET.32450146 | 13008286 | 2026-07-26 | Performed
| 625 | 533111-01-1 | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 29.Jul.2026 08:16 | 0.14514 |  | 0.042361 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) |  | 2 / 2 | [] |  |  | MET.25336513 | 13003390 | 2026-07-29 | Performed
| 626 | 533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0875 | 17.Jul.2026 22:00 | 0.0875 | 29.Jul.2026 08:17 | 0.86319 |  | 0.25694 | Closed | 0 | T: 4; O: 0; C: 4 | 53 |  | [] |  |  |  |  | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) |  | 3 / 3 | [] |  |  | MET.32450148 | 40000930 | 2026-07-30 | Performed
| 627 | 533139-02-1 | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 29.Jul.2026 11:46 | 0.71667 |  | 0.12639 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, INSPECTION, -- |  |  |  | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) |  | 3 / 3 | [] |  |  | MET.25336237 | 13008286 | 2026-07-30 | Performed
| 629 | 534107-03-1 | 534107-03-1 (0) / REAR FUSELAGE | 534107-03-1 (0) / REAR FUSELAGE (32450155) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 | 27.Jul.2026 14:31 | 0.76319 |  | 0.11458 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534107-03-1 (0) / REAR FUSELAGE (32450155) |  | 3 / 3 | [] |  |  | MET.32450155 | 13003390 | 2026-07-28 | Performed
| 637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.050694 | 17.Jul.2026 22:00 | 0.047917 | 21.Jul.2026 15:00 | 1899-12-31 16:19 |  | 0.29167 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) |  | 4 / 4 | [] |  |  | MET.32713050 | 13008286 | 2026-07-23 | Performed
| 638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038889 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 14:53 | 0.98194 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) |  | 4 / 4 | [] |  |  | MET.32713048 | 13008286 | 2026-07-23 | Performed
| 651 | 572044-01-2-001 | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:47 | 1899-12-31 05:06 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) |  | 4 / 4 | [] |  |  | MET.26209161 | 13008286 | 2026-07-26 | Performed
| 652 | 572044-01-2-002 | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 15:43 | 0.17639 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-SETUP |  |  |  | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) |  | 4 / 4 | [] |  |  | MET.26290432 | 13008286 | 2026-07-26 | Performed
| 653 | 572062-01-1-001 | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 24.Jul.2026 15:19 | 1900-01-01 04:52 |  | 0.11458 | Closed | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) |  | 4 / 4 | [] |  |  | MET.32713037 | 13008286 | 2026-07-27 | Performed
| 654 | 572062-01-1-002 | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 23.Jul.2026 18:53 | 0.038194 |  | 0.052083 | Closed | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) |  | 4 / 4 | [] |  |  | MET.32713013 | 13008286 | 2026-07-26 | Performed
| 659 | 572111-01-1-001 | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 24.Jul.2026 15:09 | 1900-01-01 05:03 |  | 0.0625 | Closed | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) |  | 4 / 4 | [] |  |  | MET.28325749 | 13008286 | 2026-07-27 | Performed
| 660 | 572111-01-1-002 | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 23.Jul.2026 18:50 | 0.041667 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) |  | 4 / 4 | [] |  |  | MET.28325815 | 13008286 | 2026-07-26 | Performed
| 661 | 572111-02-1 | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 | 24.Jul.2026 13:29 | 1900-01-01 05:52 |  | 0.036806 | Closed | 0 | T: 8; O: 0; C: 8 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) |  | 3 / 3 | [] |  |  | MET.32450174 | 13008286 | 2026-07-27 | Performed
| 662 | 572112-01-1-001 | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP (25336200) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 15:11 | 1900-01-01 05:00 |  | 0.090278 | Closed | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 4 |  | 4 / 4 | [] |  |  | MET.25336200 | 13008286 | 2026-07-27 | Performed
| 663 | 572112-01-1-002 | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 13:56 | 1899-12-31 19:08 |  | 0.052083 | Closed | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) |  | 4 / 4 | [] |  |  | MET.25336328 | 13003390 | 2026-07-26 | Performed
| 668 | 572607-01-1-001 | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31498801) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 | 24.Jul.2026 15:21 | 1900-01-01 04:46 |  | 0.16111 | Closed | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.31498801 | 13008286 | 2026-07-27 | Performed
| 669 | 572607-01-1-002 | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 | 23.Jul.2026 15:36 | 0.17778 |  | 0.30208 | Closed | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) |  | 4 / 4 | [] |  |  | MET.31497936 | 13008286 | 2026-07-26 | Performed
| 670 | 572610-02-1-001 | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:27 | 1900-01-05 09:40 |  | 0.29167 | Closed | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) |  | 4 / 4 | [] |  |  | MET.32712825 | 13008286 | 2026-07-27 | Performed
| 671 | 572610-02-1-002 | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:28 | 1900-01-02 09:28 |  | 0.53125 | Closed | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) |  | 4 / 4 | [] |  |  | MET.32712722 | 13008286 | 2026-07-26 | Performed
| 672 | 574101-01-3-001 | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 | 24.Jul.2026 15:28 | 1899-12-31 17:36 |  | 0.083333 | Closed | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) |  | 4 / 4 | [] |  |  | MET.32713045 | 13003390 | 2026-07-26 | Performed
| 673 | 574101-01-3-002 | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP (32713035) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 | 23.Jul.2026 15:17 | 1900-01-01 19:47 |  | 0.36458 | Closed | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32713035 | 13003390 | 2026-07-26 | Performed
| 674 | 574202-01-2-001 | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 28.Jul.2026 18:30 | 0.54514 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) |  | 4 / 4 | [] |  |  | MET.32713043 | 13003390 | 2026-07-29 | Performed
| 675 | 574202-01-2-002 | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713031) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 24.Jul.2026 14:23 | 1900-01-04 19:14 |  | 0.89583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713031 | 40000010 | 2026-07-30 | Performed
| 676 | 574205-01-1-001 | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP (32713033) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:45 | 1899-12-31 17:00 |  | 0.022917 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713033 | 13003390 | 2026-07-26 | Performed
| 677 | 574205-01-1-002 | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP (32713018) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:31 | 1899-12-31 18:39 |  | 0.055556 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 4 / 4 | [] |  |  | MET.32713018 | 13003390 | 2026-07-26 | Performed
| 678 | 574302-01-2-001 | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:35 | 0.08125 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) |  | 4 / 4 | [] |  |  | MET.32712905 | 13003390 | 2026-07-27 | Performed
| 679 | 574302-01-2-002 | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:24 | 1900-01-02 05:26 |  | 0.18056 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) |  | 4 / 4 | [] |  |  | MET.32713020 | 13008286 | 2026-07-28 | Performed
| 680 | 574305-01-1-001 | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP (32713038) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:42 | 1899-12-31 18:10 |  | 0.10486 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, --, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713038 | 13003390 | 2026-07-26 | Performed
| 681 | 574305-01-1-002 | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:13 | 1899-12-31 18:56 |  | 0.045139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) |  | 4 / 4 | [] |  |  | MET.32713029 | 13003390 | 2026-07-26 | Performed
| 682 | 574402-01-2-001 | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:29 | 0.086111 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) |  | 4 / 4 | [] |  |  | MET.32713028 | 13003390 | 2026-07-27 | Performed
| 683 | 574402-01-2-002 | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:08 | 1899-12-31 19:03 |  | 0.22222 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) |  | 4 / 4 | [] |  |  | MET.32713010 | 13003390 | 2026-07-26 | Performed
| 684 | 574405-01-1-001 | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION (32713012) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:26 | 1899-12-31 18:24 |  | 0.14653 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713012 | 13003390 | 2026-07-26 | Performed
| 685 | 574405-01-1-002 | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:11 | 1899-12-31 18:57 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) |  | 4 / 4 | [] |  |  | MET.32713030 | 13003390 | 2026-07-26 | Performed
| 686 | 574502-01-2-001 | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 12:16 | 0.13819 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) |  | 4 / 4 | [] |  |  | MET.32713015 | 13003390 | 2026-07-27 | Performed
| 687 | 574502-01-2-002 | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713034) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:38 | 1899-12-31 18:35 |  | 0.21181 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713034 | 13003390 | 2026-07-26 | Performed
| 688 | 574505-01-1-001 | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION (32713024) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:16 | 1899-12-31 18:02 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 4 / 4 | [] |  |  | MET.32713024 | 13003390 | 2026-07-26 | Performed
| 689 | 574505-01-1-002 | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 13:36 | 1899-12-31 19:32 |  | 0.045139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) |  | 4 / 4 | [] |  |  | MET.32713011 | 13003390 | 2026-07-26 | Performed
| 690 | 574602-01-2-001 | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:33 | 0.13819 |  | 0.09375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) |  | 4 / 4 | [] |  |  | MET.32713025 | 13003390 | 2026-07-27 | Performed
| 691 | 574602-01-2-002 | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 13:27 | 1899-12-31 20:41 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) |  | 4 / 4 | [] |  |  | MET.32713005 | 13003390 | 2026-07-26 | Performed
| 692 | 574605-01-1-001 | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION (32713014) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 15:11 | 1899-12-31 18:09 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713014 | 13003390 | 2026-07-26 | Performed
| 693 | 574605-01-1-002 | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION (32713009) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 13:46 | 1899-12-31 21:22 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713009 | 13003390 | 2026-07-26 | Performed
| 694 | 575107-01-1-001 | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 | 26.Jul.2026 06:24 | 1899-12-31 02:28 |  | 1899-12-31 01:00 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) |  | 4 / 4 | [] |  |  | MET.32713004 | 40000930 | 2026-07-27 | Performed
| 695 | 575107-01-1-002 | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 | 24.Jul.2026 14:28 | 1899-12-31 18:27 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) |  | 4 / 4 | [] |  |  | MET.32713022 | 13003390 | 2026-07-26 | Performed
| 696 | 575120-03-1-001 | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 | 29.Jul.2026 08:16 | 1899-12-31 01:24 |  | 0.0625 | Closed | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) |  | 4 / 4 | [] |  |  | MET.32712998 | 40000010 | 2026-07-30 | Performed
| 697 | 575120-03-1-002 | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 | 24.Jul.2026 13:36 | 1899-12-31 06:14 |  | 0.065972 | Closed | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) |  | 4 / 4 | [] |  |  | MET.32712999 | 13008286 | 2026-07-26 | Performed
| 698 | 575150-01-2-001 | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 19.Jul.2026 16:36 | 1900-01-05 22:36 |  | 0.61111 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) |  | 4 / 4 | [] |  |  | MET.32713008 | 40000010 | 2026-07-26 | Performed
| 699 | 575150-01-2-002 | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP (32713016) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 29.Jul.2026 06:14 | 1899-12-31 00:02 |  | 0.34722 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32713016 | 13008286 | 2026-07-30 | Performed
| 700 | 575158-01-5-001 | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 15:48 | 1899-12-31 04:04 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) |  | 4 / 4 | [] |  |  | MET.25336910 | 13008286 | 2026-07-26 | Performed
| 701 | 575158-01-5-002 | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP (25336066) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 29.Jul.2026 07:15 | 0.95903 |  | 0.25139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.25336066 | 13008286 | 2026-07-30 | Performed
| 702 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.19444 | 17.Jul.2026 22:00 | 0.19444 | 31.Jul.2026 10:56 | 1899-12-31 06:42 |  | 1899-12-31 18:10 | Closed | 0 | T: 0; O: 0; C: 0 | 78-30 |  | [] |  |  |  |  | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) |  | 3 / 3 | [] |  |  | MET.26290436 | 13008286 | 2026-08-02 | Performed
| 703 | 22586962 | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION | 22586962 / 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 10:20 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 22586962 / 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) |  | 0 / 1 | [] |  |  | MET.22586962 | 40000929 | 2026-07-29 | Performed
| 704 | 23464908 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 | 23464908 / 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 10:30 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 23464908 / 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) |  | 0 / 1 | [] |  |  | MET.23464908 | 40000929 | 2026-07-29 | Performed
| 705 | 31905379 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) | Single Running Taskcard | RI | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 17:31 | 1900-01-02 00:35 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) |  | 2 / 2 | [] |  |  | MET.31905379 | 13003390 | 2026-07-23 | Performed
| 706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 29294847 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29294847) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 | 22.Jul.2026 04:55 | 0.14931 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 1 / 5 |  | 0 / 1 | [] |  |  | ME.29294847 | 13003390 | 2026-07-22 | Performed
| 708 | 29749798 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 27.Jul.2026 16:26 | 1900-01-03 18:23 |  | 0.91667 | Closed | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) |  | 0 / 4 | [] |  |  | ME.29749798 | 40000930 | 2026-08-02 | Performed
| 717 | 30482091 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 02:16 | 1899-12-31 05:19 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) |  | 0 / 6 | [] |  |  | ME.30482091 | 40000010 | 2026-07-26 | Performed
| 718 | 30481965 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20486 | 17.Jul.2026 22:00 | 0.20486 | 30.Jul.2026 10:20 | 1900-01-01 19:15 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) |  | 0 / 6 | [] |  |  | ME.30481965 | 40000930 | 2026-08-02 | Performed
| 719 | 29155526 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 27.Jul.2026 09:51 | 0.12639 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) |  | 0 / 6 | [] |  |  | ME.29155526 | 40000930 | 2026-08-02 | Performed
| 749 | 32362499 | S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 25.Jul.2026 23:42 | 0.44514 |  | 0.10833 | Closed | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] | --, --, --, CLOSE-UP |  |  |  | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) |  | 0 / 4 | [] |  |  | ME.32362499 | 13003390 | 2026-07-26 | Performed
| 752 | 30358131 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 11:53 | 0.21528 |  | 0.875 | Closed | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) |  | 0 / 3 | [] |  |  | ME.30358131 | 13008286 | 2026-08-03 | Performed
| 771 | 30304386 | CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.56667 | 17.Jul.2026 22:00 | 0.33403 | 27.Jul.2026 15:50 | 1899-12-31 17:12 |  | 1900-01-04 05:31 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP |  |  |  | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) |  | 0 / 7 | [] |  | ENG200 | ME.30304386 | 40000930 | 2026-07-30 | Performed
| 782 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.375 | 18.Jul.2026 13:46 | 0.51806 |  | 0.071528 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) |  | 9 / 9 | [] |  |  | JCA.32924592 | 13008286 | 2026-07-20 | Performed
| 786 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) | Jobcard | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.37847 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) |  | 20 / 20 | [] |  |  | JCA.32924606 | 13003081 | 2026-08-03 | Performed
| 802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0013889 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:36 | 0.11944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) |  | 1 / 1 | [] |  |  | MET.32608234 | 13008286 | 2026-07-22 | Performed
| 814 | 32977684 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 27.Jul.2026 15:39 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) |  | 0 / 1 | [] |  |  | WO.32977684 | 40000010 | 2026-07-27 | Performed
| 819 | 32977874 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 03.Aug.2026 03:00 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) |  | 0 / 1 | [] |  |  | WO.32977874 | 40000929 | 2026-08-03 | Performed
| 820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 15:58 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) |  | 0 / 1 | [] |  |  | WO.32977881 | 13003390 | 2026-07-23 | Performed
| 824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 12:12 | 0.16667 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) |  | 0 / 1 | [] |  |  | WO.32977904 | 13003390 | 2026-07-21 | Performed
| 825 | 32977905 | PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 05:46 | 0.27083 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) |  | 0 / 1 | [] |  |  | WO.32977905 | 13003390 | 2026-08-03 | Performed
| 829 | 32977909 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 11:19 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) |  | 0 / 1 | [] |  |  | WO.32977909 | 40000930 | 2026-07-28 | Performed
| 831 | 32977911 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 24.Jul.2026 04:24 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) |  | 0 / 1 | [] |  |  | WO.32977911 | 13008286 | 2026-07-26 | Performed
| 832 | 32978070 | FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 09:05 | 0.093056 |  | 0.045139 | Closed | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] |  |  |  |  | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) |  | 0 / 1 | [] |  | 01 | WO.32978070 | 13003390 | 2026-08-03 | Performed
| 833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 04:38 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) |  | 0 / 1 | [] |  |  | WO.32978236 | 13003390 | 2026-07-22 | Performed
| 835 | 32978240 | NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 02.Aug.2026 06:15 | 0.042361 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) |  | 0 / 1 | [] |  |  | WO.32978240 | 13008286 | 2026-08-02 | Performed
| 836 | 32978243 | NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:43 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) |  | 0 / 1 | [] |  |  | WO.32978243 | 13008286 | 2026-07-26 | Performed
| 837 | 32978247 | NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 11:34 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) |  | 0 / 1 | [] |  |  | WO.32978247 | 13003390 | 2026-08-02 | Performed
| 838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 05:29 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) |  | 0 / 1 | [] |  |  | WO.32978249 | 13003390 | 2026-07-22 | Performed
| 839 | 32978253 | LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:24 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) |  | 0 / 1 | [] |  |  | WO.32978253 | 13008286 | 2026-07-26 | Performed
| 843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 17:15 | 0.20903 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) |  | 0 / 1 | [] |  |  | WO.32978273 | 13008286 | 2026-07-22 | Performed
| 844 | 32978279 | RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:19 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) |  | 0 / 1 | [] |  |  | WO.32978279 | 13008286 | 2026-07-26 | Performed
| 845 | 32978280 | MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 09:54 | 0.064583 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) |  | 0 / 1 | [] |  |  | WO.32978280 | 13003390 | 2026-08-02 | Performed
| 848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:59 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) |  | 0 / 1 | [] |  |  | WO.32978291 | 13008286 | 2026-07-21 | Performed
| 849 | 32978481 | RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 28.Jul.2026 04:30 | 0.28264 |  | 0.39583 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] |  |  |  |  | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) |  | 0 / 1 | [] |  |  | WO.32978481 | 13003390 | 2026-07-28 | Performed
| 850 | 32978506 | LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. | 32978506 / LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. (32978506) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 26.Jul.2026 08:19 | 0.047222 |  | 0.048611 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] |  |  |  |  | 32978506 / LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. (32978506) |  | 0 / 1 | [] |  |  | WO.32978506 | 13003390 | 2026-07-26 | Performed
| 858 | 32978568 | FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:33 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) |  | 0 / 1 | [] |  |  | WO.32978568 | 40000010 | 2026-07-30 | Performed
| 859 | 32978570 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 28.Jul.2026 07:03 | 0.17708 |  | 0.67708 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) |  | 0 / 1 | [] |  |  | WO.32978570 | 13003390 | 2026-07-28 | Performed
| 860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 21:01 | 0.14653 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) |  | 0 / 1 | [] |  |  | WO.32978583 | 13008286 | 2026-07-22 | Performed
| 862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 20:28 | 0.084722 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) |  | 0 / 1 | [] |  |  | WO.32978590 | 13008286 | 2026-07-22 | Performed
| 870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 16:18 | 0.25 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) |  | 0 / 1 | [] |  |  | WO.32978648 | 13008286 | 2026-07-22 | Performed
| 871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 21.Jul.2026 15:51 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) |  | 0 / 1 | [] |  |  | WO.32978649 | 13008286 | 2026-07-22 | Performed
| 872 | 32978650 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 25.Jul.2026 01:18 | 0.25 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) |  | 0 / 1 | [] |  |  | WO.32978650 | 40000930 | 2026-07-26 | Performed
| 874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 10:40 | 0.25 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) |  | 0 / 1 | [] |  |  | WO.32978848 | 40000010 | 2026-07-21 | Performed
| 875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-04 | 17.Jul.2026 22:00 | 0.27778 | 19.Jul.2026 03:10 | 1900-01-01 05:17 |  | 1900-01-04 00:30 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) |  | 0 / 1 | [] |  |  | WO.32978869 | 40000010 | 2026-07-21 | Performed
| 877 | 32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.91667 | 17.Jul.2026 22:00 | 0.22917 | 21.Jul.2026 01:47 | 1900-01-03 10:04 |  | 0.91667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) |  | 0 / 1 | [] |  |  | WO.32978900 | 40000010 | 2026-07-26 | Performed
| 878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:00 | 0.20833 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) |  | 0 / 1 | [] |  |  | WO.32978919 | 40000930 | 2026-07-21 | Performed
| 879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 15:11 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) |  | 0 / 1 | [] |  |  | WO.32978925 | 40000010 | 2026-07-21 | Performed
| 880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:38 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) |  | 0 / 1 | [] |  |  | WO.32978965 | 40000930 | 2026-07-21 | Performed
| 881 | 32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 02:18 | 1900-01-03 09:41 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) |  | 0 / 1 | [] |  |  | WO.32979121 | 40000010 | 2026-07-26 | Performed
| 882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 22.Jul.2026 14:02 | 0.12639 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) |  | 0 / 1 | [] |  |  | WO.32979157 | 13003390 | 2026-07-22 | Performed
| 883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:23 | 0.17083 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) |  | 0 / 1 | [] |  |  | WO.32979156 | 13008286 | 2026-07-21 | Performed
| 884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 06:43 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) |  | 0 / 1 | [] |  |  | WO.32979222 | 13008286 | 2026-07-21 | Performed
| 885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 04:06 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) |  | 0 / 1 | [] |  |  | WO.32979231 | 40000930 | 2026-07-21 | Performed
| 887 | 32979285 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. | 32979285 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. (32979285) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 02.Aug.2026 06:16 | 0.10417 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979285 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. (32979285) |  | 0 / 1 | [] |  |  | WO.32979285 | 40000010 | 2026-08-02 | Performed
| 895 | 32979731 | FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. | 32979731 / FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 05:27 | 0.11875 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32979731 / FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) |  | 0 / 1 | [] |  |  | WO.32979731 | 13008286 | 2026-07-26 | Performed
| 896 | 32979723 | APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 03:35 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 36-12 |  | [] |  |  |  |  | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) |  | 0 / 1 | [] |  |  | WO.32979723 | 40000010 | 2026-07-19 | Performed
| 897 | 32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:25 | 1900-01-04 08:36 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) |  | 0 / 1 | [] |  |  | WO.32979981 | 40000010 | 2026-07-26 | Performed
| 898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:26 | 0.33333 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) |  | 0 / 1 | [] |  |  | WO.32980018 | 40000010 | 2026-07-21 | Performed
| 899 | 32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 23:00 | 17.Jul.2026 22:00 | 0.29167 | 21.Jul.2026 01:48 | 1900-01-01 08:05 |  | 1899-12-31 23:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) |  | 0 / 1 | [] |  |  | WO.32980020 | 40000010 | 2026-07-26 | Performed
| 921 | 30205720 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 | 29.Jul.2026 10:42 | 0.042361 |  | 0.069444 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] | INSPECTION |  |  |  | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) |  | 0 / 1 | [] |  |  | ME.30205720 | 13003390 | 2026-07-29 | Performed
| 925 | 32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.0625 | 19.Jul.2026 12:05 | 0.18403 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 38 |  | [] |  |  |  |  | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) |  | 0 / 1 | [] |  |  | ME.32930830 | 13003390 | 2026-07-19 | Performed
| 927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 05:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) |  | 0 / 1 | [] |  |  | WO.32980031 | 40000930 | 2026-07-21 | Performed
| 933 | 32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 04:16 | 1900-01-01 11:17 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) |  | 0 / 1 | [] |  |  | WO.32980070 | 40000010 | 2026-07-26 | Performed
| 935 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 02.Aug.2026 17:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) |  | 1 / 1 | [] |  |  | MET.32807083 | 13008286 | 2026-08-03 | Performed
| 936 | 32980091 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 07:55 | 0.05625 |  | 0.12847 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) |  | 0 / 1 | [] |  |  | WO.32980091 | 13003390 | 2026-08-02 | Performed
| 940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14583 | 21.Jul.2026 15:12 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) |  | 0 / 1 | [] |  |  | WO.32980087 | 40000010 | 2026-07-21 | Performed
| 942 | 32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 05:00 | 17.Jul.2026 22:00 | 0.27083 | 20.Jul.2026 03:27 | 1900-01-04 08:38 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) |  | 0 / 1 | [] |  |  | WO.32980133 | 40000010 | 2026-07-26 | Performed
| 946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:11 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) |  | 0 / 1 | [] |  |  | WO.32980135 | 13003390 | 2026-07-22 | Performed
| 951 | 32980175 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP LWR KICK SEAL WITH CUT DIM: L=1 IN | 32980175 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP LWR KICK SEAL WITH CUT DIM: L=1 IN (32980175) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 04:43 | 0.15139 |  | 0.46181 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980175 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP LWR KICK SEAL WITH CUT DIM: L=1 IN (32980175) |  | 0 / 1 | [] |  |  | WO.32980175 | 40000010 | 2026-08-03 | Performed
| 952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:37 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) |  | 0 / 1 | [] |  |  | WO.32980177 | 13008286 | 2026-07-21 | Performed
| 956 | 32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 32981647 / AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY (32981647) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 11:09 | 0.13611 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32981647 / AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY (32981647) |  | 0 / 1 | [] |  |  | WO.32981647 | 40000010 | 2026-07-30 | Performed
| 958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:14 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) |  | 0 / 1 | [] |  |  | WO.32981716 | 13003390 | 2026-07-22 | Performed
| 959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 11:18 | 0.25069 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) |  | 0 / 1 | [] |  |  | WO.32981721 | 13003390 | 2026-07-22 | Performed
| 961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:25 | 0.125 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) |  | 0 / 1 | [] |  |  | WO.32981754 | 40000930 | 2026-07-21 | Performed
| 962 | 32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 15:52 | 1899-12-31 20:17 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) |  | 0 / 1 | [] |  |  | WO.32981772 | 40000010 | 2026-07-26 | Performed
| 963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:28 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) |  | 0 / 1 | [] |  |  | WO.32981774 | 13003390 | 2026-07-22 | Performed
| 965 | 32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 32982133 / CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING (32982133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 13:01 | 0.1 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] |  |  |  |  | 32982133 / CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING (32982133) |  | 0 / 1 | [] |  |  | WO.32982133 | 40000010 | 2026-07-20 | Performed
| 967 | 32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 12:20 | 0.090278 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) |  | 0 / 1 | [] |  |  | WO.32982191 | 13003390 | 2026-07-20 | Performed
| 975 | 32982253 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:34 | 0.78889 |  | 1900-01-01 18:30 | Closed | 0 | T: 6; O: 0; C: 6 | 27-84 |  | [] |  |  |  |  | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) |  | 0 / 1 | [] |  |  | WO.32982253 | 13003390 | 2026-07-20 | Performed
| 976 | 32982260 | R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:40 | 0.8125 |  | 1900-01-01 20:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-84 |  | [] |  |  |  |  | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) |  | 0 / 1 | [] |  |  | WO.32982260 | 13003390 | 2026-07-20 | Performed
| 977 | 32982263 | BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 03:00 | 0.38889 |  | 0.66319 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] |  |  |  |  | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) |  | 0 / 1 | [] |  |  | WO.32982263 | 13003390 | 2026-07-20 | Performed
| 980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 18:11 | 0.16736 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) |  | 0 / 1 | [] |  |  | WO.32983866 | 13008286 | 2026-07-22 | Performed
| 982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:11 | 0.10417 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) |  | 0 / 1 | [] |  |  | WO.32983882 | 13003390 | 2026-07-23 | Performed
| 983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 23.Jul.2026 13:45 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) |  | 0 / 1 | [] |  |  | WO.32983893 | 13003390 | 2026-07-23 | Performed
| 986 | 32983910 | PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 24.Jul.2026 23:49 | 1900-01-04 05:33 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) |  | 0 / 1 | [] |  |  | WO.32983910 | 13008286 | 2026-07-30 | Performed
| 990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) |  | 0 / 1 | [] |  |  | WO.32983950 | 13003390 | 2026-07-23 | Performed
| 994 | 32984140 | AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 07:37 | 0.95 |  | 0.40972 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) |  | 0 / 1 | [] |  |  | WO.32984140 | 40000930 | 2026-08-03 | Performed
| 995 | 32984158 | PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 14:50 | 1900-01-04 14:40 |  | 0.1875 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) |  | 0 / 1 | [] |  |  | WO.32984158 | 13003390 | 2026-07-27 | Performed
| 998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) |  | 0 / 1 | [] |  |  | WO.32984375 | 13008286 | 2026-07-21 | Performed
| 1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:46 | 0.60208 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) |  | 0 / 1 | [] |  |  | WO.32984479 | 13009981 | 2026-07-23 | Performed
| 1001 | 32984513 | R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 29.Jul.2026 11:01 | 0.96111 |  | 0.76042 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) |  | 0 / 1 | [] |  |  | WO.32984513 | 40000010 | 2026-07-30 | Performed
| 1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:43 | 0.60347 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) |  | 0 / 1 | [] |  |  | WO.32984550 | 13009981 | 2026-07-23 | Performed
| 1009 | 32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 11:06 | 0.1875 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) |  | 0 / 1 | [] |  |  | WO.32984823 | 13003390 | 2026-07-23 | Performed
| 1013 | 32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 08:36 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) |  | 0 / 1 | [] |  |  | WO.32984883 | 13008286 | 2026-07-26 | Performed
| 1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 15:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) |  | 0 / 1 | [] |  |  | WO.32984905 | 13003390 | 2026-07-21 | Performed
| 1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 18:00 | 0.27847 |  | 0.44444 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) |  | 0 / 1 | [] |  |  | WO.32984942 | 13008286 | 2026-07-23 | Performed
| 1017 | 32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 25.Jul.2026 01:00 | 0.16736 |  | 0.16736 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) |  | 0 / 1 | [] |  |  | WO.32984945 | 40000930 | 2026-07-28 | Performed
| 1018 | 32984975 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 26.Jul.2026 07:59 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) |  | 0 / 1 | [] |  |  | WO.32984975 | 13003390 | 2026-07-26 | Performed
| 1022 | 32985009 | PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 25.Jul.2026 00:48 | 1900-01-04 04:27 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) |  | 0 / 1 | [] |  |  | WO.32985009 | 13008286 | 2026-07-30 | Performed
| 1024 | 32985016 | PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 07:33 | 0.17361 |  | 0.12153 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) |  | 0 / 1 | [] |  |  | WO.32985016 | 13003390 | 2026-07-26 | Performed
| 1026 | 32985022 | --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 20.Jul.2026 11:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 53-79 |  | [] |  |  |  |  | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) |  | 0 / 1 | [] |  |  | WO.32985022 | 13003390 | 2026-07-20 | Performed
| 1028 | 32985066 | PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 22:24 | 1900-01-05 08:43 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) |  | 0 / 1 | [] |  |  | WO.32985066 | 13008286 | 2026-07-30 | Performed
| 1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 06:58 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) |  | 0 / 1 | [] |  |  | WO.32985081 | 13008286 | 2026-07-21 | Performed
| 1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 15:15 | 0.076389 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) |  | 0 / 1 | [] |  |  | WO.32985124 | 13003390 | 2026-07-23 | Performed
| 1034 | 32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 32985127 / CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 03.Aug.2026 02:36 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] |  |  |  |  | 32985127 / CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) |  | 0 / 1 | [] |  |  | WO.32985127 | 40000929 | 2026-08-03 | Performed
| 1039 | 32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:43 | 0.088194 |  | 0.24306 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) |  | 0 / 1 | [] |  |  | WO.32985334 | 13008286 | 2026-07-26 | Performed
| 1040 | 32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:22 | 0.10625 |  | 0.25694 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) |  | 0 / 1 | [] |  |  | WO.32985336 | 13008286 | 2026-07-26 | Performed
| 1041 | 32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 14:41 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) |  | 0 / 1 | [] |  |  | WO.32985337 | 13003390 | 2026-08-02 | Performed
| 1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:56 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) |  | 0 / 1 | [] |  |  | WO.32985338 | 13003390 | 2026-07-22 | Performed
| 1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:05 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) |  | 0 / 1 | [] |  |  | WO.32985341 | 13003390 | 2026-07-22 | Performed
| 1044 | 32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) |  | 0 / 1 | [] |  |  | WO.32985342 | 13008286 | 2026-07-26 | Performed
| 1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:04 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) |  | 0 / 1 | [] |  |  | WO.32985347 | 13003390 | 2026-07-22 | Performed
| 1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:47 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) |  | 0 / 1 | [] |  |  | WO.32985351 | 13003390 | 2026-07-22 | Performed
| 1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:40 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) |  | 0 / 1 | [] |  |  | WO.32985352 | 13003390 | 2026-07-22 | Performed
| 1052 | 32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 15:43 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) |  | 0 / 1 | [] |  |  | WO.32985353 | 13003390 | 2026-08-02 | Performed
| 1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:21 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) |  | 0 / 1 | [] |  |  | WO.32985355 | 13003390 | 2026-07-22 | Performed
| 1055 | 32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 14:57 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) |  | 0 / 1 | [] |  |  | WO.32985357 | 13003390 | 2026-08-02 | Performed
| 1056 | 32985503 | VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 24.Jul.2026 16:25 | 1900-01-01 00:42 |  | 0.52083 | Closed | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] |  |  |  |  | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) |  | 0 / 1 | [] |  |  | WO.32985503 | 13008286 | 2026-07-27 | Performed
| 1057 | 32985575 | RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 11:00 | 0.3125 |  | 0.79514 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] |  |  |  |  | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) |  | 0 / 1 | [] |  |  | WO.32985575 | 13003390 | 2026-07-20 | Performed
| 1058 | 32985619 | ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 15:20 | 0.055556 |  | 0.10764 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPEN-UP |  |  |  | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) |  | 0 / 1 | [] |  |  | WO.32985619 | 13003390 | 2026-07-20 | Performed
| 1059 | 32985582 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 14:20 | 0.090278 |  | 0.16667 | Closed | 0 | T: 3; O: 0; C: 3 | 57-41 |  | [] | OPEN-UP |  |  |  | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) |  | 0 / 1 | [] |  |  | WO.32985582 | 13003390 | 2026-07-20 | Performed
| 1060 | 32985655 | BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 16:35 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] |  |  |  |  | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) |  | 0 / 1 | [] |  |  | WO.32985655 | 13003390 | 2026-07-20 | Performed
| 1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 22.Jul.2026 03:13 | 1899-12-31 06:00 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) |  | 0 / 1 | [] |  |  | WO.32985861 | 13009981 | 2026-07-23 | Performed
| 1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 20:37 | 0.52431 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) |  | 0 / 1 | [] |  |  | WO.32985871 | 13009981 | 2026-07-23 | Performed
| 1067 | 32985872 | THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 05:22 | 0.20903 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) |  | 0 / 1 | [] |  |  | WO.32985872 | 40000930 | 2026-07-26 | Performed
| 1069 | 32985875 | ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 07:52 | 0.16042 |  | 0.66875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) |  | 0 / 1 | [] |  |  | WO.32985875 | 13003390 | 2026-07-28 | Performed
| 1070 | 32985877 | ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 07:08 | 0.19028 |  | 0.20972 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) |  | 0 / 1 | [] |  |  | WO.32985877 | 13003390 | 2026-07-28 | Performed
| 1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 19:30 | 0.68056 |  | 1899-12-31 04:50 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | OPEN-UP |  |  |  | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) |  | 0 / 1 | [] |  |  | WO.32985880 | 40000930 | 2026-07-22 | Performed
| 1072 | 32986985 | PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. | 32986985 / PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. (32986985) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 16:40 | 0.089583 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32986985 / PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. (32986985) |  | 0 / 1 | [] |  |  | WO.32986985 | 40000930 | 2026-08-02 | Performed
| 1076 | 32987146 | AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS | 32987146 / AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS (32987146) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 28.Jul.2026 02:00 | 0.33542 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 32987146 / AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS (32987146) |  | 0 / 1 | [] |  |  | WO.32987146 | 13003390 | 2026-07-28 | Performed
| 1080 | 32987301 | DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 07:06 | 1900-01-03 02:24 |  | 0.11111 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) |  | 0 / 1 | [] |  |  | WO.32987301 | 13008286 | 2026-07-27 | Performed
| 1089 | 32987725 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 06:51 | 1900-01-04 21:49 |  | 0.034722 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) |  | 0 / 1 | [] |  |  | WO.32987725 | 13003390 | 2026-07-29 | Performed
| 1090 | 32987776 | --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 21.Jul.2026 03:00 | 0.97917 |  | 1899-12-31 05:00 | Closed | 0 | T: 1; O: 0; C: 1 | 11-21 |  | [] |  |  |  |  | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) |  | 0 / 1 | [] |  |  | WO.32987776 | 40000930 | 2026-07-22 | Performed
| 1093 | 32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:56 | 0.23333 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) |  | 0 / 1 | [] |  |  | WO.32987952 | 13008286 | 2026-07-23 | Performed
| 1097 | 32987964 | DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 08:32 | 1900-01-03 00:57 |  | 0.13194 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) |  | 0 / 1 | [] |  |  | WO.32987964 | 13008286 | 2026-07-27 | Performed
| 1098 | 32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:29 | 0.25 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) |  | 0 / 1 | [] |  |  | WO.32987966 | 13008286 | 2026-07-23 | Performed
| 1105 | 32988015 | PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED | 32988015 / PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED (32988015) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 29.Jul.2026 05:59 | 0.31944 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32988015 / PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED (32988015) |  | 0 / 1 | [] |  |  | WO.32988015 | 40000010 | 2026-07-29 | Performed
| 1109 | 32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 32988470 / CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. (32988470) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 29.Jul.2026 11:22 | 0.125 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988470 / CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. (32988470) |  | 0 / 1 | [] |  |  | WO.32988470 | 13003390 | 2026-07-29 | Performed
| 1117 | 32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 32988794 / PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA (32988794) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 06:28 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988794 / PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA (32988794) |  | 0 / 1 | [] |  |  | WO.32988794 | 13008286 | 2026-07-26 | Performed
| 1119 | 32989018 | PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:24 | 0.27153 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) |  | 0 / 1 | [] |  |  | WO.32989018 | 13008286 | 2026-07-23 | Performed
| 1120 | 32989039 | PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. | 32989039 / PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. (32989039) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 24.Jul.2026 19:10 | 1900-01-04 09:13 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989039 / PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. (32989039) |  | 0 / 1 | [] |  |  | WO.32989039 | 13008286 | 2026-07-30 | Performed
| 1125 | 32989174 | BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:16 | 0.27083 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-56 |  | [] |  |  |  |  | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) |  | 0 / 1 | [] |  |  | WO.32989174 | 13008286 | 2026-07-23 | Performed
| 1136 | 32989545 | L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. | 32989545 / L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. (32989545) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.27083 | 24.Jul.2026 11:03 | 1900-01-04 02:30 |  | 0.56597 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32989545 / L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. (32989545) |  | 0 / 1 | [] |  |  | WO.32989545 | 13008286 | 2026-07-30 | Performed
| 1137 | 32989556 | R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... | 32989556 / R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... (32989556) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 11:02 | 1900-01-05 02:32 |  | 1899-12-31 07:00 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32989556 / R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... (32989556) |  | 0 / 1 | [] |  |  | WO.32989556 | 40000010 | 2026-07-30 | Performed
| 1138 | 32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 32989575 / PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989575) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 15:40 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989575 / PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989575) |  | 0 / 1 | [] |  |  | WO.32989575 | 40000010 | 2026-07-28 | Performed
| 1139 | 32989577 | BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION | 32989577 / BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION (32989577) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.83333 | 17.Jul.2026 22:00 | 0.20833 | 23.Jul.2026 00:00 | 1900-01-02 09:45 |  | 0.93125 | Closed | 0 | T: 0; O: 0; C: 0 | 50-11-33 |  | [] |  |  |  |  | 32989577 / BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION (32989577) |  | 0 / 1 | [] |  | BULK CARGO COM | WO.32989577 | 13008286 | 2026-07-27 | Performed
| 1140 | 32989579 | AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. | 32989579 / AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. (32989579) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.625 | 17.Jul.2026 22:00 | 0.20833 | 30.Jul.2026 04:28 | 1900-01-03 03:05 |  | 0.50347 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989579 / AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. (32989579) |  | 0 / 1 | [] |  |  | WO.32989579 | 40000929 | 2026-08-03 | Performed
| 1151 | 32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 32989888 / PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989888) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 15:42 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989888 / PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989888) |  | 0 / 1 | [] |  |  | WO.32989888 | 40000010 | 2026-07-28 | Performed
| 1152 | 32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:41 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) |  | 0 / 1 | [] |  |  | WO.32989938 | 13003390 | 2026-07-23 | Performed
| 1153 | 32989942 | #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 32989942 / #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32989942) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 17:23 | 1899-12-31 02:23 |  | 0.73264 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989942 / #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32989942) |  | 0 / 1 | [] |  | #2 ENG | WO.32989942 | 40000010 | 2026-07-28 | Performed
| 1155 | 32989944 | #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... | 32989944 / #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... (32989944) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 01.Aug.2026 06:14 | 0.084028 |  | 0.45833 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989944 / #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... (32989944) |  | 0 / 1 | [] |  | #2 ENG | WO.32989944 | 40000930 | 2026-08-03 | Performed
| 1157 | 32989954 | #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 32989954 / #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32989954) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:53 | 0.083333 |  | 0.083333 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989954 / #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32989954) |  | 0 / 1 | [] |  | #2 ENG | WO.32989954 | 40000010 | 2026-07-30 | Performed
| 1159 | 32989953 | FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 02:56 | 0.27222 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 11-35 |  | [] |  |  |  |  | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) |  | 0 / 1 | [] |  | UNDER FLOOR | WO.32989953 | 13003390 | 2026-07-22 | Performed
| 1161 | 32989964 | #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . | 32989964 / #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . (32989964) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 28.Jul.2026 06:19 | 0.10417 |  | 0.27083 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989964 / #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . (32989964) |  | 0 / 1 | [] |  | #2 ENG | WO.32989964 | 40000930 | 2026-07-28 | Performed
| 1162 | 32989965 | #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). | 32989965 / #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). (32989965) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 11:27 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 30-21 |  | [] |  |  |  |  | 32989965 / #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). (32989965) |  | 0 / 1 | [] |  | #2 ENG | WO.32989965 | 13008286 | 2026-08-02 | Performed
| 1167 | 32989975 | #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 32989975 / #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32989975) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 09:33 | 0.024306 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32989975 / #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32989975) |  | 0 / 1 | [] |  | #2 ENG | WO.32989975 | 13008286 | 2026-08-02 | Performed
| 1168 | 32989976 | #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . | 32989976 / #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . (32989976) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 10:17 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989976 / #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . (32989976) |  | 0 / 1 | [] |  | #2 ENG | WO.32989976 | 13008286 | 2026-08-02 | Performed
| 1173 | 32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 22.Jul.2026 16:10 | 0.070139 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) |  | 0 / 1 | [] |  |  | WO.32990006 | 13003390 | 2026-07-22 | Performed
| 1180 | 32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 16:10 | 0.072917 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) |  | 0 / 1 | [] |  |  | WO.32990021 | 13003390 | 2026-07-22 | Performed
| 1181 | 32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:53 | 1899-12-31 06:50 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) |  | 0 / 1 | [] |  |  | WO.32990026 | 13003390 | 2026-07-23 | Performed
| 1182 | 32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 08:00 | 1899-12-31 05:44 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) |  | 0 / 1 | [] |  |  | WO.32990029 | 13003390 | 2026-07-23 | Performed
| 1183 | 32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:00 | 1899-12-31 06:42 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) |  | 0 / 1 | [] |  |  | WO.32990034 | 13003390 | 2026-07-23 | Performed
| 1184 | 32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:03 | 1899-12-31 06:41 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) |  | 0 / 1 | [] |  |  | WO.32990037 | 13003390 | 2026-07-23 | Performed
| 1185 | 32990036 | #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 32990036 / #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32990036) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 16:43 | 1900-01-03 03:02 |  | 1899-12-31 00:05 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32990036 / #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32990036) |  | 0 / 1 | [] |  | #1 ENG | WO.32990036 | 40000010 | 2026-07-28 | Performed
| 1190 | 32990167 | #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 32990167 / #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32990167) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:41 | 0.083333 |  | 0.083333 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990167 / #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32990167) |  | 0 / 1 | [] |  | #1 ENG | WO.32990167 | 40000010 | 2026-07-30 | Performed
| 1194 | 32990173 | #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. | 32990173 / #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. (32990173) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:57 | 0.083333 |  | 0.09375 | Closed | 0 | T: 1; O: 0; C: 1 | 24-92 |  | [] |  |  |  |  | 32990173 / #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. (32990173) |  | 0 / 1 | [] |  | #1 ENG | WO.32990173 | 40000010 | 2026-07-30 | Performed
| 1197 | 32990203 | #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 32990203 / #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32990203) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 09:05 | 0.025694 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32990203 / #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32990203) |  | 0 / 1 | [] |  | #1 ENG | WO.32990203 | 13008286 | 2026-08-02 | Performed
| 1203 | 32991517 | PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 32991517 / PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. (32991517) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 23.Jul.2026 14:37 | 1900-01-02 14:08 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991517 / PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. (32991517) |  | 0 / 1 | [] |  |  | WO.32991517 | 40000930 | 2026-07-28 | Performed
| 1208 | 32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:33 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) |  | 0 / 1 | [] |  |  | WO.32991585 | 13003390 | 2026-07-22 | Performed
| 1226 | 32992522 | RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT | 32992522 / RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT (32992522) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 03:00 | 1900-01-03 00:10 |  | 1900-01-01 14:50 | Closed | 0 | T: 0; O: 0; C: 0 | 55-10-00 |  | [] |  |  |  |  | 32992522 / RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT (32992522) |  | 0 / 1 | [] |  |  | WO.32992522 | 40000929 | 2026-07-26 | Performed
| 1237 | 32993180 | FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. | 32993180 / FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. (32993180) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:10 | 1900-01-01 13:20 |  | 0.28472 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 32993180 / FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. (32993180) |  | 0 / 1 | [] |  |  | WO.32993180 | 40000929 | 2026-07-26 | Performed
| 1238 | 32993201 | L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION | 32993201 / L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION (32993201) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.79167 | 17.Jul.2026 22:00 | 0.20833 | 25.Jul.2026 00:39 | 0.27153 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] |  |  |  |  | 32993201 / L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION (32993201) |  | 0 / 1 | [] |  |  | WO.32993201 | 40000930 | 2026-07-26 | Performed
| 1239 | 32993252 | ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT | 32993252 / ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT (32993252) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 18:14 | 0.083333 |  | 0.17708 | Closed | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] |  |  |  |  | 32993252 / ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT (32993252) |  | 0 / 1 | [] |  |  | WO.32993252 | 40000010 | 2026-08-02 | Performed
| 1242 | 32993275 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. | 32993275 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. (32993275) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-01 16:50 |  | 1899-12-31 03:20 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993275 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. (32993275) |  | 0 / 1 | [] |  |  | WO.32993275 | 40000929 | 2026-07-26 | Performed
| 1243 | 32993277 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. | 32993277 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. (32993277) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-01 17:10 |  | 0.55556 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993277 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. (32993277) |  | 0 / 1 | [] |  |  | WO.32993277 | 40000929 | 2026-07-26 | Performed
| 1244 | 32993284 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. | 32993284 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. (32993284) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-01 17:30 |  | 0.51389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993284 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. (32993284) |  | 0 / 1 | [] |  |  | WO.32993284 | 40000929 | 2026-07-26 | Performed
| 1245 | 32993287 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN | 32993287 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN (32993287) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 17:47 | 1899-12-31 14:58 |  | 0.8875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993287 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN (32993287) |  | 0 / 1 | [] |  |  | WO.32993287 | 40000010 | 2026-08-02 | Performed
| 1246 | 32993288 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. | 32993288 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. (32993288) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 19:05 | 1899-12-31 13:39 |  | 0.67292 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993288 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. (32993288) |  | 0 / 1 | [] |  |  | WO.32993288 | 40000010 | 2026-08-02 | Performed
| 1247 | 32994020 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS | 32994020 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS (32994020) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 01:49 | 0.33403 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994020 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS (32994020) |  | 0 / 1 | [] |  |  | WO.32994020 | 40000010 | 2026-07-26 | Performed
| 1248 | 32994039 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS | 32994039 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS (32994039) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 05:20 | 1900-01-01 13:24 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994039 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS (32994039) |  | 0 / 1 | [] |  |  | WO.32994039 | 40000010 | 2026-07-26 | Performed
| 1249 | 32994166 | FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:32 | 0.12153 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) |  | 0 / 1 | [] |  |  | WO.32994166 | 13003390 | 2026-07-23 | Performed
| 1251 | 32994173 | FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 02:00 | 0.35139 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) |  | 0 / 1 | [] |  |  | WO.32994173 | 13003390 | 2026-07-23 | Performed
| 1252 | 32994187 | FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:42 | 0.1125 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) |  | 0 / 1 | [] |  |  | WO.32994187 | 13003390 | 2026-07-23 | Performed
| 1253 | 32994193 | FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:58 | 0.10139 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) |  | 0 / 1 | [] |  |  | WO.32994193 | 13003390 | 2026-07-23 | Performed
| 1256 | 32995398 | NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING | 32995398 / NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING (32995398) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 03:48 | 0.12569 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32995398 / NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING (32995398) |  | 0 / 1 | [] |  |  | WO.32995398 | 40000930 | 2026-07-26 | Performed
| 1257 | 32995496 | L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS | 32995496 / L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS (32995496) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:00 | 1900-01-01 21:50 |  | 0.51389 | Closed | 0 | T: 0; O: 0; C: 0 | 55-33 |  | [] |  |  |  |  | 32995496 / L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS (32995496) |  | 0 / 1 | [] |  |  | WO.32995496 | 40000929 | 2026-07-26 | Performed
| 1258 | 32995553 | AP---CALLBACK---LH WING LH WING INTERCONNECT STRUT LOWER KINK SEAL WITH CUT | 32995553 / AP---CALLBACK---LH WING LH WING INTERCONNECT STRUT LOWER KINK SEAL WITH CUT (32995553) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 04:36 | 0.15556 |  | 0.67014 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] |  |  |  |  | 32995553 / AP---CALLBACK---LH WING LH WING INTERCONNECT STRUT LOWER KINK SEAL WITH CUT (32995553) |  | 0 / 1 | [] |  |  | WO.32995553 | 40000010 | 2026-08-03 | Performed
| 1259 | 32995625 | RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE | 32995625 / RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE (32995625) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:20 | 1900-01-01 15:00 |  | 0.29861 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 32995625 / RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE (32995625) |  | 0 / 1 | [] |  |  | WO.32995625 | 40000929 | 2026-07-26 | Performed
| 1260 | 32995946 | FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. | 32995946 / FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. (32995946) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 13:22 | 0.097222 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-25 |  | [] |  |  |  |  | 32995946 / FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. (32995946) |  | 0 / 1 | [] |  |  | WO.32995946 | 40000010 | 2026-07-26 | Performed
| 1264 | 32996610 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. | 32996610 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. (32996610) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 08:53 | 0.28056 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32996610 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. (32996610) |  | 0 / 1 | [] |  |  | WO.32996610 | 40000010 | 2026-07-26 | Performed
| 1265 | 32996715 | FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. | 32996715 / FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. (32996715) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 01.Aug.2026 17:57 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] |  |  |  |  | 32996715 / FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. (32996715) |  | 0 / 1 | [] |  |  | WO.32996715 | 40000010 | 2026-08-02 | Performed
| 1267 | 32996759 | R/H WING REFUEL/DEFUEL COUPLING===AP====RII R/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING | 32996759 / R/H WING REFUEL/DEFUEL COUPLING===AP====RII R/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING (32996759) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 23:00 | 1900-01-01 08:09 |  | 0.39097 | Closed | 0 | T: 0; O: 0; C: 0 | 28-25 |  | [] |  |  |  |  | 32996759 / R/H WING REFUEL/DEFUEL COUPLING===AP====RII R/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING (32996759) |  | 0 / 1 | [] |  |  | WO.32996759 | 13008286 | 2026-08-02 | Performed
| 1268 | 32996857 | CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" | 32996857 / CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" (32996857) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 08:53 | 0.083333 |  | 0.11458 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32996857 / CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" (32996857) |  | 0 / 1 | [] |  |  | WO.32996857 | 13003390 | 2026-07-26 | Performed
| 1275 | 32998246 | FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 32998246 / FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998246) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 | 24.Jul.2026 07:26 | 0.042361 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 52-30-00 |  | [] |  |  |  |  | 32998246 / FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998246) |  | 0 / 1 | [] |  |  | WO.32998246 | 40000930 | 2026-07-26 | Performed
| 1276 | 32998252 | AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 32998252 / AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998252) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 | 24.Jul.2026 07:30 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 52-30-00 |  | [] |  |  |  |  | 32998252 / AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998252) |  | 0 / 1 | [] |  |  | WO.32998252 | 40000930 | 2026-07-26 | Performed
| 1277 | 32998934 | FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... | 32998934 / FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... (32998934) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-03 04:00 | 17.Jul.2026 22:00 | 1900-01-01 02:00 | 29.Jul.2026 07:01 | 1899-12-31 03:02 |  | 0.13542 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32998934 / FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... (32998934) |  | 0 / 1 | [] |  |  | WO.32998934 | 13003390 | 2026-08-03 | Performed
| 1283 | 33001199 | AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN | 33001199 / AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN (33001199) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 15:59 | 0.16736 |  | 0.34583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 33001199 / AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN (33001199) |  | 0 / 1 | [] |  |  | WO.33001199 | 40000010 | 2026-08-02 | Performed
| 1285 | 33001460 | LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS | 33001460 / LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS (33001460) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 25.Jul.2026 17:30 | 0.50694 |  | 0.74306 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] |  |  |  |  | 33001460 / LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS (33001460) |  | 0 / 1 | [] |  |  | WO.33001460 | 40000929 | 2026-07-26 | Performed
| 1288 | 33002750 | PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF | 33002750 / PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF (33002750) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.66667 | 28.Jul.2026 02:18 | 0.27639 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33002750 / PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF (33002750) |  | 0 / 1 | [] |  |  | WO.33002750 | 40000930 | 2026-07-28 | Performed
| 1292 | 33003265 | FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--CALLBACK LH WING SLAT N.O 4 INNER RUBBER SEAL TORN 2 EA | 33003265 / FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--CALLBACK LH WING SLAT N.O 4 INNER RUBBER SEAL TORN 2 EA (33003265) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 05:59 | 0.125 |  | 0.52431 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] |  |  |  |  | 33003265 / FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--CALLBACK LH WING SLAT N.O 4 INNER RUBBER SEAL TORN 2 EA (33003265) |  | 0 / 1 | [] |  |  | WO.33003265 | 13003390 | 2026-08-02 | Performed
| 1300 | 33007172 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 33007172 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (33007172) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 07:10 | 0.91319 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 33007172 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (33007172) |  | 0 / 6 | [] |  |  | ME.33007172 | 13003390 | 2026-08-03 | Performed
| 1302 | 33011258 | PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) | 33011258 / PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) (33011258) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 30.Jul.2026 13:31 | 0.1875 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33011258 / PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) (33011258) |  | 0 / 1 | [] |  |  | WO.33011258 | 40000010 | 2026-07-30 | Performed
| 1303 | 33011331 | FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF | 33011331 / FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF (33011331) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.66667 | 28.Jul.2026 02:15 | 0.27153 |  | 0.70833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33011331 / FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF (33011331) |  | 0 / 1 | [] |  |  | WO.33011331 | 40000930 | 2026-07-28 | Performed
| 1306 | 33012961 | L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY | 33012961 / L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY (33012961) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 02.Aug.2026 08:56 | 0.092361 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33012961 / L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY (33012961) |  | 0 / 1 | [] |  |  | WO.33012961 | 13003390 | 2026-08-02 | Performed
| 1307 | 33013426 | L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY | 33013426 / L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY (33013426) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 19:56 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33013426 / L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY (33013426) |  | 0 / 1 | [] |  |  | WO.33013426 | 40000930 | 2026-07-30 | Performed
| 1312 | 33013510 | AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST | 33013510 / AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST (33013510) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 06:58 | 0.16667 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 33013510 / AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST (33013510) |  | 0 / 1 | [] |  |  | WO.33013510 | 40000929 | 2026-08-03 | Performed
| 1313 | 33013536 | VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION | 33013536 / VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION (33013536) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 17:59 | 1899-12-31 13:33 |  | 0.50347 | Closed | 0 | T: 0; O: 0; C: 0 | 55-36 |  | [] |  |  |  |  | 33013536 / VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION (33013536) |  | 0 / 1 | [] |  |  | WO.33013536 | 40000929 | 2026-08-03 | Performed
| 1326 | 33019665 | FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION | 33019665 / FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION (33019665) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.83333 | 17.Jul.2026 22:00 | 0.27778 | 29.Jul.2026 00:38 | 1899-12-31 09:26 |  | 0.84375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33019665 / FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION (33019665) |  | 0 / 1 | [] |  |  | WO.33019665 | 40000010 | 2026-07-30 | Performed
| 1332 | 33020601 | FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . | 33020601 / FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . (33020601) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 28.Jul.2026 16:47 | 1899-12-31 23:25 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 33020601 / FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . (33020601) |  | 0 / 1 | [] |  |  | WO.33020601 | 40000010 | 2026-07-30 | Performed
| 1333 | 33020680 | AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. | 33020680 / AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. (33020680) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 28.Jul.2026 14:49 | 1900-01-01 01:08 |  | 0.6875 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 33020680 / AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. (33020680) |  | 0 / 1 | [] |  |  | WO.33020680 | 40000010 | 2026-07-30 | Performed
| 1346 | 33022924 | RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW | 33022924 / RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW (33022924) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 11:00 | 0.083333 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33022924 / RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW (33022924) |  | 0 / 1 | [] |  |  | WO.33022924 | 40000010 | 2026-07-28 | Performed
| 1350 | 33023367 | AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB | 33023367 / AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB (33023367) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 29.Jul.2026 13:49 | 0.076389 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33023367 / AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB (33023367) |  | 0 / 1 | [] |  |  | WO.33023367 | 40000010 | 2026-07-29 | Performed
| 1351 | 33023576 | AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED | 33023576 / AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED (33023576) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 14:01 | 0.068056 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33023576 / AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED (33023576) |  | 0 / 1 | [] |  |  | WO.33023576 | 40000010 | 2026-07-29 | Performed
| 1352 | 33023575 | FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 33023575 / FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023575) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.375 | 29.Jul.2026 04:22 | 0.21458 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33023575 / FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023575) |  | 0 / 1 | [] |  |  | WO.33023575 | 13003390 | 2026-07-29 | Performed
| 1354 | 33023735 | FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 33023735 / FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023735) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 29.Jul.2026 04:24 | 0.21181 |  | 0.33333 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] |  |  |  |  | 33023735 / FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023735) |  | 0 / 1 | [] |  |  | WO.33023735 | 13003390 | 2026-07-29 | Performed
| 1355 | 33023745 | CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. | 33023745 / CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. (33023745) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 03:17 | 0.22639 |  | 0.27431 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023745 / CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. (33023745) |  | 0 / 1 | [] |  |  | WO.33023745 | 13003390 | 2026-08-03 | Performed
| 1362 | 33025883 | RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) | 33025883 / RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) (33025883) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 08:42 | 1899-12-31 00:38 |  | 0.40625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025883 / RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) (33025883) |  | 0 / 1 | [] |  |  | WO.33025883 | 40000930 | 2026-07-30 | Performed
| 1363 | 33025887 | RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) | 33025887 / RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) (33025887) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 29.Jul.2026 06:28 | 0.35972 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025887 / RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) (33025887) |  | 0 / 1 | [] |  |  | WO.33025887 | 40000930 | 2026-07-30 | Performed
| 1364 | 33025881 | ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... | 33025881 / ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... (33025881) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 12:02 | 0.31944 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 33025881 / ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... (33025881) |  | 0 / 1 | [] |  |  | WO.33025881 | 13003390 | 2026-08-03 | Performed
| 1366 | 33025896 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF | 33025896 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF (33025896) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.40625 | 17.Jul.2026 22:00 | 0.28125 | 29.Jul.2026 08:03 | 1899-12-31 00:40 |  | 0.44792 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025896 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF (33025896) |  | 0 / 1 | [] |  |  | WO.33025896 | 13007897 | 2026-07-30 | Performed
| 1367 | 33025897 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF | 33025897 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF (33025897) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 29.Jul.2026 06:53 | 0.34097 |  | 0.38542 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025897 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF (33025897) |  | 0 / 1 | [] |  |  | WO.33025897 | 40000930 | 2026-07-30 | Performed
| 1370 | 33027335 | OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. | 33027335 / OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. (33027335) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 30.Jul.2026 11:22 | 0.27222 |  | 1899-12-31 02:00 | Closed | 0 | T: 0; O: 0; C: 0 | 56-21 |  | [] |  |  |  |  | 33027335 / OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. (33027335) |  | 0 / 1 | [] |  |  | WO.33027335 | 40000929 | 2026-08-03 | Performed
| 1371 | 33027363 | FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF | 33027363 / FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF (33027363) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 08:15 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027363 / FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF (33027363) |  | 0 / 1 | [] |  |  | WO.33027363 | 13003390 | 2026-07-29 | Performed
| 1383 | 33029195 | ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP | 33029195 / ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029195) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 11:04 | 1900-01-03 00:47 |  | 0.62847 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 33029195 / ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029195) |  | 0 / 1 | [] |  |  | WO.33029195 | 13003390 | 2026-08-03 | Performed
| 1386 | 33029270 | RH WING MLG SUPPORT RIBS=====AP====NO CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC | 33029270 / RH WING MLG SUPPORT RIBS=====AP====NO CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC (33029270) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 13:43 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] |  |  |  |  | 33029270 / RH WING MLG SUPPORT RIBS=====AP====NO CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC (33029270) |  | 0 / 1 | [] |  |  | WO.33029270 | 40000010 | 2026-08-02 | Performed
| 1392 | 33033307 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED | 33033307 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED (33033307) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 08:00 | 17.Jul.2026 22:00 | 1899-12-31 08:00 | 30.Jul.2026 10:22 | 0.31181 |  | 1899-12-31 07:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33033307 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED (33033307) |  | 0 / 1 | [] |  |  | WO.33033307 | 40000010 | 2026-07-30 | Performed