## Sheet1
Workpack Checklist | 31.Aug.2026 | Page 21 / 21 | 12:26 | 13010253 | A/C Registration: A/C Type: A/C Description: Workpackage: | ASP 321 HZ-ASP AIRBUS 321-211 ASP/H-26 C7-CHK | Planned Date: Check Ref: Project No.: Workorder: | 04.Sep.2026 A_N (A_N10), C_N (C_N07) 01BASPC72608 31909295, 31956352
A/C Area | ()
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
130 | 243000-13-1 | DC GENERATION | C_N (C_N07) | ACFT_TECH, AV
131 | 243000-14-1 | DC GENERATION | C_N (C_N07) | ACFT_TECH, AV
15 | 25-10-00-00-SVA | COCKPIT CHECK | A_N (A_N10) | ACFT_TECH, CAB
21 | 25-22-00-00-SVA | CABIN CREW SEAT DEEP INSP | A_N (A_N10) | ACFT_TECH, CAB
139 | 25-28-00-04-0-SVA-004 | A321 (HZ-ASH TO ASW) CARPETS&MATS R/R | C_N (C_N07) | ACFT_TECH, CAB
26 | 25-32-00-00-SVA | GALLEY CHECK | A_N (A_N10) | ACFT_TECH, CAB
152 | 256535-04-1 | EXTERNAL FIX ELT ANTENNA INSPECTION | C_N (C_N07) | ACFT_TECH, AV, II, INSP
153 | 256652-01-1-SVA | LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
43 | 261600-06-1 | CARGO COMPARTMENT SMOKE DETECTION | A_N (A_N10) | ACFT_TECH, AV
44 | 261700-06-1 | LAVATORY SMOKE DETECTION | A_N (A_N10) | ACFT_TECH, AV
46 | 27-92-00-01-SVA | CAPTAIN AND FIRST OFFICER RADIO PTT SWITCH REPLACEMENT | A_N (A_N10) | ACFT_TECH, AV
160 | 272100-12-1 | LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | C_N (C_N07) | ACFT_TECH, AF
170 | 274451-14-1 | THS ACTUATOR ELECTRICAL LOAD OPC | C_N (C_N07) | ACFT_TECH, AF
56 | 281100-05-1 | GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | A_N (A_N10), C_N (C_N07) | ACFT_TECH, AF, II, INSP
57 | 281100-06-1 | OPERATIONAL CHECK OF WATER DRAIN VALVES | A_N (A_N10), C_N (C_N07) | ACFT_TECH, AF, II, INSP
359 | 282200-04-1 | APU FUEL PUMP SYSTEM AND FUEL FEED LINE |  | ACFT_TECH, AP, II, INSP
193 | 291000-25-1 | MAIN AND AUXILIARY HYDRAULIC POWER | C_N (C_N07) | ACFT_TECH, AP
365 | 291000-26-1 | MAIN AND AUXILIARY HYDRAULIC POWER |  | ACFT_TECH, AP
66 | 32-47-00-SVA | BRAKE TEMPRETURE SENSOR CLEANING | A_N (A_N10) | ACFT_TECH, AF
78 | 38-10-00-SVA | DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | A_N (A_N10) | ACFT_TECH, CAB
81 | 491200-B2-1 | GVI OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY. | A_N (A_N10) | ACFT_TECH, AP, II, INSP
229 | 491300-B1-1 | GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | C_N (C_N07) | ACFT_TECH, AP, II, INSP
230 | 491600-B1-1 | DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | C_N (C_N07) | ACFT_TECH, AP, II, INSP
371 | 493000-B1-1 | DISCARD FUEL INLET FILTER ELEMENT |  | ACFT_TECH, AP, INSP, RII
231 | 498000-B1-1 | GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | C_N (C_N07) | II, INSP
82 | 52-31-00-01-0-SVA | FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | A_N (A_N10) | ACFT_TECH, AP
83 | 52-32-00-01-0-SVA | AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | A_N (A_N10) | ACFT_TECH, AP, AV
252 | 531151-02-1 | DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
253 | 531176-02-1 | GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | C_N (C_N07) | ACFT_TECH, AP, II, INSP
254 | 531178-02-1 | GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | C_N (C_N07) | ACFT_TECH, AP, II, INSP
255 | 531182-02-1 | DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
257 | 531900-10-1 | FUSELAGE DRAINAGE | C_N (C_N07) | ACFT_TECH, AP, INSP, RII
259 | 532176-01-1 | FORWARD FUSELAGE | C_N (C_N07) | ACFT_TECH, AP, II, INSP
260 | 532181-03-1 | FORWARD FUSELAGE | C_N (C_N07) | ACFT_TECH, AP, II, INSP
89 | 533154-05-1-A | MLG ACT FITTINGS KEEL BEAM INSP | A_N (A_N10) | ACFT_TECH, AF, II, INSP, NDT, NDT_INSP
262 | 534134-02-1 | DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
264 | 534307-03-1 | REAR FUSELAGE | C_N (C_N07) | ACFT_TECH, AP, II, INSP
265 | 534308-02-1 | REAR FUSELAGE | C_N (C_N07) | ACFT_TECH, AP, II, INSP
272 | 545000-05-1-001 | L/H PYLON FIRE SEALS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
273 | 545000-05-1-002 | R/H PYLON FIRE SEALS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
274 | 545000-06-1-001 | L/H PYLONS CAF 4 SEALANT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
275 | 545000-06-1-002 | R/H PYLONS CAF 4 SEALANT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
92 | 561000-02-1 | DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS. | A_N (A_N10) | II, INSP
277 | 572178-01-1-001 | L/H OUTER WING, TOP SKIN INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
278 | 572178-01-1-002 | R/H OUTER WING, TOP SKIN INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
279 | 572179-01-1-001 | L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
280 | 572179-01-1-002 | R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
291 | 711300-01-2 | GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | C_N (C_N07) | II, INSP
320 | 783209-01-1 | DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | C_N (C_N07) | ACFT_TECH, II, INSP, PP
378 | ZL-161-02-3 | BULK CARGO COMPARTMENT |  | ACFT_TECH, AP, II, INSP
380 | ZL-193-02-1 | UPPER WING FAIRING SLIDE STOWAGE |  | ACFT_TECH, AP, II, INSP
328 | ZL-315-01-1 | GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | C_N (C_N07) | II, INSP
A/C Area | 00 (Multiple Area Tasks)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
113 | 08-10-00-01-0-A | WIGHT & BALANCE | C_N (C_N07) | ACFT_TECH, AF, II, INSP
8 | 23-71-00-00-A | CVR DATA DOWNLOADING ON WING | A_N (A_N10) | ACFT_TECH, AV, CAB
23 | 25-26-00-08-0-SVA | PASSNGER COMPT CURTAINS REPLACEMENT | A_N (A_N10) | ACFT_TECH, CAB
162 | 272400-02-1 | FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | C_N (C_N07) | ACFT_TECH, AF, II, INSP
187 | 282300-01-2 | FUEL CROSSFEED VALVE OPERATIONAL | C_N (C_N07) | ACFT_TECH, AF
71 | 331400-01-1 | ANNUNCIATOR LIGHTS OPERATIONAL CHECK | A_N (A_N10) | ACFT_TECH, AV
75 | 36-11-00-SVA-02-001 | NO. 1 ENGINE BLEED AIR SYSTEM (EBAS) HEALTH CHECK PREVENTEN MAINTENANCE PROGRAM | A_N (A_N10) | ACFT_TECH, AP, II, INSP
224 | 361100-SVA-01 | ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | C_N (C_N07) | ACFT_TECH, AP, II, INSP, PP
250 | 527100-01-1 | DOOR WARNING SYSTEM OPERATIONAL TEST | C_N (C_N07) | ACFT_TECH, AV
105 | FRSEO722061 | ACFT FAN FRAME ASSY-ON WING INSP | A_N (A_N10) | ACFT_TECH, II, INSP, PP
325 | ZL-161-01-1 | BULK CARGO COMPARTMENT ZONAL INSP | C_N (C_N07) | II, INSP
A/C Area | 01 (No. 1 Engine and Pylon)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
115 | 200435-01-1-001 | NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
117 | 200453-01-1-001 | NO. 1 ENG HOT SECTION WIRING INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
11 | 242100-01-1-001 | NO.1 ENG (QAD)ADAPTER TENSION BOLT | A_N (A_N10) | ACFT_TECH, II, INSP, PP
155 | 262100-02-1-001 | NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | C_N (C_N07) | ACFT_TECH, II, INSP, PP
185 | 282100-05-1-001 | NO. 1 ENGINE PIPES, COUPLINGS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
360 | 282400-01-1-001 | NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC |  | ACFT_TECH, AP, INSP, RII
362 | 282400-02-1-001 | NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS |  | ACFT_TECH, PP
196 | 302149-C1-1-001 | NO.1 ENG INTAKE ANTI-ICE DUCT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
222 | 361100-01-1-001 | NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | C_N (C_N07) | ACFT_TECH, II, INSP, PP
76 | 361100-08-2-001-SVA | NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | A_N (A_N10) | ACFT_TECH, AP, II, INSP, NDT_INSP
268 | 545000-01-1-001 | NO. 1 ENGINE PYLON DRAIN SYS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
270 | 545000-04-1-001 | NO.1 ENG PYLN COMPT DRAIN SYS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
281 | 711000-C1-1-001 | #1 ENG INTAKE COWL AFT BULKHEAD INSP | C_N (C_N07) | II, INSP
283 | 711000-C4-2-001 | GENERAL VISUAL INSPECTION OF FAN COWL DOORS | C_N (C_N07) | ACFT_TECH, II, INSP, PP
285 | 711000-C5-1-001 | NO. 1 ENG PRESSURE RELIEF DOOR FUC | C_N (C_N07) | ACFT_TECH, II, INSP, PP
287 | 711000-C6-1-001 | NO.1 ENG FAN COW LATCH & AJCNT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
289 | 711000-C7-1-001 | NO.1 ENG FAN COWL DOOR FIRESEAL INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
293 | 711300-C1-1-002 | NO. 2 ENGINE FAN COWL LATCH TENSION | C_N (C_N07) | ACFT_TECH, PP
93 | 711300-C2-1-001 | NO. 1 ENG FAN COWL LOCKING DEVICE INSP | A_N (A_N10) | ACFT_TECH, II, INSP, PP
294 | 712111-05-4-001 | NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
296 | 712112-01-1-001 | NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | C_N (C_N07) | ACFT_TECH, INSP, PP, RII
298 | 712211-03-1-001 | NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | C_N (C_N07) | II, INSP
300 | 712211-05-1-001 | NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
302 | 712212-01-1-001 | NO. 1 ENG AFT MOUNT LINK LUGS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
304 | 712213-01-1-001 | NO. 1 ENGINE AFT MOUNT PINS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP, RII
95 | 72-00-00-01-0-SVA-001 | NO. 1 ENGINE COMPRESSOR WASH | A_N (A_N10) | ACFT_TECH, INSP, PLANNER, PP, PROD, RII
306 | 72-00-00-25-0-SVA-001 | PRE C-CHK PRESERVATION ON ENG#1 OIL | C_N (C_N07) | ACFT_TECH, AP
307 | 72-00-00-25-0-SVA-002 | PRE C-CHK PRESERVATION ON ENG#2 OIL | C_N (C_N07) | ACFT_TECH, AP
308 | 72-00-00-27-0-SVA-001 | DEPERSERVATION OF ENG# 1 POST C-CHK | C_N (C_N07) | ACFT_TECH, AP
97 | 722000-C1-1-001 | NO. 1 ENGINE INLET FAN SECTION INSP | A_N (A_N10) | ACFT_TECH, II, INSP, PP
310 | 783000-C2-1-001 | NO.1 ENGINE BLOCKER DOOR SEALS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
312 | 783000-C4-1-001 | NO.1 ENG T/R TENSION HOK&AJCNT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
314 | 783100-C6-1-001 | NO.1 ENGINE ACTU SECONDARY LOCK INSP | C_N (C_N07) | ACFT_TECH, PP
316 | 783100-C7-1-001 | NO.1 ENG PRIMARY LATCH MECHNISM INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
318 | 783200-01-1-001 | NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP, PP
99 | 792000-C8-1-001 | NO. 1 ENGINE EMCD CHECK | A_N (A_N10) | ACFT_TECH, PP
101 | 801110-C1-1-001 | NO. 1 ENGINE STARTER CHIP DETECTOR | A_N (A_N10) | ACFT_TECH, AP
103 | 801110-C3-1-001 | NO.1 ENGINE STARTER REPLENISHMENT | A_N (A_N10) | ACFT_TECH, AP, PP
107 | ZL-400-02-1-001 | NO. 1 ENG NACELLES AND PYLONS INSP | A_N (A_N10) | II, INSP
330 | ZL-411-01-3-001 | NO. 1 ENGINE UPPER FORWARD PYLON | C_N (C_N07) | II, INSP
332 | ZL-437-01-1-001 | GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | C_N (C_N07) | II, INSP
334 | ZL-451-01-1-001 | NO. 1 ENGINE THRUST REVERSER COWLING | C_N (C_N07) | ACFT_TECH, II, INSP, PP
336 | ZL-453-01-1-001 | NO.1 ENGINE HOT SECTION ZONAL INSP | C_N (C_N07) | II, INSP
338 | ZL-471-01-4-001 | NO.1 ENG PYLON L/E AND LOWER FAIRING | C_N (C_N07) | II, INSP
A/C Area | 02 (No. 2 Engine and Pylon)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
116 | 200435-01-1-002 | NO.2 ENG FAN & ACCE G/B (EWIS) INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
118 | 200453-01-1-002 | NO. 2 ENG HOT SECTION WIRING INSP | C_N (C_N07) | ACFT_TECH, AP, II, INSP, PP
12 | 242100-01-1-002 | NO.2 ENG (QAD)ADAPTER TENSION BOLT | A_N (A_N10) | ACFT_TECH, II, INSP, PP
156 | 262100-02-1-002 | NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | C_N (C_N07) | ACFT_TECH, II, INSP, PP
186 | 282100-05-1-002 | NO. 2 ENGINE PIPES, COUPLINGS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
361 | 282400-01-1-002 | NO.2 ENG LOW PRESS SHUT OFF VALVE OPC |  | ACFT_TECH, AP, INSP, RII
363 | 282400-02-1-002 | NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS |  | ACFT_TECH, PP
197 | 302149-C1-1-002 | NO.2 ENG INTAKE ANTI-ICE DUCT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
223 | 361100-01-1-002 | NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | C_N (C_N07) | ACFT_TECH, II, INSP, PP
77 | 361100-08-2-002-SVA | NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | A_N (A_N10) | ACFT_TECH, AP, II, INSP, NDT_INSP
269 | 545000-01-1-002 | NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
271 | 545000-04-1-002 | NO.2 ENG PYLN COMPT DRAIN SYS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
282 | 711000-C1-1-002 | #2 ENG INTAKE COWL AFT BULKHEAD INSP | C_N (C_N07) | II, INSP
284 | 711000-C4-2-002 | GENERAL VISUAL INSPECTION OF FAN COWL DOORS | C_N (C_N07) | ACFT_TECH, II, INSP, PP
286 | 711000-C5-1-002 | NO. 2 ENG PRESSURE RELIEF DOOR FUC | C_N (C_N07) | ACFT_TECH, II, INSP, PP
288 | 711000-C6-1-002 | NO.2 ENG FAN COW LATCH & AJCNT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
290 | 711000-C7-1-002 | NO.2 ENG FAN COWL DOOR FIRESEAL INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
292 | 711300-C1-1-001 | NO. 1 ENGINE FAN COWL LATCH TENSION | C_N (C_N07) | ACFT_TECH, PP
94 | 711300-C2-1-002 | NO. 2 ENG FAN COWL LOCKING DEVICE INSP | A_N (A_N10) | ACFT_TECH, II, INSP, PP
295 | 712111-05-4-002 | NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
297 | 712112-01-1-002 | NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | C_N (C_N07) | ACFT_TECH, INSP, PP, RII
299 | 712211-03-1-002 | NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | C_N (C_N07) | II, INSP
301 | 712211-05-1-002 | NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
303 | 712212-01-1-002 | NO. 2 ENG AFT MOUNT LINK LUGS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
305 | 712213-01-1-002 | NO. 2 ENGINE AFT MOUNT PINS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP, RII
96 | 72-00-00-01-0-SVA-002 | NO. 2 ENGINE COMPRESSOR WASH | A_N (A_N10) | ACFT_TECH, INSP, PLANNER, PP, PROD, RII
309 | 72-00-00-27-0-SVA-002 | DEPERSERVATION OF ENG# 2 POST C-CHK | C_N (C_N07) | ACFT_TECH, AP
98 | 722000-C1-1-002 | NO. 2 ENGINE INLET FAN SECTION INSP | A_N (A_N10) | ACFT_TECH, II, INSP, PP
311 | 783000-C2-1-002 | NO.2 ENGINE BLOCKER DOOR SEALS INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
313 | 783000-C4-1-002 | NO.2 ENG T/R TENSSION HOK AJCNT INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
315 | 783100-C6-1-002 | NO.2 ENGINE ACTU SECONDARY LOCK INSP | C_N (C_N07) | ACFT_TECH, PP
317 | 783100-C7-1-002 | NO.2 ENG PRIMARY LATCH MECHNISM INSP | C_N (C_N07) | ACFT_TECH, II, INSP, PP
319 | 783200-01-1-002 | NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP, PP
100 | 792000-C8-1-002 | NO. 2 ENGINE EMCD CHECK | A_N (A_N10) | ACFT_TECH, PP
102 | 801110-C1-1-002 | NO. 2 ENGINE STARTER CHIP DETECTOR | A_N (A_N10) | ACFT_TECH, AP
104 | 801110-C3-1-002 | NO.2 ENGINE STARTER REPLENISHMENT | A_N (A_N10) | ACFT_TECH, AP
108 | ZL-400-02-1-002 | NO. 2 ENG NACELLES AND PYLONS INSP | A_N (A_N10) | II, INSP
331 | ZL-411-01-3-002 | NO. 2 ENGINE UPPER FORWARD PYLON | C_N (C_N07) | II, INSP
333 | ZL-437-01-1-002 | GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | C_N (C_N07) | II, INSP
335 | ZL-451-01-1-002 | NO. 2 ENGINE THRUST REVERSER COWLING | C_N (C_N07) | ACFT_TECH, II, INSP, PP
337 | ZL-453-01-1-002 | NO.2 ENGINE HOT SECTION ZONAL INSP | C_N (C_N07) | II, INSP
339 | ZL-471-01-4-002 | NO.2 ENG PYLON L/E AND LOWER FAIRING | C_N (C_N07) | II, INSP
A/C Area | 05 (Passenger Cabin (Main & Upper Deck))
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
3 | 11-11-00-01-0-SVA | INTERIOR PLACARDS CHECK | A_N (A_N10) | A-PAINT, ACFT_TECH
5 | 212300-02-1 | LAVATORY AIR EXTRACTION FLTR R/R | A_N (A_N10) | ACFT_TECH, CAB
18 | 25-20-00-00-SVA | GENERAL CABIN DEEP INSP | A_N (A_N10) | ACFT_TECH, AP, CAB, II, INSP
19 | 25-21-00-00-SVA | B/C SEAT DEEP INSP | A_N (A_N10) | ACFT_TECH, CAB
20 | 25-21-01-00-SVA | G/C SEAT DEEP INSP | A_N (A_N10) | ACFT_TECH, CAB
22 | 25-26-00-03-0-SVA | PASS COMPT CURTAIN RAILS INSPECTION | A_N (A_N10) | II, INSP
24 | 25-28-00-03-0-SVA-003 | HZ-ASH TO ASW AISLE CARPETS R/R | A_N (A_N10) | ACFT_TECH, CAB
25 | 25-30-00-13-0-SVA | GALLY & WATER AUTO DRAIN VALVES OPC | A_N (A_N10) | ACFT_TECH, CAB
27 | 25-40-00-00-SVA | LAV CHECK | A_N (A_N10) | ACFT_TECH, CAB
28 | 25-60-00-03-0-SVA | EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | A_N (A_N10) | II, INSP
29 | 25-65-00-01-0-SVA | EMERGENCY EQUIP VALIDITY INSP | A_N (A_N10) | II, INSP
30 | 25-65-00-01-0-SVA-001 | FIRST AID MEDICAL SURVL KIT CHECK | A_N (A_N10) | II, INSP
140 | 25-SVA-01 | COCKPIT CHECK | C_N (C_N07) | ACFT_TECH, AP, CAB, II, INSP
141 | 25-SVA-02 | GENERAL CABIN ITEMS C-CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
353 | 25-SVA-03 | B/C SEAT REFRESH |  | ACFT_TECH, CAB
142 | 25-SVA-05 | G/C SEAT REFRESH | C_N (C_N07) | ACFT_TECH, AP, CAB
143 | 25-SVA-06 | GALLEY REFRESH | C_N (C_N07) | ACFT_TECH, CAB
144 | 25-SVA-07 | LAV REFRESH | C_N (C_N07) | ACFT_TECH, CAB
145 | 25-SVA-08 | CABIN CREW SEAT DEEP INSP | C_N (C_N07) | ACFT_TECH, CAB
146 | 252100-01-0-SVA | GUEST CLASS (G/C) PAX SEAT RECLINE AT EMRGENCY EXIT INSPECTION | C_N (C_N07) | II, INSP
147 | 252100-01-0-SVA-003 | PASSENGER SEAT COVERS REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB
31 | 252100-04-1 | INFLATABLE RESTRAINT SYSTEM-ELECTRONICS MODULE ASS.(EMA) BATTERY R/R | A_N (A_N10) | II, INSP
32 | 252100-05-1 | INFLATABLE RESTRAINT SYS-GAS STORAGE AND SQUIB VALIDITY CHECK | A_N (A_N10) | II, INSP
148 | 2521000103-001 | PASS COMPARTMENT SEAT BELTS CLEANING B/C | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
149 | 2521000103-002 | PASS COMPARTMENT SEAT BELTS CLEANING G/C | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
33 | 253400-01-1. | GALLEY COOLING CLEANING | A_N (A_N10) | ACFT_TECH, CAB
34 | 253400-02-1 | AIRCHILLER CONDENSER AIR FLTR CLEANING | A_N (A_N10) | ACFT_TECH, CAB
150 | 254000-04-2 | LAVATORIES FLOOR PANELS INSPECTION | C_N (C_N07) | II, INSP
37 | 256241-05-1 | CABN DOORS GIRT BAR FITT STOP CLEAN | A_N (A_N10) | ACFT_TECH, CAB, II, INSP
151 | 256535-01-1 | EMERGENCY LOCATOR TRANSMITTER OPC | C_N (C_N07) | ACFT_TECH, AV, II, INSP
38 | 256600-02-1 | SUPPLEMENTAL LIFE/RAFT PRES CHK | A_N (A_N10) | ACFT_TECH, CAB, II, INSP
45 | 262441-01-1 | PORT FIRE EXT PRESS GAUGE CHK | A_N (A_N10) | II, INSP
158 | 262541-04-1 | LAVATORY FIRE EXTG PRESS READING CHK | C_N (C_N07) | II, INSP
219 | 352142-01-1-SVA | VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
73 | 353000-01-1 | PORTABLE OXYGEN CYLINDERS OPC | A_N (A_N10), C_N (C_N07) | ACFT_TECH, CAB, II, INSP
74 | 353000-05-1 | CABIN PBE INSP | A_N (A_N10), C_N (C_N07) | ACFT_TECH, CAB, II, INSP
221 | 353000-07-1 | PORTABLE OXYGEN MASKS INSPECTION | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
79 | 383200-01-1 | WASHBASIN FILTER ELEMENT CLEANING | A_N (A_N10) | ACFT_TECH, CAB
232 | 521000-01-SVA | FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
233 | 521000-02-1 | PASSENGER/CREW DOOR SUSPENSION CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
234 | 521000-02-SVA | FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
235 | 521000-03-SVA | AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
236 | 521000-04-1-001 | L/H FWD PAX/CREW DOOR INTEGRITY CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP, RII
237 | 521000-04-1-002 | R/H FWD PAX/CREW DOOR INTEGRITY CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP, RII
238 | 521000-04-1-003 | L/H AFT PAX/CREW DOOR INTEGRITY CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP, RII
239 | 521000-04-1-004 | R/H AFT PAX/CREW DOOR INTEGRITY CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP, RII
240 | 521000-04-SVA | AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
372 | 521000-14-1 | FWD AND AFT PASS/CREW DOOR HINGE LUB |  | ACFT_TECH, CAB
241 | 521121-02-1 | PASSENGER/CREW DOORS LUBRICATION | C_N (C_N07) | ACFT_TECH, CAB
242 | 522200-01-1 | EMERGENCY EXIT DOORS OPS CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
243 | 522200-01-SVA | FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
244 | 522200-02-1 | EMER DOORS ARMED POSITION OPS CHK | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
245 | 522200-02-SVA | FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
246 | 522200-03-SVA | AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
247 | 522200-04-1 | EMER DOOR DAMPER & EMER CLY INSP | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
248 | 522200-04-SVA | AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
251 | 527300-01-1 | EMERGENCY ESCAPE SLIDE WARNING SYS | C_N (C_N07) | ACFT_TECH, AV
A/C Area | 06 (Control Cabin (Cockpit))
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
6 | 212600-02-1 | OVERRIDE FUNCTION (BLOWER AND EXTRACT) OPC | A_N (A_N10) | ACFT_TECH, AV
119 | 212600-03-1 | SMOKE CONFIGURATION CTL CIRCUIT OPC | C_N (C_N07) | ACFT_TECH, AV
121 | 213100-01-1 | PRESSURE CONTROL AND MONITORING OPC | C_N (C_N07) | ACFT_TECH, AF
122 | 213100-02-1 | CABIN PRESSURE SYS MANUAL MODE OPC | C_N (C_N07) | ACFT_TECH, AF
126 | 23-73-00-01-0-SVA | CABIN SIGNS OPS CHK | C_N (C_N07) | ACFT_TECH, IFE
9 | 237100-01-1 | COCKPIT VOICE RECORDER OPC | A_N (A_N10) | ACFT_TECH, AV
10 | 242000-01-1 | GAPCU OPERATIONAL TEST | A_N (A_N10) | ACFT_TECH, AV
128 | 242200-01-1 | ELECTRICAL TRANS INHIBITION OPC | C_N (C_N07) | ACFT_TECH, AV
129 | 242500-01-1 | AC ESSENTIAL GENRATION SWITCHING OPC | C_N (C_N07) | ACFT_TECH, AV
132 | 243200-01-1 | DC GENERATION SWITCHING OPC | C_N (C_N07) | ACFT_TECH, AV
133 | 243400-01-1 | DC EMERGY CONFIGURATION CAUTION OPC | C_N (C_N07) | ACFT_TECH, AV
14 | 243800-01-1 | BATT CHARGE LIMITER OPS CHECK | A_N (A_N10) | ACFT_TECH, AV
134 | 25-11-00-03-0-SVA-001 | THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | C_N (C_N07) | ACFT_TECH, CAB
16 | 25-11-00-07-0-SVA-001 | FOURTH OCCUPANT SEAT LUBRICATION | A_N (A_N10) | ACFT_TECH, CAB
135 | 25-11-00-08-0-SVA | CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | C_N (C_N07) | ACFT_TECH, CAB
136 | 25-11-00-09-0-SVA | CAPTAIN & F/O SEATS COVERS REPLACMENT | C_N (C_N07) | ACFT_TECH, CAB
137 | 25-11-00-17-0-SVA-002 | FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | C_N (C_N07) | ACFT_TECH, CAB
17 | 25-11-00-19-0-SVA | THIRD OCCUPANT SEAT LUBRICATION | A_N (A_N10) | ACFT_TECH, CAB
138 | 25-28-00-04-0-SVA-002 | COCKPIT COMPARTMENT CARPETS REPLCMNT | C_N (C_N07) | ACFT_TECH, CAB
39 | 261200-01-1 | ENG FIRE & OVERHEAT DETECTION TEST | A_N (A_N10) | ACFT_TECH, AV
40 | 261300-01-1 | APU FIRE AND OVERHEAT DETECTION OPC | A_N (A_N10) | ACFT_TECH, AV
41 | 261600-03-1 | CGO`S SMOKE DETECTION OPS CHK | A_N (A_N10) | ACFT_TECH, AV, II, INSP
42 | 261600-04-1 | CGO SMOKE DETECTION OPS CHK | A_N (A_N10) | ACFT_TECH, AV, II, INSP
159 | 271400-01-1 | AILERON DAMPING MEASUREMENT OPS TEST | C_N (C_N07) | ACFT_TECH, AF
357 | 272100-08-1 | RUDDER MECHANICAL CNTROL LUBRICATION |  | ACFT_TECH, AF
47 | 273400-01-1 | ELEV DAMPING MEASUREMENT OPS TEST | A_N (A_N10) | ACFT_TECH, AF, II, INSP
48 | 274000-02-1 | THS ACT OPS CHK (CMR) | A_N (A_N10) | ACFT_TECH, AF, II, INSP
171 | 275100-01-2 | FLAP SYSTEM WING TIP BRAKE OPC | C_N (C_N07) | ACFT_TECH, AV, II, INSP
179 | 278100-03-1 | SLAT SYSTEM WING TIP BRAKE OPC | C_N (C_N07) | ACFT_TECH, AF, II, INSP
190 | 291000-06-1 | PTU YELLOW TO GREEN FUNCTIONAL CHECK | C_N (C_N07) | ACFT_TECH, AV
191 | 291000-09-1 | HYDRAULIC FIRE SHUT OFF VALVES OPC | C_N (C_N07) | ACFT_TECH, AV
192 | 291000-20-1 | ENG DRIVEN PUMP (EDP) DE-PRESS OPS | C_N (C_N07) | ACFT_TECH, PP
64 | 31-63-00-01-SVA-001 | COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | A_N (A_N10) | ACFT_TECH, AV
65 | 313000-01-1 | CLASS 3 FAULTS READING CHECK | A_N (A_N10) | ACFT_TECH, AV
203 | 323000-17-1 | LGCIU POWER SUPPLY RELAYS FUNC CHK | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
205 | 323100-06-1 | GEAR NOT DOWN WARNINGS BITE CHK | C_N (C_N07) | ACFT_TECH, AF
211 | 324300-01-3 | ALTERNATE BRAKING SYS OPS CHK | C_N (C_N07) | ACFT_TECH, AF
212 | 34-55-00-03-A | VOR SYSTEM TEST | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
213 | 341300-05-1 | ADIRU 5-MINUTE TIME DELAY OPC | C_N (C_N07) | ACFT_TECH, AV
214 | 342200-01-1 | STANDBY COMPASS OPS CHK & GVI | C_N (C_N07) | ACFT_TECH, AV, II, INSP
216 | 344800-03-1 | TERRAIN AWARENESS WARNING SYSTEM RA OPC | C_N (C_N07) | ACFT_TECH, AV
366 | 345200-01-1-A | ALTITUDE REPORTING FUNCTIONAL TEST |  | ACFT_TECH, AV
367 | 345200-03-1-A | ATC MODE “S” TRANSP FUC CHK |  | ACFT_TECH, AV, II, INSP
217 | 351000-01-1 | FULL FACE/QUICK OXYGEN MASKS OPC | C_N (C_N07) | ACFT_TECH, CAB
218 | 351241-01-1 | CREW OXYGEN MASKS INSPECTION | C_N (C_N07) | ACFT_TECH, CAB, II, INSP
220 | 353000-06-1-SVA | COCKPIT (PBE) INSPECTION | C_N (C_N07) | ACFT_TECH, CAB, INSP, RII
88 | 525111-06-2 | FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | A_N (A_N10) | ACFT_TECH, CAB, II, INSP
91 | 561000-01-1-SVA | COCKPIT WINDOWS INSPECTION | A_N (A_N10) | ACFT_TECH, AF, II, INSP, STR
276 | 561200-02-1 | COCKPIT SLIDING WINDOW LUBRICATION | C_N (C_N07) | ACFT_TECH, CAB
A/C Area | 07 (Left Wing and Wing Gear)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
172 | 275100-02-1-001 | L/H WING FLAP INTERCONNECTING STRUT | C_N (C_N07) | ACFT_TECH, AF, II, INSP
174 | 275100-03-1-001 | L/H WING FLAP TRANSMISSION SYS CHK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
176 | 275144-01-1-001 | L/H WING FLAP INTERCONNECTING STRUT | C_N (C_N07) | ACFT_TECH, AF, II, INSP, RII
51 | 275446-01-1-001 | L/H FLAP TRACKS LUBRICATION | A_N (A_N10) | ACFT_TECH, AF
53 | 276400-01-1-001 | L/H SPOILER AND HYDR ACTUATION LUBR | A_N (A_N10) | ACFT_TECH, AF
180 | 278100-04-1-001 | L/H SLAT XMISION INSPECTION | C_N (C_N07) | ACFT_TECH, AF, II, INSP
58 | 281200-01-1-001 | L/H WING SURGE TANK BURST DISC INSP | A_N (A_N10) | ACFT_TECH, AF, II, INSP
183 | 281247-01-1-001 | L/H NACA INTAKE FOR SIGN OF BLOCLAGE | C_N (C_N07) | II, INSP
188 | 282541-01-1-001 | L/H REFUEL DEFUEL COUPLING DET INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
200 | 321113-04-1-001 | L/H MLG SHOCK ABSORBER PRESS CHK | C_N (C_N07) | ACFT_TECH, AF
68 | 323000-01-1-002 | LH(MLG)DOWINLOCK SPRING & ATTACHMENT | A_N (A_N10) | II, INSP
208 | 323173-00-SVA | MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | C_N (C_N07) | ACFT_TECH, AF, AV, INSP, RII
225 | 361148-01-1-001 | L/H WING APU BLEED AIR DUCT LEAK CHK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
340 | ZL-500-02-1-001 | L/H WING LOWER SURFACE ZONAL INSP | C_N (C_N07) | II, INSP
342 | ZL-537-01-2-001 | L/H FLAP TAB HINGE AND FAIRING NO.3A | C_N (C_N07) | II, INSP
346 | ZL-575-01-1-001 | L/H OUTB FIXED TRAILING EDGE INSP | C_N (C_N07) | II, INSP
A/C Area | 08 (Right Wing and Wing Gear)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
173 | 275100-02-1-002 | R/H WING FLAP INTERCONNECTING STRUT | C_N (C_N07) | ACFT_TECH, AF, II, INSP
175 | 275100-03-1-002 | R/H WING FLAP TRANSMISSION SYS CHK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
177 | 275144-01-1-002 | R/H WING FLAP INTERCONNECTING STRUT | C_N (C_N07) | ACFT_TECH, AF, II, INSP, RII
52 | 275446-01-1-002 | R/H FLAP TRACKS LUBRICATION | A_N (A_N10) | ACFT_TECH, AF
54 | 276400-01-1-002 | R/H SPOILER AND HYDR ACTUATION LUBR | A_N (A_N10) | ACFT_TECH, AF
181 | 278100-04-1-002 | R/H SLAT XMISION INSPECTION | C_N (C_N07) | ACFT_TECH, AF, II, INSP
59 | 281200-01-1-002 | R/H WING SURGE TANK BURST DISC INSP | A_N (A_N10) | ACFT_TECH, AF, II, INSP
184 | 281247-01-1-002 | R/H NACA INTAKE FOR SIGN OF BLOCKAGE | C_N (C_N07) | II, INSP
189 | 282541-01-1-002 | R/H REFUEL DEFUEL COUPLING DET INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
201 | 321113-04-1-002 | R/H MLG SHOCK ABSORBER PRESS CHK | C_N (C_N07) | ACFT_TECH, AF
69 | 323000-01-1-003 | RH(MLG)DOWINLOCK SPRING & ATTACHMENT | A_N (A_N10) | II, INSP
208 | 323173-00-SVA | MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | C_N (C_N07) | ACFT_TECH, AF, AV, INSP, RII
226 | 361148-01-1-002 | R/H WING APU BLEED AIR DUCT LEAK CHK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
341 | ZL-500-02-1-002 | R/H WING LOWER SURFACE ZONAL INSP | C_N (C_N07) | II, INSP
343 | ZL-537-01-2-002 | R/H FLAP TAB HINGE AND FAIRING NO.3A | C_N (C_N07) | II, INSP
344 | ZL-539-01-2-001 | L/H FLAP TAB HINGE AND FAIRING | C_N (C_N07) | II, INSP
345 | ZL-539-01-2-002 | R/H FLAP TAB HINGE AND FAIRING | C_N (C_N07) | II, INSP
347 | ZL-575-01-1-002 | R/H OUTB FIXED TRAILING EDGE INSP | C_N (C_N07) | II, INSP
A/C Area | 09 (Fuselage and Nose & Body Gears)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
4 | 212141-01-1 | RECIRCULATION FILTER REPLACEMENT | A_N (A_N10) | ACFT_TECH, AF
120 | 212600-08-1 | AIR INLET CHECK VLV OPERATIONAL CHK | C_N (C_N07) | ACFT_TECH, AF
7 | 212600-11-1 | DEMISTER FLTER&FILTER CARTRIDGE R&R | A_N (A_N10) | ACFT_TECH, AF
123 | 215000-03-2 | PACK RAM AIR INLET INSPECTION | C_N (C_N07) | ACFT_TECH, AF, II, INSP
124 | 215222-01-1 | AIR CYCLE MACHINE PLENUM INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
125 | 216242-01-1 | TRIM AIR CHECK VALVES FLAPPERS INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
13 | 242800-01-2 | STATIC INVERTER OPERATIONAL CHECK | A_N (A_N10) | ACFT_TECH, AV, II, INSP
35 | 255000-16-1-001 | FWD CARGO COMP DIVIDER NETS INSP | A_N (A_N10) | II, INSP
36 | 255000-16-1-002 | AFT AND BULK CARGO COMP NETS INSP | A_N (A_N10) | II, INSP
154 | 261500-03-1 | AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
157 | 262300-02-1 | CARGO COMP FIRNG CIRCT CONTU CHK | C_N (C_N07) | ACFT_TECH, AV, II, INSP, RII
161 | 272145-01-1 | RUDDER CABLE TENTION REGULATOR CHECK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
178 | 275451-01-1 | FLAP PCU GEARBOX OIL REPLENISHMENT | C_N (C_N07) | ACFT_TECH, AF, II, INSP
182 | 278451-01-1 | SLAT PCU GEARBOX OIL REPLENISHMENT | C_N (C_N07) | ACFT_TECH, AF, INSP, RII
55 | 281100-02-1 | TANKS WATER DRAIN | A_N (A_N10) | ACFT_TECH, AF, II, INSP
60 | 290000-05-1 | HYDRAULIC SYSTEM FILTERS CLOGGING INDICATORS CHECK | A_N (A_N10) | ACFT_TECH, AF
61 | 291000-01-1 | HYD RESERVOIRS FLUID LEVEL CHECK | A_N (A_N10) | ACFT_TECH, AF
62 | 291000-05-1 | MAIN HYDRAULIC POWER SERVICING | A_N (A_N10) | ACFT_TECH, AF
364 | 291000-15-1 | ANALYZE HYD FLUID FOR PARTICLE, WATER & ACIDITY CONTAMINATION |  | ACFT_TECH, AP
63 | 291000-18-1 | HYDRAULIC RECOVERY TANK DRAINAGE | A_N (A_N10) | ACFT_TECH, AF
194 | 291900-02-1 | INTERNAL LEAK RATE BLUE HYD FUN CHK | C_N (C_N07) | ACFT_TECH, AF, II, INSP
195 | 293400-01-1 | RESERVOIR PRESSURIZATION INDICATING | C_N (C_N07) | ACFT_TECH, AF
198 | 303100-01-1 | PITOT PROBE HETR INSULATION RES FNC | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
202 | 322113-01-1 | NLG SHOCK ABSORBR CHARGE PRSS CHK | C_N (C_N07) | ACFT_TECH, AF
67 | 323000-01-1-001 | (NLG) DOWNLOCK SPRING & ATTACHMENT | A_N (A_N10) | II, INSP
70 | 323000-19-1 | (LG) EXT AND RETR COMPNENTS INSP | A_N (A_N10) | ACFT_TECH, AF, II, INSP
204 | 323100-05-1 | NLG DOOR OPERATING MECHANISM INSP | C_N (C_N07) | II, INSP
206 | 323105-04-1 | NORMAL EXTENSION AND RETRACTION | C_N (C_N07) | ACFT_TECH, AF
207 | 323105-05-1 | NORMAL EXTENSION AND RETRACTION | C_N (C_N07) | ACFT_TECH, AF
208 | 323173-00-SVA | MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | C_N (C_N07) | ACFT_TECH, AF, AV, INSP, RII
209 | 324000-14-1 | NORML BRAKE MODE AUTO REACT FUN CHK | C_N (C_N07) | ACFT_TECH, AF
210 | 324000-17-1 | BRAKE ACCOMULATOR SYSTEM FUN CHK | C_N (C_N07) | ACFT_TECH, AF
215 | 342200-05-1 | STBY PNEM CIRCUT LOW RANG LEAK TEST | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
72 | 344200-03-1 | RADIO ALTIMETER & ANTENNA CLEANING | A_N (A_N10), C_N (C_N07) | ACFT_TECH, AV
227 | 361251-01-3 | APU BLEED CHECK VALVE INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
368 | 383100-02-1 | INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY |  | ACFT_TECH, AF
369 | 383100-05-1 | VACUUM TOILET SYSTEM INSPECTION |  | ACFT_TECH, AP, II, INSP
228 | 383100-07-1 | VACUUM TOILET SYSTEM CLEANING | C_N (C_N07) | ACFT_TECH, AP
370 | 470000-01-1 | D-ULPA FILTER ELEMENT REPLACEMENT |  | ACFT_TECH, AF, INSP, RII
373 | 521121-01-1 | FWD AND AFT PASS/CREW DOOR EXT LUB |  | ACFT_TECH, CAB
374 | 522200-03-1 | EMERG EXIT DOOR EXT CNTRL HNDL LUBR |  | ACFT_TECH, CAB
84 | 523000-01-1-001 | FORWARD CARGO DOOR LUBRICATION | A_N (A_N10) | ACFT_TECH, AF, II, INSP
85 | 523000-01-1-002 | AFT CARGO DOOR LUBRICATION | A_N (A_N10) | ACFT_TECH, AF, II, INSP
86 | 523000-03-1-001 | FWD CARGO DOOR HANDLE LUBRICATION | A_N (A_N10) | ACFT_TECH, AF, II, INSP
87 | 523000-03-1-002 | AFT CARGO DOOR HANDLE LUBRICATION | A_N (A_N10) | ACFT_TECH, AF, II, INSP
375 | 523300-01-1 | BULK CARGO DOOR HANDLE AND HINGE LUB |  | ACFT_TECH, AF
249 | 524100-02-1 | AVNICS COMPT DOORS HNDLE LUBRICATION | C_N (C_N07) | ACFT_TECH, AF
256 | 531900-03-1 | FUSLGE SHEL PSTN TYP DRAIN VLV OPC | C_N (C_N07) | ACFT_TECH, AF
258 | 532137-01-1 | FWD CARGO DOOR CUTOUT PANEL INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
376 | 533131-01-1 | SKIN AROUND ADF1 ANTENNA CUTOUT INSP |  | ACFT_TECH, AV, II, INSP, RII
261 | 533900-01-1 | RUBBER FLAP DRAIN VLV OPC | C_N (C_N07) | ACFT_TECH, AF
377 | 534141-01-5 | WATER SERVICE PANEL CUTOUT INSP |  | ACFT_TECH, AF, II, INSP
263 | 534144-01-1 | FUSELAG INTERNAL STRUCT FR65-70 INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
266 | 535900-01-1 | FUSELAGE DRAINAGE | C_N (C_N07) | ACFT_TECH, AF
267 | 535900-02-1 | BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | C_N (C_N07) | ACFT_TECH, AF
321 | ZL-100-02-1 | LOWER HALF OF FUSELAGE ZONAL INSP | C_N (C_N07) | II, INSP
322 | ZL-123-02-1 | NOSE LANDING GEAR WELL ZONAL INSP | C_N (C_N07) | II, INSP
323 | ZL-131-01-1 | FWD CARGO COMPARTMENT ZONAL INSP | C_N (C_N07) | II, INSP
106 | ZL-147-02-1 | MLG-WELL AND HYD COMP. ZONAL INSP | A_N (A_N10) | II, INSP
324 | ZL-151-01-1 | AFT CARGO COMPARTMENT ZONAL INSP | C_N (C_N07) | II, INSP
326 | ZL-171-01-1 | AFT CABIN UNDERFLOOR COMPART INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
379 | ZL-191-01-2 | AIR CONDITION COMPARTMENT ZONAL INSP |  | II, INSP
109 | ZL-711-01-1 | NLG AND NOSE GEAR DOORS ZONAL INSP | A_N (A_N10) | II, INSP
110 | ZL-731-01-1 | MAIN LANDING GEAR ZONAL INSPECTION | A_N (A_N10) | II, INSP
348 | ZL-734-01-1 | MLG MAIN DOOR ZONAL INSPECTION | C_N (C_N07) | II, INSP
349 | ZL-825-01-1 | FORWARD CARGO COMP. DOOR ZONAL INSP | C_N (C_N07) | II, INSP
350 | ZL-826-01-1 | AFT CARGO COMP. DOOR ZONAL INSP | C_N (C_N07) | II, INSP
351 | ZL-827-01-1 | BULK CARGO COMP. DOOR ZONAL INSP | C_N (C_N07) | II, INSP
381 | ZL-831-01-1 | AFT PASSENGER/CREW DOOR |  | II, INSP
352 | ZL-833-04-1 | FWD AND AFT EMERGENCY EXITS INSP | C_N (C_N07) | II, INSP
A/C Area | 10 (Empennage)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
114 | 200002-01-1 | THS ELECTRICAL BONDING LEADS INSP | C_N (C_N07) | II, INSP
127 | 237135-02-1 | UNDERWATER LOCATOR BEACON OPC | C_N (C_N07) | ACFT_TECH, AV, INSP, RII
356 | 272100-04-1 | RUDDER MECHANICAL CONTROL CHK |  | ACFT_TECH, AF, II, INSP
163 | 273400-02-1 | FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | C_N (C_N07) | ACFT_TECH, AF, INSP, RII
358 | 274100-03-1 | THS MECHANICAL CONTROL LUBRICATION |  | ACFT_TECH, AF
164 | 274142-01-1 | THS TRIM CTL TENSION REG CABLE CHK | C_N (C_N07) | ACFT_TECH, AF, INSP, RII
49 | 274451-01-1 | THS BALL SCREW NUT LUBRICATION | A_N (A_N10) | ACFT_TECH, AF
165 | 274451-04-1 | THS ACT NUT, SCREW & CLAW STOPS | C_N (C_N07) | ACFT_TECH, AF, II, INSP
166 | 274451-05-1 | THSA UPPER & LOWER ATTACHMENTS INSP | C_N (C_N07) | ACFT_TECH, AF, II, INSP
167 | 274451-06-1 | THS ACT THREADED NUT INSPECTION | C_N (C_N07) | II, INSP
168 | 274451-08-1 | THS BALL SCREW SHAFT INTEGRITY FNC | C_N (C_N07) | ACFT_TECH, AF, II, INSP
169 | 274451-09-1 | THS ACTUATOR GEARBOX SERVICING | C_N (C_N07) | ACFT_TECH, AF, INSP, RII
50 | 274451-11-1 | THS UPER ATTACH FOR SECOND LOAD INSP | A_N (A_N10) | ACFT_TECH, AF, AP, II, INSP, RII
199 | 313300-03-1 | DFDR SYSTEM INTERCONNECTION OPC | C_N (C_N07) | ACFT_TECH, AV
327 | ZL-300-02-1 | STABILIZERS&CONE/REAR FUSELAGE INSP | C_N (C_N07) | II, INSP
329 | ZL-334-01-1 | THS TRAILING EDGE ZONAL INSPECTION | C_N (C_N07) | II, INSP
A/C Area | 11 (APU and APU Compartment)
Seq | Taskcard | Task Title | Assigned Checks | Trade | Clear
80 | 49-90-00-01-1-SVA | APU OIL COOLER CLEANING | A_N (A_N10) | ACFT_TECH, AP
AMOS | produced by | www.swiss-as.com | Prepared by: 11023745, 04.Sep.2026