## NEW AOG LINES
NEW AOG LINES FROM AMOS — not in tracker AOG sheet · 04-Aug-2026
# | WO | Seq | Card Description | Part No. | Part Description | Qty | Unit | Availability | Transfer | Created | Note | Delivery
| 81172702 | 905 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | RD-FA5116-01 | (VHS) - LEFT-HAND HORIZONTAL | 1.00 | EA | NOT AVAILABLE | — | 05.Jul.2026 | TPR | —
| 32981683 | 957 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 1013361-039ZZ05 | SHROUD/VELCRO ASSY | 2.00 | EA | NOT AVAILABLE | — | 19.Jul.2026 | 01 EA ISSUED TO ACFT, P26733426, 06 EA, NEW PO, EDD 01SEP26 | —
| 32981726 | 960 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 1016918-115 | LATCH - BACK | 5.00 | EA | NOT AVAILABLE | — | 19.Jul.2026 | (02 EA, ISSUED), (SIT,DHL) DHL 3152883764, 15 EA, ESD 06AUG26. , P26654426, 15 EA. | —
| 32981726 | 960 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | MS51576-10 | SCREW - SHOULDER HEX HD | 8.00 | EA | NOT AVAILABLE | — | 19.Jul.2026 | (SIT,DHL) AWB 2455664665, EDD 02AUG26. , (NEVEER BEEN USED , INSERTED 2019). PO P26651826, 30 EA, NEW PO, EDD 29JUL26 | —
| 32981816 | 964 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 1073205-021ZZ18 | SHROUD CONSOLE ASSEMBLY - LIFE VEST | 2.00 | EA | NOT AVAILABLE | — | 19.Jul.2026 | S.I.T*DHL-2320857136, 06 EA P26502026, 06 EA, EDD 02NOV26. , (NEVER BEEN USED, INSRTD 2021). | —
| 32987066 | 1075 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 2185-1-291-8044 | Y-BELT ASSY W/CVR, LH | 3.00 | EA | AVAILABLE | ON_STATION | 21.Jul.2026 | AVBL | —
| 32980026 | 926 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 1013998-057KA02 | TABLE ASSY-BONDED 18.0 HS | 82.00 | EA | NOT AVAILABLE | — | 21.Jul.2026 | (13 EA ISSUED TO ACFT) P26661026, 130 EA, NEW PO, EDD 23NOV26 | —
| 32981683 | 957 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 1013361-039ZZ05 | SHROUD/VELCRO ASSY | 1.00 | EA | NOT AVAILABLE | — | 26.Jul.2026 | 01 EA ISSUED TO ACFT, P26733426, 06 EA, NEW PO, EDD 01SEP26 | —