## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Due at | To Go | Expected | Dimension
| 1 | 32797253 | 6Y_N/6Y_N YEARS STRUCTURE | 32797253 / 6Y_N/6Y_N YEARS STRUCTURE (32797253) | Check | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 32797253 / 6Y_N/6Y_N YEARS STRUCTURE (32797253) |  | 0 / 1 | [] |  |  | ME.32797253 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18472 | 17.Jul.2026 22:00 | 0.10139 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | OPS/LK, OPS/LK |  |  |  | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) |  | 0 / 2 | [] |  |  | MET.32712972 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB (32712946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB (32712946) |  | 0 / 1 | [] |  |  | MET.32712946 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) |  | 0 / 1 | [] |  |  | MET.32712992 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB (32712973) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB (32712973) |  | 0 / 1 | [] |  |  | MET.32712973 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 6 | 200121-01-1 | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | TC/P, TC/P |  |  |  | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) |  | 0 / 2 | [] |  |  | MET.32712986 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) |  | 0 / 1 | [] |  |  | MET.32712948 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 8 | 200121-04-1 | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.052778 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) |  | 0 / 1 | [] |  |  | MET.32712952 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 9 | 200125-01-1 | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) |  | 0 / 1 | [] |  |  | MET.32712957 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 11 | 200125-06-1 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP (32712938) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42292 | 17.Jul.2026 22:00 | 0.25278 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | REV 2 for T/Q#486124 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP (32712938) |  | 0 / 5 | [] |  |  | MET.32712938 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 12 | 200127-02-1 | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) |  | 0 / 1 | [] |  |  | MET.32712975 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 13 | 200127-05-1 | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION (32712929) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | TC/P |  |  |  | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION (32712929) |  | 0 / 1 | [] |  |  | MET.32712929 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34792 | 17.Jul.2026 22:00 | 0.34792 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | INSPECTION |  |  |  | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) |  | 0 / 1 | [] |  |  | MET.32712935 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 15 | 200131-01-1 | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING (32712982) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34722 | 17.Jul.2026 22:00 | 0.24653 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, CLOSE-UP, CLOSE-UP |  |  |  | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING (32712982) |  | 0 / 4 | [] |  |  | MET.32712982 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 16 | 200133-01-1 | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN (32712984) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.59583 | 17.Jul.2026 22:00 | 0.30764 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN (32712984) |  | 0 / 4 | [] |  |  | MET.32712984 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 17 | 200137-01-1 | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:04 | 17.Jul.2026 22:00 | 1899-12-31 11:24 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) |  | 0 / 3 | [] |  |  | MET.32712985 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 18 | 200145-01-1 | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING (32712930) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.4125 | 17.Jul.2026 22:00 | 0.175 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING (32712930) |  | 0 / 4 | [] |  |  | MET.32712930 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 19 | 200151-01-1 | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING (28325905) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 06:30 | 17.Jul.2026 22:00 | 1899-12-31 15:30 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION, INSPECTION, CLEAN-UP, JOB-SETUP, JOB-CLOSEUP, INSPECTION |  |  |  | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING (28325905) |  | 0 / 6 | [] |  |  | MET.28325905 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 20 | 200151-03-1 | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP (28325775) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.57431 | 17.Jul.2026 22:00 | 0.34722 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP (28325775) |  | 0 / 21 | [] |  |  | MET.28325775 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 21 | 200161-01-1 | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 09:26 | 17.Jul.2026 22:00 | 1899-12-31 00:31 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) |  | 0 / 3 | [] |  |  | MET.25336758 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 22 | 200191-01-1 | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING (28325963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 24-92 |  | [] | PWR-OFF |  |  |  | 2 / 2 |  | 0 / 1 | [] |  |  | MET.28325963 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 23 | 200211-02-1 | 200211-02-1 (01) / COCKPIT WIRING CLEANING | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23819 | 17.Jul.2026 22:00 | 0.11875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | PWR-OFF |  |  |  | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) |  | 0 / 1 | [] |  |  | MET.25336264 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.15486 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) |  | 0 / 3 | [] |  |  | MET.32712990 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 25 | 200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP (32712951) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.29792 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP (32712951) |  | 0 / 3 | [] |  |  | MET.32712951 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 26 | 200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION (32712968) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.21111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION (32712968) |  | 0 / 3 | [] |  |  | MET.32712968 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) |  | 0 / 3 | [] |  |  | MET.25335922 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) |  | 0 / 3 | [] |  |  | MET.25336676 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 30 | 212100-03-1 | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) |  | 0 / 3 | [] |  |  | MET.32450171 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 31 | 212600-09-1 | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 21-26 |  | [] | CLEAN-UP |  |  |  | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) |  | 0 / 1 | [] |  |  | MET.32712967 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 32 | 25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT (32712773) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT (32712773) |  | 0 / 1 | [] |  |  | MET.32712773 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 33 | 25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) |  | 0 / 1 | [] |  |  | MET.32713056 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 34 | 25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R (28325765) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | TC/P |  |  |  | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R (28325765) |  | 0 / 1 | [] |  |  | MET.28325765 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 35 | 253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION (32712949) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.027083 | 19.Jul.2026 04:30 | 1900-01-01 00:08 |  | 1899-12-31 20:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 1 / 5 |  | 3 / 7 | [] |  |  | MET.32712949 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 36 | 254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP (32712983) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.027083 | 19.Jul.2026 17:03 | 1899-12-31 11:35 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 4 |  | 2 / 3 | [] |  |  | MET.32712983 | 21.Apr.2029 | 1005 | 2029-04-21 | D
| 39 | 272100-13-1 | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 27 |  | [] |  |  |  |  | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) |  | 0 / 3 | [] |  |  | MET.32450169 | 23.Apr.2029 | 1007 | 2029-04-23 | D
| 41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP (32712932) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 28-18 |  | [] | INSPECTION |  |  |  | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP (32712932) |  | 0 / 1 | [] |  |  | MET.32712932 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 42 | 282800-08-1 | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC (25336812) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.025694 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 28-28 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC (25336812) |  | 0 / 3 | [] |  |  | MET.25336812 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 43 | 282800-18-1 | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC (31498211) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.061111 | 17.Jul.2026 22:00 | 0.0375 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 28-28 |  | [] | JOB-SETUP, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC (31498211) |  | 0 / 6 | [] |  |  | MET.31498211 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 44 | 323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP (32712960) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.05625 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 32-33 |  | [] | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP (32712960) |  | 0 / 16 | [] |  |  | MET.32712960 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 45 | 323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK (32712937) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022917 | 17.Jul.2026 22:00 | 0.01875 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 32-33 |  | [] | JOB-SETUP, JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK (32712937) |  | 0 / 6 | [] |  |  | MET.32712937 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 46 | 341300-13-1 | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST (32712926) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.03125 | 17.Jul.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST (32712926) |  | 0 / 3 | [] |  |  | MET.32712926 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) |  | 0 / 3 | [] |  |  | MET.32712942 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) |  | 0 / 3 | [] |  |  | MET.32712978 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 52-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) |  | 0 / 3 | [] |  |  | MET.32712931 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 50 | 530000-01-1 | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-00 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) |  | 0 / 3 | [] |  |  | MET.32712941 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 51 | 531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP (32712625) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | CLEAN-UP, INSPECTION, INSPECTION |  |  |  | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP (32712625) |  | 0 / 3 | [] |  |  | MET.32712625 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 52 | 531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION (32712605) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11875 | 17.Jul.2026 22:00 | 0.10486 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION (32712605) |  | 0 / 6 | [] |  |  | MET.32712605 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 53 | 531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION (32712603) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.12708 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION (32712603) |  | 0 / 5 | [] |  |  | MET.32712603 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 54 | 531171-01-1 | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS (32712616) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | INSPECTION, INSPECTION |  |  |  | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS (32712616) |  | 0 / 2 | [] |  |  | MET.32712616 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 55 | 531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP (32712758) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20347 | 17.Jul.2026 22:00 | 0.17569 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP (32712758) |  | 0 / 7 | [] |  |  | MET.32712758 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 56 | 531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP (32712608) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.91111 | 17.Jul.2026 22:00 | 0.58125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP (32712608) |  | 0 / 8 | [] |  |  | MET.32712608 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 57 | 531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP (32712651) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 15:48 | 17.Jul.2026 22:00 | 1899-12-31 15:28 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Rev 4 As requested T/Q 490977, add insp scop on step 4 (B) Floor panel instalation. | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP (32712651) |  | 0 / 7 | [] |  |  | MET.32712651 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 58 | 532137-03-1 | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION (32712609) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.066667 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | JOB-SETUP, INSPECTION, CLOSE-UP |  |  |  | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION (32712609) |  | 0 / 3 | [] |  |  | MET.32712609 | 10.Sep.2029 | 1147 | 2029-09-10 | D
| 59 | 533136-01-1 | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP (32712615) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 | 19.Jul.2026 16:37 | 1899-12-31 12:01 |  | 0.5 | Idle | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP (32712615) |  | 0 / 5 | [] |  |  | MET.32712615 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 60 | 534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS (32712709) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.03125 | 17.Jul.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS (32712709) |  | 0 / 3 | [] |  |  | MET.32712709 | 19.Sep.2029 | 1156 | 2029-09-19 | D
| 61 | 534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.23819 | 17.Jul.2026 22:00 | 0.19653 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) |  | 0 / 5 | [] |  |  | MET.31498197 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 62 | 534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV (32712617) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-02 17:00 | 17.Jul.2026 22:00 | 1900-01-02 11:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV (32712617) |  | 0 / 7 | [] |  |  | MET.32712617 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 63 | 534148-01-1 | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP (31497923) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.56319 | 17.Jul.2026 22:00 | 0.47986 |  | 0 |  | 0 | Not Started | 0 | T: 45; O: 0; C: 45 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 0 / 5 | [] |  |  | MET.31497923 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 64 | 534159-02-1 | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 20.Jul.2026 18:52 | 0.40694 |  | 0.20833 | Idle | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) |  | 0 / 3 | [] |  |  | MET.32712636 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 65 | 534171-02-1 | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) |  | 0 / 3 | [] |  |  | MET.32712610 | 12.Sep.2029 | 1149 | 2029-09-12 | D
| 66 | 534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN (25335797) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN (25335797) |  | 0 / 4 | [] |  |  | MET.25335797 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 67 | 534301-01-1 | 534301-01-1 (0) / REAR FUSELAGE | 534301-01-1 (0) / REAR FUSELAGE (32450153) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534301-01-1 (0) / REAR FUSELAGE (32450153) |  | 0 / 4 | [] |  |  | MET.32450153 | 30.Dec.2030 | 1623 | 2030-12-30 | D
| 68 | 535101-01-1 | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP (32712606) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 17.Jul.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP (32712606) |  | 0 / 7 | [] |  |  | MET.32712606 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 69 | 551020-01-1 | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1375 | 17.Jul.2026 22:00 | 0.072917 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 55-16 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) |  | 0 / 5 | [] |  |  | MET.32712717 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 70 | 552002-01-1 | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1375 | 17.Jul.2026 22:00 | 0.072917 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 55-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) |  | 0 / 5 | [] |  |  | MET.32712602 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 71 | 553004-01-1 | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP (32712644) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 55-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP (32712644) |  | 0 / 3 | [] |  |  | MET.32712644 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 72 | 553005-01-1 | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015972 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) |  | 0 / 5 | [] |  |  | MET.32712648 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 73 | 553006-01-2 | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) |  | 0 / 5 | [] |  |  | MET.32712614 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 74 | 554003-01-1 | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION (25336894) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION (25336894) |  | 0 / 5 | [] |  |  | MET.25336894 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 75 | 554005-01-1 | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) |  | 0 / 5 | [] |  |  | MET.32712638 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 76 | 554006-01-1 | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP (32712637) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP (32712637) |  | 0 / 5 | [] |  |  | MET.32712637 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 77 | 554008-01-1 | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP (32712641) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15625 | 17.Jul.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP (32712641) |  | 0 / 5 | [] |  |  | MET.32712641 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 78 | 554009-01-1 | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP (32712621) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.30208 | 17.Jul.2026 22:00 | 0.15069 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP (32712621) |  | 0 / 5 | [] |  |  | MET.32712621 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 79 | 562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP (32712652) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.55 | 17.Jul.2026 22:00 | 0.29444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 56-21 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP (32712652) |  | 0 / 6 | [] |  |  | MET.32712652 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 80 | 571122-01-1 | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION (32712620) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1375 | 17.Jul.2026 22:00 | 0.071528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION (32712620) |  | 0 / 5 | [] |  |  | MET.32712620 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 81 | 571157-01-1 | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP (32712981) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.32083 | 17.Jul.2026 22:00 | 0.18125 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 57-10 |  | [] | JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-SETUP |  |  |  | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP (32712981) |  | 0 / 4 | [] |  |  | MET.32712981 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) |  | 0 / 3 | [] |  |  | MET.25335733 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.011806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) |  | 0 / 3 | [] |  |  | MET.25336621 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 84 | 572065-01-1-001 | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712639) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712639) |  | 0 / 5 | [] |  |  | MET.32712639 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 85 | 572065-01-1-002 | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712642) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712642) |  | 0 / 5 | [] |  |  | MET.32712642 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.021528 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) |  | 0 / 4 | [] |  |  | MET.32712633 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.021528 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) |  | 0 / 4 | [] |  |  | MET.32712611 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 88 | 572161-01-11-001 | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP (32450259) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP (32450259) |  | 0 / 6 | [] |  |  | MET.32450259 | 29.Apr.2029 | 1013 | 2029-04-29 | D
| 89 | 572161-01-11-002 | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP (32450258) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP (32450258) |  | 0 / 6 | [] |  |  | MET.32450258 | 29.Apr.2029 | 1013 | 2029-04-29 | D
| 90 | 572651-01-2-001 | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) |  | 0 / 4 | [] |  |  | MET.32712646 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 91 | 572651-01-2-002 | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) |  | 0 / 4 | [] |  |  | MET.32712601 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 92 | 574206-01-1 | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] |  |  |  |  | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) |  | 0 / 3 | [] |  |  | MET.32712600 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 93 | 574306-01-1-001 | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) |  | 0 / 3 | [] |  |  | MET.28326012 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 94 | 574306-01-1-002 | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) |  | 0 / 3 | [] |  |  | MET.28326010 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 95 | 574406-01-1 | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) |  | 0 / 3 | [] |  |  | MET.32712904 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 96 | 574506-01-1-001 | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) |  | 0 / 3 | [] |  |  | MET.32712655 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 97 | 574506-01-1-002 | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) |  | 0 / 3 | [] |  |  | MET.32713057 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 98 | 574606-01-1 | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 57-46 |  | [] |  |  |  |  | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) |  | 0 / 3 | [] |  |  | MET.32712994 | 11.Sep.2029 | 1148 | 2029-09-11 | D
| 99 | 575151-03-1 | 575151-03-1 (0) / TRAILING EDGE | 575151-03-1 (0) / TRAILING EDGE (31481298) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 57-51 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575151-03-1 (0) / TRAILING EDGE (31481298) |  | 0 / 5 | [] |  |  | MET.31481298 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 100 | 575167-01-1-001 | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) |  | 0 / 5 | [] |  |  | MET.32712654 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 101 | 575167-01-1-002 | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) |  | 0 / 5 | [] |  |  | MET.32712881 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 102 | 783210-01-1 | 783210-01-1 (0) / THRUST REVERSER STRUCTURE | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) |  | 0 / 3 | [] |  |  | MET.32450145 | 30.Dec.2030 | 1623 | 2030-12-30 | D
| 104 | ZL-121-02-1 | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) |  | 0 / 1 | [] |  |  | MET.32712623 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 105 | ZL-125-02-1 | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP (32712901) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.053472 | 17.Jul.2026 22:00 | 0.046528 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP (32712901) |  | 0 / 4 | [] |  |  | MET.32712901 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 106 | ZL-127-02-2 | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP (32712599) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP (32712599) |  | 0 / 1 | [] |  |  | MET.32712599 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION (28325941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:18 | 17.Jul.2026 22:00 | 1899-12-31 14:18 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION (28325941) |  | 0 / 1 | [] |  |  | MET.28325941 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 108 | ZL-133-01-1 | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP (28325940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.43056 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP (28325940) |  | 0 / 4 | [] |  |  | MET.28325940 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 109 | ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION (32712626) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.47917 | 17.Jul.2026 22:00 | 0.45833 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION (32712626) |  | 0 / 6 | [] |  |  | MET.32712626 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 111 | ZL-151-02-3 | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP (28325988) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 13:00 | 17.Jul.2026 22:00 | 1899-12-31 11:00 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 28-11 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, CLOSE-UP, CLOSE-UP |  |  |  | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP (28325988) |  | 0 / 5 | [] |  |  | MET.28325988 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 112 | ZL-153-01-1 | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY (28325989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42361 | 17.Jul.2026 22:00 | 0.35417 | 20.Jul.2026 17:50 | 0.45 |  | 0.33333 | Idle | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY (28325989) |  | 0 / 8 | [] |  |  | MET.28325989 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 113 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.30069 | 17.Jul.2026 22:00 | 0.30069 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) |  | 0 / 4 | [] |  |  | MET.28325926 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 114 | ZL-163-01-1 | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP (25336492) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.4125 | 17.Jul.2026 22:00 | 0.37083 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP (25336492) |  | 0 / 4 | [] |  |  | MET.25336492 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP (28325987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 05:00 | 17.Jul.2026 22:00 | 1900-01-02 05:00 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP (28325987) |  | 0 / 1 | [] |  |  | MET.28325987 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 23; O: 0; C: 23 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) |  | 0 / 1 | [] |  |  | MET.28325991 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 117 | ZL-193-01-1 | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA (32712631) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.046528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA (32712631) |  | 0 / 4 | [] |  |  | MET.32712631 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION (25336636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION (25336636) |  | 0 / 1 | [] |  |  | MET.25336636 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 121 | ZL-200-04-1 | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE (32450172) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.525 | 17.Jul.2026 22:00 | 0.525 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE (32450172) |  | 0 / 4 | [] |  |  | MET.32450172 | 19.Apr.2029 | 1003 | 2029-04-19 | D
| 122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 15; O: 0; C: 15 | 05-22 |  | [] | INSPECTION |  |  |  | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) |  | 0 / 1 | [] |  |  | MET.32712928 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP (32712980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:43 | 0.74653 |  | 0.625 | Idle | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712980 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP (32712954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 12:42 | 0.66389 |  | 0.32639 | Idle | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712954 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 126 | ZL-325-01-1 | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP (32712961) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 16:23 | 0.51042 |  | 0.27083 | Idle | 0 | T: 4; O: 0; C: 4 | 05-23 |  | [] | PRE INSP |  |  |  | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP (32712961) |  | 0 / 1 | [] |  |  | MET.32712961 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION (32712645) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 18:07 | 0.43819 |  | 0.076389 | Idle | 0 | T: 24; O: 0; C: 24 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 5 |  | 1 / 1 | [] |  |  | MET.32712645 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 15:39 | 0.54097 |  | 0.34722 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) |  | 1 / 1 | [] |  |  | MET.28325802 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 19:25 | 0.38403 |  | 0.034722 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) |  | 1 / 1 | [] |  |  | MET.28325897 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) |  | 0 / 1 | [] |  |  | MET.32712947 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP (32712934) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:21 | 0.80347 |  | 0.010417 | Idle | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.32712934 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP (28325993) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:20 | 0.80417 |  | 0.010417 | Idle | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.28325993 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) |  | 0 / 1 | [] |  |  | MET.28325992 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 138 | ZL-531-02-1-001 | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP (25335895) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:28 | 0.71528 |  | 0.010417 | Idle | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP (25335895) |  | 0 / 1 | [] |  |  | MET.25335895 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 139 | ZL-531-02-1-002 | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING (25336980) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:29 | 0.71458 |  | 0.010417 | Idle | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING (25336980) |  | 0 / 1 | [] |  |  | MET.25336980 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP (32712979) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:29 | 0.71458 |  | 0.010417 | Idle | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP (32712979) |  | 0 / 1 | [] |  |  | MET.32712979 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 11:29 | 0.71458 |  | 0.010417 | Idle | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) |  | 0 / 1 | [] |  |  | MET.25336989 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP (32712970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:30 | 0.71389 |  | 0.010417 | Idle | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP (32712970) |  | 0 / 1 | [] |  |  | MET.32712970 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) |  | 0 / 1 | [] |  |  | MET.32712940 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP (32712969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 20.Jul.2026 09:20 | 0.80417 |  | 0.010417 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.32712969 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) |  | 0 / 2 | [] |  |  | MET.32712956 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP (32712918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP (32712918) |  | 0 / 2 | [] |  |  | MET.32712918 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP (32712974) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.32712974 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 157 | ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP (32712989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.081944 |  | 0 |  | 0 | Not Started | 0 | T: 16; O: 0; C: 16 | 05-28 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP (32712989) |  | 0 / 4 | [] |  |  | MET.32712989 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 158 | 31871161 | A_N (A_N09)/A_N-CHECK | 31871161 / A_N (A_N09)/A_N-CHECK (31871161) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31871161 / A_N (A_N09)/A_N-CHECK (31871161) |  | 0 / 1 | [] |  |  | ME.31871161 | 45735:38 | 217:59 | 2026-08-10 | H
| 159 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32807102) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 17.Jul.2026 22:00 | 0.090278 | 20.Jul.2026 13:00 | 0.65139 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32807102) |  | 0 / 2 | [] |  |  | MET.32807102 | 26.Jul.2026 | 5 | 2026-07-26 | D
| 160 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29295382) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 11-11 |  | [] | PRE INSP |  |  |  | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29295382) |  | 0 / 1 | [] |  |  | MET.29295382 | 45735:38 | 217:59 | 2026-08-10 | H
| 161 | 21-SVA-01 | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 21-61 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) |  | 0 / 3 | [] |  |  | MET.32163662 | 47735:38 | 2217:59 | 2027-02-23 | H
| 163 | 212600-11-1 | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32807103) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32807103) |  | 0 / 4 | [] |  |  | MET.32807103 | 45735:38 | 217:59 | 2026-08-10 | H
| 164 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-41 |  | [] | OPS/LK |  |  |  | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) |  | 0 / 1 | [] |  |  | MET.32807106 | 45735:38 | 217:59 | 2026-08-10 | H
| 165 | 242000-25-1 | 242000-25-1 (02) / AC GENERATION | 242000-25-1 (02) / AC GENERATION (32807088) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 242000-25-1 (02) / AC GENERATION (32807088) |  | 0 / 3 | [] |  |  | MET.32807088 | 46138:01 | 620:22 | 2026-09-19 | H
| 166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 06:45 | 1899-12-31 21:53 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 24-28 |  | [] | OPS/LK |  |  |  | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) |  | 1 / 1 | [] |  |  | MET.32807105 | 45735:38 | 217:59 | 2026-08-10 | H
| 167 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-38 |  | [] | OPS/LK |  |  |  | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) |  | 0 / 1 | [] |  |  | MET.32807109 | 45735:38 | 217:59 | 2026-08-10 | H
| 168 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 25-10-00-00-SVA (00) / COCKPIT CHECK (31784709) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28472 | 17.Jul.2026 22:00 | 0.28472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-10-00-00-SVA (00) / COCKPIT CHECK (31784709) |  | 0 / 15 | [] |  |  | MET.31784709 | 45735:38 | 217:59 | 2026-08-10 | H
| 169 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32807107) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.36806 | 17.Jul.2026 22:00 | 0.45139 | 20.Jul.2026 08:43 | 0.82986 |  | 0.22917 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32807107) |  | 1 / 22 | [] |  |  | MET.32807107 | 45735:38 | 217:59 | 2026-08-10 | H
| 170 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32807089) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32807089) |  | 0 / 14 | [] |  |  | MET.32807089 | 45735:38 | 217:59 | 2026-08-10 | H
| 171 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32807065) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 17.Jul.2026 22:00 | 0.28819 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32807065) |  | 0 / 16 | [] |  |  | MET.32807065 | 45735:38 | 217:59 | 2026-08-10 | H
| 172 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32807097) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.11458 | 20.Jul.2026 15:52 | 0.53194 |  | 0.75 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 0 / 21 |  | 6 / 6 | [] |  |  | MET.32807097 | 45735:38 | 217:59 | 2026-08-10 | H
| 173 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32807072) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-26 |  | [] | TC/P |  |  |  | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32807072) |  | 0 / 1 | [] |  |  | MET.32807072 | 45735:38 | 217:59 | 2026-08-10 | H
| 174 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R (31784913) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | PRE INSP |  |  |  | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R (31784913) |  | 0 / 1 | [] |  |  | MET.31784913 | 45735:38 | 217:59 | 2026-08-10 | H
| 175 | 25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP (28365434) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE HGR |  |  |  | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP (28365434) |  | 0 / 1 | [] |  |  | MET.28365434 | 48638:01 | 3120:22 | 2027-05-23 | H
| 176 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29295199) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE INSP |  |  |  | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29295199) |  | 0 / 1 | [] |  |  | MET.29295199 | 45735:38 | 217:59 | 2026-08-10 | H
| 177 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 25-32-00-00-SVA (01) / GALLEY CHECK (32807094) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 17.Jul.2026 22:00 | 0.28819 | 19.Jul.2026 04:00 | 1900-01-01 00:38 |  | 1899-12-31 04:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 0 / 10 |  | 0 / 16 | [] |  |  | MET.32807094 | 47590:58 | 2073:19 | 2027-02-09 | H
| 178 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 25-40-00-00-SVA (01) / LAV CHECK (32807064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30903 | 17.Jul.2026 22:00 | 0.30903 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 0 / 3 |  | 0 / 18 | [] |  |  | MET.32807064 | 47590:58 | 2073:19 | 2027-02-09 | H
| 180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29295141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:26 | 1899-12-31 22:12 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.29295141 | 45735:38 | 217:59 | 2026-08-10 | H
| 181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32807056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.041667 | 19.Jul.2026 06:36 | 1899-12-31 22:02 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  | As per requested by CONF ENGG in T/Q CONF ENGG 805450. | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807056 | 02.Oct.2026 | 73 | 2026-10-02 | D
| 182 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 253400-01-1. (03) / GALLEY COOLING CLEANING (32807071) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013889 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 253400-01-1. (03) / GALLEY COOLING CLEANING (32807071) |  | 0 / 2 | [] |  |  | MET.32807071 | 46235:38 | 717:59 | 2026-09-28 | H
| 183 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32807090) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-34 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32807090) |  | 0 / 8 | [] |  |  | MET.32807090 | 45735:38 | 217:59 | 2026-08-10 | H
| 185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32807093) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32807093) |  | 0 / 1 | [] |  |  | MET.32807093 | 45735:38 | 217:59 | 2026-08-10 | H
| 186 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 25-62 |  | [] | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK |  |  |  | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) |  | 0 / 4 | [] |  |  | MET.32807073 | 17'164 | 850 | 2027-04-03 | C
| 187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:36 | 1899-12-31 20:02 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 26-12 |  | [] | OPS/LK |  |  |  | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) |  | 1 / 1 | [] |  |  | MET.32807063 | 45735:38 | 217:59 | 2026-08-10 | H
| 188 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) |  | 0 / 3 | [] |  |  | MET.32450147 | 45867:09 | 349:30 | 2026-08-23 | H
| 189 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) |  | 0 / 3 | [] |  |  | MET.32450157 | 45867:09 | 349:30 | 2026-08-23 | H
| 190 | 262200-02-1 | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS (32807104) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS (32807104) |  | 0 / 1 | [] |  |  | MET.32807104 | 46138:01 | 620:22 | 2026-09-19 | H
| 191 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK |  |  |  | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) |  | 0 / 1 | [] |  |  | MET.32807070 | 45935:38 | 417:59 | 2026-08-30 | H
| 192 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 12-22 |  | [] | TC/P |  |  |  | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) |  | 0 / 1 | [] |  |  | MET.32807100 | 46335:38 | 817:59 | 2026-10-08 | H
| 193 | 274451-10-1 | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.44444 | 17.Jul.2026 22:00 | 0.26389 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) |  | 0 / 6 | [] |  |  | MET.32807095 | 03.Dec.2027 | 500 | 2027-12-03 | D
| 194 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.58333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) |  | 0 / 6 | [] |  |  | MET.32807068 | 03.Feb.2027 | 197 | 2027-02-03 | D
| 195 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) |  | 0 / 2 | [] |  |  | MET.32807110 | 03.Feb.2027 | 197 | 2027-02-03 | D
| 196 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) |  | 0 / 2 | [] |  |  | MET.32807091 | 03.Feb.2027 | 197 | 2027-02-03 | D
| 197 | 278468-01-1-002 | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) |  | 0 / 3 | [] |  |  | MET.32807108 | 03.Dec.2027 | 500 | 2027-12-03 | D
| 198 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | OPS/LK |  |  |  | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) |  | 0 / 1 | [] |  |  | MET.32807069 | 45735:38 | 217:59 | 2026-08-10 | H
| 199 | 281100-05-1 | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32796706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32796706) |  | 0 / 3 | [] |  |  | MET.32796706 | 02.Oct.2026 | 73 | 2026-10-02 | D
| 200 | 281100-06-1 | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32796713) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32796713) |  | 0 / 2 | [] |  |  | MET.32796713 | 02.Oct.2026 | 73 | 2026-10-02 | D
| 201 | 282800-01-1 | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK (29295120) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-28 |  | [] | OPS/LK, OPS/LK |  |  |  | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK (29295120) |  | 0 / 2 | [] |  |  | MET.29295120 | 45735:38 | 217:59 | 2026-08-10 | H
| 202 | 282800-03-1 | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK (29295092) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-32 |  | [] | TC/P, TC/P |  |  |  | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK (29295092) |  | 0 / 2 | [] |  |  | MET.29295092 | 02.Oct.2026 | 73 | 2026-10-02 | D
| 204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | TC/P |  |  |  | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) |  | 0 / 1 | [] |  |  | MET.32807081 | 45735:38 | 217:59 | 2026-08-10 | H
| 205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 29-27 |  | [] | TC/P |  |  |  | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) |  | 0 / 1 | [] |  |  | MET.32807098 | 46235:38 | 717:59 | 2026-09-28 | H
| 206 | 292251-02-1 | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29-22 |  | [] | TC/P |  |  |  | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) |  | 0 / 1 | [] |  |  | MET.32807096 | 02.Dec.2027 | 499 | 2027-12-02 | D
| 207 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29295088) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-63 |  | [] | CLEAN-UP |  |  |  | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29295088) |  | 0 / 1 | [] |  |  | MET.29295088 | 46235:38 | 717:59 | 2026-09-28 | H
| 208 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-30 |  | [] | PRE HGR |  |  |  | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) |  | 0 / 1 | [] |  |  | MET.32807112 | 45735:38 | 217:59 | 2026-08-10 | H
| 209 | 313300-08-1 | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION (32807067) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION (32807067) |  | 0 / 3 | [] |  |  | MET.32807067 | 10.Oct.2026 | 81 | 2026-10-10 | D
| 213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 32-44 |  | [] | TC/P |  |  |  | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) |  | 0 / 1 | [] |  |  | MET.32807113 | 45735:38 | 217:59 | 2026-08-10 | H
| 214 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | CLEAN-UP |  |  |  | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) |  | 0 / 1 | [] |  |  | MET.32796720 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) |  | 0 / 3 | [] |  |  | MET.32796726 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 217 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) |  | 0 / 7 | [] |  |  | MET.29294877 | 17'054 | 740 | 2027-03-01 | C
| 218 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) |  | 0 / 7 | [] |  |  | MET.29295132 | 45735:38 | 217:59 | 2026-08-10 | H
| 219 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32807111) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-32 |  | [] | CLEAN-UP, CLEAN-UP, CLEAN-UP |  |  |  | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32807111) |  | 0 / 3 | [] |  |  | MET.32807111 | 46235:38 | 717:59 | 2026-09-28 | H
| 220 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 20-00 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) |  | 0 / 3 | [] |  |  | MET.31784910 | 45735:38 | 217:59 | 2026-08-10 | H
| 221 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | JOB-SETUP, --, --, -- |  |  |  | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) |  | 0 / 4 | [] |  |  | MET.29295087 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 222 | 52-32-00-01-0-SVA | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29295104) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.055556 | 17.Jul.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | CLEAN-UP, TC/P, TC/P, --, JOB-CLOSEUP |  |  |  | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29295104) |  | 0 / 5 | [] |  |  | MET.29295104 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 223 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32807074) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 | 20.Jul.2026 08:00 | 0.85972 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32807074) |  | 0 / 3 | [] |  |  | MET.32807074 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 224 | 527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) |  | 0 / 5 | [] |  |  | MET.32807101 | 10.Apr.2027 | 263 | 2027-04-10 | D
| 225 | 533154-06-1-A | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP (28362142) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.72917 | 17.Jul.2026 22:00 | 0.52083 | 19.Jul.2026 18:38 | 1899-12-31 10:00 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, JOB-SETUP, --, --, --, --, INSPECTION, --, INSPECTION, --, --, -- |  |  |  | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP (28362142) |  | 0 / 12 | [] |  |  | MET.28362142 | 18'542 | 2'228 | 2028-05-25 | C
| 226 | 31675402 | EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE | 31675402 / EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE (31675402) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 06:20 | 17.Jul.2026 22:00 | 0.875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31675402 / EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE (31675402) |  | 0 / 21 | [] |  |  | ME.31675402 | 17'792 | 1'478 | 2027-10-10 | C
| 227 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29295131) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29295131) |  | 0 / 4 | [] |  |  | MET.29295131 | 45735:38 | 217:59 | 2026-08-10 | H
| 228 | 72-00-00-01-0-SVA-001 | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29295098) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 17.Jul.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29295098) |  | 0 / 11 | [] |  |  | MET.29295098 | 46235:38 | 717:59 | 2026-09-28 | H
| 229 | 72-00-00-01-0-SVA-002 | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29295097) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 17.Jul.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29295097) |  | 0 / 11 | [] |  |  | MET.29295097 | 46235:38 | 717:59 | 2026-09-28 | H
| 230 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29295107) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29295107) |  | 0 / 3 | [] |  |  | MET.29295107 | 45935:38 | 417:59 | 2026-08-30 | H
| 231 | 801110-C3-1-002 | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29295116) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29295116) |  | 0 / 3 | [] |  |  | MET.29295116 | 45935:38 | 417:59 | 2026-08-30 | H
| 232 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29295096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23611 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29295096) |  | 0 / 2 | [] |  |  | MET.29295096 | 46235:38 | 717:59 | 2026-09-28 | H
| 233 | 31574335 | C_N (C_N02)/C-CHECK | 31574335 / C_N (C_N02)/C-CHECK (31574335) | Check | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31574335 / C_N (C_N02)/C-CHECK (31574335) |  | 0 / 1 | [] |  |  | ME.31574335 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 234 | 05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION (32874713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | ACFT RELEASE, ACFT RELEASE |  |  |  | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION (32874713) |  | 0 / 2 | [] |  |  | MET.32874713 |  |  | 1517606
| 235 | 08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32712647) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-01 17:00 | 17.Jul.2026 22:00 | 0.83333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 08-10 |  | [] | WT&BAL |  |  |  | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32712647) |  | 0 / 1 | [] |  |  | MET.32712647 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32712874) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 17:47 | 0.45208 |  | 0.33333 | Idle | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | INSPECTION |  |  |  | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32712874) |  | 0 / 1 | [] |  |  | MET.32712874 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390064) |  | 0 / 3 | [] |  |  | MET.28390064 | 22.Aug.2027 | 397 | 2027-08-22 | D
| 238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.0375 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349854) |  | 0 / 3 | [] |  |  | MET.28349854 | 22.Aug.2027 | 397 | 2027-08-22 | D
| 239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) |  | 0 / 3 | [] |  |  | MET.32712959 | 22.Aug.2027 | 397 | 2027-08-22 | D
| 240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022222 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) |  | 0 / 3 | [] |  |  | MET.32712991 | 22.Aug.2027 | 397 | 2027-08-22 | D
| 241 | 212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 21-21 |  | [] | TC/P |  |  |  | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) |  | 0 / 1 | [] |  |  | MET.32712900 | 55763:39 | 10246:00 | 2029-04-24 | H
| 242 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) |  | 0 / 1 | [] |  |  | MET.32712724 | 49636:58 | 4119:19 | 2027-08-29 | H
| 243 | 212600-04-1 | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) |  | 0 / 3 | [] |  |  | MET.32712870 | 55763:39 | 10246:00 | 2029-04-24 | H
| 244 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) |  | 0 / 1 | [] |  |  | MET.32712746 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 245 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) |  | 0 / 1 | [] |  |  | MET.32712899 | 49636:58 | 4119:19 | 2027-08-29 | H
| 246 | 213100-02-1 | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32712679) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32712679) |  | 0 / 1 | [] |  |  | MET.32712679 | 49636:58 | 4119:19 | 2027-08-29 | H
| 247 | 213100-03-1 | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) |  | 0 / 1 | [] |  |  | MET.32712856 | 55763:39 | 10246:00 | 2029-04-24 | H
| 248 | 213100-04-1 | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712795) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712795) |  | 0 / 3 | [] |  |  | MET.32712795 | 55763:39 | 10246:00 | 2029-04-24 | H
| 250 | 215000-08-1 | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) |  | 0 / 3 | [] |  |  | MET.32450151 | 49636:58 | 4119:19 | 2027-08-29 | H
| 251 | 215000-09-1 | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450144) |  | 0 / 3 | [] |  |  | MET.32450144 | 55000:00 | 9482:21 | 2029-02-08 | H
| 252 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32712721) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.12222 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 21-52 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32712721) |  | 0 / 5 | [] |  |  | MET.32712721 | 49636:58 | 4119:19 | 2027-08-29 | H
| 253 | 215500-01-1 | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) |  | 0 / 3 | [] |  |  | MET.32712847 | 55763:39 | 10246:00 | 2029-04-24 | H
| 254 | 215500-02-1 | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-55 |  | [] | OPS/LK |  |  |  | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) |  | 0 / 1 | [] |  |  | MET.32712902 | 55763:39 | 10246:00 | 2029-04-24 | H
| 255 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-63 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK |  |  |  | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) |  | 0 / 5 | [] |  |  | MET.32712714 | 49636:58 | 4119:19 | 2027-08-29 | H
| 256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 22-10 |  | [] | OPS/LK |  |  |  | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) |  | 0 / 1 | [] |  |  | MET.32712839 | 55763:39 | 10246:00 | 2029-04-24 | H
| 257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 23-73 |  | [] | OPS/LK |  |  |  | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) |  | 0 / 1 | [] |  |  | MET.19873618 | 10.Jan.2027 | 173 | 2027-01-10 | D
| 258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-33 |  | [] | OPS/LK |  |  |  | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) |  | 0 / 1 | [] |  |  | MET.32712733 | 55763:39 | 10246:00 | 2029-04-24 | H
| 259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:14 | 0.76667 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 23-51 |  | [] | OPS/LK, OPS/LK |  |  |  | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) |  | 2 / 2 | [] |  |  | MET.25336141 | 55763:39 | 10246:00 | 2029-04-24 | H
| 260 | 237100-02-1 | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] | OPS/LK |  |  |  | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) |  | 0 / 1 | [] |  |  | MET.25336248 | 55763:39 | 10246:00 | 2029-04-24 | H
| 261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.014583 | 17.Jul.2026 22:00 | 0.011806 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 23-71 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) |  | 0 / 3 | [] |  |  | MET.32712774 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 262 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-22 |  | [] | OPS/LK |  |  |  | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) |  | 0 / 1 | [] |  |  | MET.32712665 | 49636:58 | 4119:19 | 2027-08-29 | H
| 263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) |  | 0 / 1 | [] |  |  | MET.32712832 | 55763:39 | 10246:00 | 2029-04-24 | H
| 264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-25 |  | [] | OPS/LK |  |  |  | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) |  | 0 / 1 | [] |  |  | MET.32712691 | 49636:58 | 4119:19 | 2027-08-29 | H
| 265 | 242600-02-1 | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-26 |  | [] | OPS/LK |  |  |  | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) |  | 0 / 1 | [] |  |  | MET.32712676 | 55763:39 | 10246:00 | 2029-04-24 | H
| 266 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 243000-13-1 (01) / DC GENERATION (32712892) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-13-1 (01) / DC GENERATION (32712892) |  | 0 / 3 | [] |  |  | MET.32712892 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 267 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 243000-14-1 (01) / DC GENERATION (32712858) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0020833 | 17.Jul.2026 22:00 | 0.043056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-30 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-14-1 (01) / DC GENERATION (32712858) |  | 0 / 3 | [] |  |  | MET.32712858 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-32 |  | [] | OPS/LK |  |  |  | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) |  | 0 / 1 | [] |  |  | MET.32712840 | 49636:58 | 4119:19 | 2027-08-29 | H
| 269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 24-34 |  | [] | OPS/LK |  |  |  | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) |  | 0 / 1 | [] |  |  | MET.32712850 | 49636:58 | 4119:19 | 2027-08-29 | H
| 270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) |  | 0 / 1 | [] |  |  | MET.32712666 | 55763:39 | 10246:00 | 2029-04-24 | H
| 271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 07:51 | 0.86597 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) |  | 1 / 1 | [] |  |  | MET.32712707 | 55763:39 | 10246:00 | 2029-04-24 | H
| 272 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] |  |  |  |  | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) |  | 0 / 2 | [] |  |  | MET.28325858 | 15.Sep.2026 | 56 | 2026-09-15 | D
| 273 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32712693) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | INSPECTION, -- |  |  |  | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32712693) |  | 0 / 2 | [] |  |  | MET.32712693 | 15.Sep.2026 | 56 | 2026-09-15 | D
| 274 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32712869) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P, TC/P |  |  |  | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32712869) |  | 0 / 2 | [] |  |  | MET.32712869 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 275 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (32712866) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | PRE INSP, -- |  |  |  | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (32712866) |  | 0 / 2 | [] |  |  | MET.32712866 | 15.Sep.2026 | 56 | 2026-09-15 | D
| 276 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R (28325788) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-01 | 17.Jul.2026 22:00 | 0.66667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R (28325788) |  | 0 / 4 | [] |  |  | MET.28325788 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 277 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P |  |  |  | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) |  | 0 / 1 | [] |  |  | MET.28325803 | 15.Sep.2026 | 56 | 2026-09-15 | D
| 278 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 25-SVA-01 (01) / COCKPIT CHECK (32712906) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13889 | 17.Jul.2026 22:00 | 0.14583 | 20.Jul.2026 08:47 | 0.82708 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-01 (01) / COCKPIT CHECK (32712906) |  | 1 / 17 | [] |  |  | MET.32712906 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 279 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32712740) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.48611 | 17.Jul.2026 22:00 | 0.69444 | 20.Jul.2026 08:21 | 0.84514 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 0 / 2 |  | 2 / 21 | [] |  |  | MET.32712740 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 280 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 25-SVA-03 (01) / B/C SEAT REFRESH (32450376) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.49306 | 17.Jul.2026 22:00 | 0.49306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 0 / 20 |  | 0 / 19 | [] |  |  | MET.32450376 | 26.Sep.2029 | 1163 | 2029-09-26 | D
| 281 | 25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH (32712697) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.79167 | 17.Jul.2026 22:00 | 0.79167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH (32712697) |  | 0 / 15 | [] |  |  | MET.32712697 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 282 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 25-SVA-05 (01) / G/C SEAT REFRESH (32712765) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.75 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 759627 adding step 14 | 0 / 10 |  | 0 / 14 | [] |  |  | MET.32712765 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 283 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 25-SVA-06 (01) / GALLEY REFRESH (32712754) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-06 (01) / GALLEY REFRESH (32712754) |  | 0 / 1 | [] |  |  | MET.32712754 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 284 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 25-SVA-07 (01) / LAV REFRESH (32712896) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-07 (01) / LAV REFRESH (32712896) |  | 0 / 1 | [] |  |  | MET.32712896 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 285 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32712882) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32712882) |  | 0 / 1 | [] |  |  | MET.32712882 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 286 | 25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R (32712790) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R (32712790) |  | 0 / 1 | [] |  |  | MET.32712790 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 287 | 25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R (32712824) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 692819 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R (32712824) |  | 0 / 1 | [] |  |  | MET.32712824 | 05.Feb.2028 | 564 | 2028-02-05 | D
| 288 | 252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R (23645845) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:00 | 17.Jul.2026 22:00 | 0.26389 | 20.Jul.2026 03:58 | 1899-12-31 00:40 |  | 1899-12-31 04:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  |  | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R (23645845) |  | 0 / 2 | [] |  |  | MET.23645845 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 289 | 252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP (32712784) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.19444 | 17.Jul.2026 22:00 | 0.19444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP (32712784) |  | 0 / 3 | [] |  |  | MET.32712784 | 55763:39 | 10246:00 | 2029-04-24 | H
| 290 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32712650) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  |  | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32712650) |  | 0 / 2 | [] |  |  | MET.32712650 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 291 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32712834) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.625 | 17.Jul.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32712834) |  | 0 / 4 | [] |  |  | MET.32712834 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 292 | 252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP (32712841) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.024306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | --, PRE INSP, -- |  |  |  | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP (32712841) |  | 0 / 3 | [] |  |  | MET.32712841 | 55763:39 | 10246:00 | 2029-04-24 | H
| 295 | 255000-08-1 | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:30 | 17.Jul.2026 22:00 | 0.80208 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | INSPECTION |  |  |  | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) |  | 0 / 1 | [] |  |  | MET.25336966 | 55763:39 | 10246:00 | 2029-04-24 | H
| 296 | 255000-10-1 | 255000-10-1 (3) / LOWER DECK CARGO LOADING | 255000-10-1 (3) / LOWER DECK CARGO LOADING (31497911) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.17917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 255000-10-1 (3) / LOWER DECK CARGO LOADING (31497911) |  | 0 / 7 | [] |  |  | MET.31497911 | 55763:39 | 10246:00 | 2029-04-24 | H
| 297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 07:49 | 1899-12-31 20:49 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | OPS/LK |  |  |  | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) |  | 1 / 1 | [] |  |  | MET.31498183 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 298 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.052083 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) |  | 0 / 4 | [] |  |  | MET.31498136 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 299 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28325883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.125 | 19.Jul.2026 04:30 | 1900-01-01 00:08 |  | 1899-12-31 22:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 4 | [] |  |  | MET.28325883 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 300 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 26-15 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP |  |  |  | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) |  | 0 / 5 | [] |  |  | MET.32712819 | 49763:39 | 4246:00 | 2027-09-11 | H
| 301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) |  | 0 / 1 | [] |  |  | MET.32712831 | 49636:58 | 4119:19 | 2027-08-29 | H
| 302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) |  | 0 / 1 | [] |  |  | MET.32712838 | 49636:58 | 4119:19 | 2027-08-29 | H
| 303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) |  | 0 / 3 | [] |  |  | MET.32712878 | 55763:39 | 10246:00 | 2029-04-24 | H
| 304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) |  | 0 / 3 | [] |  |  | MET.32712803 | 55763:39 | 10246:00 | 2029-04-24 | H
| 305 | 262100-05-1 | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC (32712745) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 1 / 1 |  | 0 / 1 | [] |  |  | MET.32712745 | 55763:39 | 10246:00 | 2029-04-24 | H
| 306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) |  | 0 / 4 | [] |  |  | MET.32712698 | 55763:39 | 10246:00 | 2029-04-24 | H
| 308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) |  | 0 / 3 | [] |  |  | MET.32712744 | 55763:39 | 10246:00 | 2029-04-24 | H
| 309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.020833 | 19.Jul.2026 06:46 | 1899-12-31 21:52 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) |  | 1 / 1 | [] |  |  | MET.32712716 | 21.Feb.2030 | 1311 | 2030-02-21 | D
| 310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.036806 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) |  | 0 / 4 | [] |  |  | MET.32712799 | 46763:39 | 1246:00 | 2026-11-19 | H
| 311 | 262300-03-1 | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) |  | 0 / 4 | [] |  |  | MET.32712670 | 55763:39 | 10246:00 | 2029-04-24 | H
| 313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-14 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) |  | 0 / 3 | [] |  |  | MET.32712730 | 50528:07 | 5010:28 | 2027-11-25 | H
| 314 | 271400-02-2-001 | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 02:46 | 1899-12-31 01:52 |  | 0.25 | Idle | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) |  | 1 / 4 | [] |  |  | MET.32712702 | 55763:39 | 10246:00 | 2029-04-24 | H
| 315 | 271400-02-2-002 | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 05:20 | 0.97083 |  | 0.083333 | Idle | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) |  | 1 / 4 | [] |  |  | MET.32712756 | 55763:39 | 10246:00 | 2029-04-24 | H
| 316 | 271400-03-1-001 | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK (32712849) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK (32712849) |  | 0 / 3 | [] |  |  | MET.32712849 | 47612:08 | 2094:29 | 2027-02-11 | H
| 317 | 271400-03-1-002 | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK (32712770) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK (32712770) |  | 0 / 3 | [] |  |  | MET.32712770 | 47612:08 | 2094:29 | 2027-02-11 | H
| 318 | 272100-02-1 | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP (25336083) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 03:30 | 17.Jul.2026 22:00 | 1900-01-01 03:15 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 27-21 |  | [] | TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION |  |  |  | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP (25336083) |  | 0 / 9 | [] |  |  | MET.25336083 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 319 | 272100-04-1 | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25335749) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-26 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25335749) |  | 0 / 4 | [] |  |  | MET.25335749 | 48000:00 | 2482:21 | 2027-03-21 | H
| 320 | 272100-05-1 | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.022222 | 18.Jul.2026 12:58 | 1900-01-01 15:40 |  | 0.41667 | Idle | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) |  | 3 / 3 | [] |  |  | MET.31497921 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 321 | 272100-07-1 | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE (31498738) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 13:17 | 0.63958 |  | 1899-12-31 12:00 | Idle | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.31498738 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 322 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | JOB-SETUP, --, -- |  |  |  | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) |  | 0 / 3 | [] |  |  | MET.26290694 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 323 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 27-21 |  | [] | TC/P |  |  |  | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) |  | 0 / 1 | [] |  |  | MET.26224974 | 14.Jan.2027 | 177 | 2027-01-14 | D
| 324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28325998) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 27-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28325998) |  | 0 / 8 | [] |  |  | MET.28325998 | 49763:39 | 4246:00 | 2027-09-11 | H
| 325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 27-34 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) |  | 0 / 4 | [] |  |  | MET.31481303 | 53586:06 | 8068:27 | 2028-09-21 | H
| 326 | 273400-03-1 | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.043056 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 27-34 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) |  | 0 / 3 | [] |  |  | MET.32712863 | 55763:39 | 10246:00 | 2029-04-24 | H
| 328 | 274000-24-1 | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P |  |  |  | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) |  | 0 / 1 | [] |  |  | MET.32712885 | 61636:58 | 16119:19 | 2030-11-24 | H
| 329 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 27-41 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) |  | 0 / 3 | [] |  |  | MET.32712802 | 11.Jan.2027 | 174 | 2027-01-11 | D
| 330 | 274400-03-1 | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC (32712678) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC (32712678) |  | 0 / 2 | [] |  |  | MET.32712678 | 55763:39 | 10246:00 | 2029-04-24 | H
| 331 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.00625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | INSPECTION, INSPECTION |  |  |  | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) |  | 0 / 2 | [] |  |  | MET.32712739 | 49636:58 | 4119:19 | 2027-08-29 | H
| 332 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | P/N: Changed from "MIL-PRF-680.TYPEI" TO "PD680" as requestd in T/Q:584726 T/Q: 581544 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) |  | 0 / 3 | [] |  |  | MET.32712751 | 11.Jan.2027 | 174 | 2027-01-11 | D
| 333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | PRE INSP |  |  |  | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) |  | 0 / 1 | [] |  |  | MET.32712769 | 49636:58 | 4119:19 | 2027-08-29 | H
| 334 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) |  | 0 / 2 | [] |  |  | MET.32712759 | 49636:58 | 4119:19 | 2027-08-29 | H
| 335 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P, TC/P |  |  |  | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) |  | 0 / 2 | [] |  |  | MET.32712728 | 49763:39 | 4246:00 | 2027-09-11 | H
| 336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK |  |  |  | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) |  | 0 / 1 | [] |  |  | MET.32712861 | 46755:06 | 1237:27 | 2026-11-18 | H
| 337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) |  | 0 / 3 | [] |  |  | MET.32712713 | 49636:58 | 4119:19 | 2027-08-29 | H
| 338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712880) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712880) |  | 0 / 3 | [] |  |  | MET.32712880 | 49636:58 | 4119:19 | 2027-08-29 | H
| 339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) |  | 0 / 3 | [] |  |  | MET.32712843 | 49636:58 | 4119:19 | 2027-08-29 | H
| 340 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) |  | 0 / 3 | [] |  |  | MET.32712898 | 49636:58 | 4119:19 | 2027-08-29 | H
| 341 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) |  | 0 / 3 | [] |  |  | MET.32712723 | 49636:58 | 4119:19 | 2027-08-29 | H
| 342 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) |  | 0 / 4 | [] |  |  | MET.32712748 | 49636:58 | 4119:19 | 2027-08-29 | H
| 343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) |  | 0 / 4 | [] |  |  | MET.32712877 | 49636:58 | 4119:19 | 2027-08-29 | H
| 344 | 275400-01-1-001 | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) |  | 0 / 1 | [] |  |  | MET.32712660 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 345 | 275400-01-1-002 | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) |  | 0 / 1 | [] |  |  | MET.32712871 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 346 | 275446-02-1-001 | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537) dated 20-DEC-2023 as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change the access from 733 and 744 to be 734 and 744. | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) |  | 0 / 5 | [] |  |  | MET.25337004 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 347 | 275446-02-1-002 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537 dated 20-DEC-2023)as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track 1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change Panle from 733 and 734 to be 734 and 744 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) |  | 0 / 5 | [] |  |  | MET.25336868 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 348 | 275449-06-1-001 | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS (32712643) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.73333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-13 |  | [] | TC/P |  |  |  | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS (32712643) |  | 0 / 1 | [] |  |  | MET.32712643 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 349 | 275449-06-1-002 | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES (32712640) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.73333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-13 |  | [] | TC/P |  |  |  | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES (32712640) |  | 0 / 1 | [] |  |  | MET.32712640 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 350 | 275451-01-1 | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32712844) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32712844) |  | 0 / 4 | [] |  |  | MET.32712844 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 351 | 276400-02-1-001 | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.25972 | 17.Jul.2026 22:00 | 0.12986 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) |  | 0 / 7 | [] |  |  | MET.32712686 | 55763:39 | 10246:00 | 2029-04-24 | H
| 352 | 276400-02-1-002 | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.25972 | 17.Jul.2026 22:00 | 0.14097 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) |  | 0 / 7 | [] |  |  | MET.32712857 | 55763:39 | 10246:00 | 2029-04-24 | H
| 353 | 278100-03-1 | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32712852) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-81 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32712852) |  | 0 / 3 | [] |  |  | MET.32712852 | 49636:58 | 4119:19 | 2027-08-29 | H
| 354 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) |  | 0 / 3 | [] |  |  | MET.32712848 | 49636:58 | 4119:19 | 2027-08-29 | H
| 355 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) |  | 0 / 3 | [] |  |  | MET.32712711 | 49636:58 | 4119:19 | 2027-08-29 | H
| 356 | 278400-01-1-001 | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION (32712701) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 13; O: 0; C: 13 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION (32712701) |  | 0 / 4 | [] |  |  | MET.32712701 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 357 | 278400-01-1-002 | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION (32712738) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 13; O: 0; C: 13 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION (32712738) |  | 0 / 4 | [] |  |  | MET.32712738 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 358 | 278451-01-1 | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32712785) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32712785) |  | 0 / 4 | [] |  |  | MET.32712785 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 359 | 278468-02-1-001 | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION (32712708) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18681 | 17.Jul.2026 22:00 | 0.12431 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 0 / 5 | [] |  |  | MET.32712708 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 360 | 278468-02-1-002 | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION (32712820) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18681 | 17.Jul.2026 22:00 | 0.12431 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 0 / 5 | [] |  |  | MET.32712820 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 363 | 281600-01-1-001 | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK (26224970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.011806 | 18.Jul.2026 15:52 | 1900-01-01 12:46 |  | 0.66667 | Idle | 0 | T: 2; O: 0; C: 2 | 28-16 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK (26224970) |  | 3 / 5 | [] |  |  | MET.26224970 | 49636:58 | 4119:19 | 2027-08-29 | H
| 364 | 281600-01-1-002 | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK (26290613) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.010417 | 18.Jul.2026 15:54 | 1900-01-01 12:44 |  | 0.66667 | Idle | 0 | T: 2; O: 0; C: 2 | 28-16 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK (26290613) |  | 3 / 5 | [] |  |  | MET.26290613 | 49636:58 | 4119:19 | 2027-08-29 | H
| 365 | 281800-01-1 | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK (32712845) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.15208 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 28-18 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK (32712845) |  | 0 / 3 | [] |  |  | MET.32712845 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 366 | 282100-02-1 | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC (25335835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC (25335835) |  | 0 / 4 | [] |  |  | MET.25335835 | 55763:39 | 10246:00 | 2029-04-24 | H
| 370 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32712829) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32712829) |  | 0 / 3 | [] |  |  | MET.32712829 | 20'900 | 4'586 | 2030-05-09 | C
| 371 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32712767) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32712767) |  | 0 / 3 | [] |  |  | MET.32712767 | 20'900 | 4'586 | 2030-05-09 | C
| 372 | 282800-04-1 | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC (31497920) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-28 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC (31497920) |  | 0 / 3 | [] |  |  | MET.31497920 | 54263:39 | 8746:00 | 2028-11-27 | H
| 373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:58 | 1899-12-31 21:40 |  | 0.25 | Idle | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | OPS/LK |  |  |  | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) |  | 1 / 1 | [] |  |  | MET.28325959 | 54263:39 | 8746:00 | 2028-11-27 | H
| 374 | 282800-06-1 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022917 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 28-28 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  | as req in T/Q: 764919 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) |  | 0 / 4 | [] |  |  | MET.25336404 | 46763:39 | 1246:00 | 2026-11-19 | H
| 375 | 282800-07-1 | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC (25335729) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022222 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC (25335729) |  | 0 / 7 | [] |  |  | MET.25335729 | 54263:39 | 8746:00 | 2028-11-27 | H
| 376 | 291000-04-1 | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) |  | 0 / 1 | [] |  |  | MET.32712782 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 14:03 | 1900-01-01 14:35 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) |  | 1 / 1 | [] |  |  | MET.32712779 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 14:08 | 1900-01-01 14:30 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) |  | 1 / 1 | [] |  |  | MET.32712688 | 49636:58 | 4119:19 | 2027-08-29 | H
| 379 | 291000-10-1 | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK (25336587) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.01875 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29-10 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK (25336587) |  | 0 / 4 | [] |  |  | MET.25336587 | 55763:39 | 10246:00 | 2029-04-24 | H
| 380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.034028 | 18.Jul.2026 14:06 | 1900-01-01 14:32 |  | 0.33333 | Idle | 0 | T: 3; O: 0; C: 3 | 29-23 |  | [] | OPS/LK, OPS/LK |  |  |  | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) |  | 2 / 2 | [] |  |  | MET.32712867 | 55763:39 | 10246:00 | 2029-04-24 | H
| 381 | 291000-20-1 | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32712729) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32712729) |  | 0 / 1 | [] |  |  | MET.32712729 | 09.Sep.2026 | 50 | 2026-09-09 | D
| 382 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | OPS/LK |  |  |  | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) |  | 0 / 1 | [] |  |  | MET.32712886 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 383 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32712891) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32712891) |  | 0 / 3 | [] |  |  | MET.32712891 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 384 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) |  | 0 / 3 | [] |  |  | MET.32712656 | 49636:58 | 4119:19 | 2027-08-29 | H
| 385 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 29-34 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) |  | 0 / 3 | [] |  |  | MET.32712680 | 49636:58 | 4119:19 | 2027-08-29 | H
| 386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) |  | 0 / 3 | [] |  |  | MET.26225037 | 49636:58 | 4119:19 | 2027-08-29 | H
| 387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (26290689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (26290689) |  | 0 / 3 | [] |  |  | MET.26290689 | 49636:58 | 4119:19 | 2027-08-29 | H
| 388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.01875 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 30-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) |  | 0 / 3 | [] |  |  | MET.32712674 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) |  | 0 / 1 | [] |  |  | MET.32712808 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 390 | 313300-07-1 | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION (25336435) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.052778 | 17.Jul.2026 22:00 | 0.026389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION (25336435) |  | 0 / 1 | [] |  |  | MET.25336435 | 55763:39 | 10246:00 | 2029-04-24 | H
| 391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:15 | 1899-12-31 20:23 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 31-50 |  | [] | OPS/LK |  |  |  | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) |  | 1 / 1 | [] |  |  | MET.32712854 | 55763:39 | 10246:00 | 2029-04-24 | H
| 392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 15:09 | 1900-01-01 13:29 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) |  | 2 / 2 | [] |  |  | MET.32712781 | 55763:39 | 10246:00 | 2029-04-24 | H
| 393 | 315000-04-1 | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) |  | 0 / 2 | [] |  |  | MET.32712888 | 55763:39 | 10246:00 | 2029-04-24 | H
| 394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) |  | 0 / 3 | [] |  |  | MET.25336785 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 19.Jul.2026 19:10 | 1899-12-31 09:28 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) |  | 0 / 3 | [] |  |  | MET.25336733 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) |  | 0 / 1 | [] |  |  | MET.32712855 | 14.Sep.2026 | 55 | 2026-09-14 | D
| 397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) |  | 0 / 1 | [] |  |  | MET.32712715 | 14.Sep.2026 | 55 | 2026-09-14 | D
| 398 | 321127-01-1-001 | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:41 | 17.Jul.2026 22:00 | 0.74306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-11 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) |  | 0 / 7 | [] |  |  | MET.32712696 | 26'913 | 10'599 | 2035-05-05 | C
| 399 | 321127-01-1-002 | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK (32712817) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:41 | 17.Jul.2026 22:00 | 0.74306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-11 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK (32712817) |  | 0 / 7 | [] |  |  | MET.32712817 | 26'913 | 10'599 | 2035-05-05 | C
| 400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-12 |  | [] | OPS/LK |  |  |  | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) |  | 0 / 1 | [] |  |  | MET.32712797 | 14.Sep.2026 | 55 | 2026-09-14 | D
| 401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0083333 | 19.Jul.2026 06:43 | 1899-12-31 21:55 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) |  | 1 / 1 | [] |  |  | MET.32712851 | 49636:58 | 4119:19 | 2027-08-29 | H
| 402 | 323100-04-1 | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK (32712828) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.032639 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 32-31 |  | [] | OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-SETUP, TC/P |  |  |  | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK (32712828) |  | 0 / 5 | [] |  |  | MET.32712828 | 55763:39 | 10246:00 | 2029-04-24 | H
| 404 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-61 |  | [] | OPS/LK |  |  |  | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) |  | 0 / 1 | [] |  |  | MET.32712685 | 49636:58 | 4119:19 | 2027-08-29 | H
| 405 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) |  | 0 / 1 | [] |  |  | MET.32712772 | 21'900 | 5'586 | 2031-03-08 | C
| 406 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) |  | 0 / 1 | [] |  |  | MET.32712667 | 21'900 | 5'586 | 2031-03-08 | C
| 407 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.37153 | 17.Jul.2026 22:00 | 0.32292 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | JOB-SETUP, TC/P, TC/P, CLOSE-UP |  |  |  | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) |  | 0 / 4 | [] |  |  | MET.28325784 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 408 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42153 | 17.Jul.2026 22:00 | 0.21042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | OPS/LK |  |  |  | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) |  | 0 / 1 | [] |  |  | MET.32712689 | 26.Sep.2027 | 432 | 2027-09-26 | D
| 409 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 17.Jul.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-41 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) |  | 0 / 3 | [] |  |  | MET.32712726 | 49636:58 | 4119:19 | 2027-08-29 | H
| 410 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-43 |  | [] | OPS/LK |  |  |  | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) |  | 0 / 1 | [] |  |  | MET.32712788 | 49636:58 | 4119:19 | 2027-08-29 | H
| 411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) |  | 0 / 3 | [] |  |  | MET.32712725 | 14.Oct.2027 | 450 | 2027-10-14 | D
| 412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-45 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) |  | 0 / 2 | [] |  |  | MET.32712873 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 33-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) |  | 0 / 3 | [] |  |  | MET.32712675 | 55763:39 | 10246:00 | 2029-04-24 | H
| 414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) |  | 0 / 3 | [] |  |  | MET.32712755 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) |  | 0 / 4 | [] |  |  | MET.32712762 | 55763:39 | 10246:00 | 2029-04-24 | H
| 416 | 341300-02-1 | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) |  | 0 / 3 | [] |  |  | MET.32712811 | 55763:39 | 10246:00 | 2029-04-24 | H
| 417 | 341300-03-1 | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) |  | 0 / 4 | [] |  |  | MET.32712846 | 55763:39 | 10246:00 | 2029-04-24 | H
| 418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:37 | 1899-12-31 20:01 |  | 0.16667 | Idle | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) |  | 1 / 1 | [] |  |  | MET.32712719 | 49636:58 | 4119:19 | 2027-08-29 | H
| 419 | 341300-09-1 | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) |  | 0 / 1 | [] |  |  | MET.32712704 | 55763:39 | 10246:00 | 2029-04-24 | H
| 420 | 342000-03-1 | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-20 |  | [] | OPS/LK |  |  |  | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) |  | 0 / 1 | [] |  |  | MET.32712766 | 55763:39 | 10246:00 | 2029-04-24 | H
| 421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.0076389 | 19.Jul.2026 08:08 | 1899-12-31 20:30 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) |  | 4 / 4 | [] |  |  | MET.32712695 | 49636:58 | 4119:19 | 2027-08-29 | H
| 422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) |  | 0 / 3 | [] |  |  | MET.32712749 | 49636:58 | 4119:19 | 2027-08-29 | H
| 423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:34 | 1899-12-31 20:04 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 34-48 |  | [] | TC/P |  |  |  | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) |  | 1 / 1 | [] |  |  | MET.28325742 | 49636:58 | 4119:19 | 2027-08-29 | H
| 424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.00625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) |  | 0 / 4 | [] |  |  | MET.32712786 | 55763:39 | 10246:00 | 2029-04-24 | H
| 425 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | OPS/LK |  |  |  | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) |  | 0 / 1 | [] |  |  | MET.32712798 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 427 | 352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC (32712919) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.12778 | 17.Jul.2026 22:00 | 0.063194 | 20.Jul.2026 07:22 | 0.88611 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] | JOB-SETUP, TC/P, TC/P, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 0 / 6 | [] |  |  | MET.32712919 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 428 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28325739) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.10417 | 20.Jul.2026 04:00 | 1899-12-31 00:38 |  | 1900-01-01 00:30 | Idle | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, --, --, JOB-CLOSEUP, -- |  |  | As requested in T/Q: 737585 by ENGG CONFIGRATION. | 0 / 1 |  | 3 / 5 | [] |  |  | MET.28325739 | 09.Sep.2026 | 50 | 2026-09-09 | D
| 431 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) |  | 0 / 3 | [] |  |  | MET.25336420 | 21.Oct.2026 | 92 | 2026-10-21 | D
| 432 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) |  | 0 / 3 | [] |  |  | MET.25336437 | 21.Oct.2026 | 92 | 2026-10-21 | D
| 433 | 361100-SVA-01 | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT (28326047) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59028 | 17.Jul.2026 22:00 | 0.22917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT (28326047) |  | 0 / 10 | [] |  |  | MET.28326047 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 434 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) |  | 0 / 3 | [] |  |  | MET.32712764 | 53763:39 | 8246:00 | 2028-10-09 | H
| 435 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) |  | 0 / 3 | [] |  |  | MET.32712827 | 53763:39 | 8246:00 | 2028-10-09 | H
| 438 | 361251-01-3 | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP (32712720) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 36-12 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP (32712720) |  | 0 / 7 | [] |  |  | MET.32712720 | 50636:58 | 5119:19 | 2027-12-06 | H
| 439 | 383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32712887) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-31 |  | [] | CLEAN-UP |  |  |  | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32712887) |  | 0 / 1 | [] |  |  | MET.32712887 | 49636:58 | 4119:19 | 2027-08-29 | H
| 440 | 384142-01-1 | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT (32712673) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0125 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 38-41 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT (32712673) |  | 0 / 6 | [] |  |  | MET.32712673 | 26.Sep.2029 | 1163 | 2029-09-26 | D
| 441 | 384241-01-1 | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) |  | 0 / 3 | [] |  |  | MET.28325945 | 55763:39 | 10246:00 | 2029-04-24 | H
| 442 | 384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | TC/P, OPS/LK |  |  |  | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) |  | 0 / 2 | [] |  |  | MET.25336873 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 443 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31498553) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12986 | 17.Jul.2026 22:00 | 0.12986 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 49-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31498553) |  | 0 / 3 | [] |  |  | MET.31498553 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 444 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.011806 | 17.Jul.2026 22:00 | 0.011806 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 49-16 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) |  | 0 / 3 | [] |  |  | MET.31498028 | 26.Jan.2027 | 189 | 2027-01-26 | D
| 446 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) |  | 0 / 4 | [] |  |  | MET.28325813 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 447 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32712712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 52-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32712712) |  | 0 / 9 | [] |  |  | MET.32712712 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 448 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) |  | 0 / 4 | [] |  |  | MET.28326032 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 449 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) |  | 0 / 4 | [] |  |  | MET.28325885 | 13.Sep.2026 | 54 | 2026-09-13 | D
| 450 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32712889) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 17.Jul.2026 22:00 | 0.040278 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32712889) |  | 0 / 9 | [] |  |  | MET.32712889 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 451 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32712672) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 17.Jul.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32712672) |  | 0 / 9 | [] |  |  | MET.32712672 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 452 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32712893) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 17.Jul.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32712893) |  | 0 / 9 | [] |  |  | MET.32712893 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 453 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 17.Jul.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) |  | 0 / 9 | [] |  |  | MET.32712658 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 454 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) |  | 0 / 4 | [] |  |  | MET.28325786 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 455 | 521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) |  | 0 / 4 | [] |  |  | MET.32712813 | 55763:39 | 10246:00 | 2029-04-24 | H
| 456 | 521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) |  | 0 / 4 | [] |  |  | MET.32712763 | 55763:39 | 10246:00 | 2029-04-24 | H
| 457 | 521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK (32712833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK (32712833) |  | 0 / 6 | [] |  |  | MET.32712833 | 55763:39 | 10246:00 | 2029-04-24 | H
| 458 | 521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.024306 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-10 |  | [] | OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, OPS/LK, OPS/LK |  |  |  | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) |  | 0 / 6 | [] |  |  | MET.32712735 | 55763:39 | 10246:00 | 2029-04-24 | H
| 459 | 521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) |  | 0 / 4 | [] |  |  | MET.32712737 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 460 | 521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) |  | 0 / 4 | [] |  |  | MET.32712783 | 55763:39 | 10246:00 | 2029-04-24 | H
| 461 | 521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) |  | 0 / 4 | [] |  |  | MET.32712823 | 14.Jun.2028 | 694 | 2028-06-14 | D
| 462 | 521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP (32712682) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.061111 | 17.Jul.2026 22:00 | 0.061806 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP (32712682) |  | 0 / 10 | [] |  |  | MET.32712682 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 463 | 521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.010417 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) |  | 0 / 4 | [] |  |  | MET.32712801 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 464 | 521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15347 | 17.Jul.2026 22:00 | 0.086806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) |  | 0 / 3 | [] |  |  | MET.32712671 | 55763:39 | 10246:00 | 2029-04-24 | H
| 465 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) |  | 0 / 4 | [] |  |  | MET.32712732 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 466 | 522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE (26224270) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.073611 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE (26224270) |  | 0 / 3 | [] |  |  | MET.26224270 | 49636:58 | 4119:19 | 2027-08-29 | H
| 467 | 522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC (23580025) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.094444 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC (23580025) |  | 0 / 5 | [] |  |  | MET.23580025 | 61636:58 | 16119:19 | 2030-11-24 | H
| 468 | 522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION (23625074) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.084028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION (23625074) |  | 0 / 4 | [] |  |  | MET.23625074 | 61636:58 | 16119:19 | 2030-11-24 | H
| 469 | 522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14653 | 17.Jul.2026 22:00 | 0.10486 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) |  | 0 / 4 | [] |  |  | MET.25335941 | 55763:39 | 10246:00 | 2029-04-24 | H
| 470 | 523100-01-1 | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC (32712663) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 52-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC (32712663) |  | 0 / 4 | [] |  |  | MET.32712663 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 471 | 523200-01-1 | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC (32712884) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0125 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 52-32 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC (32712884) |  | 0 / 4 | [] |  |  | MET.32712884 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 472 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) |  | 0 / 1 | [] |  |  | MET.32712822 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP (32712736) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP (32712736) |  | 0 / 3 | [] |  |  | MET.32712736 | 55763:39 | 10246:00 | 2029-04-24 | H
| 474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.0069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) |  | 0 / 1 | [] |  |  | MET.32712895 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 475 | 525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) |  | 0 / 1 | [] |  |  | MET.32712807 | 55763:39 | 10246:00 | 2029-04-24 | H
| 476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) |  | 0 / 1 | [] |  |  | MET.32712771 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 477 | 525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) |  | 0 / 1 | [] |  |  | MET.32712727 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 478 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71 |  | [] | OPS/LK |  |  |  | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) |  | 0 / 1 | [] |  |  | MET.32712814 | 49636:58 | 4119:19 | 2027-08-29 | H
| 479 | 527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32712876) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32712876) |  | 0 / 4 | [] |  |  | MET.32712876 | 10.Jan.2027 | 173 | 2027-01-10 | D
| 480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK |  |  |  | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) |  | 0 / 1 | [] |  |  | MET.32712706 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 481 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] |  |  |  |  | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) |  | 0 / 3 | [] |  |  | MET.32712794 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 482 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) |  | 0 / 3 | [] |  |  | MET.32712815 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 483 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) |  | 0 / 3 | [] |  |  | MET.32712862 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 484 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) |  | 0 / 3 | [] |  |  | MET.32712664 | 13.Sep.2026 | 54 | 2026-09-13 | D
| 485 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-19 |  | [] | OPS/LK |  |  |  | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) |  | 0 / 1 | [] |  |  | MET.32712830 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 486 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) |  | 0 / 3 | [] |  |  | MET.32712789 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP |  |  |  | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) |  | 0 / 2 | [] |  |  | MET.32712835 | 54863:39 | 9346:00 | 2029-01-25 | H
| 488 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16806 | 17.Jul.2026 22:00 | 0.16806 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) |  | 0 / 3 | [] |  |  | MET.32450143 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 489 | 532181-02-1 | 532181-02-1 (0) / FORWARD FUSELAGE | 532181-02-1 (0) / FORWARD FUSELAGE (32450165) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 532181-02-1 (0) / FORWARD FUSELAGE (32450165) |  | 0 / 3 | [] |  |  | MET.32450165 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 490 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-39 |  | [] | OPS/LK |  |  |  | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) |  | 0 / 1 | [] |  |  | MET.32712818 | 09.Sep.2026 | 50 | 2026-09-09 | D
| 491 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) |  | 0 / 3 | [] |  |  | MET.32712868 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 492 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11875 | 17.Jul.2026 22:00 | 0.097917 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) |  | 0 / 5 | [] |  |  | MET.32787526 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 493 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 534307-03-1 (0) / REAR FUSELAGE (32450173) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534307-03-1 (0) / REAR FUSELAGE (32450173) |  | 0 / 3 | [] |  |  | MET.32450173 | 20.Apr.2029 | 1004 | 2029-04-20 | D
| 494 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 534308-02-1 (0) / REAR FUSELAGE (32450166) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 13:31 | 17.Jul.2026 22:00 | 1899-12-31 13:31 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534308-02-1 (0) / REAR FUSELAGE (32450166) |  | 0 / 4 | [] |  |  | MET.32450166 | 20.Apr.2029 | 1004 | 2029-04-20 | D
| 495 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) |  | 0 / 1 | [] |  |  | MET.32712812 | 09.Sep.2026 | 50 | 2026-09-09 | D
| 496 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) |  | 0 / 1 | [] |  |  | MET.32712669 | 10.Sep.2026 | 51 | 2026-09-10 | D
| 497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) |  | 0 / 3 | [] |  |  | MET.26224706 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (26224854) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (26224854) |  | 0 / 3 | [] |  |  | MET.26224854 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) |  | 0 / 3 | [] |  |  | MET.26224971 | 49636:58 | 4119:19 | 2027-08-29 | H
| 500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) |  | 0 / 3 | [] |  |  | MET.26225034 | 49636:58 | 4119:19 | 2027-08-29 | H
| 501 | 545000-05-1-001 | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621791) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.70833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621791) |  | 0 / 4 | [] |  |  | MET.23621791 | 49636:58 | 4119:19 | 2027-08-29 | H
| 502 | 545000-05-1-002 | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642860) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.70833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642860) |  | 0 / 4 | [] |  |  | MET.23642860 | 49636:58 | 4119:19 | 2027-08-29 | H
| 503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) |  | 0 / 3 | [] |  |  | MET.19876877 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) |  | 0 / 3 | [] |  |  | MET.19876887 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) |  | 0 / 3 | [] |  |  | MET.25336918 | 53463:39 | 7946:00 | 2028-09-09 | H
| 506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) |  | 0 / 3 | [] |  |  | MET.25335813 | 53463:39 | 7946:00 | 2028-09-09 | H
| 507 | 552600-01-1 | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. (32712775) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12847 | 17.Jul.2026 22:00 | 0.11458 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 20-00 |  | [] |  |  |  |  | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. (32712775) |  | 0 / 6 | [] |  |  | MET.32712775 | 61636:58 | 16119:19 | 2030-11-24 | H
| 508 | 553600-01-1 | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION (32712710) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.24306 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 55-47 |  | [] | TC/P |  |  |  | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION (32712710) |  | 0 / 1 | [] |  |  | MET.32712710 | 61636:58 | 16119:19 | 2030-11-24 | H
| 509 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) |  | 0 / 1 | [] |  |  | MET.32712810 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 510 | 572178-01-1-001 | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32712613) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32712613) |  | 0 / 5 | [] |  |  | MET.32712613 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 511 | 572178-01-1-002 | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32712634) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32712634) |  | 0 / 5 | [] |  |  | MET.32712634 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 512 | 572179-01-1-001 | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712635) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712635) |  | 0 / 5 | [] |  |  | MET.32712635 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 513 | 572179-01-1-002 | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712598) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712598) |  | 0 / 5 | [] |  |  | MET.32712598 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | OPEN-UP, INSPECTION, CLOSE-UP |  |  |  | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325730) |  | 0 / 3 | [] |  |  | MET.28325730 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325833) |  | 0 / 3 | [] |  |  | MET.28325833 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 518 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) |  | 0 / 3 | [] |  |  | MET.26224780 | 13.Sep.2026 | 54 | 2026-09-13 | D
| 519 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) |  | 0 / 3 | [] |  |  | MET.19875152 | 13.Sep.2026 | 54 | 2026-09-13 | D
| 520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28325843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28325843) |  | 0 / 1 | [] |  |  | MET.28325843 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28325855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28325855) |  | 0 / 1 | [] |  |  | MET.28325855 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) |  | 0 / 3 | [] |  |  | MET.26224711 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) |  | 0 / 3 | [] |  |  | MET.26224781 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627239) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 11:01 | 0.73403 |  | 0.041667 | Idle | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.23627239 | 20'400 | 4'086 | 2029-12-09 | C
| 525 | 711300-C1-1-001 | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356889) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 17.Jul.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356889) |  | 0 / 2 | [] |  |  | MET.28356889 | 09.Sep.2028 | 781 | 2028-09-09 | D
| 526 | 711300-C1-1-002 | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384391) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 17.Jul.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384391) |  | 0 / 2 | [] |  |  | MET.28384391 | 09.Sep.2028 | 781 | 2028-09-09 | D
| 527 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) |  | 0 / 3 | [] |  |  | MET.28326014 | 52636:58 | 7119:19 | 2028-06-20 | H
| 528 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28326013) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28326013) |  | 0 / 3 | [] |  |  | MET.28326013 | 52636:58 | 7119:19 | 2028-06-20 | H
| 529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28326019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28326019) |  | 0 / 3 | [] |  |  | MET.28326019 | 52636:58 | 7119:19 | 2028-06-20 | H
| 530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28326018) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28326018) |  | 0 / 3 | [] |  |  | MET.28326018 | 52636:58 | 7119:19 | 2028-06-20 | H
| 531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.76667 |  | 0.041667 | Idle | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) |  | 1 / 1 | [] |  |  | MET.28326017 | 52636:58 | 7119:19 | 2028-06-20 | H
| 532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.76667 |  | 0.041667 | Idle | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) |  | 1 / 1 | [] |  |  | MET.28326023 | 52636:58 | 7119:19 | 2028-06-20 | H
| 533 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) |  | 0 / 3 | [] |  |  | MET.26290668 | 52636:58 | 7119:19 | 2028-06-20 | H
| 534 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) |  | 0 / 3 | [] |  |  | MET.26290572 | 52636:58 | 7119:19 | 2028-06-20 | H
| 535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (26290680) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (26290680) |  | 0 / 3 | [] |  |  | MET.26290680 | 52636:58 | 7119:19 | 2028-06-20 | H
| 536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (26290654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (26290654) |  | 0 / 3 | [] |  |  | MET.26290654 | 52636:58 | 7119:19 | 2028-06-20 | H
| 537 | 712213-01-1-001 | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP (26290621) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP (26290621) |  | 0 / 8 | [] |  |  | MET.26290621 | 52636:58 | 7119:19 | 2028-06-20 | H
| 538 | 712213-01-1-002 | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP (26290681) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP (26290681) |  | 0 / 8 | [] |  |  | MET.26290681 | 52636:58 | 7119:19 | 2028-06-20 | H
| 541 | 72-00-00-27-0-SVA-001 | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28325809) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28325809) |  | 0 / 1 | [] |  |  | MET.28325809 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 542 | 72-00-00-27-0-SVA-002 | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28325798) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28325798) |  | 0 / 1 | [] |  |  | MET.28325798 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 543 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.040972 | 17.Jul.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) |  | 0 / 3 | [] |  |  | MET.19873954 | 49636:58 | 4119:19 | 2027-08-29 | H
| 544 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.040972 | 17.Jul.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) |  | 0 / 3 | [] |  |  | MET.19875040 | 49636:58 | 4119:19 | 2027-08-29 | H
| 545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) |  | 0 / 3 | [] |  |  | MET.26224712 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) |  | 0 / 3 | [] |  |  | MET.26224783 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 547 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) |  | 0 / 3 | [] |  |  | MET.26290667 | 20'900 | 4'586 | 2030-05-09 | C
| 548 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) |  | 0 / 3 | [] |  |  | MET.19875078 | 20'900 | 4'586 | 2030-05-09 | C
| 549 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 17.Jul.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) |  | 0 / 3 | [] |  |  | MET.28325884 | 49636:58 | 4119:19 | 2027-08-29 | H
| 550 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 17.Jul.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) |  | 0 / 3 | [] |  |  | MET.28326044 | 49636:58 | 4119:19 | 2027-08-29 | H
| 551 | 783200-01-1-001 | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP (32712694) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP (32712694) |  | 0 / 5 | [] |  |  | MET.32712694 | 20'400 | 4'086 | 2029-12-09 | C
| 552 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) |  | 0 / 5 | [] |  |  | MET.32712897 | 20'400 | 4'086 | 2029-12-09 | C
| 553 | 783209-01-1 | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32712662) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 78-32 |  | [] |  |  |  |  | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32712662) |  | 0 / 3 | [] |  |  | MET.32712662 | 26.Sep.2029 | 1163 | 2029-09-26 | D
| 559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 03:43 | 17.Jul.2026 22:00 | 1900-01-02 03:43 |  | 0 |  | 0 | Not Started | 0 | T: 7; O: 0; C: 7 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) |  | 0 / 1 | [] |  |  | MET.31498481 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP (28326031) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP (28326031) |  | 0 / 1 | [] |  |  | MET.28326031 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 05:47 | 1899-12-31 22:51 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) |  | 0 / 1 | [] |  |  | MET.32712776 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 14:55 | 0.57153 |  | 1899-12-31 22:50 | Idle | 0 | T: 8; O: 0; C: 8 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) |  | 1 / 1 | [] |  |  | MET.32712826 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32712836) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.40417 |  | 0.076389 | Idle | 0 | T: 9; O: 0; C: 9 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712836 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32712703) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.40417 |  | 0.083333 | Idle | 0 | T: 16; O: 0; C: 16 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712703 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28325878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:20 | 1899-12-31 12:18 |  | 0.16667 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28325878) |  | 0 / 3 | [] |  |  | MET.28325878 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28325791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.030556 | 19.Jul.2026 16:20 | 1899-12-31 12:18 |  | 0.16667 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28325791) |  | 0 / 3 | [] |  |  | MET.28325791 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32712853) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:09 | 0.77014 |  | 0.041667 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 4 |  | 1 / 1 | [] |  |  | MET.32712853 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:12 | 0.76806 |  | 0.041667 | Idle | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) |  | 1 / 1 | [] |  |  | MET.32712760 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:24 | 0.38472 |  | 0.034722 | Idle | 0 | T: 12; O: 0; C: 12 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) |  | 1 / 1 | [] |  |  | MET.32712742 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:00 | 0.40139 |  | 0.048611 | Idle | 0 | T: 10; O: 0; C: 10 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) |  | 1 / 1 | [] |  |  | MET.32712778 | 12.Sep.2026 | 53 | 2026-09-12 | D
| 576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32712777) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 20.Jul.2026 07:31 | 0.87986 |  | 0.010417 | Idle | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 0 / 1 | [] |  |  | MET.32712777 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32712872) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32712872) |  | 0 / 1 | [] |  |  | MET.32712872 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 582 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | TC/P |  |  |  | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) |  | 0 / 1 | [] |  |  | MET.28375011 | 23.Aug.2026 | 33 | 2026-08-23 | D
| 583 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) |  | 0 / 3 | [] |  |  | MET.32712914 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 584 | 282200-04-1 | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32712909) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10556 | 17.Jul.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 28-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32712909) |  | 0 / 3 | [] |  |  | MET.32712909 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 585 | 282400-01-1-001 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32712913) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP |  |  |  | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32712913) |  | 0 / 6 | [] |  |  | MET.32712913 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 586 | 282400-01-1-002 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32712915) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP |  |  |  | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32712915) |  | 0 / 6 | [] |  |  | MET.32712915 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 587 | 282400-02-1-001 | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712903) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712903) |  | 0 / 3 | [] |  |  | MET.32712903 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 588 | 282400-02-1-002 | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712916) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712916) |  | 0 / 3 | [] |  |  | MET.32712916 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 589 | 344200-02-2 | 344200-02-2 (01) / RADIO ALTIMETER | 344200-02-2 (01) / RADIO ALTIMETER (32712908) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30069 | 17.Jul.2026 22:00 | 0.30069 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 34-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 344200-02-2 (01) / RADIO ALTIMETER (32712908) |  | 0 / 4 | [] |  |  | MET.32712908 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 590 | 344200-04-1 | 344200-04-1 (01) / RADIO ALTIMETER | 344200-04-1 (01) / RADIO ALTIMETER (32712907) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.42569 | 17.Jul.2026 22:00 | 0.38403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 344200-04-1 (01) / RADIO ALTIMETER (32712907) |  | 0 / 6 | [] |  |  | MET.32712907 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 591 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32712653) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 38-10 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  | AS PER T/Q: 740971 | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32712653) |  | 0 / 3 | [] |  |  | MET.32712653 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 592 | 383100-02-1 | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32712917) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12917 | 17.Jul.2026 22:00 | 0.10625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 38-31 |  | [] | JOB-SETUP, TC/P, CLOSE-UP |  |  |  | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32712917) |  | 0 / 3 | [] |  |  | MET.32712917 | 03.Apr.2028 | 622 | 2028-04-03 | D
| 593 | 494000-B2-1 | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 49-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) |  | 0 / 3 | [] |  |  | MET.32712910 | 46191:47 | 674:08 | 2026-09-24 | H
| 594 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) |  | 0 / 1 | [] |  |  | MET.32807087 | 22.Aug.2026 | 32 | 2026-08-22 | D
| 595 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) |  | 0 / 1 | [] |  |  | MET.32807086 | 22.Aug.2026 | 32 | 2026-08-22 | D
| 596 | 532178-01-1 | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00625 | 17.Jul.2026 22:00 | 0.00625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) |  | 0 / 3 | [] |  |  | MET.32450175 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 597 | 533130-01-1 | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP (32450197) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.031944 | 17.Jul.2026 22:00 | 0.028472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP (32450197) |  | 0 / 5 | [] |  |  | MET.32450197 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 598 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15 | 17.Jul.2026 22:00 | 0.14306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) |  | 0 / 7 | [] |  |  | MET.32712911 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 599 | 534112-01-1 | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION (32450199) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION (32450199) |  | 0 / 5 | [] |  |  | MET.32450199 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 600 | 572610-02-2 | 572610-02-2 (0) / OUTER WING | 572610-02-2 (0) / OUTER WING (32450162) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-2 (0) / OUTER WING (32450162) |  | 0 / 4 | [] |  |  | MET.32450162 | 19.Apr.2029 | 1003 | 2029-04-19 | D
| 603 | 05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW (32713058) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-11 |  | [] | TC/P |  |  |  | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW (32713058) |  | 0 / 1 | [] |  |  | MET.32713058 | 09.Aug.2027 | 384 | 2027-08-09 | D
| 604 | 12-21-11-01-0-SVA | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH (19231763) | On Demand Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.40625 | 17.Jul.2026 22:00 | 0.25139 | 17.Jul.2026 18:58 | 1900-01-02 09:40 |  | 0.5 | Idle | 0 | T: 0; O: 0; C: 0 | 12-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH (19231763) |  | 2 / 10 | [] |  |  | MET.19231763 |  |  | 1517606
| 605 | 12-21-11-03-0-SVA | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) | On Demand Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.625 | 17.Jul.2026 22:00 | 0.32292 | 17.Jul.2026 17:00 | 1900-01-02 11:38 |  | 1900-01-04 15:00 | Idle | 0 | T: 0; O: 0; C: 0 | 12-21 |  | [] | WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH |  |  |  | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) |  | 6 / 25 | [] |  |  | MET.23560156 |  |  | 1517606
| 606 | 32-10-00-01-0-SVA | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (30931752) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-12 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (30931752) |  | 0 / 3 | [] |  |  | MET.30931752 | 02.Aug.2026 | 12 | 2026-08-02 | D
| 607 | 321000-01-1 | 321000-01-1 (5) / MLG AND DOORS LUBRICATION | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) |  | 0 / 3 | [] |  |  | MET.32807082 | 28.Jul.2026 | 7 | 2026-07-28 | D
| 608 | 322100-07-1 | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP (32713055) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 06:38 | 17.Jul.2026 22:00 | 0.48194 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 32-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP (32713055) |  | 0 / 10 | [] |  |  | MET.32713055 | 20'000 | 3'686 | 2029-08-09 | C
| 609 | 521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) |  | 0 / 1 | [] |  |  | MET.32713053 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 610 | 521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP (32712993) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 25-62 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP (32712993) |  | 0 / 10 | [] |  |  | MET.32712993 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 611 | 521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP (32713003) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.11319 |  | 0 |  | 0 | Not Started | 0 | T: 10; O: 0; C: 10 | 52-13 |  | [] | TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION |  |  |  | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP (32713003) |  | 0 / 10 | [] |  |  | MET.32713003 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 612 | 522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION (32713039) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.42153 | 17.Jul.2026 22:00 | 0.28125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION (32713039) |  | 0 / 7 | [] |  |  | MET.32713039 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 613 | 523103-01-1 | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP (32713046) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19236 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP (32713046) |  | 0 / 6 | [] |  |  | MET.32713046 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 614 | 523109-01-1 | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP (32713017) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP (32713017) |  | 0 / 4 | [] |  |  | MET.32713017 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 615 | 523113-01-1 | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP (32713032) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19236 | 17.Jul.2026 22:00 | 0.11319 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-32 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP (32713032) |  | 0 / 6 | [] |  |  | MET.32713032 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 616 | 523119-01-2 | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-32 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) |  | 0 / 4 | [] |  |  | MET.32713047 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 617 | 523303-01-1 | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP (32713027) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-33 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP (32713027) |  | 0 / 6 | [] |  |  | MET.32713027 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 618 | 531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.2625 | 17.Jul.2026 22:00 | 0.22083 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) |  | 0 / 6 | [] |  |  | MET.32712875 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 619 | 532130-09-1 | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION (32712618) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11667 | 17.Jul.2026 22:00 | 0.10625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION (32712618) |  | 0 / 6 | [] |  |  | MET.32712618 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 620 | 532130-29-1 | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION (32712912) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18194 | 17.Jul.2026 22:00 | 0.14722 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 53-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION (32712912) |  | 0 / 10 | [] |  |  | MET.32712912 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 621 | 532132-01-1 | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32713000) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.081944 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32713000) |  | 0 / 4 | [] |  |  | MET.32713000 | 50363:39 | 4846:00 | 2027-11-09 | H
| 622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) |  | 0 / 3 | [] |  |  | MET.32712995 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 623 | 532175-01-1 | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR (32713006) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.31111 | 17.Jul.2026 22:00 | 0.18056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR (32713006) |  | 0 / 12 | [] |  |  | MET.32713006 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 624 | 532180-04-2 | 532180-04-2 (0) / FORWARD FUSELAGE | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53 |  | [] |  |  |  |  | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) |  | 0 / 3 | [] |  |  | MET.32450146 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 625 | 533111-01-1 | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) |  | 0 / 2 | [] |  |  | MET.25336513 | 48000:00 | 2482:21 | 2027-03-21 | H
| 626 | 533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0875 | 17.Jul.2026 22:00 | 0.0875 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 53 |  | [] |  |  |  |  | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) |  | 0 / 3 | [] |  |  | MET.32450148 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 627 | 533139-02-1 | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, INSPECTION, -- |  |  |  | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) |  | 0 / 3 | [] |  |  | MET.25336237 | 52900:00 | 7382:21 | 2028-07-16 | H
| 628 | 533152-01-7 | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 17.Jul.2026 22:00 | 0.1875 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) |  | 0 / 9 | [] |  |  | MET.32713023 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 629 | 534107-03-1 | 534107-03-1 (0) / REAR FUSELAGE | 534107-03-1 (0) / REAR FUSELAGE (32450155) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534107-03-1 (0) / REAR FUSELAGE (32450155) |  | 0 / 3 | [] |  |  | MET.32450155 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 630 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25336763) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.68542 | 17.Jul.2026 22:00 | 0.5625 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, -- |  |  |  | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25336763) |  | 0 / 10 | [] |  |  | MET.25336763 | 52900:00 | 7382:21 | 2028-07-16 | H
| 631 | 534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 534135-02-1 (0) / REAR FUSELAGE (32450158) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534135-02-1 (0) / REAR FUSELAGE (32450158) |  | 0 / 3 | [] |  |  | MET.32450158 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 632 | 534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (32712622) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.074306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (32712622) |  | 0 / 7 | [] |  |  | MET.32712622 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 633 | 534150-01-1 | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION (25336879) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15556 | 17.Jul.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION (25336879) |  | 0 / 8 | [] |  |  | MET.25336879 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 634 | 534164-01-1 | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC (32712624) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.060417 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC (32712624) |  | 0 / 8 | [] |  |  | MET.32712624 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 635 | 534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A (32450150) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25694 | 17.Jul.2026 22:00 | 0.25694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A (32450150) |  | 0 / 4 | [] |  |  | MET.32450150 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 636 | 534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 (32450149) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 (32450149) |  | 0 / 4 | [] |  |  | MET.32450149 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.050694 | 17.Jul.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) |  | 0 / 4 | [] |  |  | MET.32713050 | 54636:58 | 9119:19 | 2029-01-03 | H
| 638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038889 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) |  | 0 / 4 | [] |  |  | MET.32713048 | 54636:58 | 9119:19 | 2029-01-03 | H
| 639 | 545134-09-6-001 | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713052) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.053472 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713052) |  | 0 / 4 | [] |  |  | MET.32713052 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 640 | 545134-09-6-002 | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713051) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.053472 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713051) |  | 0 / 4 | [] |  |  | MET.32713051 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 641 | 571192-09-1 | 571192-09-1 (0) / CENTER WING BOX | 571192-09-1 (0) / CENTER WING BOX (32450161) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 571192-09-1 (0) / CENTER WING BOX (32450161) |  | 0 / 3 | [] |  |  | MET.32450161 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 642 | 571192-19-1 | 571192-19-1 (0) / CENTER WING BOX | 571192-19-1 (0) / CENTER WING BOX (32450142) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 571192-19-1 (0) / CENTER WING BOX (32450142) |  | 0 / 3 | [] |  |  | MET.32450142 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 643 | 572001-01-1-001 | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP (32713002) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP (32713002) |  | 0 / 5 | [] |  |  | MET.32713002 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 644 | 572001-01-1-002 | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP (32713001) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP (32713001) |  | 0 / 5 | [] |  |  | MET.32713001 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 645 | 572007-01-2-001 | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP (25336398) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.08125 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP (25336398) |  | 0 / 5 | [] |  |  | MET.25336398 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 646 | 572007-01-2-002 | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP (25336296) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.08125 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP (25336296) |  | 0 / 5 | [] |  |  | MET.25336296 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 647 | 572020-01-1-001 | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP (28325976) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.55 | 17.Jul.2026 22:00 | 0.50833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP (28325976) |  | 0 / 6 | [] |  |  | MET.28325976 | 56800:00 | 11282:21 | 2029-08-04 | H
| 648 | 572020-01-1-002 | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP (28325981) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.55 | 17.Jul.2026 22:00 | 0.50833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP (28325981) |  | 0 / 6 | [] |  |  | MET.28325981 | 56800:00 | 11282:21 | 2029-08-04 | H
| 649 | 572040-01-2-001 | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP (32713019) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP (32713019) |  | 0 / 6 | [] |  |  | MET.32713019 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 650 | 572040-01-2-002 | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP (32713041) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP (32713041) |  | 0 / 6 | [] |  |  | MET.32713041 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 651 | 572044-01-2-001 | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) |  | 0 / 4 | [] |  |  | MET.26209161 | 49236:58 | 3719:19 | 2027-07-21 | H
| 652 | 572044-01-2-002 | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-SETUP |  |  |  | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) |  | 0 / 4 | [] |  |  | MET.26290432 | 49236:58 | 3719:19 | 2027-07-21 | H
| 653 | 572062-01-1-001 | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) |  | 0 / 4 | [] |  |  | MET.32713037 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 654 | 572062-01-1-002 | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) |  | 0 / 4 | [] |  |  | MET.32713013 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 655 | 572063-01-1-001 | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12986 | 17.Jul.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) |  | 0 / 6 | [] |  |  | MET.32713040 | 22.Oct.2027 | 458 | 2027-10-22 | D
| 656 | 572063-01-1-002 | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP (32713044) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12986 | 17.Jul.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP (32713044) |  | 0 / 6 | [] |  |  | MET.32713044 | 22.Oct.2027 | 458 | 2027-10-22 | D
| 657 | 572066-01-1-001 | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712627) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712627) |  | 0 / 5 | [] |  |  | MET.32712627 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 658 | 572066-01-1-002 | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712612) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712612) |  | 0 / 5 | [] |  |  | MET.32712612 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 659 | 572111-01-1-001 | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) |  | 0 / 4 | [] |  |  | MET.28325749 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 660 | 572111-01-1-002 | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) |  | 0 / 4 | [] |  |  | MET.28325815 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 661 | 572111-02-1 | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 |  | 0 |  | 0 | Not Started | 0 | T: 8; O: 0; C: 8 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) |  | 0 / 3 | [] |  |  | MET.32450174 | 21.Jul.2028 | 731 | 2028-07-21 | D
| 662 | 572112-01-1-001 | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP (25336200) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP (25336200) |  | 0 / 4 | [] |  |  | MET.25336200 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 663 | 572112-01-1-002 | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) |  | 0 / 4 | [] |  |  | MET.25336328 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 664 | 572139-01-2-001 | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713042) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.047222 | 17.Jul.2026 22:00 | 0.040278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713042) |  | 0 / 5 | [] |  |  | MET.32713042 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 665 | 572139-01-2-002 | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713021) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.047222 | 17.Jul.2026 22:00 | 0.040278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713021) |  | 0 / 5 | [] |  |  | MET.32713021 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 666 | 572140-01-2-001 | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712996) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712996) |  | 0 / 5 | [] |  |  | MET.32712996 | 19.Apr.2029 | 1003 | 2029-04-19 | D
| 667 | 572140-01-2-002 | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712997) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712997) |  | 0 / 5 | [] |  |  | MET.32712997 | 19.Apr.2029 | 1003 | 2029-04-19 | D
| 668 | 572607-01-1-001 | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31498801) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31498801) |  | 0 / 4 | [] |  |  | MET.31498801 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 669 | 572607-01-1-002 | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) |  | 0 / 4 | [] |  |  | MET.31497936 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 670 | 572610-02-1-001 | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:27 | 0.75764 |  | 0.20833 | Idle | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) |  | 0 / 4 | [] |  |  | MET.32712825 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 671 | 572610-02-1-002 | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:28 | 0.75694 |  | 0.20833 | Idle | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) |  | 0 / 4 | [] |  |  | MET.32712722 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 672 | 574101-01-3-001 | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) |  | 0 / 4 | [] |  |  | MET.32713045 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 673 | 574101-01-3-002 | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP (32713035) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 |  | 0 |  | 0 | Not Started | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 0 / 4 | [] |  |  | MET.32713035 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 674 | 574202-01-2-001 | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) |  | 0 / 4 | [] |  |  | MET.32713043 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 675 | 574202-01-2-002 | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713031) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713031) |  | 0 / 4 | [] |  |  | MET.32713031 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 676 | 574205-01-1-001 | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP (32713033) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP (32713033) |  | 0 / 4 | [] |  |  | MET.32713033 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 677 | 574205-01-1-002 | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP (32713018) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP (32713018) |  | 0 / 4 | [] |  |  | MET.32713018 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 678 | 574302-01-2-001 | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) |  | 0 / 4 | [] |  |  | MET.32712905 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 679 | 574302-01-2-002 | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) |  | 0 / 4 | [] |  |  | MET.32713020 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 680 | 574305-01-1-001 | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP (32713038) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, --, INSPECTION, JOB-CLOSEUP |  |  |  | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP (32713038) |  | 0 / 4 | [] |  |  | MET.32713038 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 681 | 574305-01-1-002 | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) |  | 0 / 4 | [] |  |  | MET.32713029 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 682 | 574402-01-2-001 | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) |  | 0 / 4 | [] |  |  | MET.32713028 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 683 | 574402-01-2-002 | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) |  | 0 / 4 | [] |  |  | MET.32713010 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 684 | 574405-01-1-001 | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION (32713012) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION (32713012) |  | 0 / 4 | [] |  |  | MET.32713012 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 685 | 574405-01-1-002 | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) |  | 0 / 4 | [] |  |  | MET.32713030 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 686 | 574502-01-2-001 | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) |  | 0 / 4 | [] |  |  | MET.32713015 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 687 | 574502-01-2-002 | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713034) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713034) |  | 0 / 4 | [] |  |  | MET.32713034 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 688 | 574505-01-1-001 | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION (32713024) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION (32713024) |  | 0 / 4 | [] |  |  | MET.32713024 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 689 | 574505-01-1-002 | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) |  | 0 / 4 | [] |  |  | MET.32713011 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 690 | 574602-01-2-001 | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) |  | 0 / 4 | [] |  |  | MET.32713025 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 691 | 574602-01-2-002 | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) |  | 0 / 4 | [] |  |  | MET.32713005 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 692 | 574605-01-1-001 | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION (32713014) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION (32713014) |  | 0 / 4 | [] |  |  | MET.32713014 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 693 | 574605-01-1-002 | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION (32713009) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION (32713009) |  | 0 / 4 | [] |  |  | MET.32713009 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 694 | 575107-01-1-001 | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) |  | 0 / 4 | [] |  |  | MET.32713004 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 695 | 575107-01-1-002 | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) |  | 0 / 4 | [] |  |  | MET.32713022 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 696 | 575120-03-1-001 | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) |  | 0 / 4 | [] |  |  | MET.32712998 | 21.Apr.2029 | 1005 | 2029-04-21 | D
| 697 | 575120-03-1-002 | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) |  | 0 / 4 | [] |  |  | MET.32712999 | 21.Apr.2029 | 1005 | 2029-04-21 | D
| 698 | 575150-01-2-001 | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 19.Jul.2026 16:36 | 1899-12-31 12:02 |  | 0.5 | Idle | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) |  | 0 / 4 | [] |  |  | MET.32713008 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 699 | 575150-01-2-002 | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP (32713016) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP (32713016) |  | 0 / 4 | [] |  |  | MET.32713016 | 21.Oct.2027 | 457 | 2027-10-21 | D
| 700 | 575158-01-5-001 | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) |  | 0 / 4 | [] |  |  | MET.25336910 | 50800:00 | 5282:21 | 2027-12-22 | H
| 701 | 575158-01-5-002 | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP (25336066) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP (25336066) |  | 0 / 4 | [] |  |  | MET.25336066 | 50800:00 | 5282:21 | 2027-12-22 | H
| 702 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.19444 | 17.Jul.2026 22:00 | 0.19444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-30 |  | [] |  |  |  |  | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) |  | 0 / 3 | [] |  |  | MET.26290436 | 49636:58 | 4119:19 | 2027-08-29 | H
| 703 | 92339 | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) |  | 0 / 1 | [] |  |  | MET.22586962 | 17'868 | 1'554 | 2027-11-02 | C
| 704 | 92341 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) |  | 0 / 1 | [] |  |  | MET.23464908 | 17'366 | 1'052 | 2027-06-03 | C
| 705 | TPIS DEACTIVATION | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) | Single Running Taskcard | RI | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 17:31 | 0.46319 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) |  | 2 / 2 | [] |  |  | MET.31905379 | 28.Sep.2026 | 69 | 2026-09-28 | D
| 706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 29294847 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29294847) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 29294847 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29294847) |  | 0 / 1 | [] |  |  | ME.29294847 | 45735:38 | 217:59 | 2026-08-10 | H
| 707 | 29904504 | EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A | 29904504 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904504) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.64583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  | EOD can be done at Line if not reach to C-CHK or Connectivity EOD can be done at Line if not reach to C-CHK or Connectivity | 29904504 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904504) |  | 0 / 10 | [] |  |  | ME.29904504 | 16.Feb.2027 | 210 | 2027-02-16 | D
| 708 | 29749798 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) |  | 0 / 4 | [] |  |  | ME.29749798 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 709 | 20893203 | EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) | 20893203 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (20893203) | Document | PJED | <html><span style="font-weight: normal;">No part requests</span></html> | 0.38194 | 17.Jul.2026 22:00 | 0.34375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 20893203 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (20893203) |  | 0 / 9 | [] |  |  | ME.20893203 | 19'500 | 3'186 | 2029-03-11 | C
| 710 | 29715410 | EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO | 29715410 / EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO (29715410) | Document | CCHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.26042 | 17.Jul.2026 22:00 | 0.17361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 29715410 / EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO (29715410) |  | 0 / 17 | [] |  |  | ME.29715410 | 18.Dec.2027 | 515 | 2027-12-18 | D
| 711 | 30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) | Document | AD | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) |  | 0 / 4 | [] |  | 000 | ME.30970374 | 26.May.2029 | 1040 | 2029-05-26 | D
| 712 | 29411293 | EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411293 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411293) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">19</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.36458 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411293 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411293) |  | 0 / 6 | [] |  |  | ME.29411293 | 01.Oct.2029 | 1168 | 2029-10-01 | D
| 713 | 29411377 | EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411377 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411377) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">18</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.36458 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411377 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411377) |  | 0 / 6 | [] |  |  | ME.29411377 | 01.Oct.2029 | 1168 | 2029-10-01 | D
| 714 | 31889267 | EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66111 | 17.Jul.2026 22:00 | 0.6875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) |  | 0 / 12 | [] |  | 000 | ME.31889267 | 48000:00 | 2487:21 | 2027-03-22 | H
| 715 | 30839449 | EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON | 30839449 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839449) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-01 00:30 | 17.Jul.2026 22:00 | 1899-12-31 06:40 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | --, JOB-SETUP, JOB-SETUP, JOB-SETUP, --, --, --, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, CLOSE-UP, CLOSE-UP |  |  |  | 30839449 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839449) |  | 0 / 17 | [] |  |  | ME.30839449 | 01.Dec.2028 | 864 | 2028-12-01 | D
| 716 | 29500617 | EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | 29500617 / EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500617) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29500617 / EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500617) |  | 0 / 6 | [] |  |  | ME.29500617 | 28.Feb.2027 | 222 | 2027-02-28 | D
| 717 | 30482091 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) |  | 0 / 6 | [] |  |  | ME.30482091 | 01.Oct.2026 | 72 | 2026-10-01 | D
| 718 | 30481965 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20486 | 17.Jul.2026 22:00 | 0.20486 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) |  | 0 / 6 | [] |  |  | ME.30481965 | 01.Oct.2026 | 72 | 2026-10-01 | D
| 719 | 29155526 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) |  | 0 / 6 | [] |  |  | ME.29155526 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 720 | 29155624 | EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX | 29155624 / EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX (29155624) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155624 / EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX (29155624) |  | 0 / 6 | [] |  |  | ME.29155624 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 721 | 29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) |  | 0 / 6 | [] |  |  | ME.29155749 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 722 | 29155864 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 29155864 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (29155864) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155864 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (29155864) |  | 0 / 6 | [] |  |  | ME.29155864 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 723 | 23732996 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23732996 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23732996) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.53125 | 17.Jul.2026 22:00 | 0.51042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23732996 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23732996) |  | 0 / 3 | [] |  | 000 | ME.23732996 | 23'965 | 3'600 | 2029-07-14 | C
| 724 | 23745496 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.53125 | 17.Jul.2026 22:00 | 0.51042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) |  | 0 / 3 | [] |  | S32SRT731LH | ME.23745496 | 23'965 | 3'600 | 2029-07-14 | C
| 725 | 31990073 | EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED | 31990073 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (31990073) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">20</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-01 06:00 | 17.Jul.2026 22:00 | 1899-12-31 03:15 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | This modification EO can be done either in Line or Hanger Required nose jacking and nose gear swing | 31990073 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (31990073) |  | 0 / 10 | [] |  | 000 | ME.31990073 | 31.Dec.2027 | 528 | 2027-12-31 | D
| 726 | 27685448 | EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS | 27685448 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685448) | Document | CCHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.67708 | 17.Jul.2026 22:00 | 0.59375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | PART WILL BE AVL AT EDD 26-AUG-2024 | 27685448 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685448) |  | 0 / 5 | [] |  |  | ME.27685448 | 01.Oct.2027 | 437 | 2027-10-01 | D
| 727 | 30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 30817926 / EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION (30817926) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">27</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-18 15:00 | 17.Jul.2026 22:00 | 1900-01-17 23:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 30817926 / EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION (30817926) |  | 0 / 42 | [] |  |  | ME.30817926 | 01.Apr.2028 | 620 | 2028-04-01 | D
| 728 | 31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | 31328631 / EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL (31328631) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-06 02:00 | 17.Jul.2026 22:00 | 1900-01-06 02:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 31328631 / EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL (31328631) |  | 0 / 5 | [] |  |  | ME.31328631 | 08.Aug.2026 | 18 | 2026-08-08 | D
| 729 | 29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | 29155915 / EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155915) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.96528 | 17.Jul.2026 22:00 | 0.79861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29155915 / EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155915) |  | 0 / 14 | [] |  |  | ME.29155915 | 01.Sep.2027 | 407 | 2027-09-01 | D
| 730 | 29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.75 | 17.Jul.2026 22:00 | 0.4375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) |  | 0 / 8 | [] |  |  | ME.29156039 | 01.Sep.2027 | 407 | 2027-09-01 | D
| 731 | 29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.77083 | 17.Jul.2026 22:00 | 0.60417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) |  | 0 / 9 | [] |  |  | ME.29156133 | 01.Sep.2027 | 407 | 2027-09-01 | D
| 732 | 29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) |  | 0 / 5 | [] |  |  | ME.29156195 | 01.Sep.2027 | 407 | 2027-09-01 | D
| 733 | 29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | 29157165 / EOD-320-46-00008-R00/FOMAX 4 ACTIVATION (29157165) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29157165 / EOD-320-46-00008-R00/FOMAX 4 ACTIVATION (29157165) |  | 0 / 8 | [] |  |  | ME.29157165 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 734 | 29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) |  | 0 / 5 | [] |  |  | ME.29156249 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 735 | 15777417 | EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 15777417 / EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777417) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 17.Jul.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777417 / EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777417) |  | 0 / 6 | [] |  |  | ME.15777417 | 20'000 | 3'686 | 2029-08-09 | C
| 736 | 15777631 | EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 15777631 / EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777631) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777631 / EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777631) |  | 0 / 6 | [] |  |  | ME.15777631 | 20'000 | 3'686 | 2029-08-09 | C
| 737 | 16152729 | EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS | 16152729 / EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS (16152729) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 16152729 / EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS (16152729) |  | 0 / 9 | [] |  |  | ME.16152729 | 19'800 | 3'486 | 2029-06-10 | C
| 738 | 16152761 | EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS | 16152761 / EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS (16152761) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 16152761 / EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS (16152761) |  | 0 / 9 | [] |  |  | ME.16152761 | 19'800 | 3'486 | 2029-06-10 | C
| 739 | 17837147 | EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- | 17837147 / EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- (17837147) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 01:00 | 17.Jul.2026 22:00 | 0.91667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 17837147 / EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- (17837147) |  | 0 / 8 | [] |  |  | ME.17837147 | 48000:00 | 2482:21 | 2027-03-21 | H
| 740 | 18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 18607800 / EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING (18607800) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">13</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-01 14:00 | 17.Jul.2026 22:00 | 1900-01-01 04:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 18607800 / EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING (18607800) |  | 0 / 16 | [] |  |  | ME.18607800 | 48000:00 | 2482:21 | 2027-03-21 | H
| 741 | 29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 29441536 / EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441536) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 09:45 | 17.Jul.2026 22:00 | 1899-12-31 06:10 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 29441536 / EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441536) |  | 0 / 12 | [] |  |  | ME.29441536 | 20'000 | 3'686 | 2029-08-09 | C
| 742 | 28479751 | EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 | 28479751 / EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 (28479751) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">14</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.82639 | 17.Jul.2026 22:00 | 0.72222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 28479751 / EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 (28479751) |  | 0 / 10 | [] |  |  | ME.28479751 | 56500:00 | 10982:21 | 2029-07-06 | H
| 743 | 31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | 31381248 / EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 (31381248) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 18:15 | 17.Jul.2026 22:00 | 1899-12-31 05:19 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | DO SIMULTANOUSLY WITH EO-320-53-00048-R00 | 31381248 / EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 (31381248) |  | 0 / 11 | [] |  |  | ME.31381248 | 07.Oct.2031 | 1904 | 2031-10-07 | D
| 744 | 29399531 | EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI | 29399531 / EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI (29399531) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1899-12-31 04:10 | 17.Jul.2026 22:00 | 1899-12-31 00:10 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 55 |  | [] |  |  |  |  | 29399531 / EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI (29399531) |  | 0 / 12 | [] |  |  | ME.29399531 | 22.Apr.2032 | 2102 | 2032-04-22 | D
| 745 | 31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31053001 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053001) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31053001 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053001) |  | 0 / 2 | [] |  | 000 | ME.31053001 | 22.Sep.2026 | 62d, 20h | 2026-09-22 | D
| 746 | 31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31053051 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053051) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31053051 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053051) |  | 0 / 2 | [] |  | 000 | ME.31053051 | 22.Sep.2026 | 62d, 20h | 2026-09-22 | D
| 747 | 15969127 | EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. | 15969127 / EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. (15969127) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">46</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 20:10 | 17.Jul.2026 22:00 | 1899-12-31 14:25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15969127 / EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. (15969127) |  | 0 / 19 | [] |  |  | ME.15969127 | 48000:00 | 2482:21 | 2027-03-21 | H
| 748 | 10897096 | EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION | 10897096 / EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION (10897096) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">16</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.52778 | 17.Jul.2026 22:00 | 0.45833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 10897096 / EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION (10897096) |  | 0 / 12 | [] |  |  | ME.10897096 | 20'000 | 3'686 | 2029-08-09 | C
| 749 | 32362499 | S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] | --, --, --, CLOSE-UP |  |  |  | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) |  | 0 / 4 | [] |  |  | ME.32362499 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 750 | 31662556 | S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH | 31662556 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662556) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11111 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] |  |  |  |  | 31662556 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662556) |  | 0 / 4 | [] |  |  | ME.31662556 | 30.Dec.2026 | 162 | 2026-12-30 | D
| 751 | 30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | 30936889 / S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM (30936889) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.9375 | 17.Jul.2026 22:00 | 0.54167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-33 |  | [] | --, --, --, --, --, --, --, --, --, --, OPS/LK, --, --, --, CLOSE-UP |  |  |  | 30936889 / S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM (30936889) |  | 0 / 15 | [] |  |  | ME.30936889 | 21.Aug.2028 | 762 | 2028-08-21 | D
| 752 | 30358131 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) |  | 0 / 3 | [] |  |  | ME.30358131 | 45735:38 | 217:59 | 2026-08-10 | H
| 753 | 20038778 | S51-R10008/A320 FLEET // DENT AND BUCKLE CHART | 20038778 / S51-R10008/A320 FLEET // DENT AND BUCKLE CHART (20038778) | Document | HNGR | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 09:30 | 17.Jul.2026 22:00 | 0.52083 | 18.Jul.2026 13:27 | 1900-01-01 15:11 |  | 0.055556 | Idle | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 10 | [] |  |  | ME.20038778 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 754 | 31978429 | S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS | 31978429 / S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS (31978429) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.090278 | 17.Jul.2026 22:00 | 0.1875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 31978429 / S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS (31978429) |  | 0 / 4 | [] |  |  | ME.31978429 | 01.Aug.2026 | 11 | 2026-08-01 | D
| 755 | 31573583 | S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS | 31573583 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573583) | Document | CCHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31573583 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573583) |  | 0 / 7 | [] |  |  | ME.31573583 | 31.Dec.2028 | 894 | 2028-12-31 | D
| 756 | 32832482 | S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR | 32832482 / S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR (32832482) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 10:26 | 1899-12-31 18:12 |  | 0.055556 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 2 | [] |  |  | ME.32832482 | 16.Jun.2029 | 1061 | 2029-06-16 | D
| 757 | 29294848 | S73-D10063/ENGINE FUEL FILTER REPLACEMENT | 29294848 / S73-D10063/ENGINE FUEL FILTER REPLACEMENT (29294848) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 17.Jul.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 73 |  | [] |  |  |  |  | 29294848 / S73-D10063/ENGINE FUEL FILTER REPLACEMENT (29294848) |  | 0 / 7 | [] |  | 00 | ME.29294848 | 45735:38 | 217:59 | 2026-08-10 | H
| 758 | 31958880 | REPLACE 3214-31/151653 (BATTERY, EMERGENCY) | 31958880 / REPLACE 3214-31/151653 (BATTERY, EMERGENCY) (31958880) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958880 / REPLACE 3214-31/151653 (BATTERY, EMERGENCY) (31958880) |  | 0 / 1 | [] |  | 12WL | ME.31958880 | 31.Jul.2026 | 10 | 2026-07-31 | D
| 759 | 31958882 | REPLACE 3214-31/151671 (BATTERY, EMERGENCY) | 31958882 / REPLACE 3214-31/151671 (BATTERY, EMERGENCY) (31958882) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958882 / REPLACE 3214-31/151671 (BATTERY, EMERGENCY) (31958882) |  | 0 / 1 | [] |  | 10WL | ME.31958882 | 31.Jul.2026 | 10 | 2026-07-31 | D
| 760 | 31958881 | REPLACE 3214-31/151674 (BATTERY, EMERGENCY) | 31958881 / REPLACE 3214-31/151674 (BATTERY, EMERGENCY) (31958881) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958881 / REPLACE 3214-31/151674 (BATTERY, EMERGENCY) (31958881) |  | 0 / 1 | [] |  | 11WL | ME.31958881 | 31.Jul.2026 | 10 | 2026-07-31 | D
| 761 | 31958879 | REPLACE 3214-31/151687 (BATTERY, EMERGENCY) | 31958879 / REPLACE 3214-31/151687 (BATTERY, EMERGENCY) (31958879) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958879 / REPLACE 3214-31/151687 (BATTERY, EMERGENCY) (31958879) |  | 0 / 1 | [] |  | 13WL | ME.31958879 | 31.Jul.2026 | 10 | 2026-07-31 | D
| 762 | 22959389 | REPLACE 47145-267/4527 (ACTUATOR-THS) | 22959389 / REPLACE 47145-267/4527 (ACTUATOR-THS) (22959389) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 22959389 / REPLACE 47145-267/4527 (ACTUATOR-THS) (22959389) |  | 0 / 1 | [] |  | 000 | ME.22959389 | 20'000 | 3'687 | 2029-08-10 | C
| 763 | 31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) |  | 0 / 1 | [] |  | 100 | ME.31197928 | 31.Aug.2026 | 41 | 2026-08-31 | D
| 764 | 26290429 | 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) |  | 0 / 3 | [] |  | 201 | ME.26290429 | 10.Sep.2028 | 782 | 2028-09-10 | D
| 765 | 28781470 | 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) |  | 0 / 3 | [] |  | 101 | ME.28781470 | 22.Aug.2029 | 1128 | 2029-08-22 | D
| 766 | 28781472 | 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) |  | 0 / 3 | [] |  | 102 | ME.28781472 | 22.Aug.2029 | 1128 | 2029-08-22 | D
| 767 | 22574878 | 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) |  | 0 / 3 | [] |  | 000 | ME.22574878 | 24.Feb.2027 | 218 | 2027-02-24 | D
| 768 | 23772081 | 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772081 / 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772081) | Part Requirement | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 23772081 / 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772081) |  | 0 / 3 | [] |  | 002 | ME.23772081 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 769 | 23772080 | 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) | Part Requirement | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) |  | 0 / 3 | [] |  | 001 | ME.23772080 | 21.Jun.2028 | 701 | 2028-06-21 | D
| 770 | 31045000 | CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING | 31045000 / CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING (31045000) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20139 | 17.Jul.2026 22:00 | 0.10347 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 75 |  | [] |  |  |  |  | 31045000 / CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING (31045000) |  | 0 / 8 | [] |  | ENG100 | ME.31045000 | 31240:40 | 384:46 | 2026-08-26 | H
| 771 | 30304386 | CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.56667 | 17.Jul.2026 22:00 | 0.33403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP |  |  |  | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) |  | 0 / 7 | [] |  | ENG200 | ME.30304386 | 14'718 | 94 | 2026-08-17 | C
| 772 | 80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | 80944787 / PANEL 41C CEILING PANEL FOUND DAMAGE (80944787) | Workorder | PANT | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Oct.2025 06:06 | 1900-09-27 22:32 |  | 0.67361 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 80944787 / PANEL 41C CEILING PANEL FOUND DAMAGE (80944787) |  | 0 / 2 | [] |  |  | WO.80944787 | 21.Oct.2026 | 92 | 2026-10-21 | D
| 773 | 81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | 81002632 / AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR (81002632) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Apr.2026 01:29 | 1900-03-24 03:09 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 81002632 / AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR (81002632) |  | 0 / 1 | [] |  |  | WO.81002632 | 27.Apr.2027 | 280 | 2027-04-27 | D
| 774 | 94493475 | DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. | 94493475 / DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. (94493475) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 11.Jun.2026 23:28 | 1900-02-07 05:10 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493475 / DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. (94493475) |  | 0 / 1 | [] |  |  | WO.94493475 | 10.Oct.2026 | 81 | 2026-10-10 | D
| 775 | 94493476 | DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. | 94493476 / DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. (94493476) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 11.Jun.2026 23:31 | 1900-02-07 05:07 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493476 / DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. (94493476) |  | 0 / 1 | [] |  |  | WO.94493476 | 10.Oct.2026 | 81 | 2026-10-10 | D
| 776 | 94493487 | DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. | 94493487 / DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. (94493487) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Jun.2026 23:46 | 1900-02-05 04:52 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493487 / DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. (94493487) |  | 0 / 1 | [] |  |  | WO.94493487 | 11.Oct.2026 | 82 | 2026-10-11 | D
| 777 | 94493488 | DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. | 94493488 / DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. (94493488) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Jun.2026 23:51 | 1900-02-05 04:47 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493488 / DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. (94493488) |  | 0 / 1 | [] |  |  | WO.94493488 | 11.Oct.2026 | 82 | 2026-10-11 | D
| 778 | 94493489 | DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. | 94493489 / DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. (94493489) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 14.Jun.2026 00:04 | 1900-02-05 04:34 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493489 / DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. (94493489) |  | 0 / 1 | [] |  |  | WO.94493489 | 11.Oct.2026 | 82 | 2026-10-11 | D
| 779 | 94734250 | WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING | 94734250 / WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING (94734250) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 15.May.2026 22:15 | 1900-03-06 06:23 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 94734250 / WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING (94734250) |  | 0 / 1 | [] |  |  | WO.94734250 | 11.Sep.2026 | 52 | 2026-09-11 | D
| 780 | 94740818 | BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Apr.2026 10:57 | 1900-03-24 17:41 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) |  | 0 / 1 | [] |  |  | WO.94740818 | 25.Aug.2026 | 35 | 2026-08-25 | D
| 781 | 94799712 | DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED | 94799712 / DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED (94799712) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 02.Jun.2026 07:06 | 1900-02-16 21:32 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11-00 |  | [] |  |  |  |  | 94799712 / DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED (94799712) |  | 0 / 1 | [] |  |  | WO.94799712 | 30.Sep.2026 | 71 | 2026-09-30 | D
| 783 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (32924594) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE |  |  |  | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (32924594) |  | 0 / 1 | [] |  |  | JCA.32924594 |  |  | 1517606
| 784 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (32924593) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P |  |  |  | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (32924593) |  | 0 / 2 | [] |  |  | JCA.32924593 |  |  | 1517606
| 785 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (32924591) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE, ACFT RELEASE, -- |  |  |  | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (32924591) |  | 0 / 3 | [] |  |  | JCA.32924591 |  |  | 1517606
| 786 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) | Jobcard | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">10</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 17.Jul.2026 22:00 | 0.37847 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) |  | 0 / 20 | [] |  |  | JCA.32924606 |  |  | 1517606
| 787 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (32924605) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.91667 | 17.Jul.2026 22:00 | 0.46528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (32924605) |  | 0 / 18 | [] |  |  | JCA.32924605 |  |  | 1517606
| 788 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P |  |  |  | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) |  | 0 / 1 | [] |  |  | JCA.32924631 |  |  | 1517606
| 789 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (32924630) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (32924630) |  | 0 / 3 | [] |  |  | JCA.32924630 |  |  | 1517606
| 790 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (32924632) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (32924632) |  | 0 / 1 | [] |  |  | JCA.32924632 |  |  | 1517606
| 791 | STJC-AREAS-FINAL-INSPECTION-03-GA-GO | AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (32924633) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (32924633) |  | 0 / 1 | [] |  |  | JCA.32924633 |  |  | 1517606
| 792 | STJC-AREAS-FINAL-INSPECTION-04-GA-GO | EMPENNAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (32924635) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (32924635) |  | 0 / 1 | [] |  |  | JCA.32924635 |  |  | 1517606
| 793 | STJC-AREAS-FINAL-INSPECTION-05-GA-GO | AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (32924636) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (32924636) |  | 0 / 1 | [] |  |  | JCA.32924636 |  |  | 1517606
| 794 | STJC-AREAS-FINAL-INSPECTION-06-GA-GO | L/H AND R/H WINGS FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (32924653) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (32924653) |  | 0 / 1 | [] |  |  | JCA.32924653 |  |  | 1517606
| 795 | STJC-AREAS-FINAL-INSPECTION-07-GA-GO | LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (32924652) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (32924652) |  | 0 / 1 | [] |  |  | JCA.32924652 |  |  | 1517606
| 796 | STJC-AREAS-FINAL-INSPECTION-08-GA-GO | ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (32924655) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (32924655) |  | 0 / 1 | [] |  |  | JCA.32924655 |  |  | 1517606
| 797 | STJC-AREAS-FINAL-INSPECTION-09-GA-GO | APU FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (32924654) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (32924654) |  | 0 / 1 | [] |  |  | JCA.32924654 |  |  | 1517606
| 798 | STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (32924658) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-11 |  | [] | ACFT RELEASE |  |  |  | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (32924658) |  | 0 / 1 | [] |  |  | JCA.32924658 |  |  | 1517606
| 799 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (32924657) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (32924657) |  | 0 / 4 | [] |  |  | JCA.32924657 |  |  | 1517606
| 800 | 32596938 | 22-70-00-01-0-A (03) / FMC DATA UPLOAD | 32596938 / 22-70-00-01-0-A (03) / FMC DATA UPLOAD (32596938) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 22-70 |  | [] | TC/P |  |  |  | 32596938 / 22-70-00-01-0-A (03) / FMC DATA UPLOAD (32596938) |  | 0 / 1 | [] |  |  | MET.32596938 | 01.Aug.2026 | 11 | 2026-08-01 | D
| 801 | 242000-21-1-001 | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION (32450186) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.086806 | 17.Jul.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-21 |  | [] | --, TC/P, -- |  |  |  | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION (32450186) |  | 0 / 3 | [] |  |  | MET.32450186 | 45566:21 | 48:42 | 2026-07-24 | H
| 802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:36 | 1899-12-31 22:02 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) |  | 1 / 1 | [] |  |  | MET.32608234 | 45545:41 | 28:02 | 2026-07-22 | H
| 803 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 381000-01-1 (3) / WATER TANK DISINFECTION (32626111) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 38-10 |  | [] | OPS/LK |  |  |  | 381000-01-1 (3) / WATER TANK DISINFECTION (32626111) |  | 0 / 1 | [] |  |  | MET.32626111 | 23.Sep.2026 | 64 | 2026-09-23 | D
| 804 | 32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 32840057 / DCC-32S (13) / DCC A32S DAILY CABIN CHECK (32840057) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.41667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, --, --, --, --, -- |  |  | This task is not required after the CRS of a higher-level letter check (A-Check, C-Check, 6Y or 12Y) | 32840057 / DCC-32S (13) / DCC A32S DAILY CABIN CHECK (32840057) |  | 0 / 9 | [] |  |  | MET.32840057 | 18.Jul.2026 | -2d, 4h | 2026-07-18 | D
| 810 | CCC-32S | CCC-32S (05) / A32S CABIN CRITICAL CHECK | CCC-32S (05) / A32S CABIN CRITICAL CHECK (32913243) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13194 | 17.Jul.2026 22:00 | 0.13194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, -- |  |  | To Remove step H. (Remove IFE CHECK as per T/Q: 692582) that Requestd by IFE ENGG H. IFE CONNECTIVITY CHECK 1. Performs a connectivity (satcom) test in accordance with THALES supplement as per AMM 44-31-01- 710-801. rectify as required. --------------------------------------------------------------------- ------------------------------------------ STEP D REVISED as per T/Q: 757461 -------------------------------------------------------- As per T/Q: 779111and 779112 andt T/Q;779113 T/Q: 779115 to add H. IFE CONNECTIVITY CHECK 1. CHECK THE FUNCTIONALITY OF THE CONNECTIVITY SYSTEM ONBOARD AS PER AIRBUS AMM 46-41-00-720-802-A. (if applicable)” 2. If the aircraft isequivalent to the Eclipse system, verify the following: A. CONFIRM The Ground Test and Reset switches are in the DISABLED position with the switch guards engaged. B. CONFIRM The Connectivity switch in the cockpit is pressed and fully seated. | CCC-32S (05) / A32S CABIN CRITICAL CHECK (32913243) |  | 0 / 8 | [] |  |  | MET.32913243 | 18.Jul.2026 | -2d, 22h | 2026-07-18 | D
| 811 | 94844878 | O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS | 94844878 / O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS (94844878) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] |  |  |  |  | 94844878 / O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS (94844878) |  | 0 / 1 | [] |  |  | WO.94844878 | 18.Jul.2026 | -3d, 4h | 2026-07-18 | D
| 812 | 94844876 | L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 | 94844876 / L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 (94844876) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-00 |  | [] |  |  |  |  | 94844876 / L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 (94844876) |  | 0 / 1 | [] |  |  | WO.94844876 | 18.Jul.2026 | -3d, 3h | 2026-07-18 | D
| 813 | 32977683 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL | 32977683 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL (32977683) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977683 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL (32977683) |  | 0 / 1 | [] |  |  | WO.32977683 | 18.Jul.2026 | -2d, 13h | 2026-07-18 | D
| 814 | 32977684 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) |  | 0 / 1 | [] |  |  | WO.32977684 | 18.Jul.2026 | -2d, 13h | 2026-07-18 | D
| 815 | 32977685 | LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) |  | 0 / 1 | [] |  |  | WO.32977685 | 18.Jul.2026 | -2d, 13h | 2026-07-18 | D
| 816 | 32977864 | PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. | 32977864 / PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. (32977864) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977864 / PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. (32977864) |  | 0 / 1 | [] |  |  | WO.32977864 | 18.Jul.2026 | -2d, 11h | 2026-07-18 | D
| 817 | 32977871 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) |  | 0 / 1 | [] |  |  | WO.32977871 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 818 | 32977873 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) |  | 0 / 1 | [] |  |  | WO.32977873 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 819 | 32977874 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) |  | 0 / 1 | [] |  |  | WO.32977874 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) |  | 0 / 1 | [] |  |  | WO.32977881 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 821 | 32977882 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) |  | 0 / 1 | [] |  |  | WO.32977882 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 822 | 32977883 | PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:40 | 1900-01-01 00:58 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) |  | 0 / 1 | [] |  |  | WO.32977883 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 823 | 32977884 | PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:50 | 1900-01-01 00:48 |  | 0.29167 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) |  | 0 / 1 | [] |  |  | WO.32977884 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) |  | 0 / 1 | [] |  |  | WO.32977904 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 825 | 32977905 | PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) |  | 0 / 1 | [] |  |  | WO.32977905 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 826 | 32977906 | PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 32977906 / PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977906) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977906 / PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977906) |  | 0 / 1 | [] |  |  | WO.32977906 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 827 | 32977907 | PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) |  | 0 / 1 | [] |  |  | WO.32977907 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 828 | 32977908 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. | 32977908 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. (32977908) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977908 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. (32977908) |  | 0 / 1 | [] |  |  | WO.32977908 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 829 | 32977909 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) |  | 0 / 1 | [] |  |  | WO.32977909 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 830 | 32977910 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) |  | 0 / 1 | [] |  |  | WO.32977910 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 831 | 32977911 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) |  | 0 / 1 | [] |  |  | WO.32977911 | 18.Jul.2026 | -2d, 10h | 2026-07-18 | D
| 832 | 32978070 | FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] |  |  |  |  | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) |  | 0 / 1 | [] |  | 01 | WO.32978070 | 18.Jul.2026 | -2d, 7h | 2026-07-18 | D
| 833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) |  | 0 / 1 | [] |  |  | WO.32978236 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 834 | 32978238 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. | 32978238 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978238 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) |  | 0 / 1 | [] |  |  | WO.32978238 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 835 | 32978240 | NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) |  | 0 / 1 | [] |  |  | WO.32978240 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 836 | 32978243 | NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) |  | 0 / 1 | [] |  |  | WO.32978243 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 837 | 32978247 | NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) |  | 0 / 1 | [] |  |  | WO.32978247 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) |  | 0 / 1 | [] |  |  | WO.32978249 | 18.Jul.2026 | -2d, 6h | 2026-07-18 | D
| 839 | 32978253 | LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) |  | 0 / 1 | [] |  |  | WO.32978253 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 840 | 32978254 | LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. | 32978254 / LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. (32978254) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978254 / LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. (32978254) |  | 0 / 1 | [] |  |  | WO.32978254 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 841 | 32978259 | LH MLG---PNT NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. | 32978259 / LH MLG---PNT NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978259 / LH MLG---PNT NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) |  | 0 / 1 | [] |  |  | WO.32978259 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 842 | 32978265 | LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. | 32978265 / LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. (32978265) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978265 / LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. (32978265) |  | 0 / 1 | [] |  |  | WO.32978265 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) |  | 0 / 1 | [] |  |  | WO.32978273 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 844 | 32978279 | RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) |  | 0 / 1 | [] |  |  | WO.32978279 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 845 | 32978280 | MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) |  | 0 / 1 | [] |  |  | WO.32978280 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 846 | 32978281 | RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. | 32978281 / RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. (32978281) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978281 / RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. (32978281) |  | 0 / 1 | [] |  |  | WO.32978281 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 847 | 32978282 | RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" | 32978282 / RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" (32978282) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978282 / RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" (32978282) |  | 0 / 1 | [] |  |  | WO.32978282 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) |  | 0 / 1 | [] |  |  | WO.32978291 | 18.Jul.2026 | -2d, 5h | 2026-07-18 | D
| 849 | 32978481 | RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] |  |  |  |  | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) |  | 0 / 1 | [] |  |  | WO.32978481 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 850 | 32978506 | LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. | 32978506 / LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. (32978506) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] |  |  |  |  | 32978506 / LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. (32978506) |  | 0 / 1 | [] |  |  | WO.32978506 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 851 | 32978507 | FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. | 32978507 / FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. (32978507) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978507 / FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. (32978507) |  | 0 / 1 | [] |  |  | WO.32978507 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 852 | 32978509 | FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. | 32978509 / FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. (32978509) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978509 / FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. (32978509) |  | 0 / 1 | [] |  |  | WO.32978509 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 853 | 32978510 | FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 11:00 | 1899-12-31 17:38 |  | 0.93056 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) |  | 0 / 1 | [] |  |  | WO.32978510 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 854 | 32978546 | FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) |  | 0 / 1 | [] |  |  | WO.32978546 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 855 | 32978563 | FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) |  | 0 / 1 | [] |  |  | WO.32978563 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 856 | 32978565 | FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED | 32978565 / FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED (32978565) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978565 / FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED (32978565) |  | 0 / 1 | [] |  |  | WO.32978565 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 857 | 32978566 | FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. | 32978566 / FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. (32978566) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978566 / FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. (32978566) |  | 0 / 1 | [] |  |  | WO.32978566 | 19.Jul.2026 | -2d, 3h | 2026-07-19 | D
| 858 | 32978568 | FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) |  | 0 / 1 | [] |  |  | WO.32978568 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 859 | 32978570 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) |  | 0 / 1 | [] |  |  | WO.32978570 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) |  | 0 / 1 | [] |  |  | WO.32978583 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 861 | 32978585 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) |  | 0 / 1 | [] |  |  | WO.32978585 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) |  | 0 / 1 | [] |  |  | WO.32978590 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 863 | 32978591 | FWD CARGO DOOR---PNT---NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. | 32978591 / FWD CARGO DOOR---PNT---NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. (32978591) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978591 / FWD CARGO DOOR---PNT---NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. (32978591) |  | 0 / 1 | [] |  |  | WO.32978591 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 864 | 32978593 | FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT | 32978593 / FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT (32978593) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978593 / FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT (32978593) |  | 0 / 1 | [] |  |  | WO.32978593 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 865 | 32978600 | FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. | 32978600 / FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. (32978600) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978600 / FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. (32978600) |  | 0 / 1 | [] |  |  | WO.32978600 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 866 | 32978626 | FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) |  | 0 / 1 | [] |  |  | WO.32978626 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 867 | 32978634 | AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" | 32978634 / AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" (32978634) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978634 / AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" (32978634) |  | 0 / 1 | [] |  |  | WO.32978634 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 868 | 32978638 | AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" | 32978638 / AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" (32978638) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978638 / AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" (32978638) |  | 0 / 1 | [] |  |  | WO.32978638 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 869 | 32978643 | AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. | 32978643 / AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. (32978643) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978643 / AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. (32978643) |  | 0 / 1 | [] |  |  | WO.32978643 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) |  | 0 / 1 | [] |  |  | WO.32978648 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) |  | 0 / 1 | [] |  |  | WO.32978649 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 872 | 32978650 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) |  | 0 / 1 | [] |  |  | WO.32978650 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 873 | 32978651 | AFT CARGO DOOR---PNT---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. | 32978651 / AFT CARGO DOOR---PNT---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978651 / AFT CARGO DOOR---PNT---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) |  | 0 / 1 | [] |  |  | WO.32978651 | 19.Jul.2026 | -2d, 2h | 2026-07-19 | D
| 874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) |  | 0 / 1 | [] |  |  | WO.32978848 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-04 | 17.Jul.2026 22:00 | 0.27778 | 19.Jul.2026 03:10 | 1900-01-01 01:28 |  | 1900-01-03 11:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) |  | 0 / 1 | [] |  |  | WO.32978869 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 876 | 32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 32978879 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY (32978879) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978879 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY (32978879) |  | 0 / 1 | [] |  |  | WO.32978879 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 877 | 32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.91667 | 17.Jul.2026 22:00 | 0.22917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) |  | 0 / 1 | [] |  |  | WO.32978900 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) |  | 0 / 1 | [] |  |  | WO.32978919 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) |  | 0 / 1 | [] |  |  | WO.32978925 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) |  | 0 / 1 | [] |  |  | WO.32978965 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 881 | 32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) |  | 0 / 1 | [] |  |  | WO.32979121 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) |  | 0 / 1 | [] |  |  | WO.32979157 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) |  | 0 / 1 | [] |  |  | WO.32979156 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) |  | 0 / 1 | [] |  |  | WO.32979222 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) |  | 0 / 1 | [] |  |  | WO.32979231 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 886 | 32979256 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP KICK STRIP WITH CUT 0.5 IN. | 32979256 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP KICK STRIP WITH CUT 0.5 IN. (32979256) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979256 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP KICK STRIP WITH CUT 0.5 IN. (32979256) |  | 0 / 1 | [] |  |  | WO.32979256 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 887 | 32979285 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. | 32979285 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. (32979285) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979285 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. (32979285) |  | 0 / 1 | [] |  |  | WO.32979285 | 19.Jul.2026 | -1d, 22h | 2026-07-19 | D
| 888 | 32979304 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. | 32979304 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. (32979304) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979304 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. (32979304) |  | 0 / 1 | [] |  |  | WO.32979304 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 889 | 32979322 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.03 IN | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.03 IN (32979322) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.03 IN (32979322) |  | 0 / 1 | [] |  |  | WO.32979322 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 890 | 32979401 | FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 20.Jul.2026 19:00 | 0.40139 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) |  | 0 / 1 | [] |  |  | WO.32979401 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 891 | 32979406 | FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 20.Jul.2026 19:00 | 0.40139 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) |  | 0 / 1 | [] |  |  | WO.32979406 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 892 | 32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 32979530 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS (32979530) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] |  |  |  |  | 32979530 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS (32979530) |  | 0 / 1 | [] |  |  | WO.32979530 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 893 | 32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 32979557 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH (32979557) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] |  |  |  |  | 32979557 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH (32979557) |  | 0 / 1 | [] |  |  | WO.32979557 | 19.Jul.2026 | -1d, 21h | 2026-07-19 | D
| 894 | 32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] |  |  |  |  | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) |  | 0 / 1 | [] |  |  | WO.32979661 | 19.Jul.2026 | -1d, 20h | 2026-07-19 | D
| 895 | 32979731 | FWD AVIO COMP DOOR---AP---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. | 32979731 / FWD AVIO COMP DOOR---AP---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32979731 / FWD AVIO COMP DOOR---AP---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) |  | 0 / 1 | [] |  |  | WO.32979731 | 19.Jul.2026 | -1d, 20h | 2026-07-19 | D
| 897 | 32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:25 | 1899-12-31 01:13 |  | 0.91667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) |  | 0 / 1 | [] |  |  | WO.32979981 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:26 | 1899-12-31 01:12 |  | 1899-12-31 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) |  | 0 / 1 | [] |  |  | WO.32980018 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 899 | 32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) |  | 0 / 1 | [] |  |  | WO.32980020 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 900 | 32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) |  | 0 / 1 | [] |  |  | WO.32980022 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 901 | 32391506 | 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) |  | 0 / 3 | [] |  | 002 | ME.32391506 | 25.Jul.2026 | 4 | 2026-07-25 | D
| 902 | 32439904 | 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) |  | 0 / 3 | [] |  | 2522GM | ME.32439904 | 06.Oct.2026 | 77 | 2026-10-06 | D
| 903 | 32163655 | 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32163655 / 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163655) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32163655 / 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163655) |  | 0 / 4 | [] |  | 100 | ME.32163655 | 1571:23 | 217:59 | 2026-08-10 | H
| 904 | 32163652 | 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32163652 / 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163652) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32163652 / 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163652) |  | 0 / 4 | [] |  | 002 | ME.32163652 | 38063:25 | 217:59 | 2026-08-10 | H
| 905 | 81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | 81172702 / IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 (81172702) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Jul.2026 08:21 | 1900-01-16 20:17 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 44-26-00 |  | [] |  |  |  |  | 81172702 / IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 (81172702) |  | 0 / 1 | [] |  |  | WO.81172702 | 31.Oct.2026 | 102 | 2026-10-31 | D
| 906 | 94844831 | DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN | 94844831 / DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN (94844831) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:21 | 1900-01-07 20:17 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844831 / DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN (94844831) |  | 0 / 1 | [] |  |  | WO.94844831 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 907 | 94844832 | DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED | 94844832 / DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED (94844832) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:18 | 1900-01-07 20:20 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844832 / DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED (94844832) |  | 0 / 1 | [] |  |  | WO.94844832 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 908 | 94844833 | DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED | 94844833 / DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED (94844833) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:15 | 1900-01-07 20:23 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844833 / DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED (94844833) |  | 0 / 1 | [] |  |  | WO.94844833 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 909 | 94844834 | DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN | 94844834 / DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN (94844834) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:05 | 1900-01-07 21:33 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844834 / DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN (94844834) |  | 0 / 1 | [] |  |  | WO.94844834 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 910 | 94844835 | DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN | 94844835 / DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN (94844835) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:03 | 1900-01-07 21:35 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844835 / DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN (94844835) |  | 0 / 1 | [] |  |  | WO.94844835 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 911 | 94844836 | RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:49 | 1900-01-07 20:49 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) |  | 0 / 1 | [] |  |  | WO.94844836 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 912 | 94844837 | DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN | 94844837 / DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN (94844837) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 06:49 | 1900-01-07 21:49 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844837 / DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN (94844837) |  | 0 / 1 | [] |  |  | WO.94844837 | 09.Nov.2026 | 111 | 2026-11-09 | D
| 913 | 32345876 | EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 | 32345876 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345876) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 17.Jul.2026 22:00 | 0.22222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 32345876 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345876) |  | 0 / 5 | [] |  |  | ME.32345876 | 31.Dec.2026 | 163 | 2026-12-31 | D
| 914 | 32850432 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  |  | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) |  | 0 / 6 | [] |  |  | ME.32850432 | 06.Oct.2026 | 77 | 2026-10-06 | D
| 915 | 15777708 | EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | 15777708 / EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777708) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 17.Jul.2026 22:00 | 0.15278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | REVISED TO UPDATE WORKSTEP 5 TO MATCH REVISION NUMBER (02 INSTEAD OF 01) | 15777708 / EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777708) |  | 0 / 5 | [] |  |  | ME.15777708 | 22.Apr.2032 | 2102 | 2032-04-22 | D
| 916 | 15777769 | EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | 15777769 / EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777769) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19444 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777769 / EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777769) |  | 0 / 5 | [] |  |  | ME.15777769 | 22.Apr.2032 | 2102 | 2032-04-22 | D
| 917 | 28372303 | REPLACE DVE90-07/7369 (VALVE-SOLENOID) | 28372303 / REPLACE DVE90-07/7369 (VALVE-SOLENOID) (28372303) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-00 |  | [] |  |  |  |  | 28372303 / REPLACE DVE90-07/7369 (VALVE-SOLENOID) (28372303) |  | 0 / 1 | [] |  | 000 | ME.28372303 | 26.Sep.2026 | 67 | 2026-09-26 | D
| 918 | 28611923 | S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION | 28611923 / S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION (28611923) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 28611923 / S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION (28611923) |  | 0 / 4 | [] |  |  | ME.28611923 | 31.Oct.2026 | 102 | 2026-10-31 | D
| 919 | 32822269 | S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY | 32822269 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822269) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26 |  | [] |  |  |  |  | 32822269 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822269) |  | 0 / 2 | [] |  |  | ME.32822269 | 14.Dec.2026 | 146 | 2026-12-14 | D
| 920 | 32822529 | S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) |  | 0 / 2 | [] |  |  | ME.32822529 | 20.Jul.2026 | -1 | 2026-07-20 | D
| 921 | 30205720 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] | INSPECTION |  |  |  | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) |  | 0 / 1 | [] |  |  | ME.30205720 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 922 | 30262642 | S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL | 30262642 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262642) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | If the part is S/D, please hold the plan and Inform Engineering . | 30262642 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262642) |  | 0 / 4 | [] |  |  | ME.30262642 | 03.Oct.2026 | 74 | 2026-10-03 | D
| 923 | 32800094 | S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK | 32800094 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800094) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 07:00 | 17.Jul.2026 22:00 | 1899-12-31 07:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | Please C/W. This ER is issued to perform Bleed Health Check on A320 CEO fleet EBAS system. Kindly schedule this task in the C-Check. | 32800094 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800094) |  | 0 / 18 | [] |  |  | ME.32800094 | 09.Apr.2029 | 993 | 2029-04-09 | D
| 924 | 32872501 | S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) |  | 0 / 3 | [] |  |  | ME.32872501 | 07.Aug.2026 | 17 | 2026-08-07 | D
| 926 | 32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 32980026 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY (32980026) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980026 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY (32980026) |  | 0 / 1 | [] |  |  | WO.32980026 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) |  | 0 / 1 | [] |  |  | WO.32980031 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 928 | 32980047 | LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) | 32980047 / LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) (32980047) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980047 / LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) (32980047) |  | 0 / 1 | [] |  |  | WO.32980047 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 929 | 32980064 | LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) | 32980064 / LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) (32980064) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980064 / LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) (32980064) |  | 0 / 1 | [] |  |  | WO.32980064 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 930 | 32980065 | LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 | 32980065 / LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 (32980065) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980065 / LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 (32980065) |  | 0 / 1 | [] |  |  | WO.32980065 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 931 | 32980071 | LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) |  | 0 / 1 | [] |  |  | WO.32980071 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 932 | 32980080 | LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) |  | 0 / 1 | [] |  |  | WO.32980080 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 933 | 32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) |  | 0 / 1 | [] |  |  | WO.32980070 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 934 | 32980077 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. | 32980077 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. (32980077) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980077 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. (32980077) |  | 0 / 1 | [] |  |  | WO.32980077 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 935 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) |  | 0 / 1 | [] |  |  | MET.32807083 | 22.Aug.2026 | 32 | 2026-08-22 | D
| 936 | 32980091 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) |  | 0 / 1 | [] |  |  | WO.32980091 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 937 | 32980104 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. | 32980104 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. (32980104) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980104 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. (32980104) |  | 0 / 1 | [] |  |  | WO.32980104 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 938 | 32980083 | LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) |  | 0 / 1 | [] |  |  | WO.32980083 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 939 | 32980111 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE | 32980111 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE (32980111) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 14:33 | 0.58681 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980111 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE (32980111) |  | 0 / 1 | [] |  |  | WO.32980111 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) |  | 0 / 1 | [] |  |  | WO.32980087 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 941 | 32980118 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN | 32980118 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN (32980118) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980118 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN (32980118) |  | 0 / 1 | [] |  |  | WO.32980118 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 942 | 32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.22222 | 20.Jul.2026 03:27 | 1899-12-31 01:11 |  | 0.66667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) |  | 0 / 1 | [] |  |  | WO.32980133 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 943 | 44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK (32949267) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44-21 |  | [] |  |  |  |  | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK (32949267) |  | 0 / 1 | [] |  |  | MET.32949267 | 19.Jul.2026 | -2 | 2026-07-19 | D
| 944 | 32917899 | ISC/IN SERVCE CHECK_N | 32917899 / ISC/IN SERVCE CHECK_N (32917899) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 32917899 / ISC/IN SERVCE CHECK_N (32917899) |  | 0 / 1 | [] |  |  | ME.32917899 | 19.Jul.2026 | -1d, 23h | 2026-07-19 | D
| 945 | 32420054 | W_N/WEEKLY CHECK | 32420054 / W_N/WEEKLY CHECK (32420054) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 32420054 / W_N/WEEKLY CHECK (32420054) |  | 0 / 1 | [] |  |  | ME.32420054 | 27.Jul.2026 | 6 | 2026-07-27 | D
| 946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) |  | 0 / 1 | [] |  |  | WO.32980135 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 947 | ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) (32917900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11806 | 17.Jul.2026 22:00 | 0.11806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12 |  | [] | TC/P, --, --, -- |  |  |  | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) (32917900) |  | 0 / 4 | [] |  |  | MET.32917900 | 19.Jul.2026 | -2d, 4h | 2026-07-19 | D
| 948 | WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | WEEKLY-32S (05) / WEEKLY 32S CHECK (32822769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.24653 | 17.Jul.2026 22:00 | 0.24653 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12 |  | [] | TC/P, --, --, --, --, --, --, -- |  |  |  | WEEKLY-32S (05) / WEEKLY 32S CHECK (32822769) |  | 0 / 8 | [] |  |  | MET.32822769 | 27.Jul.2026 | 6 | 2026-07-27 | D
| 949 | 32980140 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) |  | 0 / 1 | [] |  |  | WO.32980140 | 19.Jul.2026 | -1d, 19h | 2026-07-19 | D
| 950 | 32980164 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) |  | 0 / 1 | [] |  |  | WO.32980164 | 19.Jul.2026 | -1d, 18h | 2026-07-19 | D
| 951 | 32980175 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP KICK STRIP WITH CUT DIM: L=1 IN | 32980175 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP KICK STRIP WITH CUT DIM: L=1 IN (32980175) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980175 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP KICK STRIP WITH CUT DIM: L=1 IN (32980175) |  | 0 / 1 | [] |  |  | WO.32980175 | 19.Jul.2026 | -1d, 18h | 2026-07-19 | D
| 952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) |  | 0 / 1 | [] |  |  | WO.32980177 | 19.Jul.2026 | -1d, 18h | 2026-07-19 | D
| 953 | 32980186 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. | 32980186 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. (32980186) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980186 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. (32980186) |  | 0 / 1 | [] |  |  | WO.32980186 | 19.Jul.2026 | -1d, 18h | 2026-07-19 | D
| 954 | 32980176 | REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) |  | 0 / 1 | [] |  |  | WO.32980176 | 19.Jul.2026 | -1d, 18h | 2026-07-19 | D
| 955 | 32980920 | FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) |  | 0 / 1 | [] |  |  | WO.32980920 | 19.Jul.2026 | -1d, 17h | 2026-07-19 | D
| 956 | 32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 32981647 / AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY (32981647) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32981647 / AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY (32981647) |  | 0 / 1 | [] |  |  | WO.32981647 | 19.Jul.2026 | -1d, 16h | 2026-07-19 | D
| 957 | 32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 32981683 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. (32981683) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981683 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. (32981683) |  | 0 / 1 | [] |  |  | WO.32981683 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) |  | 0 / 1 | [] |  |  | WO.32981716 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) |  | 0 / 1 | [] |  |  | WO.32981721 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 960 | 32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) |  | 0 / 1 | [] |  |  | WO.32981726 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) |  | 0 / 1 | [] |  |  | WO.32981754 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 962 | 32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) |  | 0 / 1 | [] |  |  | WO.32981772 | 19.Jul.2026 | -1d, 15h | 2026-07-19 | D
| 963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) |  | 0 / 1 | [] |  |  | WO.32981774 | 19.Jul.2026 | -1d, 14h | 2026-07-19 | D
| 964 | 32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.625 | 17.Jul.2026 22:00 | 0.625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) |  | 0 / 1 | [] |  |  | WO.32981816 | 19.Jul.2026 | -1d, 14h | 2026-07-19 | D
| 966 | 32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 32982172 / AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY (32982172) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982172 / AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY (32982172) |  | 0 / 1 | [] |  |  | WO.32982172 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 968 | 32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 32982194 / CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS (32982194) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 16:03 | 0.52431 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982194 / CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS (32982194) |  | 0 / 1 | [] |  |  | WO.32982194 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 969 | 32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 32982195 / S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED (32982195) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982195 / S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED (32982195) |  | 0 / 1 | [] |  |  | WO.32982195 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 970 | 32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 32982197 / CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS (32982197) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 14:54 | 1899-12-31 13:44 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982197 / CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS (32982197) |  | 0 / 1 | [] |  |  | WO.32982197 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 971 | 32982199 | RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 32982199 / RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982199) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 17:12 | 1899-12-31 11:26 |  | 0.0625 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982199 / RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982199) |  | 0 / 1 | [] |  |  | WO.32982199 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 972 | 32982200 | RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 32982200 / RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982200) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 17:00 | 1899-12-31 11:38 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982200 / RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982200) |  | 0 / 1 | [] |  |  | WO.32982200 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 973 | 32982202 | RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 32982202 / RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982202) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982202 / RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982202) |  | 0 / 1 | [] |  |  | WO.32982202 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 974 | 32982203 | RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 32982203 / RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982203) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 16:39 | 1899-12-31 11:59 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982203 / RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982203) |  | 0 / 1 | [] |  |  | WO.32982203 | 19.Jul.2026 | -1d, 10h | 2026-07-19 | D
| 978 | 32983857 | PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) |  | 0 / 1 | [] |  |  | WO.32983857 | 20.Jul.2026 | -21h, 44m | 2026-07-20 | D
| 979 | 32983861 | PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) |  | 0 / 1 | [] |  |  | WO.32983861 | 20.Jul.2026 | -21h, 39m | 2026-07-20 | D
| 980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) |  | 0 / 1 | [] |  |  | WO.32983866 | 20.Jul.2026 | -21h, 35m | 2026-07-20 | D
| 981 | 32983876 | PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. | 32983876 / PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. (32983876) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983876 / PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. (32983876) |  | 0 / 1 | [] |  |  | WO.32983876 | 20.Jul.2026 | -21h, 30m | 2026-07-20 | D
| 982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) |  | 0 / 1 | [] |  |  | WO.32983882 | 20.Jul.2026 | -21h, 27m | 2026-07-20 | D
| 983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) |  | 0 / 1 | [] |  |  | WO.32983893 | 20.Jul.2026 | -21h, 24m | 2026-07-20 | D
| 984 | 32983896 | LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION | 32983896 / LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION (32983896) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32983896 / LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION (32983896) |  | 0 / 1 | [] |  |  | WO.32983896 | 20.Jul.2026 | -21h, 22m | 2026-07-20 | D
| 985 | 32983897 | PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. | 32983897 / PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. (32983897) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983897 / PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. (32983897) |  | 0 / 1 | [] |  |  | WO.32983897 | 20.Jul.2026 | -21h, 22m | 2026-07-20 | D
| 986 | 32983910 | PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) |  | 0 / 1 | [] |  |  | WO.32983910 | 20.Jul.2026 | -21h, 20m | 2026-07-20 | D
| 987 | 32983929 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) |  | 0 / 1 | [] |  |  | WO.32983929 | 20.Jul.2026 | -21h, 18m | 2026-07-20 | D
| 988 | 32983937 | PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. | 32983937 / PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. (32983937) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 15:30 | 0.54722 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983937 / PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. (32983937) |  | 0 / 1 | [] |  |  | WO.32983937 | 20.Jul.2026 | -21h, 16m | 2026-07-20 | D
| 989 | 32983944 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. | 32983944 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. (32983944) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983944 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. (32983944) |  | 0 / 1 | [] |  |  | WO.32983944 | 20.Jul.2026 | -21h, 13m | 2026-07-20 | D
| 990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) |  | 0 / 1 | [] |  |  | WO.32983950 | 20.Jul.2026 | -21h, 10m | 2026-07-20 | D
| 991 | 32983948 | OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) |  | 0 / 1 | [] |  |  | WO.32983948 | 20.Jul.2026 | -21h, 10m | 2026-07-20 | D
| 992 | 32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 32983996 / CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. (32983996) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.35417 | 17.Jul.2026 22:00 | 0.11806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32983996 / CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. (32983996) |  | 0 / 1 | [] |  |  | WO.32983996 | 20.Jul.2026 | -20h, 58m | 2026-07-20 | D
| 993 | 32984016 | OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) | 32984016 / OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) (32984016) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984016 / OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) (32984016) |  | 0 / 1 | [] |  |  | WO.32984016 | 20.Jul.2026 | -20h, 55m | 2026-07-20 | D
| 994 | 32984140 | AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) |  | 0 / 1 | [] |  |  | WO.32984140 | 20.Jul.2026 | -20h, 15m | 2026-07-20 | D
| 995 | 32984158 | PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) |  | 0 / 1 | [] |  |  | WO.32984158 | 20.Jul.2026 | -20h, 12m | 2026-07-20 | D
| 996 | 32984174 | PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) |  | 0 / 1 | [] |  |  | WO.32984174 | 20.Jul.2026 | -20h, 6m | 2026-07-20 | D
| 997 | 32984360 | FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) |  | 0 / 1 | [] |  |  | WO.32984360 | 20.Jul.2026 | -19h, 27m | 2026-07-20 | D
| 998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) |  | 0 / 1 | [] |  |  | WO.32984375 | 20.Jul.2026 | -19h, 25m | 2026-07-20 | D
| 999 | 32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 32984263 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS (32984263) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32984263 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS (32984263) |  | 0 / 1 | [] |  |  | WO.32984263 | 20.Jul.2026 | -19h, 44m | 2026-07-20 | D
| 1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) |  | 0 / 1 | [] |  |  | WO.32984479 | 20.Jul.2026 | -19h, 16m | 2026-07-20 | D
| 1001 | 32984513 | R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) |  | 0 / 1 | [] |  |  | WO.32984513 | 20.Jul.2026 | -19h, 8m | 2026-07-20 | D
| 1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) |  | 0 / 1 | [] |  |  | WO.32984550 | 20.Jul.2026 | -19h, 5m | 2026-07-20 | D
| 1003 | 32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 32984585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS (32984585) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32984585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS (32984585) |  | 0 / 1 | [] |  |  | WO.32984585 | 20.Jul.2026 | -18h, 58m | 2026-07-20 | D
| 1004 | 32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 32984729 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. (32984729) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984729 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. (32984729) |  | 0 / 1 | [] |  |  | WO.32984729 | 20.Jul.2026 | -18h, 16m | 2026-07-20 | D
| 1005 | 32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 32984742 / CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. (32984742) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984742 / CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. (32984742) |  | 0 / 1 | [] |  |  | WO.32984742 | 20.Jul.2026 | -18h, 14m | 2026-07-20 | D
| 1006 | 32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 32984765 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. (32984765) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984765 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. (32984765) |  | 0 / 1 | [] |  |  | WO.32984765 | 20.Jul.2026 | -18h, 7m | 2026-07-20 | D
| 1007 | 32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) |  | 0 / 1 | [] |  |  | WO.32984781 | 20.Jul.2026 | -18h, 4m | 2026-07-20 | D
| 1008 | 32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) |  | 0 / 1 | [] |  |  | WO.32984766 | 20.Jul.2026 | -18h, 7m | 2026-07-20 | D
| 1009 | 32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) |  | 0 / 1 | [] |  |  | WO.32984823 | 20.Jul.2026 | -17h, 59m | 2026-07-20 | D
| 1010 | 32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) |  | 0 / 1 | [] |  |  | WO.32984820 | 20.Jul.2026 | -17h, 59m | 2026-07-20 | D
| 1011 | 32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) |  | 0 / 1 | [] |  |  | WO.32984829 | 20.Jul.2026 | -17h, 58m | 2026-07-20 | D
| 1012 | 32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) |  | 0 / 1 | [] |  |  | WO.32984848 | 20.Jul.2026 | -17h, 56m | 2026-07-20 | D
| 1013 | 32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) |  | 0 / 1 | [] |  |  | WO.32984883 | 20.Jul.2026 | -17h, 50m | 2026-07-20 | D
| 1014 | 32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 32984906 / CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 (32984906) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38 |  | [] |  |  |  |  | 32984906 / CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 (32984906) |  | 0 / 1 | [] |  |  | WO.32984906 | 20.Jul.2026 | -17h, 47m | 2026-07-20 | D
| 1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) |  | 0 / 1 | [] |  |  | WO.32984905 | 20.Jul.2026 | -17h, 47m | 2026-07-20 | D
| 1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) |  | 0 / 1 | [] |  |  | WO.32984942 | 20.Jul.2026 | -17h, 36m | 2026-07-20 | D
| 1017 | 32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) |  | 0 / 1 | [] |  |  | WO.32984945 | 20.Jul.2026 | -17h, 36m | 2026-07-20 | D
| 1018 | 32984975 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) |  | 0 / 1 | [] |  |  | WO.32984975 | 20.Jul.2026 | -17h, 29m | 2026-07-20 | D
| 1019 | 32984986 | AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) |  | 0 / 1 | [] |  |  | WO.32984986 | 20.Jul.2026 | -17h, 27m | 2026-07-20 | D
| 1020 | 32984983 | PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. | 32984983 / PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. (32984983) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32984983 / PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. (32984983) |  | 0 / 1 | [] |  |  | WO.32984983 | 20.Jul.2026 | -17h, 28m | 2026-07-20 | D
| 1021 | 32985000 | AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE | 32985000 / AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE (32985000) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985000 / AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE (32985000) |  | 0 / 1 | [] |  |  | WO.32985000 | 20.Jul.2026 | -17h, 26m | 2026-07-20 | D
| 1022 | 32985009 | PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) |  | 0 / 1 | [] |  |  | WO.32985009 | 20.Jul.2026 | -17h, 25m | 2026-07-20 | D
| 1023 | 32984981 | DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... | 32984981 / DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... (32984981) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32984981 / DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... (32984981) |  | 0 / 1 | [] |  |  | WO.32984981 | 20.Jul.2026 | -17h, 29m | 2026-07-20 | D
| 1024 | 32985016 | PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) |  | 0 / 1 | [] |  |  | WO.32985016 | 20.Jul.2026 | -17h, 23m | 2026-07-20 | D
| 1025 | 32985033 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. | 32985033 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. (32985033) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985033 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. (32985033) |  | 0 / 1 | [] |  |  | WO.32985033 | 20.Jul.2026 | -17h, 19m | 2026-07-20 | D
| 1027 | 32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) |  | 0 / 1 | [] |  |  | WO.32985067 | 20.Jul.2026 | -17h, 11m | 2026-07-20 | D
| 1028 | 32985066 | PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) |  | 0 / 1 | [] |  |  | WO.32985066 | 20.Jul.2026 | -17h, 11m | 2026-07-20 | D
| 1029 | 32985072 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) |  | 0 / 1 | [] |  |  | WO.32985072 | 20.Jul.2026 | -17h, 9m | 2026-07-20 | D
| 1030 | 32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 32985083 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985083) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985083 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985083) |  | 0 / 1 | [] |  |  | WO.32985083 | 20.Jul.2026 | -17h, 6m | 2026-07-20 | D
| 1031 | 32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 32985088 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985088) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985088 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985088) |  | 0 / 1 | [] |  |  | WO.32985088 | 20.Jul.2026 | -17h, 4m | 2026-07-20 | D
| 1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) |  | 0 / 1 | [] |  |  | WO.32985081 | 20.Jul.2026 | -17h, 7m | 2026-07-20 | D
| 1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) |  | 0 / 1 | [] |  |  | WO.32985124 | 20.Jul.2026 | -16h, 59m | 2026-07-20 | D
| 1034 | 32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 32985127 / CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] |  |  |  |  | 32985127 / CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) |  | 0 / 1 | [] |  |  | WO.32985127 | 20.Jul.2026 | -16h, 57m | 2026-07-20 | D
| 1035 | 32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 32985290 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT (32985290) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985290 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT (32985290) |  | 0 / 1 | [] |  |  | WO.32985290 | 20.Jul.2026 | -14h, 49m | 2026-07-20 | D
| 1036 | 32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT | 32985304 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT (32985304) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985304 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT (32985304) |  | 0 / 1 | [] |  |  | WO.32985304 | 20.Jul.2026 | -14h, 42m | 2026-07-20 | D
| 1037 | 32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 32985321 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985321) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985321 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985321) |  | 0 / 1 | [] |  |  | WO.32985321 | 20.Jul.2026 | -14h, 39m | 2026-07-20 | D
| 1038 | 32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 32985332 / CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY (32985332) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985332 / CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY (32985332) |  | 0 / 1 | [] |  |  | WO.32985332 | 20.Jul.2026 | -14h, 38m | 2026-07-20 | D
| 1039 | 32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) |  | 0 / 1 | [] |  |  | WO.32985334 | 20.Jul.2026 | -14h, 36m | 2026-07-20 | D
| 1040 | 32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) |  | 0 / 1 | [] |  |  | WO.32985336 | 20.Jul.2026 | -14h, 35m | 2026-07-20 | D
| 1041 | 32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) |  | 0 / 1 | [] |  |  | WO.32985337 | 20.Jul.2026 | -14h, 33m | 2026-07-20 | D
| 1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) |  | 0 / 1 | [] |  |  | WO.32985338 | 20.Jul.2026 | -14h, 32m | 2026-07-20 | D
| 1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) |  | 0 / 1 | [] |  |  | WO.32985341 | 20.Jul.2026 | -14h, 31m | 2026-07-20 | D
| 1044 | 32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) |  | 0 / 1 | [] |  |  | WO.32985342 | 20.Jul.2026 | -14h, 30m | 2026-07-20 | D
| 1045 | 32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 32985343 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY (32985343) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985343 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY (32985343) |  | 0 / 1 | [] |  |  | WO.32985343 | 20.Jul.2026 | -14h, 30m | 2026-07-20 | D
| 1046 | 32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 32985344 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED (32985344) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985344 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED (32985344) |  | 0 / 1 | [] |  |  | WO.32985344 | 20.Jul.2026 | -14h, 28m | 2026-07-20 | D
| 1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) |  | 0 / 1 | [] |  |  | WO.32985347 | 20.Jul.2026 | -14h, 27m | 2026-07-20 | D
| 1048 | 32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 32985349 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985349) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985349 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985349) |  | 0 / 1 | [] |  |  | WO.32985349 | 20.Jul.2026 | -14h, 26m | 2026-07-20 | D
| 1049 | 32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 32985350 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985350) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985350 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985350) |  | 0 / 1 | [] |  |  | WO.32985350 | 20.Jul.2026 | -14h, 26m | 2026-07-20 | D
| 1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) |  | 0 / 1 | [] |  |  | WO.32985351 | 20.Jul.2026 | -14h, 24m | 2026-07-20 | D
| 1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) |  | 0 / 1 | [] |  |  | WO.32985352 | 20.Jul.2026 | -14h, 23m | 2026-07-20 | D
| 1052 | 32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) |  | 0 / 1 | [] |  |  | WO.32985353 | 20.Jul.2026 | -14h, 21m | 2026-07-20 | D
| 1053 | 32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 32985354 / CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT (32985354) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985354 / CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT (32985354) |  | 0 / 1 | [] |  |  | WO.32985354 | 20.Jul.2026 | -14h, 21m | 2026-07-20 | D
| 1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) |  | 0 / 1 | [] |  |  | WO.32985355 | 20.Jul.2026 | -14h, 20m | 2026-07-20 | D
| 1055 | 32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) |  | 0 / 1 | [] |  |  | WO.32985357 | 20.Jul.2026 | -14h, 18m | 2026-07-20 | D
| 1056 | 32985503 | VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] |  |  |  |  | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) |  | 0 / 1 | [] |  |  | WO.32985503 | 20.Jul.2026 | -13h, 58m | 2026-07-20 | D
| 1061 | 32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 32985832 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, (32985832) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] |  |  |  |  | 32985832 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, (32985832) |  | 0 / 1 | [] |  |  | WO.32985832 | 20.Jul.2026 | -10h, 38m | 2026-07-20 | D
| 1062 | 32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 32985833 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. (32985833) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] |  |  |  |  | 32985833 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. (32985833) |  | 0 / 1 | [] |  |  | WO.32985833 | 20.Jul.2026 | -10h, 17m | 2026-07-20 | D
| 1063 | 32985836 | RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) |  | 0 / 1 | [] |  |  | WO.32985836 | 20.Jul.2026 | -9h, 57m | 2026-07-20 | D
| 1064 | 32985860 | L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) |  | 0 / 1 | [] |  |  | WO.32985860 | 20.Jul.2026 | -9h, 40m | 2026-07-20 | D
| 1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) |  | 0 / 1 | [] |  |  | WO.32985861 | 20.Jul.2026 | -9h, 38m | 2026-07-20 | D
| 1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) |  | 0 / 1 | [] |  |  | WO.32985871 | 20.Jul.2026 | -9h, 33m | 2026-07-20 | D
| 1067 | 32985872 | THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) |  | 0 / 1 | [] |  |  | WO.32985872 | 20.Jul.2026 | -9h, 30m | 2026-07-20 | D
| 1068 | 32985870 | L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH | 32985870 / L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH (32985870) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985870 / L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH (32985870) |  | 0 / 1 | [] |  |  | WO.32985870 | 20.Jul.2026 | -9h, 36m | 2026-07-20 | D
| 1069 | 32985875 | ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) |  | 0 / 1 | [] |  |  | WO.32985875 | 20.Jul.2026 | -9h, 26m | 2026-07-20 | D
| 1070 | 32985877 | ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) |  | 0 / 1 | [] |  |  | WO.32985877 | 20.Jul.2026 | -9h, 20m | 2026-07-20 | D
| 1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 19:30 | 0.38056 |  | 0.58333 | Idle | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | OPEN-UP |  |  |  | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) |  | 0 / 1 | [] |  |  | WO.32985880 | 20.Jul.2026 | -9h, 14m | 2026-07-20 | D