## ASF 05 JULY
Seq. No. | WO / Event Number | Task Description | Category | Status | Priority | Specialty | PARTS REQ. | Remarks
3 | 08-10-00-01-0-A | 08-10-00-01-0-A (01) / WIGHT & BALANCE | TASK CARD | Open | Normal | AP |  | CHECKLIST TO DO
24 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | TASK CARD | Open | Normal | CAB | Requested | TO DO
25 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (02) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | TASK CARD | Open | Normal | CAB | Requested | TO BE CLOSED
26 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (03) / CAPTAIN & F/O SEATS COVERS REPLACMENT | TASK CARD | Open | Normal | CAB | Requested | TO BE CLOSED
27 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (02) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | TASK CARD | Open | Normal | CAB | Requested | TO DO
28 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | TASK CARD | Open | Normal | CAB | Requested | I/W
29 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | TASK CARD | Open | Normal | CAB | Requested | TO BE CLOSED
30 | 25-SVA-01 | 25-SVA-01 (00) / COCKPIT CHECK | TASK CARD | Open | Normal | CAB |  | TO BE CLOSED (REQ INSP STAMP)
32 | 25-SVA-05 | 25-SVA-05 (00) / G/C SEAT REFRESH | TASK CARD | Open | Normal | SEAT |  | TO BE CLOSED
42 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | TASK CARD | Open | Normal | JOINT |  | TO DO
114 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | TASK CARD | Open | Normal | JOINT |  | TO DO (LAST 2 STEPS)
139 | 527100-01-1 | 527100-01-1 (5) / DOOR WARNING SYSTEM OPERATIONAL TEST | TASK CARD | Open | Normal | AV
274 | 30817928 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
275 | 30695782 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
276 | 29155917 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
277 | 29156041 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
278 | 29156135 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
279 | 29156197 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
280 | 29157167 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
281 | 29156251 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | EOD |  |  | FOMAX |  | NEED DETAILED CHECK OF PAPERWORK
317 | 32022300 | DOCTR KIT EXPIRY [30JUN 2026]. DOCTOR KIT WILL EXP ON 30 JUNE 2026 DEK # 096 DEK SN 7160 | GENERAL CABIN | Open | Normal | CAB |  | TO DO
319 | 80794771 | METAL STRIP LAV D BESIDE COMPARTMENT S302 AFT LWR SIDE METAL STRIP FOUND BROKEN. PIC ATTACHED | GENERAL CABIN | Open | Normal | CAB |  | REF TO WO 32788809
341 | 32787419 | LAV FLOOR PAN---SM--RII LAV-D FLOOR PAN UNDER COMMODE VERTICAL PANEL SCREW HOLE CRACKED ALL THE WAY | LAVATORY | Open | Normal | S/M |  | TO BE CLOSED
342 | 32787446 | LAVE COMMODE SHROUDE---CAB---NO CALL BACK LAV-A FLOOR PAN COMMODE BOTTOM VERTICAL PANEL 01EA SCREW MISSING | LAVATORY | Open | Normal | CAB |  | TO DO
354 | 381000-01-1 | 381000-01-1 (02) / WATER TANK DISINFECTION | TASK CARD | Open | Normal | CAB
390 | 25-21-01-00-SVA | 25-21-01-00-SVA (00) / G/C SEAT DEEP INSP | TASK CARD | Open | Normal | SEAT |  | STEP 8 TO DO
393 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (04) / PASSNGER COMPT CURTAINS REPLACEMENT | TASK CARD | Open | Normal | CAB | Requested | TO DO
394 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | TASK CARD | Open | Normal | CAB |  | TO DO
396 | 25-32-00-00-SVA | 25-32-00-00-SVA (00) / GALLEY CHECK | TASK CARD | Open | Normal | CAB |  | TO BE CLOSED
454 | 38-10-00-SVA | 38-10-00-SVA (00) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | TASK CARD | Open | Normal | AP/CAB
499 | 32788738 | CABIN - FWD CABINET - NO CALL / 25-SVA-02 FWD CABINET C101 OUTER AFT TRIM WITH 2EA DENTS MID AREA . | GENERAL CABIN | Open | AOG | CAB |  | F/UP WITH S/M
506 | 32788809 | S/M - AFT LH CABINET - RII / 25-SVA-02 COMPARTMENT S303, AFT POST , LOWER AREA TRIM MISSING , & WITH DELAMINATION AND MISSING HONEYCOMB . L= 3" W= 0.3" . | GENERAL CABIN | Open | Normal | S/M |  | I/W BY S/M
507 | 32788810 | S/M - AFT LH CABINET - RII / 25-SVA-02 INSIDE COMPARTMENT S303 , BULGE UNDER LOWER AFT RUB STRIP. | GENERAL CABIN | Open | Normal | CAB |  | F/UP WITH S/M - COMPOSITE
511 | 32788817 | CABIN - AFT RH CABINET - NO CALL / 25-SVA-02 INSIDE OF COMPARTMENT C202 , BOTTOM AREA , 3EA MOUNT COVERS MISSING . | GENERAL CABIN | Open | AOG | CAB | Requested | AOG - EDD 11/07/2026 - C/O
565 | 32395971 | CCC-32S (03) / A32S CABIN CRITICAL CHECK | TASK CARD |  |  | CAB |  | LAST
566 | 32349954 | DCC-32S (11) / DCC A32S DAILY CABIN CHECK | TASK CARD |  |  | CAB |  | LAST
567 | 32384091 | ISC/IN SERVCE CHECK_N | TASK CARD |  |  | AP/CAB |  | LAST
580 | 32793815 | CAB-FWD RH FIRST AID KIT- RII FIRST AID KIT FWD RH, EXPIRT DATE IS WITHIN 6 MONTH | GENERAL CABIN | Open | Normal | CAB |  | TO DO
581 | 32795576 | CAB--AFT RH FIRST AID KIT- RII FIRST AID KIT AFT RH, EXPIRT DATE IS WITHIN 6 MONTH ON DEC/2026 | GENERAL CABIN | Open | Normal | CAB |  | TO DO
587 | 32796515 | CAB-OXYGEN CYLINDER-RII AFT L/H OXYGEN CYLINDER MOUNT BRACKET DETACHED FROM WALL . | GENERAL CABIN | Open | Normal | S/M |  | REFER TO WO 32800175 (REQ INST. OXY)
611 | 32797284 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 501 DOOR HINGE BROKEN. | GALLEY | Open | Normal | CAB | Requested | F/UP - TEDLAR
616 | 32797333 | CAB - NO CALLBACK - OSB OSB DOOR WITH INSIDE DENT AT 1AC, 3AC, 4LJ, 5LJ, FWD OF 30JKL, 30 ABC AND 44 JKL. | GENERAL CABIN | Open | Normal | CAB |  | SENT TO PAINT
687 | 32798821 | CABIN FLOOR PANEL--CAB--CALLBACK COCKPIT/CABIN FLOOR PANEL NO: 241EF, 241KF, 241LF, 241MF, 242FF, 242KF, 242LF, 242MF AND 211FF REQUIRES REMOVAL FOR ACCESS. | GENERAL CABIN | Open | Normal | CAB |  | TO BE CLOSED
688 | 32798972 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 1AC AND 2AC WILL EXPIRE AT 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
689 | 32798977 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 3AC AND 4AC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
690 | 32798980 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 5AC AND WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
691 | 32798982 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 30ABC WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
692 | 32798987 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 31ABC WILL EXPIRE ON 10/2026 AND AT 32ABC EXPIRED ON 04/2010 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
693 | 32799012 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 33ABC AND 34ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
695 | 32799029 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 36ABC AND 37ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
696 | 32799031 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 38ABC EXPIRES ON 9/2026 AND 40ABC WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
697 | 32799033 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 42ABC AND 43ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
698 | 32799036 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 44ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
699 | 32799038 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 1JL AND 2JL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
700 | 32799049 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 3JL AND 4JL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
701 | 32799051 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 5JL WILL EXPIRE ON 09/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
702 | 32799053 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 30JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
703 | 32799054 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 31JKL AND 32JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
704 | 32799060 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 33JKL AND 34JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
705 | 32799062 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 35JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
706 | 32799063 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 36JKL AND 37JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
707 | 32799064 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 39JKL AND 40JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
708 | 32799065 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 41JKL AND 42JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
709 | 32799066 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 44JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
710 | 32799069 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT FWD DOOR LH AND FWD DOOR RH WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
711 | 32799071 | CAB - RII - OXYGEN GENERATOR AFT DOOR CTR #1 AND AFT DOOR CTR #2 OXYGEN GENERATOR WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
712 | 32799080 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT AFT DOOR RH WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | TO BE CLOSED
718 | 32799347 | CAB - NO CALL BACK G1 GALLEY COMPARTMENT 101 DOOR HINGE LOOSE | GALLEY | Open | Normal | CAB |  | F/UP WITH S/M
744 | 32801209 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY (G1-G2) GALLEY WORKTOP SEALANT PARTIALLY MISSING. | GALLEY | Open | Normal | CAB | Requested | SEALANT EXCESS - TO DO AGAIN
757 | 32801649 | ESCAPE SLIDE---RII ESCAPE SLIDE L/H FWD REQ REMOVAL FOR ACCESS | PAX DOORS | In Progress | Normal | CAB |  | CLOSE UP TO DO
758 | 32801735 | ESCAPE SLIDE---RII ESCAPE SLIDE R/H FWD REQ REMOVAL FOR ACCESS | PAX DOORS | In Progress | Normal | CAB |  | CLOSE UP TO DO
779 | 32804054 | ESCAPE SLIDE---RII L2 DOOR ESCAPE SLIDE REQ REMOVAL FOR ACCESS | PAX DOORS | In Progress | Normal | CAB |  | CLOSE UP TO DO
780 | 32804056 | ESCAPE SLIDE---RII R2 DOOR ESCAPE SLIDE REQ REMOVAL FOR ACCESS | PAX DOORS | In Progress | Normal | CAB |  | CLOSE UP TO DO
792 | 32804543 | AVIO - NO CALL BACK FWD GALLEY LIGHT LENS DISCOLORATION | GALLEY | Open | Normal | CAB |  | PAINT
794 | 32804554 | CAB - NO CALL BACK - COCKPIT SEAT CAPTAIN SEAT PLACRAD DEATTACHED | FLIGHT DECK | Open | Normal | PAINT |  | TO BE CLOSED
801 | 32804568 | CAB - NO CALL BACK - COCKPIT MEAL TABLE CAPTAIN AND F/O MEAL TABLE DISCOLORED | FLIGHT DECK | Open | Normal | PAINT | Requested - CR | TO BE PAINTED IN POSITION
826 | 32817167 | PAX DOOR LINING FWD R/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
827 | 32817204 | PAX DOOR LINING FWD L/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
828 | 32817224 | PAX DOOR LINING AFT L/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
829 | 32817230 | PAX DOOR LINING ALL PAX DOOR SLIDE COVER REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
839 | 32823153 | CAB - RII -L2 F/A L2 F/A REMOVED FOR ACCESS | F/A SEAT | Open | Normal | CAB |  | OPS AND CLOSE UP TO DO (AVIO)
843 | 32823272 | CAB-CALL BACK SEAT#5JL,5AC,30ABC,31ABC,32ABC,33ABC34ABC,30JKL,31JKL.32JKL,33JKL&34JKL REQ REMOVAL SEAT`S FOR ACCESS. | PAX SEAT | Open | Normal | CAB |  | 5AC , 5JL OPS TO DO
866 | 32825358 | PAX DOOR LINING FWD R/H AND L/H PAX DOOR ALL LINING REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
867 | 32825368 | PAX DOOR LINING AFT R/H AND L/H PAX DOOR ALL LINING REQ PNT | PAX DOORS | Open | Normal | PAINT |  | F/UP
922 | 32828386 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND SIDE WALL PANEL AT SEATS 4 AC ,5 AC ,39 ABC ,40 ABC ,33 JKL ,38 JKL ,39 JKL TEDLAR DAMAGED | TEDLAR/SIDEWALL | Open | Normal | S/W |  | TO BE CLOSED
947 | 32836864 | CAB - RII - L1 F/A SEAT L1 INBOARD AND OUTBOARD F/A SEAT REQUIRE REMOVAL FOR ACCESS. | F/A SEAT | Open | Normal | CAB |  | INST. TO DO
965 | 32849950 | CAB - NO CALLBACK - LAV D LAVATORY "D" MIRROR LOWER SIDE FADED. | LAVATORY | Open | AOG | CAB | Requested | P/S: 4477955 - AOG EDD:
980 | 32853382 | FINDING (NRC) DOCUMENT EOD-320-46-00005-R00 CEILING PNL BET FR-24- TO FR-26 LH REQ REMOVAL FOR ACCESS | GENERAL CABIN | Open | Normal | CAB |  | REQ CLOSE-UP
981 | 32854724 | COCKPIT CEILING PANEL- CAB - RII REMOVAL OF COCKPIT CEILING PNL/S 211AC, 212AC, 211BC, 212BC, 211DC, 212DC, 211EC, 212EC, 211FC 212FC ,211LC,212LC,211MW, AND 211LW FOR ACCESS | FLIGHT DECK | Open | Normal | CAB | N/R | CHECK WITH A/P FOR OK TO CLOSE
995 | 352142-01-1 | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS | GENERAL CABIN | Open | Normal | CAB | Requested | TO DO
998 | 32867427 | CAB - RII - CAPTAIN SEAT BELT CAPTAIN SEAT BELT L/H SHOULDER HARNESS FRAYED AND LAP BELT DETERIORATED | FLIGHT DECK | Open | Normal | CAB | Requested - R | TO BE CLOSED
999 | 32867877 | CAB - RII - FIRST OFFICER SEAT BELT F/O SEAT BELT SHOULDER HARNESS WEAK RETRACTION AND LAP BELTS DETERIORATED | FLIGHT DECK | Open | Normal | CAB | Requested - R | TORQUE AND OPS
1000 | 32867879 | CAB - RII - 3D OBSERVER SEAT BELT 3RD OBSERVER SEAT BELT DETERIORATED | FLIGHT DECK | Open | Normal | CAB | Requested | TO BE CLOSED
1006 | 32458025 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | PAX DOORS |  |  | CAB |  | IW
1015 | 32912808 | CAB - RII - R2 F/A SEAT R2 DOUBLE WALL-MOUNTED F/A SEAT REQUIRE REMOVAL FOR ACCESS | F/A SEAT | Open | Normal | CAB |  | OPS AND CLOSE UP TO DO (AVIO)
1016 | 32912820 | CAB - RII - SWIVEL F/A SEAT SWIVEL F/A SEAT REQUIRE REMOVAL FOR ACCESS | F/A SEAT | Open | Normal | CAB |  | OPS AND CLOSE UP TO DO (AVIO)