## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Due at | To Go | Expected | Dimension
| 5 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32722040) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-23 |  | [] | TC/P, TC/P |  |  |  | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32722040) |  | 0 / 2 | [] |  |  | MET.32722040 | 37508:14 | 309:36 | 2026-10-05 | H
| 8 | 23-71-00-00-A | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING (32722034) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] |  |  |  |  | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING (32722034) |  | 0 / 5 | [] |  |  | MET.32722034 | 07.Mar.2027 | 188 | 2027-03-07 | D
| 15 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 25-10-00-00-SVA (00) / COCKPIT CHECK (31510236) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28472 | 04.Sep.2026 22:00 | 0.28472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-10-00-00-SVA (00) / COCKPIT CHECK (31510236) |  | 0 / 15 | [] |  |  | MET.31510236 | 37508:14 | 309:36 | 2026-10-05 | H
| 16 | 25-11-00-07-0-SVA-001 | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION (32722032) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION (32722032) |  | 0 / 1 | [] |  |  | MET.32722032 | 37650:09 | 451:31 | 2026-10-22 | H
| 17 | 25-11-00-19-0-SVA | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION (32722039) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION (32722039) |  | 0 / 1 | [] |  |  | MET.32722039 | 37900:09 | 701:31 | 2026-11-21 | H
| 18 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32722042) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.45139 | 04.Sep.2026 22:00 | 0.45139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32722042) |  | 0 / 22 | [] |  |  | MET.32722042 | 37508:14 | 309:36 | 2026-10-05 | H
| 19 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32722001) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25347 | 04.Sep.2026 22:00 | 0.25347 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32722001) |  | 0 / 13 | [] |  |  | MET.32722001 | 37508:14 | 309:36 | 2026-10-05 | H
| 20 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32722043) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 04.Sep.2026 22:00 | 0.28819 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32722043) |  | 0 / 16 | [] |  |  | MET.32722043 | 37508:14 | 309:36 | 2026-10-05 | H
| 21 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32722017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11458 | 04.Sep.2026 22:00 | 0.11458 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32722017) |  | 0 / 6 | [] |  |  | MET.32722017 | 37508:14 | 309:36 | 2026-10-05 | H
| 23 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32722047) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-26 |  | [] | TC/P |  |  |  | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32722047) |  | 0 / 1 | [] |  |  | MET.32722047 | 37508:14 | 309:36 | 2026-10-05 | H
| 24 | 25-28-00-03-0-SVA-003 | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R (31764964) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | PRE INSP |  |  |  | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R (31764964) |  | 0 / 1 | [] |  |  | MET.31764964 | 37508:14 | 309:36 | 2026-10-05 | H
| 25 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29291052) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE INSP |  |  |  | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29291052) |  | 0 / 1 | [] |  |  | MET.29291052 | 37508:14 | 309:36 | 2026-10-05 | H
| 26 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 25-32-00-00-SVA (01) / GALLEY CHECK (32721818) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 04.Sep.2026 22:00 | 0.28819 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-32-00-00-SVA (01) / GALLEY CHECK (32721818) |  | 0 / 16 | [] |  |  | MET.32721818 | 37508:14 | 309:36 | 2026-10-05 | H
| 27 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 25-40-00-00-SVA (01) / LAV CHECK (32721822) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30903 | 04.Sep.2026 22:00 | 0.30903 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-40-00-00-SVA (01) / LAV CHECK (32721822) |  | 0 / 18 | [] |  |  | MET.32721822 | 37508:14 | 309:36 | 2026-10-05 | H
| 33 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 253400-01-1. (03) / GALLEY COOLING CLEANING (32721999) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013889 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 253400-01-1. (03) / GALLEY COOLING CLEANING (32721999) |  | 0 / 2 | [] |  |  | MET.32721999 | 38008:14 | 809:36 | 2026-12-04 | H
| 34 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32722013) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-34 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32722013) |  | 0 / 8 | [] |  |  | MET.32722013 | 37508:14 | 309:36 | 2026-10-05 | H
| 37 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32721817) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK |  |  |  | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32721817) |  | 0 / 4 | [] |  |  | MET.32721817 | 29'769 | 583 | 2026-11-19 | C
| 38 | 256600-02-1 | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK (29290983) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-66 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK (29290983) |  | 0 / 3 | [] |  |  | MET.29290983 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 73 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32722008) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 04.Sep.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32722008) |  | 0 / 3 | [] |  |  | MET.32722008 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 74 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 353000-05-1 (5) / CABIN PBE INSP (32722019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 353000-05-1 (5) / CABIN PBE INSP (32722019) |  | 0 / 3 | [] |  |  | MET.32722019 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 78 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32721821) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-10 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  | AS PER T/Q: 740971 | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32721821) |  | 0 / 3 | [] |  |  | MET.32721821 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 79 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32722044) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-32 |  | [] | CLEAN-UP, CLEAN-UP, CLEAN-UP |  |  |  | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32722044) |  | 0 / 3 | [] |  |  | MET.32722044 | 38008:14 | 809:36 | 2026-12-04 | H
| 88 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32722049) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32722049) |  | 0 / 3 | [] |  |  | MET.32722049 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 134 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019483) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] |  |  |  |  | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019483) |  | 0 / 2 | [] |  |  | MET.33019483 | 25.Sep.2029 | 1121 | 2029-09-25 | D
| 135 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32721841) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | INSPECTION, -- |  |  |  | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32721841) |  | 0 / 2 | [] |  |  | MET.32721841 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 136 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32721894) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P, TC/P |  |  |  | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32721894) |  | 0 / 2 | [] |  |  | MET.32721894 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 137 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019482) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | PRE INSP, -- |  |  |  | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019482) |  | 0 / 2 | [] |  |  | MET.33019482 | 25.Sep.2029 | 1121 | 2029-09-25 | D
| 138 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT (33113081) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P |  |  |  | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT (33113081) |  | 0 / 1 | [] |  |  | MET.33113081 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 139 | 25-28-00-04-0-SVA-004 | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R (28342269) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 12:00 | 04.Sep.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P, TC/P, TC/P, TC/P, -- |  |  |  | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R (28342269) |  | 0 / 5 | [] |  |  | MET.28342269 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 140 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 25-SVA-01 (01) / COCKPIT CHECK (32721918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14583 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-01 (01) / COCKPIT CHECK (32721918) |  | 0 / 17 | [] |  |  | MET.32721918 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 141 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32721948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.69444 | 04.Sep.2026 22:00 | 0.69444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32721948) |  | 0 / 21 | [] |  |  | MET.32721948 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 142 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 25-SVA-05 (01) / G/C SEAT REFRESH (32721941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.75 | 04.Sep.2026 22:00 | 0.75 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 759627 adding step 14 | 25-SVA-05 (01) / G/C SEAT REFRESH (32721941) |  | 0 / 14 | [] |  |  | MET.32721941 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 143 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 25-SVA-06 (01) / GALLEY REFRESH (32721969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-06 (01) / GALLEY REFRESH (32721969) |  | 0 / 1 | [] |  |  | MET.32721969 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 144 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 25-SVA-07 (01) / LAV REFRESH (32721846) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-07 (01) / LAV REFRESH (32721846) |  | 0 / 1 | [] |  |  | MET.32721846 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 145 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32721914) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32721914) |  | 0 / 1 | [] |  |  | MET.32721914 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 147 | 252100-01-0-SVA-003 | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT (23589458) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">13</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-02 | 04.Sep.2026 22:00 | 0.5 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  | as REQ in T/Q: 791821. | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT (23589458) |  | 0 / 2 | [] |  |  | MET.23589458 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 148 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32721974) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  | As per T/Q: 791828 from INT ENGG PN has been updated. | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32721974) |  | 0 / 2 | [] |  |  | MET.32721974 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 149 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32721823) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.625 | 04.Sep.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32721823) |  | 0 / 4 | [] |  |  | MET.32721823 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 153 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28342303) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.13542 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP |  |  |  | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28342303) |  | 0 / 4 | [] |  |  | MET.28342303 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 217 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32721924) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | OPS/LK |  |  |  | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32721924) |  | 0 / 1 | [] |  |  | MET.32721924 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 218 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32721888) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 04.Sep.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32721888) |  | 0 / 3 | [] |  |  | MET.32721888 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 219 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28342158) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.21528 | 04.Sep.2026 22:00 | 0.13194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, TC/P, --, JOB-CLOSEUP, -- |  |  | As requested in T/Q: 737585 by ENGG CONFIGRATION. | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28342158) |  | 0 / 5 | [] |  |  | MET.28342158 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 220 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28342488) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.09375 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-64 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | as per MGR Mial ear @Jinoy Jose, Thanks for the email. As discussed further, the referenced task cards will be revised to change the replacement interval from 6 months to 02 months prior to expiry. Dear @Mohammed A Albukhari, Refer email below. As discussed, please revised the text for following tasks to change the replacement interval from 6 months to 2 month prior to expiry. Remaining instructions (2 & 3 ) will be deleted from the task as well. MP Task Number Title PBE replacement interval 333 353250-01-1-SVA CABIN ATTENDANTS PORTABLE BREATHING EQUIPMENT (PBE) PERIODIC CHECK FOR EXPIRATION 6 Months 773 25-180-00-SVA PROTECTIVE BREATHING EQUIPMENT (PBE) EXPIRATION DATE CHECK 6 Months 787 25-060-00-01-SVA SMOK HOODS PERIODIC CHECK FOR EXPIRATION 6 Months 32S 353000-06-1-SVA PROTECT. BREATHING EQPT (CKPT & CABIN) PERIODIC CHECK FOR EXPIRATION 6 Months Regards, Muhammad Noor Manager, Maintenance Program E-mail: MONOOR@saudia.com Office: +966126867409 Maintenance Program, JED, SA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28342488) |  | 0 / 3 | [] |  |  | MET.28342488 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 221 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32721953) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32721953) |  | 0 / 3 | [] |  |  | MET.32721953 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 232 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342232) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342232) |  | 0 / 4 | [] |  |  | MET.28342232 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 233 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32721891) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.029167 | 04.Sep.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32721891) |  | 0 / 9 | [] |  |  | MET.32721891 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 234 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342455) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342455) |  | 0 / 4 | [] |  |  | MET.28342455 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 235 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342305) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342305) |  | 0 / 4 | [] |  |  | MET.28342305 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 236 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32721901) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.040278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32721901) |  | 0 / 9 | [] |  |  | MET.32721901 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 237 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32721832) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32721832) |  | 0 / 9 | [] |  |  | MET.32721832 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 238 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32721923) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32721923) |  | 0 / 9 | [] |  |  | MET.32721923 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 239 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32721958) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32721958) |  | 0 / 9 | [] |  |  | MET.32721958 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 240 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342204) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342204) |  | 0 / 4 | [] |  |  | MET.28342204 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 241 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32721904) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32721904) |  | 0 / 4 | [] |  |  | MET.32721904 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 242 | 522200-01-1 | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK (28342424) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK (28342424) |  | 0 / 4 | [] |  |  | MET.28342424 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 243 | 522200-01-SVA | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342155) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342155) |  | 0 / 4 | [] |  |  | MET.28342155 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 244 | 522200-02-1 | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK (28342452) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK (28342452) |  | 0 / 4 | [] |  |  | MET.28342452 | 40988:17 | 3789:39 | 2027-11-24 | H
| 245 | 522200-02-SVA | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342206) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342206) |  | 0 / 4 | [] |  |  | MET.28342206 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 246 | 522200-03-SVA | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342280) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342280) |  | 0 / 4 | [] |  |  | MET.28342280 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 247 | 522200-04-1 | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP (28365333) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP (28365333) |  | 0 / 4 | [] |  |  | MET.28365333 | 45878:57 | 8680:19 | 2029-06-29 | H
| 248 | 522200-04-SVA | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342476) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342476) |  | 0 / 4 | [] |  |  | MET.28342476 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 252 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32721952) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32721952) |  | 0 / 3 | [] |  |  | MET.32721952 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 255 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32721916) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32721916) |  | 0 / 3 | [] |  |  | MET.32721916 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 262 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32721820) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32721820) |  | 0 / 3 | [] |  |  | MET.32721820 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 276 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32721873) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32721873) |  | 0 / 1 | [] |  |  | MET.32721873 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 353 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 25-SVA-03 (01) / B/C SEAT REFRESH (32722075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42361 | 04.Sep.2026 22:00 | 0.42361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 25-SVA-03 (01) / B/C SEAT REFRESH (32722075) |  | 0 / 19 | [] |  |  | MET.32722075 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 372 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32721988) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32721988) |  | 0 / 1 | [] |  |  | MET.32721988 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 373 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32721980) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32721980) |  | 0 / 1 | [] |  |  | MET.32721980 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 374 | 522200-03-1 | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR (28377189) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR (28377189) |  | 0 / 1 | [] |  |  | MET.28377189 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 385 | 352142-01-1 | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS (32722073) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1875 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS (32722073) |  | 0 / 3 | [] |  |  | MET.32722073 | 10.Feb.2027 | 163 | 2027-02-10 | D
| 386 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 381000-01-1 (3) / WATER TANK DISINFECTION (32626072) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 04.Sep.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-10 |  | [] | OPS/LK |  |  |  | 381000-01-1 (3) / WATER TANK DISINFECTION (32626072) |  | 0 / 1 | [] |  |  | MET.32626072 | 13.Oct.2026 | 43 | 2026-10-13 | D
| 390 | 531101-02-1 | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH (31575944) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH (31575944) |  | 0 / 10 | [] |  |  | MET.31575944 | 32'743 | 3'557 | 2028-01-06 | C
| 391 | 531101-04-1 | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH (31575943) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.72083 | 04.Sep.2026 22:00 | 0.39444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH (31575943) |  | 0 / 10 | [] |  |  | MET.31575943 | 32'743 | 3'557 | 2028-01-06 | C
| 395 | 531131-02-1 | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP (32722079) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19792 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, X-RAY / NDT, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP (32722079) |  | 0 / 8 | [] |  |  | MET.32722079 | 35'343 | 6'157 | 2029-01-01 | C
| 396 | 531135-03-1 | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH (32722081) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.875 | 04.Sep.2026 22:00 | 0.52083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH (32722081) |  | 0 / 11 | [] |  |  | MET.32722081 | 33'743 | 4'557 | 2028-05-24 | C
| 397 | 531153-04-1 | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH (25434854) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.62153 | 04.Sep.2026 22:00 | 0.42014 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, --, JOB-CLOSEUP, JOB-CLOSEUP |  |  | T/Q: 846599 --------------------------------------------------------------------- ------------------------------------------------------------ mail has been sent from production to remove INSP SCOPE from STEP 11. Greetings ,, Ref. To the below email , Need your assistance on WORKSTEP No. 11 Kindly remove INSP Scop from the mentioned work step as LAVATORY OK TO INSTALL Is not required. Regards, Alaa Fageeh Designee Supervisor, Aircraft Maintenance Heavy Maint Cabin Narrow Body A321/A320 Tel:+966 12-2729001 ¦ Extn:77772 Email:A.Fageeh@saudiatechnic.com PO Box 167 - Jeddah 21231 - Saudi Arabia | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH (25434854) |  | 0 / 12 | [] |  |  | MET.25434854 | 34'043 | 4'857 | 2028-07-05 | C
| 398 | 531155-04-1 | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH (25524033) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25347 | 04.Sep.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-CLOSEUP |  |  |  | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH (25524033) |  | 0 / 12 | [] |  |  | MET.25524033 | 34'043 | 4'857 | 2028-07-05 | C
| 401 | 532130-39-1 | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION (32721991) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22222 | 04.Sep.2026 22:00 | 0.22014 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | To remove panles T/Q: 851220 Dear Concerned, The requested action has been completed. The Work Template has been revised in accordance with AMM 53-21-00-220-827-A. Access panels 231FF, 231NF, 231TF, 231YF, 232FF, 232PF, 232UF, and 232YF have been removed from the access requirements, and only Access Door 831 remains applicable for task accomplishment. The Work Template revision has been reviewed, approved, and activated. Production action is required to discard any printed copies of the previous Work Template revision and reprint/use the latest activated revision for task accomplishment. Regards, MPDC | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION (32721991) |  | 0 / 13 | [] |  |  | MET.32721991 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 411 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25450096) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.68542 | 04.Sep.2026 22:00 | 0.5625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, -- |  |  |  | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25450096) |  | 0 / 10 | [] |  |  | MET.25450096 | 32'843 | 3'657 | 2028-01-20 | C
| 412 | 534124-01-3 | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP (31486331) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.077778 | 04.Sep.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | As REQ per T/C: 850864. | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP (31486331) |  | 0 / 8 | [] |  |  | MET.31486331 | 01.Nov.2027 | 427 | 2027-11-01 | D
| 413 | 534126-01-3 | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP (25383414) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11875 | 04.Sep.2026 22:00 | 0.10833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | CLEAN-UP, INSPECTION, X-RAY / NDT |  |  |  | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP (25383414) |  | 0 / 3 | [] |  |  | MET.25383414 | 35'100 | 5'914 | 2028-11-29 | C
| 414 | 534127-01-3 | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP (25402520) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP (25402520) |  | 0 / 8 | [] |  |  | MET.25402520 | 33'843 | 4'657 | 2028-06-07 | C
| 418 | 534189-02-1 | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER (25383649) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 04.Sep.2026 22:00 | 0.053472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER (25383649) |  | 0 / 5 | [] |  |  | MET.25383649 | 36'000 | 6'814 | 2029-04-03 | C
| 419 | 535163-01-1 | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP (28342398) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.4125 | 04.Sep.2026 22:00 | 0.4125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-51 |  | [] | CLEAN-UP, INSPECTION, X-RAY / NDT |  |  |  | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP (28342398) |  | 0 / 3 | [] |  |  | MET.28342398 | 37'300 | 8'114 | 2029-09-30 | C
| 535 | 27936373 | REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) | 27936373 / REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) (27936373) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 27936373 / REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) (27936373) |  | 0 / 1 | [] |  | 004 | ME.27936373 | 36118:45 | 492:45 | 2026-10-27 | H
| 536 | 27946863 | REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) | 27946863 / REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) (27946863) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 27946863 / REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) (27946863) |  | 0 / 1 | [] |  | 005 | ME.27946863 | 26585:13 | 509:39 | 2026-10-29 | H
| 540 | 22579023 | REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) | 22579023 / REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) (22579023) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-63-05 |  | [] |  |  |  |  | 22579023 / REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) (22579023) |  | 0 / 1 | [] |  | 001 | ME.22579023 | 17.Dec.2026 | 108 | 2026-12-17 | D
| 570 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (33019441) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P |  |  |  | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (33019441) |  | 0 / 1 | [] |  |  | JCA.33019441 |  |  | 1517606
| 572 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (33019460) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (33019460) |  | 0 / 1 | [] |  |  | JCA.33019460 |  |  | 1517606