## ASF Tracker
POOL CABIN ✈ HZ-ASF ✈ C7-CHECK WORK PACKAGE TRACKER |  |  |  | Day 35/36 |  | ✅ 347 / 385 Closed (90%)
UPDATED: 12 JULY -- DAY SHIFT | [5 empty] | AOG/Critical: 3
Seq. No. | WO / Event Number | Task Description | Category | Status | Priority | Specialty | PARTS REQ. | Remarks | Time EVAL? | AREA
1 | 31956294 | C_N (C_N07)/C-CHECK | TASK CARD | Open | Normal | AP |  |  | N/A | N/A
2 | 05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | TASK CARD | Open | Normal | INSP |  |  | N/A | N/A
3 | 08-10-00-01-0-A | 08-10-00-01-0-A (01) / WIGHT & BALANCE | TASK CARD | Closed | Normal | AP |  |  | N/A | N/A
24 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | TASK CARD | Closed | Normal | CAB | Requested | C/W | N/A | FWD
25 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (02) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | TASK CARD | Closed | Normal | CAB | Requested |  | N/A | FWD
26 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (03) / CAPTAIN & F/O SEATS COVERS REPLACMENT | TASK CARD | Closed | Normal | CAB | Requested |  | N/A | FWD
27 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (02) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | TASK CARD | Closed | Normal | CAB | Requested | C/W | N/A | FWD
28 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | TASK CARD | Closed | Normal | CAB | Requested | TO BE CLOSED | N/A | JOINT
29 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | TASK CARD | Closed | Normal | CAB | Requested | P/S 4467511 | N/A | FWD
30 | 25-SVA-01 | 25-SVA-01 (00) / COCKPIT CHECK | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
31 | 25-SVA-02 | 25-SVA-02 (00) / GENERAL CABIN ITEMS C-CHK | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
32 | 25-SVA-05 | 25-SVA-05 (00) / G/C SEAT REFRESH | TASK CARD | Open | Normal | SEAT |  |  | N/A
33 | 25-SVA-06 | 25-SVA-06 (00) / GALLEY REFRESH | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
34 | 25-SVA-07 | 25-SVA-07 (00) / LAV REFRESH | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
39 | 254000-04-2 | 254000-04-2 (03) / LAVATORIES FLOOR PANELS INSPECTION | TASK CARD | Closed | Normal | JOINT |  |  | N/A
42 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | TASK CARD | Closed | Normal | JOINT |  | TO BE CLOSED | N/A
47 | 262541-04-1 | 262541-04-1 (02) / LAVATORY FIRE EXTG PRESS READING CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A
112 | 351000-01-1 | 351000-01-1 (02) / FULL FACE/QUICK OXYGEN MASKS OPC | TASK CARD | Closed | Normal | JOINT |  |  | N/A
113 | 351241-01-1 | 351241-01-1 (02) / CREW OXYGEN MASKS INSPECTION | TASK CARD | Closed | Normal | JOINT |  |  | N/A
114 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | TASK CARD | Closed | Normal | JOINT |  | TO BE CLOSED | N/A
115 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | TASK CARD | Closed | Normal | JOINT |  |  | N/A
116 | 353000-07-1 | 353000-07-1 (03) / PORTABLE OXYGEN MASKS INSPECTION | TASK CARD | Closed | Normal | JOINT |  |  | N/A
123 | 383100-07-1 | 383100-07-1 (06) / VACUUM TOILET SYSTEM CLEANING | TASK CARD | Closed | Normal | AP |  |  | N/A
127 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
128 | 521000-02-1 | 521000-02-1 (02) / PASSENGER/CREW DOOR SUSPENSION CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A | JOINT
129 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
130 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | TASK CARD | Closed | Normal | CAB |  |  | N/A | AFT
131 | 521000-04-1-001 | 521000-04-1-001 (02) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A | FWD
132 | 521000-04-1-002 | 521000-04-1-002 (02) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A | FWD
133 | 521000-04-1-003 | 521000-04-1-003 (02) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A | AFT
134 | 521000-04-1-004 | 521000-04-1-004 (02) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | TASK CARD | Closed | Normal | JOINT |  |  | N/A | AFT
135 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | TASK CARD | Closed | Normal | CAB |  |  | N/A | AFT
136 | 521121-02-1 | 521121-02-1 (03) / PASSENGER/CREW DOORS LUBRICATION | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
139 | 527100-01-1 | 527100-01-1 (5) / DOOR WARNING SYSTEM OPERATIONAL TEST | TASK CARD | Closed | Normal | AV |  |  | N/A
140 | 527300-01-1 | 527300-01-1 (03) / EMERGENCY ESCAPE SLIDE WARNING SYS | TASK CARD | Closed | Normal | AV |  |  | N/A
141 | 531151-02-1 | 531151-02-1 (00) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | TASK CARD | Closed | Normal | JOINT |  |  | N/A
162 | 561200-02-1 | 561200-02-1 (01) / COCKPIT SLIDING WINDOW LUBRICATION | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
260 | 30970373 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
265 | 29500619 | EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | TASK CARD | Closed | Normal | AV |  |  | N/A
266 | 30482093 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | TASK CARD | Closed | Normal | AV |  |  | N/A
267 | 30481967 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | TASK CARD | Closed | Normal | AV |  |  | N/A
268 | 29155528 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | TASK CARD | Closed | Normal | AV |  |  | N/A
269 | 29155626 | EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX | TASK CARD | Closed | Normal | AV |  |  | N/A
270 | 29155751 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | TASK CARD | Closed | Normal | AV |  |  | N/A
271 | 29155866 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | TASK CARD | Closed | Normal | AV |  |  | N/A
274 | 30817928 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | TASK CARD | Open | Normal | AV |  |  | N/A
275 | 30695782 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | TASK CARD | Closed | Normal | AV |  |  | N/A
276 | 29155917 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | TASK CARD | Closed | Normal | AV |  |  | N/A
277 | 29156041 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | TASK CARD | Closed | Normal | AV |  |  | N/A
278 | 29156135 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | TASK CARD | Closed | Normal | AV |  |  | N/A
279 | 29156197 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | TASK CARD | Closed | Normal | AV |  |  | N/A
280 | 29157167 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | TASK CARD | Closed | Normal | AV |  |  | N/A
281 | 29156251 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | TASK CARD | Closed | Normal | AV |  |  | N/A
287 | 15969129 | EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. | TASK CARD | Open | Normal | AP |  |  | N/A
296 | 27731511 | S51-R10016/A320 // DENT AND BUCKLE CHART UPDATE | TASK CARD | Open | Normal | INSP |  |  | N/A
299 | 32023170 | REPLACE 3214-31/151721 (BATTERY, EMERGENCY) | TASK CARD | Closed | Normal | AV |  | ACCESS | N/A
300 | 32023140 | REPLACE 3214-31/151783 (BATTERY, EMERGENCY) | TASK CARD | Closed | Normal | AV |  | ACCESS | N/A
301 | 32023261 | REPLACE 3214-31/159075 (BATTERY, EMERGENCY) | TASK CARD | Closed | Normal | AV |  | ACCESS | N/A
302 | 32023581 | REPLACE 3214-31/961564 (BATTERY, EMERGENCY) | TASK CARD | Closed | Normal | AV |  | ACCESS | N/A
303 | 31449237 | REPLACE 60592-203/A25974 (RESERVOIR AND VALVE ASSEMBLY) | TASK CARD | Closed | Normal | AP |  |  | N/A | N/A
304 | 27027164 | REPLACE 60592-203/ALT749-11441 (RESERVOIR AND VALVE ASSEMBLY) | TASK CARD | Closed | Normal | AP |  |  | N/A | N/A
305 | 29160779 | REPLACE 755D0000-01/81210-68985 (REHEATER) | TASK CARD | Closed | Normal | AP |  |  | N/A | N/A
306 | 29540806 | REPLACE 9700-C1A-BF23A/P21110181 (BOTTEL PORTABLE OXY.) | TASK CARD | Closed | Normal | CAB |  |  | N/A
308 | 21620684 | 34100005-1/39235D1 WC(WEIGHT CHECK) / WEIGHT CHECK | TASK CARD | Closed | Normal | AP |  |  | N/A
309 | 21620578 | 34100005-1/40474D1 WC(WEIGHT CHECK) / WEIGHT CHECK | TASK CARD | Closed | Normal | AP |  |  | N/A
310 | 21620847 | 34100005-1/42779D1 WC(WEIGHT CHECK) / WEIGHT CHECK | TASK CARD | Closed | Normal | AP |  |  | N/A
311 | 21620638 | 34100005-1/57001D1 WC(WEIGHT CHECK) / WEIGHT CHECK | TASK CARD | Closed | Normal | AP |  |  | N/A
316 | 23905848 | DENT AND BUCKLE CHART /1/ MAKE SURE THAT AIRCRAFT IS SAFE AND READY FOR MAINTENANCE BEFORE YOU START THIS TASK TO AVOID PERSONNEL INJURY AND AIRCRAFT DAMAGE. /2/ THIS ER DIRECTS THE DETAIL VISUAL INSPECTION OF ALL AIRCRAFT EXTERIOR SURFACE... | TASK CARD | Open | Normal | INSP |  |  | N/A
317 | 32022300 | DOCTR KIT EXPIRY [30JUN 2026]. DOCTOR KIT WILL EXP ON 30 JUNE 2026 DEK # 096 DEK SN 7160 | GENERAL CABIN | Closed | Normal | CAB |  | TO BE CLOSED | N/A | AFT
319 | 80794771 | METAL STRIP LAV D BESIDE COMPARTMENT S302 AFT LWR SIDE METAL STRIP FOUND BROKEN. PIC ATTACHED | GENERAL CABIN | Open | Normal | CAB |  |  | N/A | AFT
320 | 81012325 | COVER R2 DOOR MIS BUSTLE COVER HAS DAMAGE. | PAX DOORS | Closed | Normal | CAB | Requested |  | N/A | AFT
322 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | TASK CARD | Closed | Normal | INSP |  |  | N/A
323 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | TASK CARD | Open | Normal | AP |  | C/W CHECK W/HPC | N/A
324 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | TASK CARD | Open | Normal | PLN |  |  | N/A
325 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | TASK CARD | Open | Normal | AP |  |  | N/A
326 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | TASK CARD | Closed | Normal | AP |  |  | N/A
327 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | TASK CARD | Open | Normal | AP |  |  | N/A
328 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | TASK CARD | Closed | Normal | CAB |  |  | N/A
329 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | TASK CARD | Open | Normal | INSP |  |  | N/A
330 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | TASK CARD | Open | Normal | CAB |  |  | N/A
339 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | TASK CARD | Open | Normal | AP |  |  | N/A
341 | 32787419 | LAV FLOOR PAN---SM--RII LAV-D FLOOR PAN UNDER COMMODE VERTICAL PANEL SCREW HOLE CRACKED ALL THE WAY | LAVATORY | Closed | Normal | S/M |  |  | N/A
342 | 32787446 | LAVE COMMODE SHROUDE---CAB---NO CALL BACK LAV-A FLOOR PAN COMMODE BOTTOM VERTICAL PANEL 01EA SCREW MISSING | LAVATORY | Closed | Normal | CAB |  |  | N/A | AFT
343 | 32787479 | LAVE FLOOR PAN---SM---RII LAV-E FLOOR PAN COMMODE BOTTOM SIDE VERTICAL PANEL SCREW HOLE CRACKED ALL THE WAY | TASK CARD | Closed | Normal | S/M |  |  | N/A
348 | 29534232 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | TASK CARD | Closed | Normal | INSP |  |  | N/A
354 | 381000-01-1 | 381000-01-1 (02) / WATER TANK DISINFECTION | TASK CARD | Closed | Normal | CAB |  | CW TO BE CLOSED | N/A
368 | 32070218 | S35-D10066/A320/21 - PBE SERIAL NUMBER VERIFICATION. | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
372 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
373 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | TASK CARD | Closed | Normal | PAINT |  |  | N/A
374 | 212300-02-1 | 212300-02-1 (03) / LAVATORY AIR EXTRACTION FLTR R/R | TASK CARD | Closed | Normal | CAB | Requested |  | N/A
375 | 212600-11-1 | 212600-11-1 (03) / DEMISTER FLTER&FILTER CARTRIDGE R&R | TASK CARD | Closed | Normal | AP |  |  | N/A
376 | 216000-01-1-001 | 216000-01-1-001 (05) / CLEANING OF COCKPIT SENSOR DUCT AND TEMPERATURE SENSOR. | TASK CARD | Closed | Normal | AV |  |  | N/A
377 | 216000-01-1-002 | 216000-01-1-002 (04) / CLEANING OF CABIN SENSOR DUCT AND TEMPERATURE SENSOR. | TASK CARD | Closed | Normal | AV |  |  | N/A
379 | 237100-01-1 | 237100-01-1 (02) / COCKPIT VOICE RECORDER OPC | TASK CARD | Closed | Normal | AV |  |  | N/A
384 | 243800-01-1 | 243800-01-1 (02) / BATT CHARGE LIMITER OPS CHECK | TASK CARD | Closed | Normal | AV |  |  | N/A
385 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
386 | 25-11-00-07-0-SVA-001 | 25-11-00-07-0-SVA-001 (03) / FOURTH OCCUPANT SEAT LUBRICATION | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
387 | 25-11-00-19-0-SVA | 25-11-00-19-0-SVA (01) / THIRD OCCUPANT SEAT LUBRICATION | TASK CARD | Closed | Normal | CAB |  |  | N/A | FWD
388 | 25-20-00-00-SVA | 25-20-00-00-SVA (00) / GENERAL CABIN DEEP INSP | TASK CARD | Closed | Normal | CAB |  |  | N/A
389 | 25-21-00-00-SVA | 25-21-00-00-SVA (00) / B/C SEAT DEEP INSP | TASK CARD | Open | Normal | SEAT |  |  | N/A
390 | 25-21-01-00-SVA | 25-21-01-00-SVA (00) / G/C SEAT DEEP INSP | TASK CARD | Open | Normal | SEAT |  |  | N/A
391 | 25-22-00-00-SVA | 25-22-00-00-SVA (00) / CABIN CREW SEAT DEEP INSP | TASK CARD | Closed | Normal | CAB |  |  | N/A
392 | 25-26-00-03-0-SVA | 25-26-00-03-0-SVA (03) / PASS COMPT CURTAIN RAILS INSPECTION | TASK CARD | Closed | Normal | INSP |  |  | N/A
393 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (04) / PASSNGER COMPT CURTAINS REPLACEMENT | TASK CARD | Closed | Normal | CAB | Requested | TO BE CLOSED | N/A | JOINT
394 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | TASK CARD | Closed | Normal | CAB |  | TO BE CLOSED | N/A | JOINT
395 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
396 | 25-32-00-00-SVA | 25-32-00-00-SVA (00) / GALLEY CHECK | TASK CARD | Closed | Normal | CAB |  |  | N/A
397 | 25-40-00-00-SVA | 25-40-00-00-SVA (00) / LAV CHECK | TASK CARD | Closed | Normal | CAB |  |  | N/A
398 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | TASK CARD | Closed | Normal | INSP |  |  | N/A
399 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | TASK CARD | Closed | Normal | INSP |  |  | N/A
400 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | TASK CARD | Closed | Normal | INSP |  |  | N/A
401 | 253000-02-1 | 253000-02-1 (03) / GALLY AIR EXTRACTION FLTR ELMNT R*R | TASK CARD | Closed | Normal | CAB | Requested |  | N/A | JOINT
402 | 253400-01-1. | 253400-01-1. (02) / GALLEY COOLING CLEANING | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
403 | 253400-02-1 | 253400-02-1 (02) / AIRCHILLER CONDENSER AIR FLTR CLEANING | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
406 | 256241-05-1 | 256241-05-1 (03) / CABN DOORS GIRT BAR FITT STOP CLEAN | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
411 | 262441-01-1 | 262441-01-1 (02) / PORT FIRE EXT PRESS GAUGE CHK | TASK CARD | Closed | Normal | INSP |  |  | N/A
434 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | TASK CARD | Closed | Normal | AV |  |  | N/A | FWD
448 | 353000-01-1 | 353000-01-1 (04) / PORTABLE OXYGEN CYLINDERS OPC | TASK CARD | Closed | Normal | INSP |  |  | N/A
449 | 353000-05-1 | 353000-05-1 (04) / CABIN PBE INSP | TASK CARD | Closed | Normal | INSP |  |  | N/A
454 | 38-10-00-SVA | 38-10-00-SVA (00) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | TASK CARD | Open | Normal | AP |  |  | N/A
455 | 383200-01-1 | 383200-01-1 (02) / WASHBASIN FILTER ELEMENT CLEANING | TASK CARD | Closed | Normal | CAB |  |  | N/A | JOINT
464 | 525111-06-2 | 525111-06-2 (01) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | TASK CARD | Closed | Normal | JOINT |  |  | N/A | FWD
498 | 32788737 | CABIN IFE - SMOKE SIGN - NO CALL / 25-SVA-02 SMOKE SIGN LIGHT INOP ABOVE SEAT 42JKL . | GENERAL CABIN | Closed | Normal | AV |  |  | Yes | AFT
499 | 32788738 | CABIN - FWD CABINET - NO CALL / 25-SVA-02 FWD CABINET C101 OUTER AFT TRIM WITH 2EA DENTS MID AREA . | GENERAL CABIN | Closed | AOG | CAB |  | S/M INFORMED | Yes | FWD
500 | 32788746 | CABIN - FWD CABINET - NO CALL / 25-SVA-02 FWD CABINET C101 , DOOR OUTER , LOWER TEDLER WOROUT . | GENERAL CABIN | Closed | Normal | S/W |  |  | Yes | FWD
502 | 32788761 | CABIN - FWD CABINET - NO CALL / 25-SVA-02 FWD SIDE , GAP SEAL WITH UPPER STOWAGE TORN . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | FWD
501 | 32788747 | PAINT - CABIN FWD CABINET - NO CALL / 25-SVA-02 COMPARTMENT C102 , ID DECAL TORN , MEGAPHONE DECAL TORN , DESCRIPTION " EMER. EQUIP. ONLY " DECAL TORN . | GENERAL CABIN | Closed | Normal | PAINT |  |  | Yes
503 | 32788793 | CABIN - MID CABIN CARPET - NO CALL / 25-SVA-02 FRAYED CARPET , JUST BELOW MID PATITIONS AFT SIDE . | GENERAL CABIN | Closed | Normal | CAB |  | CARPET R/R | Yes | FWD
504 | 32788801 | CABIN - AFT LH CABINET - NO CALL / 25-SVA-02 COMPARTMENT S302 , INNER BOTTOM RED LATCH LOOSE . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
505 | 32788806 | CABIN - AFT LH CABINET - NO CALL / 25-SVA-02 INSIDE COMPARTMENT S303 , CART FOLDING RAMP HINGE PIN MIGRATED OUT ., + 1EA MISSING SCREW . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
508 | 32788811 | CABIN - AFT LH CABINET - NO CALL / 25-SVA-02 INSIDE OF S303, AFT MID AREA RUB STRIP LOOSE . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
509 | 32788813 | CABIN - AFT LH CABINET - NO CALL / 25-SVA-02 COMPARTMENT S304 , LATCH NOT LOCKING ON TABLE CART . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
510 | 32788815 | CABIN - AFT CABINETS LATCHES - NO CALL / 25-SVA-02 COMPARTMENT DOORS S303 & C202 BOTTOM LOCKS , INNER PLATE EACH WITH MISSING SCREW . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
506 | 32788809 | S/M - AFT LH CABINET - RII / 25-SVA-02 COMPARTMENT S303, AFT POST , LOWER AREA TRIM MISSING , & WITH DELAMINATION AND MISSING HONEYCOMB . L= 3" W= 0.3" . | GENERAL CABIN | Closed | Normal | S/M |  | C/W S/M coc to do | Yes
507 | 32788810 | S/M - AFT LH CABINET - RII / 25-SVA-02 INSIDE COMPARTMENT S303 , BULGE UNDER LOWER AFT RUB STRIP. | GENERAL CABIN | Closed | Normal | CAB |  | TO DO | Yes
511 | 32788817 | CABIN - AFT RH CABINET - NO CALL / 25-SVA-02 INSIDE OF COMPARTMENT C202 , BOTTOM AREA , 3EA MOUNT COVERS MISSING . | GENERAL CABIN | Open | AOG | CAB | Requested | C/O | Yes | AFT
512 | 32788819 | CABIN - AFT CURTAIN - NO CALL / 25-SVA-02 AFT CURTAIN RAIL LOOSE ON RH END . | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
538 | 32791503 | FINDING (NRC) JOBCARD STJC-20-00-00-01-GA-GO L1 DOOR LWR SIDE PNT FOUND FADED & BLACK STAINS. | GENERAL CABIN | Closed | Normal | PAINT |  |  | Yes | FWD
564 | 32401880 | 44-SVA-01 (00) / PANASONIC LEVEL 1 CHECK | TASK CARD | Closed | Normal | AV |  |  | N/A
565 | 32395971 | CCC-32S (03) / A32S CABIN CRITICAL CHECK | TASK CARD | Open | Normal | CAB |  |  | N/A
566 | 32349954 | DCC-32S (11) / DCC A32S DAILY CABIN CHECK | TASK CARD | Open | Normal | CAB |  |  | N/A
567 | 32384091 | ISC/IN SERVCE CHECK_N | TASK CARD | Open | Normal | AP |  |  | N/A
570 | 32721788 | S44-R10249/PANASONIC JUNE 26 CYCLE | TASK CARD | Open | Normal | AV |  |  | N/A
571 | 32258914 | W_N/WEEKLY CHECK | TASK CARD | Open | Normal | JOINT |  |  | N/A
579 | ISC-32S | ISC-32S (13) / 32S IN-SERVEICE-CHECK (ISC) | TASK CARD | Open | Normal | JOINT |  |  | N/A
580 | 32793815 | CAB-FWD RH FIRST AID KIT- RII FIRST AID KIT FWD RH, EXPIRT DATE IS WITHIN 6 MONTH | GENERAL CABIN | Open | Normal | CAB |  | INSP | Yes | FWD
581 | 32795576 | CAB--AFT RH FIRST AID KIT- RII FIRST AID KIT AFT RH, EXPIRT DATE IS WITHIN 6 MONTH ON DEC/2026 | GENERAL CABIN | Closed | Normal | CAB |  | FROM CATRION | Yes | AFT
583 | 32795656 | CAB- CUTAIN RAIL-CALL BACK FWD CURTAIN HOOKS BROKEN 2EA | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | FWD
584 | 32796462 | CAB- CUTAIN RAIL MID-CALL BACK MID DIVIDER CURTAIN HOOKS BROKEN AND STOPER MISSING. | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | FWD
585 | 32796473 | CAB- CUTAIN RAIL AFT-CALL BACK AFT GALLEY CURTAIN STOPER MISSING | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | AFT
586 | WEEKLY-32S | WEEKLY-32S (04) / WEEKLY 32S CHECK | TASK CARD | Open | Normal | JOINT |  |  | Yes
587 | 32796515 | CAB-OXYGEN CYLINDER-RII AFT L/H OXYGEN CYLINDER MOUNT BRACKET DETACHED FROM WALL . | GENERAL CABIN | Closed | Normal | S/M |  |  | Yes | AFT
589 | 32796954 | CAB - NO CALLBACK - LAV A LAVATORY A NURSING TABLE WITH MISSING BUMPER. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | FWD
591 | 32796966 | CAB - NO CALLBACK - LAV A LAVATORY A SERVICE CABINET STORAGE DRAWER RUBBER SEAL NOT SECURED. | LAVATORY | Closed | Normal | CAB | N/R |  | Yes | FWD
593 | 32796982 | CAB - NO CALLBACK - LAV A "LAVATORY A" TOILET SHROUD WITH MISSING 2 EA SCREWS. | LAVATORY | Closed | Normal | JOINT | Requested | REQ S/M | Yes | FWD
594 | 32796995 | CAB - NO CALLBACK - LAV A LAVATORY A TOILET PAPER DISPENSER COVER COLOR FADED. | LAVATORY | Closed | Normal | PAINT |  |  | Yes | FWD
596 | 32796996 | CAB - NO CALLBACK - LAV E "LAVATORY E" TOILET SHROUD NOT SECURED. | LAVATORY | Closed | Normal | JOINT | Requested |  | Yes | AFT
597 | 32797001 | PNT - NO CALLBACK - LAV E "LAVATORY E" TOILET SHROUD COVER DISCOLOURED. | LAVATORY | Closed | Normal | PAINT |  |  | Yes | AFT
598 | 32797014 | CAB - NO CALLBACK - LAV E "LAVATORY E" NURSING TABLE WITH MISSING BUMPER. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
599 | 32797104 | CAB - NO CALLBACK - LAV E "LAVATORY E" AIR VENTILATION GRILLE BROKEN. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
600 | 32797124 | CAB - NO CALLBACK - LAV D "LAVATORY D" TOILET SHROUD COVER NOT SECURED. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
601 | 32797137 | CAB - NO CALLBACK - LAV D "LAVATORY D" TOILET PAPER ROLLER IS MISSING. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
602 | 32797145 | CAB - NO CALLBACK - LAV D "LAVATORY D" SINK SIEVE NOT SECURED. | LAVATORY | Closed | Normal | CAB | N/R |  | Yes | AFT
603 | 32797156 | CAB - NO CALLBACK - LAV D "LAVATORY D" WASHBASIN SINK DRAINAGE RESTRICTION. | LAVATORY | Closed | Normal | CAB | N/R |  | Yes | AFT
604 | 32797165 | CAB - NO CALLBACK - LAV D "LAVATORY D" DOOR HANDLE IS LOOSE. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
605 | 32797176 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY CART TURN CATCH AT 109 AND 111 FOUND LOOSE. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
606 | 32797185 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY CART COMPT. 109 MID LATCH LEVER IS MISSING. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
607 | 32797195 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY COUNTERTOP SEALANT DETERIORATED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
608 | 32797223 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY COMPT. 211 LOWER BUMPER IS MISSING. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
609 | 32797267 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY FOOTSTEP FOUND INOP. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
610 | 32797278 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY COMPT. 210 DOOR LOCK LOOSE. | GALLEY | Closed | Normal | CAB | N/R |  | Yes | FWD
611 | 32797284 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 501 DOOR HINGE BROKEN. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
612 | 32797296 | PNT - NO CALLBACK - AFT GALLEY AFT GALLEY ALL OVENS REQUIRE PAINT. | GALLEY | Closed | Normal | PAINT |  |  | Yes | AFT
613 | 32797302 | PNT - NO CALLBACK - FWD GALLEY FWD GALLEY OVENS REQUIRE PAINT. | GALLEY | Closed | Normal | PAINT |  |  | Yes | FWD
614 | 32797315 | CAB - NO CALLBACK - OSB MOST FWD VIDEO EQUIPMENT OVERHEAD STOWAGE DOOR OPENS FAST. | GENERAL CABIN | Closed | Normal | CAB | N/R |  | Yes | FWD
615 | 32797329 | CAB - NO CALLBACK - OSB MOST FWD RH MEDICAL KIT OVERHEAD STOWAGE BIN WITH INSIDE DENT. | GENERAL CABIN | Closed | Normal | CAB | N/R |  | Yes | FWD
616 | 32797333 | CAB - NO CALLBACK - OSB OSB DOOR WITH INSIDE DENT AT 1AC, 3AC, 4LJ, 5LJ, FWD OF 30JKL, 30 ABC AND 44 JKL. | GENERAL CABIN | Open | Normal | CAB |  | REQ PNT ACTION | Yes | JOINT
617 | 32797337 | CAB - NO CALLBACK - OSB OSB DOOR MISSING WITH RUBBER BUMPER AT 1AC, 4LJ, 4AC, 5LJ, FWD OF 30 JKL, 30ABC, 31ABC AND 33ABC. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | JOINT
618 | 32797381 | CAB - NO CALLBACK - OSB DOOR WITH MISSING RUBBER BUMPER AT 34ABC, 37ABC, 38ABC, 40JKL, 41JKL, 42JKL, 44JKL AND 44ABC. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | JOINT
619 | 32797382 | CAB - NO CALLBACK - OSB OSB WITH MISSING UPPER BUMPER AT 1AC, 5AC, 5LJ, 30JKL, 32JKL, 33JKL, 33JKL AND 34ABC. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | JOINT
620 | 32797384 | CAB - NO CALLBACK - OSB OSB WITH MISSING UPPER BUMPER AT 36ABC, 38ABC, 38JKL, 40JKL, 40ABC, 41JKL AND 42JKL. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
621 | 32797396 | CAB - NO CALLBACK - OSB OSB SIDE TRIM BROKEN AT 4LJ AND 39 JKL. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
622 | 32797399 | CAB - NO CALLBACK - OSB OSB UPPER TRIM BROKEN AT 30ABC. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | FWD
623 | 32797402 | CAB - NO CALLBACK - OSB OSB HANDRAIL BROKEN AT 34ABC, 30JKL. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
624 | 32797436 | CAB - NO CALLBACK - OSB OSB HANDRAIL SEAT MARKING CLEAR PLASTIC PIECE BROKEN AT 3AC AND 31JKL. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
645 | 32798020 | FINDING (NRC) TASKCARD 25-SVA-08 (00) / ITEM ONE L1 F/A LEFT SIDE NEEDS PAINT | F/A SEAT | Closed | Normal | PAINT |  |  | Yes | FWD
646 | 32798034 | FINDING (NRC) TASKCARD 25-SVA-08 (00) / ITEM ONE L1 F/A RIGHT SIDE NEEDS PAINT | F/A SEAT | Closed | Normal | PAINT |  |  | Yes | FWD
648 | 32798035 | CAB NO CALL BACK F/A R2 R/H F/A SEAT COLOUR FADED | F/A SEAT | Closed | Normal | PAINT |  |  | Yes | AFT
649 | 32798041 | CAB NO CALL BACK PAINT L2 L/H F/A SEAT COLOUR FADED | F/A SEAT | Closed | Normal | PAINT |  |  | Yes | AFT
650 | 32798047 | CAB NO CALL BACK L1 L/H F/A SEAT CUSHION HEAD PEN MARK | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
653 | 32798059 | CAB NO CALL BACK L1 L/H F/A SEAT UPPER BACK CUSHION PEN MARK | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
655 | 32798062 | CAB NO CALL BACK L1 L/H F/A SEAT BOTTOM CUSHION PEN MARK | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
656 | 32798069 | CAB NO CALL BACK L1 L/H F/A SEAT BOTTOM CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
657 | 32798105 | CAB NO CALL BACK L1 L/H F/A SEAT LOWER BACK CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
658 | 32798107 | CAB NO CALL BACK L1 L/H F/A SEAT BOTTOM RUB STRIP DAMAGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
659 | 32798117 | CAB NO CALL BACK L1 L/H F/A SEAT UPPER RUB STRIP DAMAGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
660 | 32798118 | CAB NO CALL BACK L1 R/H F/A SEAT BOTTOM RUB STRIP DAMAGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
661 | 32798119 | CAB NO CALL BACK L1 R/H F/A SEAT UPPER RUB STRIP DAMAGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
662 | 32798140 | CAB NO CALL BACK L1 R/H F/A SEAT CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
663 | 32798159 | CAB NO CALL BACK L1 R/H F/A SEAT UPPER BACK PEN MARK | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | FWD
664 | 32798183 | CAB NO CALL BACK R2 F/A SEAT CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
665 | 32798189 | CAB NO CALL BACK L2 F/A SEAT BOTTOM CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
666 | 32798191 | CAB NO CALL BACK L2 F/A SEAT LOWER BACK CUSHION DEFLATED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
667 | 32798204 | CAB NO CALL BACK L2 F/A SEAT LOWER RUB STRIP DAMGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
668 | 32798205 | CAB NO CALL BACK L2 F/A SEAT UPPER RUB STRIP DAMGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
669 | 32798221 | CAB NO CALL BACK R2 F/A SEAT LOWER RUB STRIP DAMGED | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes | AFT
680 | 32798602 | CAB - NO CALL BACK - ALL LAVS ALL LAVS SHROUD MISSING SCREWS | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | JOINT
681 | 32798604 | CAB - NO CALL BACK - LAV A LAV A LOWER CABINET LATCH MISSING SCREW | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | FWD
682 | 32798606 | CAB - NO CALL BACK - LAV D LAV D TOILET LID BROKEN | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
683 | 32798626 | CAB - NO CALL BACK - LAV E LAV E INSIDE ASHTRAY CHIPPED | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
684 | 32798683 | PNT - NO CALL BACK - LAV A LAV A NURSING TABLE REQ PNT | LAVATORY | Closed | Normal | PAINT |  |  | Yes | FWD
685 | 32798689 | CAB - NO CALL BACK - LAV E LAV E SIDE WALL PAINT PEELED OFF | LAVATORY | Closed | Normal | S/W |  |  | Yes | JOINT
686 | 32798787 | CAB - NO CALL BACK - LAV A LAV A FUACET LEAKING | LAVATORY | Closed | Normal | CAB | Requested - R |  | Yes | FWD
687 | 32798821 | CABIN FLOOR PANEL--CAB--CALLBACK COCKPIT/CABIN FLOOR PANEL NO: 241EF, 241KF, 241LF, 241MF, 242FF, 242KF, 242LF, 242MF AND 211FF REQUIRES REMOVAL FOR ACCESS. | GENERAL CABIN | Open | Normal | CAB |  | REQ RE-ISNP | Yes
688 | 32798972 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 1AC AND 2AC WILL EXPIRE AT 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
689 | 32798977 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 3AC AND 4AC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | C/W CHECK W/HPC | Yes
690 | 32798980 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 5AC AND WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
691 | 32798982 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 30ABC WILL EXPIRE ON 10/2026 | GENERAL CABIN | Open | Normal | CAB | Requested - R | C/W CHECK W/HPC | Yes
692 | 32798987 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 31ABC WILL EXPIRE ON 10/2026 AND AT 32ABC EXPIRED ON 04/2010 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
693 | 32799012 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 33ABC AND 34ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
695 | 32799029 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 36ABC AND 37ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
696 | 32799031 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 38ABC EXPIRES ON 9/2026 AND 40ABC WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
697 | 32799033 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 42ABC AND 43ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
698 | 32799036 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 44ABC WILL EXPIRE ON 9/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
699 | 32799038 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 1JL AND 2JL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
700 | 32799049 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 3JL AND 4JL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
701 | 32799051 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 5JL WILL EXPIRE ON 09/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
702 | 32799053 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 30JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
703 | 32799054 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 31JKL AND 32JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
704 | 32799060 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 33JKL AND 34JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
705 | 32799062 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 35JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
706 | 32799063 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 36JKL AND 37JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
707 | 32799064 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 39JKL AND 40JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
708 | 32799065 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 41JKL AND 42JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
709 | 32799066 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT 44JKL WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes
710 | 32799069 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT FWD DOOR LH AND FWD DOOR RH WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes | FWD
711 | 32799071 | CAB - RII - OXYGEN GENERATOR AFT DOOR CTR #1 AND AFT DOOR CTR #2 OXYGEN GENERATOR WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes | AFT
712 | 32799080 | CAB - RII - OXYGEN GENERATOR OXYGEN GENERATOR AT AFT DOOR RH WILL EXPIRE ON 10/2026 | GENERAL CABIN | Closed | Normal | CAB | Requested - R | C/W | Yes | AFT
713 | 32799332 | CAB-NO CALL BACK AFT GALLEY CART COMPARTMENT AT 519 T-DIVIDER WITH BROKEN BUMPER. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
714 | 32799335 | CAB-NO CALL BACK AFT GALLEY CART COMPARTMENT AT 519 T-DIVIDER WITH BROKEN BUMPER. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
715 | 32799336 | CAB - NO CALL BACK AFT GALLEY CART COMPARTMENT AT 518 T-DIVIDER WITH BROKEN BUMPER. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
716 | 32799338 | CAB - NO CALL BACK AFT GALLEY COMPARTMENT DOOR NO.504 LOOSE | GALLEY | Closed | Normal | CAB | N/R |  | Yes | AFT
717 | 32799344 | CAB - NO CALL BACK AFT GALLEY FOOT STEP INOP. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
718 | 32799347 | CAB - NO CALL BACK G1 GALLEY COMPARTMENT 101 DOOR HINGE LOOSE | GALLEY | Open | Normal | CAB |  | C/W CHECK W/HPC | Yes | AFT
719 | 32799351 | CAB - NO CALL BACK AFT GALLEY DIVIDER RED LATCH (3 R/H SIDE) AND (1 L/H SIDE) REQ.REPLACEMENT | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
720 | 32799639 | CAB - NO CALL BACK LAVATORY "E" WATER HEATER INOP. | LAVATORY | Closed | Normal | CAB | Requested - R | OPS CHECK | Yes | AFT
721 | 32799641 | CAB - NO CALL BACK LAV "E" WATER FAUCET LEAKING | LAVATORY | Closed | Normal | CAB | Requested - CR |  | Yes | AFT
722 | 32799647 | PAINT - NO CALL BACK LAV "A" NURSING TABLE DISCOLORED | LAVATORY | Closed | Normal | PAINT |  |  | Yes | FWD
723 | 32800126 | AVIO---------RII--------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA FWD MEGAPHONE WILL EXPIRE ON 23JUN2026 P/N A12SA S/N 1143748 | GENERAL CABIN | Closed | Normal | AV |  |  | Yes | FWD
724 | 32800141 | CABIN-----NO CALL BACK------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA PORTABLE OXYGEN CYLINDER AFT OF SEAT 5JL WILL EXPIRE ON 14 AUG 2026 P/N 9700-C1A-BF23A S/N P21110181 | GENERAL CABIN | Closed | Normal | CAB |  |  | Yes | FWD
725 | 32800163 | CABIN--------RII--------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA LOWER PORTABLE OXYGEN CYLINDER MISSING OVERHAUL CERTIFICATE TAG AT AFT OF SEAT 5JL | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | FWD
726 | 32800175 | S/M--------RII--------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA PORTABLE OXYGEN CYLINDER HOLDER BROKEN AT AFT OF SEAT 44ABC | GENERAL CABIN | Closed | Normal | S/M |  |  | Yes | AFT
728 | 32800196 | CABIN--------RII--------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA R2 DOOR PORTABLE FIRE EXTINGUSHER OVERHAUL CERTIFICATE TAG INSPECTION STAMP FADED P/N P3APP003010D S/N 103900 EXP 12MAR2037 | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
729 | 32800225 | CABIN--------RII--------FINDING (NRC) TASKCARD 25-65-00-01-0-SVA L2 DOOR PORTABLE FIRE EXTINGUSHER OVERHAUL CERTIFICATE TAG INSPECTION STAMP UNREADABLE P/N P3APP003010D S/N 104285 EXP 12MAR2037 | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | AFT
742 | 32801170 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY COMP. 201 DOOR FRAME DETTACHED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
743 | 32801193 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY COMP. 209 DOOR SLAMLATCH LOOSE. | GALLEY | Closed | Normal | CAB | N/R |  | Yes | FWD
744 | 32801209 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY (G1-G2) GALLEY WORKTOP SEALANT PARTIALLY MISSING. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
748 | 32801440 | CAB - NO CALLBACK - SIDEWALL SIDEWALL SPLINE AT 1LJ B/C CHIPPED. | TEDLAR/SIDEWALL | Closed | Normal | CAB | Requested |  | Yes | FWD
749 | 32801510 | CAB - NO CALLBACK - SIDEWALL SIDEWALL SPLINE AT 4LJ B/C CHIPPED. | TEDLAR/SIDEWALL | Closed | Normal | CAB | Requested |  | Yes | FWD
751 | 32801511 | CAB - NO CALLBACK RUBBER SEAL IS CUT AT FWD GALLEY DIRECTLY ABOVE COMP. 101 | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
752 | 32801532 | CAB - NO CALLBACK RUBBER SEAL BETWEEN FWD GALLEY AND COCKPIT MISSING. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
753 | 32801634 | CAB - NO CALLBACK - STOWAGE BIN STOWAGE BIN DIRECTLY INFRONT OF SEAT 30LKJ MISSING DOOR DAMPENER. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | FWD
754 | 32801637 | CAB - NO CALLBACK - STOWAGE BIN STOWAGE BIN OF SEAT 4LJ MISSING 2EA DOOR DAMPENER. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | FWD
755 | 32801640 | CAB - NO CALLBACK - STOWAGE BIN STOWAGE BIN OF SEAT 5LJ MISSING DOOR DAMPENER. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes | FWD
756 | 32801651 | CAB - NO CALL BACK - CAPTAIN ARMREST CAPTAIN ARMREST UPPER SHROUD LOOSE. | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
757 | 32801649 | ESCAPE SLIDE---RII ESCAPE SLIDE L/H FWD REQ REMOVAL FOR ACCESS | PAX DOORS | Closed | Normal | CAB |  | CLOSE UP TO DO | Yes | FWD
758 | 32801735 | ESCAPE SLIDE---RII ESCAPE SLIDE R/H FWD REQ REMOVAL FOR ACCESS | PAX DOORS | Closed | Normal | CAB |  | CLOSE UP TO DO | Yes | FWD
759 | 32801738 | CAB - NO CALL BACK - CAPTAIN SEAT CAPTAIN SEAT AFT SHROUD CRACKED. | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
779 | 32804054 | ESCAPE SLIDE---RII L2 DOOR ESCAPE SLIDE REQ REMOVAL FOR ACCESS | PAX DOORS | Closed | Normal | CAB |  | CLOSE UP TO DO | Yes | AFT
780 | 32804056 | ESCAPE SLIDE---RII R2 DOOR ESCAPE SLIDE REQ REMOVAL FOR ACCESS | PAX DOORS | Closed | Normal | CAB |  | CLOSE UP TO DO | Yes | AFT
785 | 32804526 | CAB - NO CALL BACK LAV A BABY BASSINET TABLE LATCH DIRTY | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | FWD
786 | 32804529 | CAB - NO CALL BACK LAV E BABY BASSINET TABLE LATCH DIRTY | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
787 | 32804530 | CAB - NO CALL BACK LAV D BABY BASSINET TABLE LATCH DIRTY | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | AFT
788 | 32804532 | CAB - NO CALL BACK FWD GALLEY COMPT 208 ICE BOX SURFACE DIRTY AND MISSING SEALANT. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
789 | 32804533 | PAINT - NO CALL BACK FWD GALLEY COMPT 214 LONG AND SHORT CART CATCHES CHIPPED PAINT. | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
790 | 32804535 | CAB - NO CALL BACK FWD GALLEY BUN WARMER LATCH LOOSE. | GALLEY | Closed | Normal | CAB | Requested - R |  | Yes | FWD
791 | 32804540 | CAB - NO CALL BACK FWD GALLEY CART CATCHES 3EA LONG NO. 111 , 110 AND 109 1 SHORT CART CATCHES NO.111 | GALLEY | Closed | Normal | CAB | Requested |  | Yes | FWD
792 | 32804543 | AVIO - NO CALL BACK FWD GALLEY LIGHT LENS DISCOLORATION | GALLEY | Closed | Normal | AV |  |  | Yes | FWD
793 | 32804553 | CAB - NO CALL BACK - COCKPIT SEAT CAPTIN AND FIRST OFFICER SEAT AFT SHROUD CRACKED | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
794 | 32804554 | CAB - NO CALL BACK - COCKPIT SEAT CAPTAIN SEAT PLACRAD DEATTACHED | FLIGHT DECK | Closed | Normal | PAINT |  |  | Yes | FWD
795 | 32804556 | CAB - NO CALL BACK - COCKPIT FROUTH OBSERVER FOURTH OBSERVER CUP HOLDER LOOSE | FLIGHT DECK | Closed | Normal | CAB | N/R |  | Yes | FWD
796 | 32804558 | CAB - NO CALL BACK - COCKPIT ESCAPE ROPE COVER VELCRO DETACHED. | FLIGHT DECK | Closed | Normal | CAB | N/R |  | Yes | FWD
797 | 32804560 | CAB - NO CALL BACK - COCKPIT DISC STOWAGE F/O DISC STOWAGE LATCH INOP | FLIGHT DECK | Closed | Normal | CAB | Requested - CR |  | Yes | FWD
798 | 32804565 | CAB - NO CALL BACK - COCKPT CAPTIN WASTE AND OXY DOOR MAKE NOISY SOUND | FLIGHT DECK | Closed | Normal | CAB | N/R |  | Yes | FWD
799 | 32804566 | CAB - NO CALL BACK - COCKPIT CAPTAIN ARMREST CAPTAIN ARMREST DISCOLORED | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
800 | 32804567 | CAB - NO CALL BACK - COCKPIT CAPTAIN ARMREST COCKPIT CAPTAIN ARMREST LOOSE | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
801 | 32804568 | CAB - NO CALL BACK - COCKPIT MEAL TABLE CAPTAIN AND F/O MEAL TABLE DISCOLORED | FLIGHT DECK | Closed | Normal | PAINT | Requested - CR |  | Yes | FWD
802 | 32804570 | CAB - NO CALL BACK - COCKPIT SPEAKERS COCKPIT CAPTAIN AND F/O SPEAKERS PANEL SCREWS MISSING | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
803 | 32804571 | CAB - NO CALL BACK - COCKPIT LIFE VEST COVER THIRD OBSERVER LIFE VEST COVER MISALIGNED | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
804 | 32804573 | CAB - NO CALL BACK - COCKPIT LIGHT PNL COCKPIT OVER HEAD LIGHT PNL SCREW MISSING | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
805 | 32804575 | CAB - RII - COCKPIT SEAT BELT COCKPIT FOURTH OBSERVER SEAT BELT INOP | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
806 | 32804576 | CAB - NO CALL BACK - COCKPIT F/O WASTE DOOR COCKPIT F/O WASTE DOOR MAKE NOISY SOUND | FLIGHT DECK | Closed | Normal | CAB | N/R |  | Yes | FWD
807 | 32804577 | CAB - NO CALL BACK - COCKPIT CAPTAIN SEAT COCKPIT CAPTAIN SEAT AFT SHROUD MISSING SCREW | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes | FWD
826 | 32817167 | PAX DOOR LINING FWD R/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Closed | Normal | PAINT |  |  | Yes | FWD
827 | 32817204 | PAX DOOR LINING FWD L/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Closed | Normal | PAINT |  |  | Yes | FWD
828 | 32817224 | PAX DOOR LINING AFT L/H PAX DOOR SUPPORT ARM LINING REQ PNT | PAX DOORS | Closed | Normal | PAINT |  |  | Yes | AFT
829 | 32817230 | PAX DOOR LINING ALL PAX DOOR SLIDE COVER REQ PNT | PAX DOORS | Closed | Normal | PAINT |  |  | Yes | JOINT
839 | 32823153 | CAB - RII -L2 F/A L2 F/A REMOVED FOR ACCESS | F/A SEAT | Closed | Normal | CAB |  |  | Yes | AFT
840 | 32823140 | AV - NO CALL BACK REMOVE ELECTRICAL WIRE B/C SEAT 5A , 5L | PAX SEAT | Closed | Normal | AV |  |  | Yes | JOINT
841 | 32823160 | AV - NO CALL BACK REMOVE ELECTRICAL WIRE SEAT 30ABC TO 34ABC . | PAX SEAT | Closed | Normal | AV |  |  | Yes | JOINT
842 | 32823162 | AV - NO CALL BACK REMOVE ELECTRICAL WIRE SEAT 30JKL TO 34JKL . | PAX SEAT | Closed | Normal | AV |  |  | Yes | JOINT
843 | 32823272 | CAB-CALL BACK SEAT#5JL,5AC,30ABC,31ABC,32ABC,33ABC34ABC,30JKL,31JKL.32JKL,33JKL&34JKL REQ REMOVAL SEAT`S FOR ACCESS. | PAX SEAT | Open | Normal | CAB |  | 5AC , 5JL OPS TO DO | Yes | JOINT
852 | 32824863 | CAB - NO CALLBACK - SIDEWALL SIDEWALL SPLINE AT 1AC - B/C SHIFTED DOWNWARD. | TEDLAR/SIDEWALL | Closed | Normal | CAB | N/R |  | Yes | FWD
866 | 32825358 | PAX DOOR LINING FWD R/H AND L/H PAX DOOR ALL LINING REQ PNT | PAX DOORS | Closed | Normal | PAINT |  |  | Yes | FWD
867 | 32825368 | PAX DOOR LINING AFT R/H AND L/H PAX DOOR ALL LINING REQ PNT | PAX DOORS | Closed | Normal | PAINT |  | 462 | Yes | AFT
869 | 32825361 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1AC,2AC,3AC,4AC,5CJ FOOD TRAY DOOR - SHROUD ASSEMBLY BROKEN | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
870 | 32825385 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1ACL,3C,4L OVERRIDE - MANUAL BROKEN | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
871 | 32825434 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1ACJL,2C,3ACJ,5CJL ARMREST LOOSE | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
875 | 32825488 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY G2 MODULE COMPT. 209 DOOR HINGE LOOSE. | GALLEY | Closed | Normal | CAB | N/R |  | Yes | FWD
876 | 32825451 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 4J,5C RUBSTRIP - FRONT BROKEN | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
877 | 32825594 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1J RUBSTRIP - SHELL BROKEN | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
878 | 32825599 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1C,5A PANEL ASSEMBLY - ACCESS CRACK | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
879 | 32825631 | CAB - NO CALLBACK - LAV A "LAVATORY A" AIR VENTILATION HOOD FOUND BROKEN. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes | FWD
880 | 32825612 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 1A SEAT CLOSEOUT ASSEMBLY MISSING | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
881 | 32825658 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
882 | 32825968 | FINDING (NRC) TASKCARD 2521000103-001 (04) / ITEM-1 ALL B/C SEAT BELT DIRTY | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
883 | 32825978 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
884 | 32825996 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
885 | 32826054 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE ALL B/C SEAT HEADREST REQUIRED REMOVAL FOR ACCESS | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
886 | 32826162 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
887 | 32826217 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
888 | 32826246 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
908 | 32827664 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE G/C SEAT# 30B SIDE PAD CRACK | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
909 | 32827686 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE ALL G/C SEAT FOODTRAY DIRTY | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
913 | 32827700 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE G/C SEAT# 37J BUMPER – ENDBAY DAMAGE | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
914 | 32827716 | FINDING (NRC) TASKCARD 2521000103-002 (05) / ITEM-1 ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
915 | 32827826 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT#2JL,3L,5L LATCH - BACK MISSING | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
916 | 32828287 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND LAV A INNER DOOR TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
917 | 32828299 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND LAV A OUTER DOOR TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
918 | 32828375 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND UPPER SIDE OF COCKPIT DOOR OUTER SIDE TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
919 | 32828382 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND GALLEY DOOR 210 TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
920 | 32828383 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND GALLEY DOOR 205 TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
921 | 32828385 | MACHINE SHOP FWD GALLEY AND AFT GALLEY ALL OVENS FOUND BOLTS FROZEN | GALLEY | Closed | Normal | S/M |  |  | Yes | JOINT
922 | 32828386 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND SIDE WALL PANEL AT SEATS 4 AC ,5 AC ,39 ABC ,40 ABC ,33 JKL ,38 JKL ,39 JKL TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  | C/W | Yes | JOINT
923 | 32828395 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND FWD OUTER WALL OF LAV D TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
924 | 32828415 | FINDING (NRC) TASKCARD DCC-32S (11) / ITEM ONE DURING DCC FOUND AFT WALL OF LAV D BESIDE F/A SEAT TEDLAR DAMAGED | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
925 | 32829036 | CAB - NO CALL BACK - AFT GALLEY AIR CHILLET AFT GALLEY AIR CHILLER FILTER MISSING | GALLEY | Closed | Normal | CAB | Requested |  | Yes | AFT
929 | 32830299 | L2 DOOR SILL PANEL REQ REMOVAL FOR ACCESS | PAX DOORS | Closed | Normal | CAB |  |  | Yes | AFT
931 | 32830452 | CAB - NO CALL BACK - SIDEWALL MISSING SPLINE AT 5 AC | TEDLAR/SIDEWALL | Closed | Normal | CAB |  |  | Yes | FWD
932 | 32830902 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE G/C SEAT#37B,C,K 38A VIDEO BEZEL ASSEMBLY CRACK | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
933 | 32831610 | FINDING (NRC) TASKCARD 25-SVA-03 (00) / ITEM ONE B/C SEAT# 2AC, 3J AND 4L SHROUD - CONSOLE SIDE DAMAGED. | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
938 | 32832622 | CKPT,,,,,PNT,,,,NO CALL BACK DURING INSP OF INTERNAL STRUCTURE OF THESE SLIDING WINDOW FOUND CAPTIN & F/O INNER FRAME PNT PEELED OFF | FLIGHT DECK | Closed | Normal | PAINT |  |  | Yes
941 | 32835180 | R1 DOOR DAMPER GUIDE WITH CRACK | PAX DOORS | Closed | Normal | CAB | Requested - R |  | Yes
947 | 32836864 | CAB - RII - L1 F/A SEAT L1 INBOARD AND OUTBOARD F/A SEAT REQUIRE REMOVAL FOR ACCESS. | F/A SEAT | Closed | Normal | CAB |  | TO BE CLOSED | Yes
954 | 32849864 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPARTMENT 520 MID LATCH LEVER LOOSE. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
955 | 32849891 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY 7 EA SMALL CART TURN CATCHES AND 7 EA LONG CART CATCHES PAINT FADED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
956 | 32849898 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY CART COMPT. 213 T-DIVIDER BUMPER DETACHED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
957 | 32849904 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY COMPT. 204 TURN CATCHES PAINT FADED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
958 | 32849910 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 3 EA MID LATCH LEVER LOOSE. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
959 | 32849919 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY CART COMPT. 111 T-DIVIDER BUMPER DAMAGED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
960 | 32849934 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY CART COMPT. 110 UPPER LH AIR FLAP SEAL TORN. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
961 | 32849935 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA SHORT CART CATCHES AND 1 EA LONG CART CATCH PAINT FADED. | GALLEY | Closed | Normal | CAB | Requested |  | Yes
962 | 32849936 | CAB - NO CALLBACK - FWD GALLEY G2 GALLEY ALL CART TURN CATCHES PAINT FADED. | GALLEY | Closed | Normal | CAB | Requested | AFTER S/M REPAIR | Yes
963 | 32849940 | CAB - NO CALLBACK - STOWAGE C201 STOWAGE C201 INNER DOOR SURFACE WITH PEN MARKS. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes
964 | 32849947 | PAINT - NO CALLBACK - LAV E LAVATORY "E" WASHBASIN PANELS WITH CHIPPED PAINT. | LAVATORY | Closed | Normal | PAINT |  |  | Yes
965 | 32849950 | CAB - NO CALLBACK - LAV D LAVATORY "D" MIRROR LOWER SIDE FADED. | LAVATORY | Open | AOG | CAB | Requested | NEF | Yes
967 | 32849953 | CAB - NO CALLBACK - FLIGHT DECK CAPTAIN PEDAL RUBBER MAT DETACHED AND DIRTY. | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes
968 | 32849961 | CAB - NO CALLBACK - FLIGHT DECK F/O PEDAL RUBBER MAT DETACHED AND DIRTY. | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes
971 | 32850062 | CAB - RII - LAV A LAVATORY "A" WASTE FLAP FOUND WITH FAST RETRACTING. | LAVATORY | Closed | Normal | CAB | Requested |  | Yes
972 | 32850080 | CAB - NO CALLBACK - FLIGHT DECK CAPTAIN SLIDING TABLE WITH MISSING PAPER CLIP. | FLIGHT DECK | Closed | Normal | CAB |  |  | Yes
973 | 32850114 | CAB - NO CALLBACK - STOWAGE S3 STOWAGE S3 THRESHOLD WARNING TAPE FADED. | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes
978 | 32850652 | PNT - NO CALLBACK - FWD GALLEY G1 GALLEY SLIDING TABLE WITH CHIPPED PAINT. | GALLEY | Closed | Normal | PAINT |  |  | Yes
980 | 32853382 | FINDING (NRC) DOCUMENT EOD-320-46-00005-R00 CEILING PNL BET FR-24- TO FR-26 LH REQ REMOVAL FOR ACCESS | GENERAL CABIN | Closed | Normal | CAB
981 | 32854724 | COCKPIT CEILING PANEL- CAB - RII REMOVAL OF COCKPIT CEILING PNL/S 211AC, 212AC, 211BC, 212BC, 211DC, 212DC, 211EC, 212EC, 211FC 212FC ,211LC,212LC,211MW, AND 211LW FOR ACCESS | FLIGHT DECK | Open | Normal | CAB | N/R | C/W CHECK W/HPC | Yes
993 | 32867377 | CAB - RII - R2 F/A SEAT R2 F/A SEAT BELT FRAYED. | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes
994 | 32867426 | CAB - RII - L1 F/A SEAT L1 INBOARD AND OUTBOARD F/A SEAT BELTS FRAYED. | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes
995 | 352142-01-1 | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS | GENERAL CABIN | Closed | Normal | CAB | Requested | INSP | Yes
996 | 32867568 | CAB - RII - L2 F/A SEAT L2 F/A SEAT BELT FRAYED. | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes
997 | 32867643 | CAB - RII - SWIVEL F/A SEAT SWIVEL F/A SEAT BELT FRAYED. | F/A SEAT | Closed | Normal | CAB | Requested |  | Yes
998 | 32867427 | CAB - RII - CAPTAIN SEAT BELT CAPTAIN SEAT BELT L/H SHOULDER HARNESS FRAYED AND LAP BELT DETERIORATED | FLIGHT DECK | Closed | Normal | CAB | Requested - R | C/W | Yes
999 | 32867877 | CAB - RII - FIRST OFFICER SEAT BELT F/O SEAT BELT SHOULDER HARNESS WEAK RETRACTION AND LAP BELTS DETERIORATED | FLIGHT DECK | Closed | Normal | CAB | Requested - R | TO BE CLOSED | Yes
1000 | 32867879 | CAB - RII - 3D OBSERVER SEAT BELT 3RD OBSERVER SEAT BELT DETERIORATED | FLIGHT DECK | Closed | Normal | CAB | Requested |  | Yes
1006 | 32458025 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | PAX DOORS | Open | Normal | CAB |  | C/W CHECK W/HPC | Yes
1010 | 32888552 | FINDING (NRC) TASKCARD 25-SVA-05 (00) / ITEM ONE G/C SEATS# 30ACJK ARMCAP LOOSE. | PAX SEAT | Closed | Normal | SEAT |  |  | Yes
1011 | 32890903 | CAB - NO CALLBACK - LAV E LAV E HOLDER PAPER ROLL BROKEN | LAVATORY | Closed | Normal | CAB | Requested |  | Yes
1012 | 32898948 | CAB - NO CALL BACK LAV E PAPER ROLL HOLDER INSIDE FRAME BROKEN | LAVATORY | Closed | Normal | CAB |  |  | Yes
1013 | 32898937 | CABIN - NO CALL BACK DURING DCC FOUND OVHD HINGE FITTING INOP AT SEAT 2AC, 30LJ, 38LJ, 41AC, 34AC | GENERAL CABIN | Closed | Normal | CAB | Requested |  | Yes
1014 | 32904467 | PAINT - NO CALLBACK - LAV E LAV E WASHBASIN PANEL PAINT SCRATCHED | LAVATORY | Closed | Normal | PAINT |  |  | Yes
1015 | 32912808 | CAB - RII - R2 F/A SEAT R2 DOUBLE WALL-MOUNTED F/A SEAT REQUIRE REMOVAL FOR ACCESS | F/A SEAT | Closed | Normal | CAB |  | TO BE CLOSED | Yes
1016 | 32912820 | CAB - RII - SWIVEL F/A SEAT SWIVEL F/A SEAT REQUIRE REMOVAL FOR ACCESS | F/A SEAT | Closed | Normal | CAB |  | TO BE CLOSED | Yes
1017 | 32925363 | AFT L/H STOWAGE WALL TEDLAR CHIPPED OFF | TEDLAR/SIDEWALL | Closed | Normal | S/W |  |  | Yes
1019 | 26451608 | TSV 10-3093 R02/(A320)(HZ-ASA THRU HZ-ASG) WEIGHING CHECK LIST | GENERAL CABIN | Closed | Normal | JOINT |  |  | Yes
1023 | 32929120 | 29 LIFE VEST WILL EXPIRE WITHIN 6 MONTHS AT THE FOLLOWING LOCATIONS: 43A,43C, 43J, 43K, 43L, 44J, 44K, 2J, 30K, 30L, 33J, 33L, 34K, 38K, 40K, 40L, 41A, 41B, 41C, 44L, 42A, 42B, 42C, 43B, 44B, 44C, SPARE NO.2, SPARE NO.3, SPARE NO.4. | GENERAL CABIN | Closed | Normal | CAB | Requested - CR | TO BE CLOSED | Yes
1049 | 32952652 | PAINT - NO CALL BACK LAV D SIDE WALL REQ PNT | LAVATORY | Open | Normal | PAINT
1050 | 32956184 | CAB - NO CALLBACK - LAV A "LAVATORY A" TOILET VACUUM ASSEMBLY WITH LEAKING. | LAVATORY | Open | Normal | CAB | Requested - R
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal

## DASHBOARD
📊 ASF C3-CHECK — WORK PACKAGE DASHBOARD | [5 empty] | Day 35/36
All figures update automatically from ASF Tracker
STATUS OVERVIEW
| Total Items/WOs | 385 | Closed | 347 | Completion | 90%
| Open | 38 | In Progress | 0 | Deferred / Hold | 0
PRIORITY ALERTS
| AOG | 3 | Critical | 0 | High | 0
PARTS REQUIREMENTS (count of WOs with each status)
| Requested | 112 | Requested – CR | 4 | Requested – R | 31
| Pending - Require Evaluation | 0 | N/R (not required) | 15 | N/A (Not available) | 0
BY CATEGORY
| TASK CARD | 101 / 125 | LAVATORY | 34 / 37 | GALLEY | 38 / 39
| Completion: 81% |  | Completion: 92% |  | Completion: 97%
| GENERAL CABIN | 69 / 76 | TEDLAR/SIDEWALL | 13 / 13 | PAX SEAT | 26 / 27
| Completion: 91% |  | Completion: 100% |  | Completion: 96%
| PAX DOORS | 13 / 14 | F/A SEAT | 29 / 29 | OTHERS | 0 / 0
| Completion: 93% |  | Completion: 100% |  | -
| FLIGHT DECK | 24 / 25
Completion: 96%
SPECIALTY
| CABIN | 212 / 228 | SEAT SHOP | 23 / 26 | AV/FOMAX | 32 / 34
| Completion: 93% |  | Completion: 88% |  | Completion: 94%
| SIDEWALL | 11 / 11 | S/M | 6 / 6 | PAINT | 25 / 26
| Completion: 100% |  | Completion: 100% |  | Completion: 96%
| JOINT | 18 / 21 | INSP | 9 / 13 | A/P | 11 / 19
| Completion: 86% |  | Completion: 69% |  | Completion: 58%

## Findings Draft
📋 FINDINGS DRAFT — Pre-AMOS
Findings sourced from ACFT Finding Report App · Review & assign P/N before raising on AMOS
# | By | Category | Sub-Category | Finding Description | Remarks | Photo URL | AMOS Status | WO No. | P/N Required | Qty
1 | BAY 4 CREW | LAVATORY | LAV A | LAVATORY A NURSING TABLE WITH MISSING BUMPER. |  |  | Raised
2 | BAY 4 CREW | LAVATORY |  | LAVATORY A NURSING TABLE DISCOLORED. | PAINT |  | Not Raised
3 | BAY 4 CREW | LAVATORY |  | LAVATORY A SERVICE CABINET STORAGE DRAWER RUBBER SEAL NOT SECURED. |  |  | Raised
4 | BAY 4 CREW | LAVATORY |  | LAVATORY A TOILET SHROUD WITH MISSING 2 EA SCREWS. |  |  | Raised
5 | BAY 4 CREW | LAVATORY |  | LAVATORY A TOILET PAPER DISPENSER COVER COLOR FADED. |  |  | Raised
6 | BAY 4 CREW | LAVATORY |  | LAVATORY A FAUCET LEAKING |  |  | Raised
7 | BAY 4 CREW | LAVATORY | LAV E | LAVATORY E TOILET SHROUD NOT SECURED. |  |  | Raised
8 | BAY 4 CREW | LAVATORY |  | LAVATORY E TOILET SHROUD SCREW CORRODED |  |  | Not Raised
9 | BAY 4 CREW | LAVATORY |  | LAVATORY E TOILET SHROUD COVER DISCOLORED. | PAINT |  | Raised
10 | BAY 4 CREW | LAVATORY |  | LAVATORY E NURSING TABLE WITH MISSING BUMPER. |  |  | Raised
11 | BAY 4 CREW | LAVATORY |  | LAVATORY E FAUCET LEAKING. |  |  | Raised
12 | BAY 4 CREW | LAVATORY |  | LAVATORY E WATER HEATER INOP. |  |  | Raised
13 | BAY 4 CREW | LAVATORY |  | LAVATORY E AIR VENTILATION COVER BROKEN. |  |  | Raised
14 | BAY 4 CREW | LAVATORY | LAV D | LAVATORY D TOILET SHROUD COVER NOT SECURED. |  |  | Raised
15 | BAY 4 CREW | LAVATORY |  | LAVATORY D WASHBASIN ACCESS DOOR REQ PAINT. |  |  | Not Raised
16 | BAY 4 CREW | LAVATORY |  | LAVATORY D TOILET PAPER ROLLER IS MISSING. |  |  | Raised
17 | BAY 4 CREW | LAVATORY |  | LAVATORY D FAUCET IS LEAKING. |  |  | Not Raised
18 | BAY 4 CREW | LAVATORY |  | LAVATORY D SINK SIEVE NOT SECURED. |  |  | Raised
19 | BAY 4 CREW | LAVATORY |  | LAVATORY D WASHBASIN SINK DRAINING SLOWLY. |  |  | Raised
20 | BAY 4 CREW | LAVATORY |  | LAVATORY D DOOR HANDLE LOOSE. |  |  | Raised
21 | BAY 4 CREW | LAVATORY |  | LAVATORY D TEDLAR DAMAGED. | OUTERBOARD TEDLAR |  | Not Raised
22 | BAY 4 CREW | GALLEY |  | G1 GALLEY CART TURN CATCH AT 109 AND 111 FOUND LOOSE. |  |  | Raised
23 | BAY 4 CREW | GALLEY |  | FWD GALLEY CART COMPT. 109 MID LATCH LEVER IS MISSING. |  |  | Raised
24 | BAY 4 CREW | GALLEY |  | FWD GALLEY COUNTERTOP SEALANT DETERIORATED. | REQ REWORK |  | Raised
25 | BAY 4 CREW | GALLEY |  | G1 GALLEY COMPT. 101 DOOR HINGE LOOSE. |  |  | Not Raised
26 | BAY 4 CREW | GALLEY |  | G2 GALLEY ICE BOX LOWER TRIM WITH CORROSION | REQ EVAL DONT RAISE NOW |  | Not Raised
27 | BAY 4 CREW | GALLEY |  | G2 GALLEY COMPT. 211 LOWER BUMPER IS MISSING. |  |  | Raised
28 | BAY 4 CREW | GALLEY |  | G2 GALLEY COMPT. 210 DOOR TEDLAR CHIPPED OFF. |  |  | Not Raised
29 | BAY 4 CREW | GALLEY |  | G2 GALLEY COUNTERTOP BULGED. | REQ EVAL DONT RAISE NOW |  | Not Raised
30 | BAY 4 CREW | GALLEY |  | G2 GALLEY FOOTSTEP INOP. |  |  | Raised
31 | BAY 4 CREW | GALLEY |  | G2 GALLEY COMPT. 210 DOOR LOCK LOOSE. |  |  | Raised
32 | BAY 4 CREW | GALLEY |  | AFT GALLEY COMPT. 501 DOOR HINGE BROKEN. |  |  | Raised
33 | BAY 4 CREW | GALLEY |  | AFT GALLEY COMPT. 501, 503 AND 504 STC DIVIDER KNOB BROKEN (WITHOUT LOCK). | REQ EVAL |  | Not Raised
34 | BAY 4 CREW | GALLEY |  | AFT GALLEY 3 LONG CART CATCH AND 2 SHORT CART TURN CATCH REQ REPLACEMENT. |  |  | Not Raised
35 | BAY 4 CREW | GALLEY |  | AFT GALLEY ALL OVENS REQ PAITN. |  |  | Raised
36 | BAY 4 CREW | GALLEY |  | AFT GALLEY CART COMPARTMENT AT 517 T-DIVIDER WITH MISSING BUMPER. |  |  | Not Raised
37 | BAY 4 CREW | GALLEY |  | AFT GALLEY CART COMPARTMENT AT 519 T-DIVIDER WITH BROKEN BUMPER. |  |  | Not Raised
38 | BAY 4 CREW | GALLEY |  | AFT GALLEY CART COMPARTMENT AT 518 T-DIVIDER WITH BROKEN BUMPER. |  |  | Not Raised
39 | BAY 4 CREW | GALLEY |  | AFT GALLEY COMPT. 504 DOOR LOOSE. |  |  | Not Raised
40 | BAY 4 CREW | GENERAL CABIN |  | MOST FWD VIDEO EQUIPMENT OVERHEAD STOWAGE DOOR OPENS FAST. |  |  | Raised
41 | BAY 4 CREW | GENERAL CABIN |  | MOST FWD RH MEDICAL KIT OVERHEAD STOWAGE BIN WITH INSIDE DENT. |  |  | Raised
42 | BAY 4 CREW | GENERAL CABIN |  | OSB DOOR WITH INSIDE DENT AT 1AC, 3AC, 4LJ, 5LJ, FWD OF 30JKL, 30 ABC AND 44 JKL. |  |  | Raised
43 | BAY 4 CREW | GENERAL CABIN |  | OSB DOOR MISSING WITH RUBBER BUMPER AT 1AC, 4LJ, 4AC, 5LJ, FWD OF 30 JKL, 30ABC, 31ABC AND 33ABC. |  |  | Raised
44 | BAY 4 CREW | GENERAL CABIN |  | OSB DOOR WITH MISSING RUBBER BUMPER AT 34ABC, 37ABC, 38ABC, 40JKL, 41JKL, 42JKL, 44JKL AND 44ABC. |  |  | Raised
45 | BAY 4 CREW | GENERAL CABIN |  | OSB WITH MISSING UPPER BUMPER AT 1AC, 5AC, 5LJ, 30JKL, 32JKL, 33JKL, 33JKL AND 34ABC. |  |  | Raised
46 | BAY 4 CREW | GENERAL CABIN |  | OSB WITH MISSING UPPER BUMPER AT 36ABC, 38ABC, 38JKL, 40JKL, 40ABC, 41JKL AND 42JKL. |  |  | Raised
47 | BAY 4 CREW | GENERAL CABIN |  | OSB SIDE TRIM BROKEN AT 4LJ AND 39 JKL. |  |  | Raised
48 | BAY 4 CREW | GENERAL CABIN |  | OSB UPPER TRIM BROKEN AT 30ABC. |  |  | Raised
49 | BAY 4 CREW | GENERAL CABIN |  | OSB HANDRAIL BROKEN AT 34ABC, 30JKL. |  |  | Raised
50 | BAY 4 CREW | GENERAL CABIN |  | OSB HANDRAIL SEAT MARKING CLAER PLASTIC PIECE BROKEN AT 3AC AND 31JKL. |  |  | Raised
51 | BAY 4 CREW | FLIGHT DECK |  | ALL FLIGHT PANELS REQUIRE CLEANING. |  |  | Raised
52 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK CAPTAIN FOOT REST RUBBER TORN. |  |  | Not Raised
53 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK CAPTAIN PEDALS DISK PAINT CHIPPED OFF. |  |  | Not Raised
54 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK F/O ASHTRAY BROKEN. |  |  | Not Raised
55 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK CAPTAIN SEAT R/H ARMREST RUBBER DETATCHED. |  |  | Not Raised
56 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK F/O DISK STOWAGE HANDLE BROKEN. |  |  | Not Raised
57 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK CAPTAIN SEAT L/H ARMREST LEATHER DIRTY. |  |  | Not Raised
58 | BAY 4 CREW | FLIGHT DECK |  | FKUGHT DECK F/O SEATBELT PAINT CHIPPED OFF. |  |  | Not Raised
59 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK DOOR LOCK SCREWS FOUND LOOSE |  |  | Not Raised
60 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK FIRST OBSERVER SEAT PAINT CHIPPED OFF. |  |  | Not Raised
61 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK FIRST OBSERVER SEAT HEAD WITH REST MISSING SCREWS. |  |  | Not Raised
62 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK CAPTAIN AND F/O SEAT SHROUD FOUND BROKEN. |  |  | Not Raised
63 | BAY 4 CREW | FLIGHT DECK |  | FLIGHT DECK F/O SEAT R/H ARMREST GAUGE DIRTY. |  |  | Not Raised
64 | FADUL | TEDLAR/SIDEWALL | 1AC | THE SPLINE BETWEEN SIDEWALLS SHIFTED DOWNWARD |  | https://i.ibb.co/QvkGH4GN/2133f228a54e.jpg | Not Raised
65 | FADUL | GENERAL CABIN | 1AC | CHIPPED RUBBER SEAL |  | https://i.ibb.co/9kG3gS87/885f1263c4b8.jpg | Not Raised
66 | FADUL | GENERAL CABIN | 1AC | DIRTY INTERIOR ON THE OVRHD COPMT |  | https://i.ibb.co/Q3qcK5VM/9f8fcdd169e1.jpg | Not Raised
67 | FADUL | GENERAL CABIN | 2AC | SMALL PAINT CHIPPED OF ON STOWAGE COMPT. HANDLE |  | https://i.ibb.co/C3x90KXc/6a668d46a2cf.jpg | Not Raised
68 | FADUL | GENERAL CABIN | 1AC | THE SMALL COMPT. STOWAGE STUCK IN THE CEILING AND NEED ADJUSTMENT |  | https://i.ibb.co/jvCZhrmg/7d9768c8e308.jpg | Not Raised
69 | FADUL | GENERAL CABIN | 1AC | MISSING DAMPER INSIDE STOWAGE COMPT. |  | https://i.ibb.co/Z6wVYkxP/5c3d5c9daf60.jpg | Not Raised
70 | FADUL | GENERAL CABIN | 1AC | TINY PAINT CHIPPED ABOVE PAX SEAT |  | https://i.ibb.co/QFscwxjY/8ad08b79170d.jpg | Not Raised
71 | FADUL | GENERAL CABIN | 1AC | MISSING SCREW ABOVE MIRROR INSIDE STOWAGE COMPT. |  | https://i.ibb.co/1Y4wsYSJ/813e1a75ef91.jpg | Not Raised
72 | FADUL | GENERAL CABIN | 1AC | MISSING SCREW ABOVE MIRROR INSIDE STOWAGE COMPT. |  | https://i.ibb.co/1Y4wsYSJ/813e1a75ef91.jpg | Not Raised
73 | FADUL | GENERAL CABIN | 30ABC | SMALL CHIPPED OF PAINT ON PSU |  |  | Not Raised
74 | FADUL | TEDLAR/SIDEWALL | 2AC | DIRTY LOWER SIDEWALL |  |  | Not Raised
75 | FADUL | GENERAL CABIN | 3AC | SMALL CHIPP OF PAINT ON STOWAGE COMPT |  |  | Not Raised
76 | FADUL | GENERAL CABIN | C101 | COMPT. C101 TEDLAR CHIPPED OF AND DIRTY |  |  | Not Raised
77 | FADUL | GENERAL CABIN | C101 | MISSING HINGE SCREW ON COMPT. C101 |  |  | Not Raised
78 | FADUL | GENERAL CABIN | 2AC | CHIPPED STOWAGE COMPT HANDLE |  |  | Not Raised
79 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | F/O WASTE | F/O WASTER DOOR MAKE NOISY SOUND |  | https://i.ibb.co/jvwwc8nF/9906f344dd92.jpg | Not Raised
80 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | FOURTH OBSERVER | FOURTH OBSERVER SEAT BELT INOP |  | https://i.ibb.co/Z65R8btD/ba3eb900cb73.jpg | Not Raised
81 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT OVERHEAD LIGHT SCREW MISSING |  | https://i.ibb.co/HTct01dB/c871b1f2c316.jpg | Not Raised
82 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | THIRD OBSERVER | THIRD OBSERVER LIFE VEST COVER MISSALIGNMENT |  | https://i.ibb.co/d46MH5DN/a29b0249d1be.jpg https://i.ibb.co/RGGnWLqK/67b761ee5f93.jpg | Not Raised
83 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | SEATBELT | BOTH SEATBELT FOR CAPTAIN, F/O ( DOWN) FRYED |  | https://i.ibb.co/1J2sWRj4/fe904fa9e410.jpg https://i.ibb.co/60HdM7sk/e732d4c17fad.jpg | Not Raised
84 | FADUL | GENERAL CABIN | 3AC | DIRTY INTERIOR STOWAGE COMPT |  | https://i.ibb.co/DHV4TfTZ/becdfce1cd48.jpg | Not Raised
85 | FADUL | GENERAL CABIN | 3AC | DEEP SCRATCH ON STOWAGE COMPT |  |  | Not Raised
86 | FADUL | GENERAL CABIN | 4AC | MISSING DAMPER ON STOWAGE COMPT. |  | https://i.ibb.co/Vc23wV6s/d97b3d0f503d.jpg | Not Raised
87 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | SPEAKERS PANEL | SPEAKERS PANEL FOR CAPTAIN , F/O MISSING SCREW |  | https://i.ibb.co/j9Sx4rbp/8d68053ab10f.jpg | Not Raised
88 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | MEAL TABLE | F/O MEAL TABLE DISCOLORED |  | https://i.ibb.co/v4xWgNG2/ca55a6de0799.jpg | Not Raised
89 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | MEAL TABLE | CAPTAIN MEAL TABLE DISCOLORED |  | https://i.ibb.co/cX1YSVxz/e4fdcb10fd6f.jpg | Not Raised
90 | FADUL | GENERAL CABIN | 5AC | WHITE PAINT ON THE ROUBBER SEAL |  |  | Not Raised
91 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT ARM REST LH DISCOLORED |  | https://i.ibb.co/j9Ph7zwF/cff2b7d75a45.jpg | Not Raised
92 | FADUL | TEDLAR/SIDEWALL | 5AC | DEEP SCRATCH ON THE SIDEWALL |  | https://i.ibb.co/sJHHgLJ5/05dabf7f4f6d.jpg | Not Raised
93 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT RH ARMREST LOOSE |  | https://i.ibb.co/RkQZ0nm8/e63f1c035f2f.jpg | Not Raised
94 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | CAPTAIN SEAT | WASTE AND OXYGEN MASK COVER MAKE NOISY SOUNDS WHEN OPEN AND CLOSE THE DOOR |  | https://i.ibb.co/tMv1RN30/a8351414fa95.jpg | Not Raised
95 | FADUL | TEDLAR/SIDEWALL | 5AC | DEEP SCRATCH ON THE SIDEWALL |  |  | Not Raised
96 | FADUL | TEDLAR/SIDEWALL | 5AC | DEEP SCRATCH ON THE SIDEWALL |  |  | Not Raised
97 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | DISC STOWAGE | DISC STOWAGE FOR F/O LATCH INOP |  | https://i.ibb.co/KQZC85f/f229511eccc0.jpg | Not Raised
98 | HOSSAM ALTHOBAITI 30001461 | FLIGHT DECK | ESCAPE ROPE | ESCAPE ROPE COVER ADHESIVE FOR CAPTAIN, F/O IS DAMAGED |  | https://i.ibb.co/bgykmt5v/3655217e4941.jpg | Not Raised
99 | FADUL | TEDLAR/SIDEWALL | 5AC | TWO BATCHES ON THE SIDEWALL |  | https://i.ibb.co/ZRR3xZ6x/dbb1d6096baf.jpg | Not Raised
100 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT ARMREST SHROUD COVER NOT SECURED |  | https://i.ibb.co/0p70syTY/a44d76f59e12.jpg | Not Raised
101 | 30001451 | GALLEY | FWD GALLEY | COMP.211 LOWER BUMPER MISSING |  | https://i.ibb.co/3yBSQLFR/ba2604ed74d5.jpg | Not Raised
102 | 30001451 | GALLEY | FWD GALLEY | COMP. 208 ICEBOX SURFACE DIRTY AND MISSING SEALANT |  | https://i.ibb.co/YFnXFqdt/99d9f5a0d515.jpg https://i.ibb.co/zhPBsr8V/7dbd40be0697.jpg | Not Raised
103 | 30001451 | GALLEY | FWD GALLEY | COMP. 201 DOOR FRAME DETTACHED |  | https://i.ibb.co/tp5YzfQc/c17e312b3f39.jpg | Not Raised
104 | 30001451 | GALLEY | FWD GALLEY | COMP. 209 SLAMLATCH LOOSE |  | https://i.ibb.co/wh6B6TTw/19cf42c4cdbd.jpg | Not Raised
105 | 30001451 | GALLEY | FWD GALLEY | COMP. 209 DOOR LOOSE |  | https://i.ibb.co/3yg3R11B/41e240e81c2d.jpg | Not Raised
106 | 30001451 | GALLEY | FWD GALLEY | COMP. 210 TEDLAR CHIPED OFF |  | https://i.ibb.co/gb1JSvc1/9fef0d776685.jpg | Not Raised
107 | 30001451 | GALLEY | FWD GALLEY | COMP .101 DOOR LOOSE |  | https://i.ibb.co/Z6kMgkgd/ad0cfff2568b.jpg | Not Raised
108 | 30001451 | GALLEY | FWD GALLEY | COMP.214 LONG AND SHORT CART CATCHES CHIPED PAINT |  | https://i.ibb.co/XZ3tSKZs/ca53d9566c66.jpg https://i.ibb.co/C3dZF01L/3d450b97a6ef.jpg | Not Raised
109 | 30001451 | GALLEY | FWD GALLEY | FWD GALLEY LIGHTS LENS SHROUD DISCOLORATION |  | https://i.ibb.co/QjbQbThx/ff93fdd4330b.jpg https://i.ibb.co/GvXF4mMv/1a7f9414dfc8.jpg | Not Raised
110 | 30001451 | GALLEY | FWD GALLEY | FWD GALLEY BOTH OVENS NEED PAINT |  | https://i.ibb.co/zWZ9jrft/0b6752a9105c.jpg https://i.ibb.co/KcDr903X/18573f4ff7c0.jpg | Not Raised
111 | 30001451 | GALLEY | FWD GALLEY | FWD GALLEY FWD AND AFT MODULE WORKTOP SEALANT PARTIALLY MISSING |  | https://i.ibb.co/yBcZ7W7Z/9968f3fc5e32.jpg https://i.ibb.co/3yRWvSb3/2ac6d645f036.jpg | Not Raised
112 | 30001451 | GALLEY | FWD GALLEY | FWD GALLEY BUN WARMER LATCH LOOSE |  | https://i.ibb.co/cSn68Zf6/69056fb21851.jpg | Not Raised
113 | 30001451 | GALLEY | FWD GALLEY CART CATCHES | 3 LONG CART CATCH : 111,110,109 1 SHORT CART CATCH : 111 |  |  | Not Raised
114 | SHAREEF | TEDLAR/SIDEWALL | N/A | RUBBER SEAL IS CUT AT FWD GALLEY DIRECTLY ABOVE COMP. 101 |  | https://i.ibb.co/TyF7Ybm/3b9bb8dcead2.jpg | Not Raised
115 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT AFT SHROUD CRACKED |  |  | Not Raised
116 | SHAREEF | TEDLAR/SIDEWALL | N/A | CIELING PANEL SLIGHTLY DIRTY ABOVE 1CA |  | https://i.ibb.co/XrprLVsh/c4d70a313317.jpg | Not Raised
117 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | THIRD OBSERVER | THIRD OBSERVER CUP HOLDER NOT SECURED |  |  | Not Raised
118 | FADUL | GENERAL CABIN | LEFT MID CURTAIN | DISCONNECTED |  |  | Not Raised
119 | SHAREEF | TEDLAR/SIDEWALL | N/A | RUBBER SEAL CIELING PANEL ABOVE 3LJ |  | https://i.ibb.co/99zSdFRL/369e3462cd19.jpg https://i.ibb.co/hJFwM5gR/40ec0aadabb4.jpg | Not Raised
120 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT AFT SHROUD MISSING FASTENER |  | https://i.ibb.co/Cp9nLFGy/8533411807a8.jpg | Not Raised
121 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | CAPTAIN SEAT | CAPTAIN SEAT PLACARD FOR LIFE VEST CUTS |  | https://i.ibb.co/zTjMwz6W/b91e98834bf2.jpg | Not Raised
122 | SHAREEF | TEDLAR/SIDEWALL | N/A | RUBBER SEAL OF CIELING PANEL SLIGHTLY DISCOLORED AT 3CA |  | https://i.ibb.co/ycwRPVns/dd45fd4fede7.jpg https://i.ibb.co/tTwW7L6r/eff3971594a1.jpg | Not Raised
123 | FADUL | GENERAL CABIN | 30 ABC | PAINT ON PSU |  |  | Not Raised
124 | FADUL | GENERAL CABIN | 30 ABC | BATCH ON STOWAGE COMPT. |  |  | Not Raised
125 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | F/O SEAT | ASH TRAY NOT SECURED |  | https://i.ibb.co/7Jffd0NP/011fe2f3747b.jpg | Not Raised
126 | 30001461 HOSSAM ALTHOBAITI | FLIGHT DECK | F/O SEAT | CRACK IN THE AFT SHROUD OF F/O SEAT |  | https://i.ibb.co/q3FhB31S/295166227df7.jpg https://i.ibb.co/TDfXZ1LQ/9162131ab1a5.jpg | Not Raised
127 | FADUL | TEDLAR/SIDEWALL | 5 AC | MISSING SPLINCE |  | https://i.ibb.co/j9RY234h/b7d69dc95e94.jpg | Not Raised
128 | SHAREEF | TEDLAR/SIDEWALL | N/A | SIDEWALL SPLINE AT 1LJ |  | https://i.ibb.co/S4JHx2gV/2d9ab6b8876e.jpg | Not Raised
129 | FADUL | TEDLAR/SIDEWALL | 5 AC | SCRATCHES ON THE SIDEWALL |  | https://i.ibb.co/k2SZGzng/8371a4639a64.jpg | Not Raised
130 | SHAREEF | TEDLAR/SIDEWALL | N/A | SMALL STOWAGE BIN DIRECTLY INFRONT OF 1LJ |  | https://i.ibb.co/5xGghRLG/fa453adcd9f2.jpg | Not Raised
131 | FADUL | GENERAL CABIN | 30CBA | DIRTY CEILING |  | https://i.ibb.co/QF0k1Z1r/0f159391b7f8.jpg | Not Raised
132 | FADUL | GENERAL CABIN | 30CBA | OVRHD DIRTY |  | https://i.ibb.co/Ldw5YQGq/8d7dbcfa18b2.jpg | Not Raised
133 | FADUL | GENERAL CABIN | 30CBA | MISSING DAMPER |  | https://i.ibb.co/pjBnRKrb/383da810c34a.jpg | Not Raised
134 | SHAREEF | TEDLAR/SIDEWALL | N/A | STOWAGE BIN 4LJ |  | https://i.ibb.co/2787tV8G/f3f0bf71606b.jpg https://i.ibb.co/VYC19fFR/aabaa3b3bc06.jpg https://i.ibb.co/1GRD8VcV/5892c7e47f10.jpg | Not Raised
135 | SHAREEF | TEDLAR/SIDEWALL | N/A | STOWAGE BIN THATS DIRECTLY INFRONT OF 5LJ IS SLIGHTLY DIRTY |  | https://i.ibb.co/hJrBrZ0Z/658903e811ab.jpg | Not Raised
136 | SHAREEF | TEDLAR/SIDEWALL | N/A | STOWAGE BIN AT 5LJ |  | https://i.ibb.co/h1tTqR9r/ab7db8e1e1c6.jpg https://i.ibb.co/Q3nsVB9g/a2109a796d79.jpg | Not Raised
137 | SHAREEF | TEDLAR/SIDEWALL | N/A | OXYGEN PANEL AT 4LJ IS SLAGGING/LOWERED |  | https://i.ibb.co/jkHgvHN2/e4a5d430bd6b.jpg | Not Raised
138 | SHAREEF | TEDLAR/SIDEWALL | N/A | R/H SIDEWALL B/C 4LJ SPLINE CRACKED AT BOTTOM |  | https://i.ibb.co/N25bxGVg/6fedffd831a8.jpg | Not Raised
139 | SHAREEF | TEDLAR/SIDEWALL | N/A | R/H B/C PAX WINDOW FRAME DISCOLORED. |  | https://i.ibb.co/bjj98wjR/4f6287c9ed81.jpg https://i.ibb.co/m58Yfstw/20e6cd6772cc.jpg | Not Raised
140 | SHAREEF | TEDLAR/SIDEWALL | N/A | CIELING RUBBER SEAL AT R/H AND DIRECTLY AT THE BACK OF BUSINESS CLASS IS DISCOLORED. |  | https://i.ibb.co/Qq0CfWg/61f4131f873c.jpg | Not Raised
141 | 30001452 | PAX DOORS | R2 DOOR | HINGE COVER ( HAS A WORKORDER ALREADY) DOOR LINING MULTIPLE MARKS DOOR LINING PAINT CHIPPING AND BUBBLING OXYGEN GENERATOR COVER DMG DOOR HANDLE AFT DOOR CUTOUT |  | https://i.ibb.co/ycK9dghH/e6c85d02efd4.jpg https://i.ibb.co/gM8S79dM/1a55b9aa8d06.jpg https://i.ibb.co/5h3Rjt6w/6baad3680f1e.jpg https://i.ibb.co/S4bRmHvk/6513e7d3c61d.jpg https://i.ibb.co/qMkwfVg2/17db69ab86d9.jpg | Not Raised
142 | 30001452 | PAX DOORS | L2 DOOR LINING | DOOR LINING L/H MARKING |  | https://i.ibb.co/VYJ2hmp8/f4745d62c3ae.jpg | Not Raised
143 | 30001452 | PAX DOORS | L2 DOOR | SCRATCHES ON HINGE COVER BUBBLING PAINT ON SLIDE RAFT COVER MULTIPLE MARKINGS ON SLIDE RAFT COVER |  | https://i.ibb.co/vvfg3DMN/53243bc7870c.jpg https://i.ibb.co/ymXGHZRZ/776c1684c8a6.jpg https://i.ibb.co/DgGWsc1B/d08953bb7656.jpg https://i.ibb.co/RkVdPVF2/d858bde3ba35.jpg | Not Raised
144 | SHAREEF | TEDLAR/SIDEWALL | N/A | RUBBER SEAL AT R/H EMERGENCY HATCH HAS SMALL TEARINGS |  | https://i.ibb.co/wFFVY5F2/1dee7c2062c2.jpg https://i.ibb.co/tpwN3D0q/1ff64b8c0f2d.jpg | Not Raised
145 | SHAREEF | TEDLAR/SIDEWALL | N/A | SIDEWALL AT R/H EMERGENCY HATCH SLIGHTLY DIRTY |  | https://i.ibb.co/qYsQtymV/051170f66490.jpg | Not Raised
146 | SHAREEF | TEDLAR/SIDEWALL | N/A | CRACK AT STOWAGE BIN THATS DIRECTLY INFRONT OF THE 31 LKJ |  | https://i.ibb.co/CKLXDv05/31e2a52c6e94.jpg | Not Raised
147 | SHAREEF | TEDLAR/SIDEWALL | N/A | SUSPICION ONLY: |  | https://i.ibb.co/ZRgD9Vt9/1bccac82848f.jpg | Not Raised
148 | SHAREEF | TEDLAR/SIDEWALL | N/A | THE STOWAGE BIN THAT IS INFRONT OF 30LKJ |  | https://i.ibb.co/mVQTQ8RX/3b60c49a30ae.jpg https://i.ibb.co/jksNdvBr/203600e4f78b.jpg https://i.ibb.co/Gf4qgSRV/d45f3263d861.jpg https://i.ibb.co/tpgH00Zq/0a8b748a5872.jpg | Not Raised
149 | 30001452 | PAX DOORS | L1 DOOR LINING | DOOR LINING AFT LINING DMG NEAR SCREW |  |  | Not Raised
150 | 30001452 | PAX DOORS | L1 DOOR S/R COVER | SLIDE RAFT COVER NEED PAINT AND COMP SHOP |  |  | Not Raised
151 | 30001452 | PAX DOORS | L1 DOOR | HINGE COVER MULTIPLE DMG LOCATIONS |  |  | Not Raised
152 | 30001452 | PAX DOORS | R1 DOOR LINING | FWD CUTOUT |  |  | Not Raised
153 | 30001452 | PAX DOORS | R1 DOOR | SLIDE RAFT COVER MULTIPLE DMG HINGE COVER MULTIPLE DMG |  |  | Not Raised