## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Due at | To Go | Expected | Dimension
| 1 | 32797253 | 6Y_N/6Y_N YEARS STRUCTURE | 32797253 / 6Y_N/6Y_N YEARS STRUCTURE (32797253) | Check | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | ME.32797253 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 11 | 200125-06-1 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP (32712938) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.25278 | 02.Aug.2026 04:19 | 1900-01-05 06:14 |  | 0.9375 | Idle | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | REV 2 for T/Q#486124 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP (32712938) |  | 3 / 5 | [] |  |  | MET.32712938 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 15 | 200131-01-1 | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING (32712982) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13889 | 17.Jul.2026 22:00 | 0.24653 | 21.Jul.2026 14:29 | 1900-01-16 20:04 |  | 1899-12-31 11:30 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, CLOSE-UP, CLOSE-UP |  |  |  | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING (32712982) |  | 2 / 4 | [] |  |  | MET.32712982 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 16 | 200133-01-1 | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN (32712984) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34583 | 17.Jul.2026 22:00 | 0.30764 | 21.Jul.2026 16:32 | 1900-01-16 18:01 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 2 / 4 | [] |  |  | MET.32712984 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 18 | 200145-01-1 | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING (32712930) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20417 | 17.Jul.2026 22:00 | 0.175 | 02.Aug.2026 12:00 | 1900-01-04 22:33 |  | 0.58333 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING (32712930) |  | 2 / 4 | [] |  |  | MET.32712930 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 19 | 200151-01-1 | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING (28325905) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 15:30 | 17.Jul.2026 22:00 | 1899-12-31 15:30 | 02.Aug.2026 05:12 | 1900-01-05 05:21 |  | 0.35417 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION, INSPECTION, CLEAN-UP, JOB-SETUP, JOB-CLOSEUP, INSPECTION |  |  |  | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING (28325905) |  | 2 / 6 | [] |  |  | MET.28325905 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 20 | 200151-03-1 | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP (28325775) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.49097 | 17.Jul.2026 22:00 | 0.34722 | 02.Aug.2026 01:31 | 1900-01-05 09:02 |  | 1899-12-31 01:00 | Idle | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP (28325775) |  | 4 / 21 | [] |  |  | MET.28325775 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 25 | 200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP (32712951) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.29792 | 21.Jul.2026 12:07 | 1900-01-16 22:26 |  | 0.45833 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP (32712951) |  | 2 / 3 | [] |  |  | MET.32712951 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 26 | 200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION (32712968) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.089583 | 17.Jul.2026 22:00 | 0.21111 | 21.Jul.2026 12:44 | 1900-01-16 21:49 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION (32712968) |  | 2 / 3 | [] |  |  | MET.32712968 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 32 | 25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT (32712773) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 12:54 | 1900-01-08 21:39 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT (32712773) |  | 1 / 1 | [] |  |  | MET.32712773 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 33 | 25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) |  | 0 / 1 | [] |  |  | MET.32713056 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 34 | 25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R (28325765) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | TC/P |  |  |  | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R (28325765) |  | 0 / 1 | [] |  |  | MET.28325765 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 35 | 253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION (32712949) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.027083 | 19.Jul.2026 04:30 | 1900-01-19 06:03 |  | 1899-12-31 20:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 1 / 5 |  | 3 / 7 | [] |  |  | MET.32712949 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 36 | 254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP (32712983) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.027083 | 19.Jul.2026 17:03 | 1900-01-18 17:30 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 5 |  | 2 / 3 | [] |  |  | MET.32712983 | 21.Apr.2029 | 987 | 2029-04-21 | D
| 42 | 282800-08-1 | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC (25336812) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.025694 | 26.Jul.2026 03:03 | 1900-01-12 07:30 |  | 0.875 | Idle | 0 | T: 2; O: 0; C: 2 | 28-28 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC (25336812) |  | 0 / 3 | [] |  |  | MET.25336812 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 43 | 282800-18-1 | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC (31498211) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.061111 | 17.Jul.2026 22:00 | 0.0375 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 28-28 |  | [] | JOB-SETUP, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC (31498211) |  | 0 / 6 | [] |  |  | MET.31498211 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 44 | 323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP (32712960) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15417 | 17.Jul.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 32-33 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, --, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP (32712960) |  | 0 / 15 | [] |  |  | MET.32712960 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 45 | 323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK (32712937) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.019444 | 17.Jul.2026 22:00 | 0.01875 | 22.Jul.2026 06:06 | 1900-01-16 04:27 |  | 0.083333 | Idle | 0 | T: 8; O: 0; C: 8 | 32-33 |  | [] | JOB-SETUP, JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK (32712937) |  | 1 / 6 | [] |  |  | MET.32712937 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 52 | 531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION (32712605) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.10486 | 25.Jul.2026 08:00 | 1900-01-13 02:33 |  | 0.13194 | Idle | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 6 | [] |  |  | MET.32712605 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 53 | 531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION (32712603) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054167 | 17.Jul.2026 22:00 | 0.12708 | 02.Aug.2026 04:20 | 1900-01-05 06:13 |  | 0.97917 | Idle | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 5 | [] |  |  | MET.32712603 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 54 | 531171-01-1 | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS (32712616) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.025694 | 17.Jul.2026 22:00 | 0.025694 | 24.Jul.2026 12:15 | 1900-01-13 22:18 |  | 0.00069444 | Idle | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | INSPECTION, INSPECTION |  |  |  | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS (32712616) |  | 1 / 2 | [] |  |  | MET.32712616 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 55 | 531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP (32712758) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.17569 | 02.Aug.2026 04:14 | 1900-01-05 06:19 |  | 1899-12-31 13:00 | Idle | 0 | T: 3; O: 0; C: 3 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP (32712758) |  | 3 / 7 | [] |  |  | MET.32712758 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 56 | 531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP (32712608) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.40278 | 17.Jul.2026 22:00 | 0.58125 | 27.Jul.2026 05:09 | 1900-01-11 05:24 |  | 1900-01-04 07:30 | Idle | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 7 |  | 3 / 8 | [] |  |  | MET.32712608 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 57 | 531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP (32712651) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15833 | 17.Jul.2026 22:00 | 1899-12-31 15:28 | 23.Jul.2026 07:00 | 1900-01-15 03:33 |  | 1900-01-01 17:30 | Idle | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Rev 4 As requested T/Q 490977, add insp scop on step 4 (B) Floor panel instalation. | 0 / 1 |  | 2 / 7 | [] |  |  | MET.32712651 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 59 | 533136-01-1 | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP (32712615) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.016667 | 19.Jul.2026 16:37 | 1900-01-18 17:56 |  | 0.5625 | Idle | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP (32712615) |  | 3 / 5 | [] |  |  | MET.32712615 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 61 | 534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.19653 | 28.Jul.2026 05:03 | 1900-01-10 05:30 |  | 1899-12-31 00:01 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) |  | 2 / 5 | [] |  |  | MET.31498197 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 62 | 534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV (32712617) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">23</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-01 02:00 | 17.Jul.2026 22:00 | 1900-01-02 11:00 | 22.Jul.2026 05:00 | 1900-01-16 05:33 |  | 1900-01-08 19:30 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 7 |  | 3 / 7 | [] |  |  | MET.32712617 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 63 | 534148-01-1 | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP (31497923) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.47986 | 25.Jul.2026 19:00 | 1900-01-12 15:33 |  | 0.22222 | Idle | 0 | T: 45; O: 0; C: 45 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 5 / 7 |  | 3 / 5 | [] |  |  | MET.31497923 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 66 | 534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN (25335797) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 13:20 | 1900-01-10 21:13 |  | 0.91667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN (25335797) |  | 2 / 4 | [] |  |  | MET.25335797 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 68 | 535101-01-1 | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP (32712606) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.13056 | 17.Jul.2026 22:00 | 0.20139 | 24.Jul.2026 06:15 | 1900-01-14 04:18 |  | 0.1875 | Idle | 0 | T: 1; O: 0; C: 1 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 7 | [] |  |  | MET.32712606 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 69 | 551020-01-1 | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.068056 | 17.Jul.2026 22:00 | 0.072917 | 24.Jul.2026 06:03 | 1900-01-14 04:30 |  | 0.19444 | Idle | 0 | T: 16; O: 0; C: 16 | 55-16 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) |  | 3 / 5 | [] |  |  | MET.32712717 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 70 | 552002-01-1 | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.068056 | 17.Jul.2026 22:00 | 0.072917 | 24.Jul.2026 07:00 | 1900-01-14 03:33 |  | 0.11111 | Idle | 0 | T: 16; O: 0; C: 16 | 55-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) |  | 3 / 5 | [] |  |  | MET.32712602 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 71 | 553004-01-1 | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP (32712644) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.020833 | 25.Jul.2026 11:04 | 1900-01-12 23:29 |  | 1899-12-31 01:00 | Idle | 0 | T: 2; O: 0; C: 2 | 55-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 2 / 3 | [] |  |  | MET.32712644 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 72 | 553005-01-1 | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.015972 | 23.Jul.2026 12:30 | 1900-01-14 22:03 |  | 0.10417 | Idle | 0 | T: 2; O: 0; C: 2 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) |  | 3 / 5 | [] |  |  | MET.32712648 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 73 | 553006-01-2 | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.011111 | 23.Jul.2026 13:30 | 1900-01-14 21:03 |  | 0.083333 | Idle | 0 | T: 4; O: 0; C: 4 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) |  | 3 / 5 | [] |  |  | MET.32712614 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 75 | 554005-01-1 | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0083333 | 17.Jul.2026 22:00 | 0.015278 | 23.Jul.2026 12:30 | 1900-01-14 22:03 |  | 0.083333 | Idle | 0 | T: 2; O: 0; C: 2 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) |  | 3 / 5 | [] |  |  | MET.32712638 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 76 | 554006-01-1 | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP (32712637) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.011111 | 23.Jul.2026 13:30 | 1900-01-14 21:03 |  | 0.14583 | Idle | 0 | T: 3; O: 0; C: 3 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 5 | [] |  |  | MET.32712637 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 79 | 562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP (32712652) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.13333 | 17.Jul.2026 22:00 | 0.29444 | 26.Jul.2026 04:30 | 1900-01-12 06:03 |  | 1900-01-04 16:30 | Idle | 0 | T: 0; O: 0; C: 0 | 56-21 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 4 / 6 | [] |  |  | MET.32712652 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 80 | 571122-01-1 | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION (32712620) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.088889 | 17.Jul.2026 22:00 | 0.071528 | 27.Jul.2026 04:27 | 1900-01-11 06:06 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 57-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 2 / 5 | [] |  |  | MET.32712620 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 81 | 571157-01-1 | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP (32712981) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.18125 | 03.Aug.2026 13:51 | 1900-01-03 20:42 |  | 0.36389 | Idle | 0 | T: 7; O: 0; C: 7 | 57-10 |  | [] | JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-SETUP |  |  |  | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP (32712981) |  | 3 / 4 | [] |  |  | MET.32712981 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 84 | 572065-01-1-001 | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712639) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 14:35 | 1900-01-13 19:58 |  | 0.034722 | Idle | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 5 | [] |  |  | MET.32712639 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 85 | 572065-01-1-002 | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712642) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 23.Jul.2026 18:52 | 1900-01-14 15:41 |  | 0.03125 | Idle | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712642) |  | 3 / 5 | [] |  |  | MET.32712642 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 88 | 572161-01-11-001 | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP (32450259) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.054861 | 28.Jul.2026 06:11 | 1900-01-10 04:22 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | PNLS 540HB, 540JB, 540KB, 540LB,540MB, 540NB, 540PB, 540QB, 540RB, 550AB, 550CB, 550DB, 560AB OK GIVEN BY INSP 726 REF WO # 32991584 | 1 / 1 |  | 5 / 6 | [] |  |  | MET.32450259 | 29.Apr.2029 | 995 | 2029-04-29 | D
| 89 | 572161-01-11-002 | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP (32450258) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.054861 | 28.Jul.2026 06:13 | 1900-01-10 04:20 |  | 0.47917 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | PNLS 640HB, 640JB, 640KB, 640LB,640MB, 640NB, 640PB, 640QB, 640RB, 650AB, 650CB, 650DB, 660AB OK GIVEN BY INSP 726 REF WO # 32991563 | 1 / 1 |  | 5 / 6 | [] |  |  | MET.32450258 | 29.Apr.2029 | 995 | 2029-04-29 | D
| 99 | 575151-03-1 | 575151-03-1 (0) / TRAILING EDGE | 575151-03-1 (0) / TRAILING EDGE (31481298) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:41 | 1900-01-13 20:52 |  | 0.041667 | Idle | 0 | T: 10; O: 0; C: 10 | 57-51 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 5 | [] |  |  | MET.31481298 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 100 | 575167-01-1-001 | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0076389 | 17.Jul.2026 22:00 | 0.016667 | 24.Jul.2026 15:08 | 1900-01-13 19:25 |  | 0.10417 | Idle | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) |  | 3 / 5 | [] |  |  | MET.32712654 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 101 | 575167-01-1-002 | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0076389 | 17.Jul.2026 22:00 | 0.016667 | 23.Jul.2026 15:41 | 1900-01-14 18:52 |  | 0.23958 | Idle | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) |  | 3 / 5 | [] |  |  | MET.32712881 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 105 | ZL-125-02-1 | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP (32712901) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.032639 | 17.Jul.2026 22:00 | 0.046528 | 25.Jul.2026 08:03 | 1900-01-13 02:30 |  | 0.27083 | Idle | 0 | T: 3; O: 0; C: 3 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 2 / 4 | [] |  |  | MET.32712901 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 108 | ZL-133-01-1 | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP (28325940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13889 | 17.Jul.2026 22:00 | 0.33333 | 24.Jul.2026 14:47 | 1900-01-13 19:46 |  | 0.042361 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP (28325940) |  | 2 / 4 | [] |  |  | MET.28325940 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 109 | ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION (32712626) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.29167 | 17.Jul.2026 22:00 | 0.45833 | 27.Jul.2026 05:02 | 1900-01-11 05:31 |  | 1900-01-03 11:30 | Idle | 0 | T: 16; O: 0; C: 16 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 4 |  | 2 / 6 | [] |  |  | MET.32712626 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 111 | ZL-151-02-3 | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP (28325988) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.83333 | 17.Jul.2026 22:00 | 1899-12-31 11:00 | 27.Jul.2026 04:51 | 1900-01-11 05:42 |  | 0.5 | Idle | 0 | T: 16; O: 0; C: 16 | 28-11 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, CLOSE-UP, CLOSE-UP |  |  |  | 1 / 2 |  | 2 / 5 | [] |  |  | MET.28325988 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 112 | ZL-153-01-1 | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY (28325989) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.28472 | 17.Jul.2026 22:00 | 0.35417 | 20.Jul.2026 17:50 | 1900-01-17 16:43 |  | 1899-12-31 01:50 | Idle | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY (28325989) |  | 3 / 8 | [] |  |  | MET.28325989 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 114 | ZL-163-01-1 | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP (25336492) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12083 | 17.Jul.2026 22:00 | 0.37083 | 24.Jul.2026 14:28 | 1900-01-13 20:05 |  | 0.024306 | Idle | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP (25336492) |  | 2 / 4 | [] |  |  | MET.25336492 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 117 | ZL-193-01-1 | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA (32712631) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.046528 | 25.Jul.2026 04:22 | 1900-01-13 06:11 |  | 0.79167 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA (32712631) |  | 3 / 4 | [] |  |  | MET.32712631 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 158 | 31871161 | A_N (A_N09)/A_N-CHECK | 31871161 / A_N (A_N09)/A_N-CHECK (31871161) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 1 / 1 |  | 0 / 1 | [] |  |  | ME.31871161 | 45735:38 | 217:59 | 2026-08-29 | H
| 159 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32807102) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 17.Jul.2026 22:00 | 0.090278 | 20.Jul.2026 13:00 | 1900-01-17 21:33 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32807102) |  | 0 / 2 | [] |  |  | MET.32807102 | 26.Jul.2026 | -13 | 2026-07-26 | D
| 160 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29295382) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 11-11 |  | [] | PRE INSP |  |  |  | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29295382) |  | 0 / 1 | [] |  |  | MET.29295382 | 45735:38 | 217:59 | 2026-08-28 | H
| 163 | 212600-11-1 | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32807103) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.0090278 | 31.Jul.2026 17:30 | 1900-01-06 17:03 |  | 0.125 | Idle | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32807103) |  | 4 / 4 | [] |  |  | MET.32807103 | 45735:38 | 217:59 | 2026-08-28 | H
| 165 | 242000-25-1 | 242000-25-1 (02) / AC GENERATION | 242000-25-1 (02) / AC GENERATION (32807088) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 242000-25-1 (02) / AC GENERATION (32807088) |  | 0 / 3 | [] |  |  | MET.32807088 | 46138:01 | 620:22 | 2026-10-07 | H
| 168 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 25-10-00-00-SVA (00) / COCKPIT CHECK (31784709) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.18056 | 17.Jul.2026 22:00 | 0.28472 | 21.Jul.2026 04:00 | 1900-01-17 06:33 |  | 1899-12-31 14:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 3 / 11 |  | 6 / 15 | [] |  |  | MET.31784709 | 45735:38 | 217:59 | 2026-08-28 | H
| 169 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32807107) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.24306 | 17.Jul.2026 22:00 | 0.45139 | 20.Jul.2026 08:43 | 1900-01-18 01:50 |  | 1899-12-31 02:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 3 / 14 |  | 7 / 22 | [] |  |  | MET.32807107 | 45735:38 | 217:59 | 2026-08-28 | H
| 170 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32807089) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.26736 | 21.Jul.2026 07:55 | 1900-01-17 02:38 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 1 / 1 |  | 9 / 14 | [] |  |  | MET.32807089 | 45735:38 | 217:59 | 2026-08-28 | H
| 171 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32807065) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.28819 | 21.Jul.2026 07:43 | 1900-01-17 02:50 |  | 0.25 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32807065) |  | 12 / 16 | [] |  |  | MET.32807065 | 45735:38 | 217:59 | 2026-08-29 | H
| 172 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32807097) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0.11458 | 20.Jul.2026 15:52 | 1900-01-17 18:41 |  | 0.85417 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 16 / 22 |  | 6 / 6 | [] |  |  | MET.32807097 | 45735:38 | 217:59 | 2026-08-28 | H
| 173 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32807072) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-26 |  | [] | TC/P |  |  |  | 0 / 1 |  | 0 / 1 | [] |  |  | MET.32807072 | 45735:38 | 217:59 | 2026-08-28 | H
| 174 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R (31784913) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | PRE INSP |  |  |  | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R (31784913) |  | 0 / 1 | [] |  |  | MET.31784913 | 45735:38 | 217:59 | 2026-08-28 | H
| 175 | 25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP (28365434) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE HGR |  |  |  | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP (28365434) |  | 0 / 1 | [] |  |  | MET.28365434 | 48638:01 | 3120:22 | 2027-06-10 | H
| 176 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29295199) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE INSP |  |  |  | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29295199) |  | 0 / 1 | [] |  |  | MET.29295199 | 45735:38 | 217:59 | 2026-08-28 | H
| 177 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 25-32-00-00-SVA (01) / GALLEY CHECK (32807094) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 17.Jul.2026 22:00 | 0.28819 | 19.Jul.2026 04:00 | 1900-01-19 06:33 |  | 1899-12-31 04:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 5 / 29 |  | 0 / 16 | [] |  |  | MET.32807094 | 47590:58 | 2073:19 | 2027-02-28 | H
| 178 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 25-40-00-00-SVA (01) / LAV CHECK (32807064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30903 | 17.Jul.2026 22:00 | 0.30903 | 21.Jul.2026 15:12 | 1900-01-16 19:21 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 4 / 20 |  | 0 / 18 | [] |  |  | MET.32807064 | 47590:58 | 2073:19 | 2027-02-27 | H
| 182 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 253400-01-1. (03) / GALLEY COOLING CLEANING (32807071) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.013889 | 04.Aug.2026 07:27 | 1900-01-03 03:06 |  | 0.875 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.32807071 | 46235:38 | 717:59 | 2026-10-16 | H
| 183 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32807090) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0020833 | 17.Jul.2026 22:00 | 0.018056 | 04.Aug.2026 07:32 | 1900-01-03 03:01 |  | 0.72917 | Idle | 0 | T: 0; O: 0; C: 0 | 25-34 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32807090) |  | 7 / 8 | [] |  |  | MET.32807090 | 45735:38 | 217:59 | 2026-08-28 | H
| 190 | 262200-02-1 | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS (32807104) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS (32807104) |  | 0 / 1 | [] |  |  | MET.32807104 | 46138:01 | 620:22 | 2026-10-07 | H
| 191 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK |  |  |  | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) |  | 0 / 1 | [] |  |  | MET.32807070 | 45935:38 | 417:59 | 2026-09-17 | H
| 193 | 274451-10-1 | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.44444 | 17.Jul.2026 22:00 | 0.26389 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) |  | 0 / 6 | [] |  |  | MET.32807095 | 03.Dec.2027 | 482 | 2027-12-03 | D
| 194 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.58333 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) |  | 0 / 6 | [] |  |  | MET.32807068 | 03.Feb.2027 | 179 | 2027-02-03 | D
| 199 | 281100-05-1 | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32796706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32796706) |  | 0 / 3 | [] |  |  | MET.32796706 | 02.Oct.2026 | 55 | 2026-10-02 | D
| 200 | 281100-06-1 | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32796713) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32796713) |  | 0 / 2 | [] |  |  | MET.32796713 | 02.Oct.2026 | 55 | 2026-10-02 | D
| 201 | 282800-01-1 | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK (29295120) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-28 |  | [] | OPS/LK, OPS/LK |  |  |  | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK (29295120) |  | 0 / 2 | [] |  |  | MET.29295120 | 45735:38 | 217:59 | 2026-08-28 | H
| 202 | 282800-03-1 | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK (29295092) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-32 |  | [] | TC/P, TC/P |  |  |  | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK (29295092) |  | 0 / 2 | [] |  |  | MET.29295092 | 02.Oct.2026 | 55 | 2026-10-02 | D
| 206 | 292251-02-1 | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29-22 |  | [] | TC/P |  |  |  | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) |  | 0 / 1 | [] |  |  | MET.32807096 | 02.Dec.2027 | 481 | 2027-12-02 | D
| 219 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32807111) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-32 |  | [] | CLEAN-UP, CLEAN-UP, CLEAN-UP |  |  |  | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32807111) |  | 0 / 3 | [] |  |  | MET.32807111 | 46235:38 | 717:59 | 2026-10-16 | H
| 221 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | JOB-SETUP, --, --, -- |  |  |  | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) |  | 0 / 4 | [] |  |  | MET.29295087 | 03.Oct.2026 | 56 | 2026-10-03 | D
| 222 | 52-32-00-01-0-SVA | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29295104) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.055556 | 17.Jul.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | CLEAN-UP, TC/P, TC/P, --, JOB-CLOSEUP |  |  |  | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29295104) |  | 0 / 5 | [] |  |  | MET.29295104 | 03.Oct.2026 | 56 | 2026-10-03 | D
| 224 | 527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013889 | 17.Jul.2026 22:00 | 0.018056 | 29.Jul.2026 03:28 | 1900-01-09 07:05 |  | 0.083333 | Idle | 0 | T: 5; O: 0; C: 5 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) |  | 1 / 5 | [] |  |  | MET.32807101 | 10.Apr.2027 | 245 | 2027-04-10 | D
| 225 | 533154-06-1-A | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP (28362142) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.72917 | 17.Jul.2026 22:00 | 0.52083 | 19.Jul.2026 18:38 | 1900-01-18 15:55 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, JOB-SETUP, --, --, --, --, INSPECTION, --, INSPECTION, --, --, -- |  |  |  | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP (28362142) |  | 0 / 12 | [] |  |  | MET.28362142 | 18'542 | 2'228 | 2028-06-12 | C
| 226 | 31675402 | EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE | 31675402 / EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE (31675402) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 06:20 | 17.Jul.2026 22:00 | 0.875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | update priority | 31675402 / EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE (31675402) |  | 0 / 21 | [] |  |  | ME.31675402 | 17'792 | 1'478 | 2027-10-29 | C
| 228 | 72-00-00-01-0-SVA-001 | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29295098) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 17.Jul.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29295098) |  | 0 / 11 | [] |  |  | MET.29295098 | 46235:38 | 717:59 | 2026-10-16 | H
| 229 | 72-00-00-01-0-SVA-002 | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29295097) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 17.Jul.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29295097) |  | 0 / 11 | [] |  |  | MET.29295097 | 46235:38 | 717:59 | 2026-10-16 | H
| 230 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29295107) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29295107) |  | 0 / 3 | [] |  |  | MET.29295107 | 45935:38 | 417:59 | 2026-09-17 | H
| 231 | 801110-C3-1-002 | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29295116) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29295116) |  | 0 / 3 | [] |  |  | MET.29295116 | 45935:38 | 417:59 | 2026-09-17 | H
| 233 | 31574335 | C_N (C_N02)/C-CHECK | 31574335 / C_N (C_N02)/C-CHECK (31574335) | Check | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31574335 / C_N (C_N02)/C-CHECK (31574335) |  | 0 / 1 | [] |  |  | ME.31574335 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 234 | 05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION (32874713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | ACFT RELEASE, ACFT RELEASE |  |  |  | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION (32874713) |  | 0 / 2 | [] |  |  | MET.32874713 |  |  | 1517606
| 235 | 08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32712647) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-01 17:00 | 17.Jul.2026 22:00 | 0.83333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 08-10 |  | [] | WT&BAL |  |  |  | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32712647) |  | 0 / 1 | [] |  |  | MET.32712647 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 245 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) |  | 0 / 1 | [] |  |  | MET.32712899 | 49636:58 | 4119:19 | 2027-09-16 | H
| 246 | 213100-02-1 | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32712679) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32712679) |  | 0 / 1 | [] |  |  | MET.32712679 | 49636:58 | 4119:19 | 2027-09-16 | H
| 248 | 213100-04-1 | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712795) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712795) |  | 0 / 3 | [] |  |  | MET.32712795 | 55763:39 | 10246:00 | 2029-05-12 | H
| 252 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32712721) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.12222 | 29.Jul.2026 05:20 | 1900-01-09 05:13 |  | 0.85417 | Idle | 0 | T: 2; O: 0; C: 2 | 21-52 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 5 | [] |  |  | MET.32712721 | 49636:58 | 4119:19 | 2027-09-16 | H
| 253 | 215500-01-1 | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) |  | 0 / 3 | [] |  |  | MET.32712847 | 55763:39 | 10246:00 | 2029-05-12 | H
| 254 | 215500-02-1 | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-55 |  | [] | OPS/LK |  |  |  | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) |  | 0 / 1 | [] |  |  | MET.32712902 | 55763:39 | 10246:00 | 2029-05-12 | H
| 255 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.10972 | 31.Jul.2026 17:21 | 1900-01-06 17:12 |  | 0.45833 | Idle | 0 | T: 1; O: 0; C: 1 | 21-63 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK |  |  |  | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) |  | 4 / 5 | [] |  |  | MET.32712714 | 49636:58 | 4119:19 | 2027-09-16 | H
| 272 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] |  |  |  |  | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) |  | 0 / 2 | [] |  |  | MET.28325858 | 15.Sep.2026 | 38 | 2026-09-15 | D
| 273 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32712693) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | INSPECTION, -- |  |  |  | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32712693) |  | 0 / 2 | [] |  |  | MET.32712693 | 15.Sep.2026 | 38 | 2026-09-15 | D
| 274 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32712869) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P, TC/P |  |  |  | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32712869) |  | 0 / 2 | [] |  |  | MET.32712869 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 275 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (32712866) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | PRE INSP, -- |  |  |  | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (32712866) |  | 0 / 2 | [] |  |  | MET.32712866 | 15.Sep.2026 | 38 | 2026-09-15 | D
| 276 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R (28325788) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-01 | 17.Jul.2026 22:00 | 0.66667 | 06.Aug.2026 03:00 | 1900-01-01 07:33 |  | 1900-01-01 17:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 0 / 1 |  | 0 / 4 | [] |  |  | MET.28325788 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 277 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P |  |  |  | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) |  | 0 / 1 | [] |  |  | MET.28325803 | 15.Sep.2026 | 38 | 2026-09-15 | D
| 278 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 25-SVA-01 (01) / COCKPIT CHECK (32712906) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13889 | 17.Jul.2026 22:00 | 0.14583 | 20.Jul.2026 08:47 | 1900-01-18 01:46 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 1 / 1 |  | 1 / 17 | [] |  |  | MET.32712906 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 279 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32712740) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.48611 | 17.Jul.2026 22:00 | 0.69444 | 20.Jul.2026 08:21 | 1900-01-18 02:12 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 0 / 3 |  | 2 / 21 | [] |  |  | MET.32712740 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 280 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 25-SVA-03 (01) / B/C SEAT REFRESH (32450376) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.21528 | 17.Jul.2026 22:00 | 0.49306 | 21.Jul.2026 15:17 | 1900-01-16 19:16 |  | 0.29167 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 16 / 24 |  | 8 / 19 | [] |  |  | MET.32450376 | 26.Sep.2029 | 1145 | 2029-09-26 | D
| 281 | 25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH (32712697) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.79167 | 22.Jul.2026 15:25 | 1900-01-15 19:08 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH (32712697) |  | 9 / 15 | [] |  |  | MET.32712697 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 282 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 25-SVA-05 (01) / G/C SEAT REFRESH (32712765) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.75 | 21.Jul.2026 01:18 | 1900-01-17 09:15 |  | 0.60417 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 759627 adding step 14 | 10 / 13 |  | 10 / 14 | [] |  |  | MET.32712765 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 283 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 25-SVA-06 (01) / GALLEY REFRESH (32712754) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 12:22 | 1900-01-16 22:11 |  | 0.47917 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-06 (01) / GALLEY REFRESH (32712754) |  | 0 / 1 | [] |  |  | MET.32712754 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 284 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 25-SVA-07 (01) / LAV REFRESH (32712896) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 15:14 | 1900-01-16 19:19 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-07 (01) / LAV REFRESH (32712896) |  | 0 / 1 | [] |  |  | MET.32712896 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 285 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32712882) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32712882) |  | 0 / 1 | [] |  |  | MET.32712882 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 286 | 25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R (32712790) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R (32712790) |  | 0 / 1 | [] |  |  | MET.32712790 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 287 | 25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R (32712824) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 27.Jul.2026 02:26 | 1900-01-11 08:07 |  | 1900-01-05 13:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 692819 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R (32712824) |  | 0 / 1 | [] |  |  | MET.32712824 | 05.Feb.2028 | 546 | 2028-02-05 | D
| 288 | 252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R (23645845) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:00 | 17.Jul.2026 22:00 | 0.26389 | 20.Jul.2026 03:58 | 1900-01-18 06:35 |  | 1900-01-09 14:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  |  | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R (23645845) |  | 0 / 2 | [] |  |  | MET.23645845 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 289 | 252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP (32712784) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.19444 | 21.Jul.2026 11:37 | 1900-01-16 22:56 |  | 0.8125 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 6 / 11 |  | 2 / 3 | [] |  |  | MET.32712784 | 55763:39 | 10246:00 | 2029-05-12 | H
| 290 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32712650) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:07 | 1900-01-17 04:26 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  |  | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32712650) |  | 1 / 2 | [] |  |  | MET.32712650 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 291 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32712834) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 21.Jul.2026 05:08 | 1900-01-17 05:25 |  | 0.25 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32712834) |  | 2 / 4 | [] |  |  | MET.32712834 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 292 | 252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP (32712841) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.024306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | --, PRE INSP, -- |  |  |  | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP (32712841) |  | 0 / 3 | [] |  |  | MET.32712841 | 55763:39 | 10246:00 | 2029-05-12 | H
| 296 | 255000-10-1 | 255000-10-1 (3) / LOWER DECK CARGO LOADING | 255000-10-1 (3) / LOWER DECK CARGO LOADING (31497911) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.075 | 17.Jul.2026 22:00 | 0.17917 | 26.Jul.2026 15:45 | 1900-01-11 18:48 |  | 0.65972 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 255000-10-1 (3) / LOWER DECK CARGO LOADING (31497911) |  | 5 / 7 | [] |  |  | MET.31497911 | 55763:39 | 10246:00 | 2029-05-12 | H
| 298 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.010417 | 17.Jul.2026 22:00 | 0.048611 | 23.Jul.2026 20:53 | 1900-01-14 13:40 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) |  | 3 / 4 | [] |  |  | MET.31498136 | 12.Sep.2026 | 35 | 2026-09-12 | D
| 299 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28325883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.125 | 19.Jul.2026 04:30 | 1900-01-19 06:03 |  | 1899-12-31 22:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 4 | [] |  |  | MET.28325883 | 11.Sep.2026 | 34 | 2026-09-11 | D
| 300 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0055556 | 29.Jul.2026 03:33 | 1900-01-09 07:00 |  | 0.35417 | Idle | 0 | T: 1; O: 0; C: 1 | 26-15 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP |  |  |  | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) |  | 3 / 5 | [] |  |  | MET.32712819 | 49763:39 | 4246:00 | 2027-09-29 | H
| 305 | 262100-05-1 | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC (32712745) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 1 / 1 |  | 0 / 1 | [] |  |  | MET.32712745 | 55763:39 | 10246:00 | 2029-05-12 | H
| 311 | 262300-03-1 | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) |  | 0 / 4 | [] |  |  | MET.32712670 | 55763:39 | 10246:00 | 2029-05-12 | H
| 316 | 271400-03-1-001 | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK (32712849) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 04:49 | 1900-01-16 05:44 |  | 0.52083 | Idle | 0 | T: 1; O: 0; C: 1 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK (32712849) |  | 1 / 3 | [] |  |  | MET.32712849 | 47612:08 | 2094:29 | 2027-03-01 | H
| 317 | 271400-03-1-002 | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK (32712770) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 04:37 | 1900-01-16 05:56 |  | 0.66667 | Idle | 0 | T: 1; O: 0; C: 1 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK (32712770) |  | 1 / 3 | [] |  |  | MET.32712770 | 47612:08 | 2094:29 | 2027-03-01 | H
| 318 | 272100-02-1 | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP (25336083) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-01 21:00 | 17.Jul.2026 22:00 | 1900-01-01 03:15 | 03.Aug.2026 04:25 | 1900-01-04 06:08 |  | 0.9375 | Idle | 0 | T: 3; O: 0; C: 3 | 27-21 |  | [] | TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION |  |  |  | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP (25336083) |  | 1 / 9 | [] |  |  | MET.25336083 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 319 | 272100-04-1 | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25335749) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0076389 | 17.Jul.2026 22:00 | 0.014583 | 27.Jul.2026 04:04 | 1900-01-11 06:29 |  | 0.875 | Idle | 0 | T: 1; O: 0; C: 1 | 27-26 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25335749) |  | 3 / 4 | [] |  |  | MET.25335749 | 48000:00 | 2482:21 | 2027-04-08 | H
| 320 | 272100-05-1 | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 18.Jul.2026 12:58 | 1900-01-19 21:35 |  | 0.66667 | Idle | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) |  | 0 / 3 | [] |  |  | MET.31497921 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 322 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | JOB-SETUP, --, -- |  |  |  | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) |  | 0 / 3 | [] |  |  | MET.26290694 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 323 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 27-21 |  | [] | TC/P |  |  |  | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) |  | 0 / 1 | [] |  |  | MET.26224974 | 14.Jan.2027 | 159 | 2027-01-14 | D
| 326 | 273400-03-1 | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.043056 | 17.Jul.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 27-34 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) |  | 0 / 3 | [] |  |  | MET.32712863 | 55763:39 | 10246:00 | 2029-05-12 | H
| 328 | 274000-24-1 | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P |  |  |  | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) |  | 0 / 1 | [] |  |  | MET.32712885 | 61636:58 | 16119:19 | 2030-12-12 | H
| 329 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 27-41 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) |  | 0 / 3 | [] |  |  | MET.32712802 | 11.Jan.2027 | 156 | 2027-01-11 | D
| 330 | 274400-03-1 | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC (32712678) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC (32712678) |  | 0 / 2 | [] |  |  | MET.32712678 | 55763:39 | 10246:00 | 2029-05-12 | H
| 331 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.00625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | INSPECTION, INSPECTION |  |  |  | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) |  | 0 / 2 | [] |  |  | MET.32712739 | 49636:58 | 4119:19 | 2027-09-16 | H
| 332 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | P/N: Changed from "MIL-PRF-680.TYPEI" TO "PD680" as requestd in T/Q:584726 T/Q: 581544 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) |  | 0 / 3 | [] |  |  | MET.32712751 | 11.Jan.2027 | 156 | 2027-01-11 | D
| 334 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) |  | 0 / 2 | [] |  |  | MET.32712759 | 49636:58 | 4119:19 | 2027-09-16 | H
| 335 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P, TC/P |  |  |  | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) |  | 0 / 2 | [] |  |  | MET.32712728 | 49763:39 | 4246:00 | 2027-09-29 | H
| 346 | 275446-02-1-001 | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029167 | 17.Jul.2026 22:00 | 0.048611 | 24.Jul.2026 14:40 | 1900-01-13 19:53 |  | 0.25694 | Idle | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537) dated 20-DEC-2023 as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change the access from 733 and 744 to be 734 and 744. | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) |  | 3 / 5 | [] |  |  | MET.25337004 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 347 | 275446-02-1-002 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029167 | 17.Jul.2026 22:00 | 0.048611 | 23.Jul.2026 15:39 | 1900-01-14 18:54 |  | 0.44792 | Idle | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537 dated 20-DEC-2023)as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track 1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change Panle from 733 and 734 to be 734 and 744 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) |  | 3 / 5 | [] |  |  | MET.25336868 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 348 | 275449-06-1-001 | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS (32712643) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.73333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-13 |  | [] | TC/P |  |  |  | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS (32712643) |  | 0 / 1 | [] |  |  | MET.32712643 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 349 | 275449-06-1-002 | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES (32712640) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.73333 | 17.Jul.2026 22:00 | 0.73333 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 12-13 |  | [] | TC/P |  |  |  | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES (32712640) |  | 0 / 1 | [] |  |  | MET.32712640 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 350 | 275451-01-1 | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32712844) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32712844) |  | 0 / 4 | [] |  |  | MET.32712844 | 12.Sep.2026 | 35 | 2026-09-12 | D
| 353 | 278100-03-1 | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32712852) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-81 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32712852) |  | 0 / 3 | [] |  |  | MET.32712852 | 10.Sep.2027 | 398 | 2027-09-10 | D
| 356 | 278400-01-1-001 | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION (32712701) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 15:15 | 1900-01-13 19:18 |  | 0.063194 | Idle | 0 | T: 13; O: 0; C: 13 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION (32712701) |  | 3 / 4 | [] |  |  | MET.32712701 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 357 | 278400-01-1-002 | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION (32712738) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 14:02 | 1900-01-13 20:31 |  | 0.055556 | Idle | 0 | T: 13; O: 0; C: 13 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION (32712738) |  | 3 / 4 | [] |  |  | MET.32712738 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 358 | 278451-01-1 | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32712785) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32712785) |  | 0 / 4 | [] |  |  | MET.32712785 | 12.Sep.2026 | 35 | 2026-09-12 | D
| 359 | 278468-02-1-001 | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION (32712708) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.12431 | 24.Jul.2026 15:06 | 1900-01-13 19:27 |  | 0.10417 | Idle | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 5 | [] |  |  | MET.32712708 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 360 | 278468-02-1-002 | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION (32712820) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.12431 | 24.Jul.2026 14:07 | 1900-01-13 20:26 |  | 0.14931 | Idle | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 5 | [] |  |  | MET.32712820 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 363 | 281600-01-1-001 | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK (26224970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.011806 | 18.Jul.2026 15:52 | 1900-01-19 18:41 |  | 0.66667 | Idle | 0 | T: 2; O: 0; C: 2 | 28-16 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK (26224970) |  | 3 / 5 | [] |  |  | MET.26224970 | 49636:58 | 4119:19 | 2027-09-16 | H
| 364 | 281600-01-1-002 | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK (26290613) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.010417 | 18.Jul.2026 15:54 | 1900-01-19 18:39 |  | 0.66667 | Idle | 0 | T: 2; O: 0; C: 2 | 28-16 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK (26290613) |  | 3 / 5 | [] |  |  | MET.26290613 | 49636:58 | 4119:19 | 2027-09-16 | H
| 365 | 281800-01-1 | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK (32712845) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 17.Jul.2026 22:00 | 0.15208 |  | 0 |  | 0 | Not Started | 0 | T: 4; O: 0; C: 4 | 28-18 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK (32712845) |  | 0 / 3 | [] |  |  | MET.32712845 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 366 | 282100-02-1 | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC (25335835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC (25335835) |  | 0 / 4 | [] |  |  | MET.25335835 | 55763:39 | 10246:00 | 2029-05-12 | H
| 372 | 282800-04-1 | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC (31497920) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-28 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC (31497920) |  | 0 / 3 | [] |  |  | MET.31497920 | 54263:39 | 8746:00 | 2028-12-15 | H
| 375 | 282800-07-1 | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC (25335729) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022222 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC (25335729) |  | 0 / 7 | [] |  |  | MET.25335729 | 54263:39 | 8746:00 | 2028-12-15 | H
| 376 | 291000-04-1 | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) |  | 0 / 1 | [] |  |  | MET.32712782 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 379 | 291000-10-1 | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK (25336587) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.01875 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29-10 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK (25336587) |  | 0 / 4 | [] |  |  | MET.25336587 | 55763:39 | 10246:00 | 2029-05-12 | H
| 381 | 291000-20-1 | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32712729) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32712729) |  | 0 / 1 | [] |  |  | MET.32712729 | 09.Sep.2026 | 32 | 2026-09-09 | D
| 382 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | OPS/LK |  |  |  | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) |  | 0 / 1 | [] |  |  | MET.32712886 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 383 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32712891) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 29 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32712891) |  | 0 / 3 | [] |  |  | MET.32712891 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 384 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) |  | 0 / 3 | [] |  |  | MET.32712656 | 49636:58 | 4119:19 | 2027-09-16 | H
| 385 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 29-34 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) |  | 0 / 3 | [] |  |  | MET.32712680 | 49636:58 | 4119:19 | 2027-09-16 | H
| 398 | 321127-01-1-001 | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">14</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.27847 | 17.Jul.2026 22:00 | 0.74306 | 04.Aug.2026 08:32 | 1900-01-03 02:01 |  | 1900-01-02 11:30 | Idle | 0 | T: 0; O: 0; C: 0 | 32-11 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) |  | 6 / 7 | [] |  |  | MET.32712696 | 26'913 | 10'599 | 2035-05-23 | C
| 402 | 323100-04-1 | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK (32712828) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 17.Jul.2026 22:00 | 0.032639 | 04.Aug.2026 11:06 | 1900-01-02 23:27 |  | 0.042361 | Idle | 0 | T: 2; O: 0; C: 2 | 32-31 |  | [] | OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-SETUP, TC/P |  |  |  | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK (32712828) |  | 0 / 5 | [] |  |  | MET.32712828 | 55763:39 | 10246:00 | 2029-05-12 | H
| 404 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-61 |  | [] | OPS/LK |  |  |  | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) |  | 0 / 1 | [] |  |  | MET.32712685 | 49636:58 | 4119:19 | 2027-09-16 | H
| 405 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) |  | 0 / 1 | [] |  |  | MET.32712772 | 21'900 | 5'586 | 2031-03-26 | C
| 406 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) |  | 0 / 1 | [] |  |  | MET.32712667 | 21'900 | 5'586 | 2031-03-26 | C
| 407 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.32292 | 23.Jul.2026 09:59 | 1900-01-15 00:34 |  | 0.70833 | Idle | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | JOB-SETUP, TC/P, TC/P, CLOSE-UP |  |  |  | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) |  | 2 / 4 | [] |  |  | MET.28325784 | 10.Sep.2026 | 33 | 2026-09-10 | D
| 408 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42153 | 17.Jul.2026 22:00 | 0.21042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | OPS/LK |  |  |  | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) |  | 0 / 1 | [] |  |  | MET.32712689 | 26.Sep.2027 | 414 | 2027-09-26 | D
| 409 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 17.Jul.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-41 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) |  | 0 / 3 | [] |  |  | MET.32712726 | 49636:58 | 4119:19 | 2027-09-16 | H
| 410 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-43 |  | [] | OPS/LK |  |  |  | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) |  | 0 / 1 | [] |  |  | MET.32712788 | 49636:58 | 4119:19 | 2027-09-16 | H
| 425 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | OPS/LK |  |  |  | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) |  | 0 / 1 | [] |  |  | MET.32712798 | 10.Sep.2026 | 33 | 2026-09-10 | D
| 427 | 352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC (32712919) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.082639 | 17.Jul.2026 22:00 | 0.063194 | 20.Jul.2026 07:22 | 1900-01-18 03:11 |  | 1899-12-31 21:00 | Idle | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] | JOB-SETUP, TC/P, TC/P, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 2 / 6 | [] |  |  | MET.32712919 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 428 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28325739) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.10417 | 20.Jul.2026 04:00 | 1900-01-18 06:33 |  | 1900-01-01 00:30 | Idle | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, --, --, JOB-CLOSEUP, -- |  |  | As requested in T/Q: 737585 by ENGG CONFIGRATION. | 0 / 1 |  | 3 / 5 | [] |  |  | MET.28325739 | 09.Sep.2026 | 32 | 2026-09-09 | D
| 433 | 361100-SVA-01 | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT (28326047) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.11806 | 17.Jul.2026 22:00 | 0.22917 | 31.Jul.2026 11:32 | 1900-01-06 23:01 |  | 1899-12-31 20:00 | Idle | 0 | T: 0; O: 0; C: 0 | 36 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 8 / 10 | [] |  |  | MET.28326047 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 434 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) |  | 0 / 3 | [] |  |  | MET.32712764 | 53763:39 | 8246:00 | 2028-10-27 | H
| 435 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) |  | 0 / 3 | [] |  |  | MET.32712827 | 53763:39 | 8246:00 | 2028-10-27 | H
| 438 | 361251-01-3 | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP (32712720) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.025 | 23.Jul.2026 18:18 | 1900-01-14 16:15 |  | 0.11458 | Idle | 0 | T: 2; O: 0; C: 2 | 36-12 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 7 | [] |  |  | MET.32712720 | 50636:58 | 5119:19 | 2027-12-24 | H
| 439 | 383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32712887) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-31 |  | [] | CLEAN-UP |  |  |  | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32712887) |  | 0 / 1 | [] |  |  | MET.32712887 | 49636:58 | 4119:19 | 2027-09-16 | H
| 440 | 384142-01-1 | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT (32712673) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0125 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 38-41 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT (32712673) |  | 0 / 6 | [] |  |  | MET.32712673 | 26.Sep.2029 | 1145 | 2029-09-26 | D
| 442 | 384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | TC/P, OPS/LK |  |  |  | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) |  | 0 / 2 | [] |  |  | MET.25336873 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 446 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.13889 | 28.Jul.2026 10:30 | 1900-01-10 00:03 |  | 1900-01-01 06:00 | Idle | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) |  | 4 / 4 | [] |  |  | MET.28325813 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 447 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32712712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.01875 | 17.Jul.2026 22:00 | 0.023611 | 28.Jul.2026 08:00 | 1900-01-10 02:33 |  | 1899-12-31 02:00 | Idle | 0 | T: 6; O: 0; C: 6 | 52-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32712712) |  | 3 / 9 | [] |  |  | MET.32712712 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 448 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.13889 | 28.Jul.2026 10:00 | 1900-01-10 00:33 |  | 1900-01-01 10:30 | Idle | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) |  | 4 / 4 | [] |  |  | MET.28326032 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 449 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.13889 | 03.Aug.2026 05:09 | 1900-01-04 05:24 |  | 1900-01-01 20:16 | Idle | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) |  | 4 / 4 | [] |  |  | MET.28325885 | 13.Sep.2026 | 36 | 2026-09-13 | D
| 450 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32712889) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.040278 | 29.Jul.2026 09:29 | 1900-01-09 01:04 |  | 0.39583 | Idle | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32712889) |  | 5 / 9 | [] |  |  | MET.32712889 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 451 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32712672) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.042361 | 29.Jul.2026 17:00 | 1900-01-08 17:33 |  | 0.22917 | Idle | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32712672) |  | 5 / 9 | [] |  |  | MET.32712672 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 452 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32712893) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.042361 | 29.Jul.2026 09:30 | 1900-01-09 01:03 |  | 0.27083 | Idle | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32712893) |  | 5 / 9 | [] |  |  | MET.32712893 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 453 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.042361 | 29.Jul.2026 09:30 | 1900-01-09 01:03 |  | 0.22917 | Idle | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) |  | 5 / 9 | [] |  |  | MET.32712658 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 454 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.13889 | 03.Aug.2026 04:58 | 1900-01-04 05:35 |  | 0.63542 | Idle | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) |  | 2 / 4 | [] |  |  | MET.28325786 | 12.Sep.2026 | 35 | 2026-09-12 | D
| 457 | 521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK (32712833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.025 | 26.Jul.2026 08:13 | 1900-01-12 02:20 |  | 0.3125 | Idle | 0 | T: 2; O: 0; C: 2 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 2 / 2 |  | 3 / 6 | [] |  |  | MET.32712833 | 55763:39 | 10246:00 | 2029-05-12 | H
| 458 | 521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.024306 | 26.Jul.2026 08:16 | 1900-01-12 02:17 |  | 0.47917 | Idle | 0 | T: 2; O: 0; C: 2 | 52-10 |  | [] | OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, OPS/LK, OPS/LK |  |  |  | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) |  | 3 / 6 | [] |  |  | MET.32712735 | 55763:39 | 10246:00 | 2029-05-12 | H
| 462 | 521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP (32712682) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.019444 | 17.Jul.2026 22:00 | 0.061806 | 30.Jul.2026 07:51 | 1900-01-08 02:42 |  | 1899-12-31 04:00 | Idle | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP (32712682) |  | 6 / 10 | [] |  |  | MET.32712682 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 466 | 522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE (26224270) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.073611 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE (26224270) |  | 0 / 3 | [] |  |  | MET.26224270 | 49636:58 | 4119:19 | 2027-09-16 | H
| 467 | 522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC (23580025) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.094444 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC (23580025) |  | 0 / 5 | [] |  |  | MET.23580025 | 61636:58 | 16119:19 | 2030-12-12 | H
| 468 | 522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION (23625074) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 17.Jul.2026 22:00 | 0.084028 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION (23625074) |  | 0 / 4 | [] |  |  | MET.23625074 | 61636:58 | 16119:19 | 2030-12-12 | H
| 469 | 522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14653 | 17.Jul.2026 22:00 | 0.10486 |  | 0 |  | 0 | Not Started | 0 | T: 6; O: 0; C: 6 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) |  | 0 / 4 | [] |  |  | MET.25335941 | 55763:39 | 10246:00 | 2029-05-12 | H
| 470 | 523100-01-1 | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC (32712663) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 52-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC (32712663) |  | 0 / 4 | [] |  |  | MET.32712663 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 471 | 523200-01-1 | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC (32712884) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0125 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 52-32 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC (32712884) |  | 0 / 4 | [] |  |  | MET.32712884 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 484 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013889 | 17.Jul.2026 22:00 | 0.097222 | 06.Aug.2026 09:38 | 1900-01-01 00:55 |  | 0.083333 | Idle | 0 | T: 3; O: 0; C: 3 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) |  | 2 / 3 | [] |  |  | MET.32712664 | 13.Sep.2026 | 36 | 2026-09-13 | D
| 485 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-19 |  | [] | OPS/LK |  |  |  | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) |  | 0 / 1 | [] |  |  | MET.32712830 | 10.Sep.2026 | 33 | 2026-09-10 | D
| 490 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-39 |  | [] | OPS/LK |  |  |  | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) |  | 0 / 1 | [] |  |  | MET.32712818 | 09.Sep.2026 | 32 | 2026-09-09 | D
| 492 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.097917 | 24.Jul.2026 06:52 | 1900-01-14 03:41 |  | 0.12569 | Idle | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) |  | 3 / 5 | [] |  |  | MET.32787526 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 495 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) |  | 0 / 1 | [] |  |  | MET.32712812 | 09.Sep.2026 | 32 | 2026-09-09 | D
| 496 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) |  | 0 / 1 | [] |  |  | MET.32712669 | 10.Sep.2026 | 33 | 2026-09-10 | D
| 501 | 545000-05-1-001 | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.066667 | 17.Jul.2026 22:00 | 0.70833 | 21.Jul.2026 15:20 | 1900-01-16 19:13 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621791) |  | 3 / 4 | [] |  |  | MET.23621791 | 49636:58 | 4119:19 | 2027-09-16 | H
| 502 | 545000-05-1-002 | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642860) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.066667 | 17.Jul.2026 22:00 | 0.70833 | 21.Jul.2026 14:44 | 1900-01-16 19:49 |  | 0.22222 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642860) |  | 3 / 4 | [] |  |  | MET.23642860 | 49636:58 | 4119:19 | 2027-09-16 | H
| 507 | 552600-01-1 | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. (32712775) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.048611 | 17.Jul.2026 22:00 | 0.11458 | 26.Jul.2026 02:00 | 1900-01-12 08:33 |  | 1900-01-02 12:00 | Idle | 0 | T: 8; O: 0; C: 8 | 20-00 |  | [] |  |  |  |  | 1 / 1 |  | 5 / 6 | [] |  |  | MET.32712775 | 61636:58 | 16119:19 | 2030-12-12 | H
| 508 | 553600-01-1 | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION (32712710) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.24306 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 11; O: 0; C: 11 | 55-47 |  | [] | TC/P |  |  |  | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION (32712710) |  | 0 / 1 | [] |  |  | MET.32712710 | 61636:58 | 16119:19 | 2030-12-12 | H
| 509 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.018056 | 06.Aug.2026 03:06 | 1900-01-01 07:27 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) |  | 1 / 1 | [] |  |  | MET.32712810 | 12.Sep.2026 | 35 | 2026-09-12 | D
| 510 | 572178-01-1-001 | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32712613) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 15:01 | 1900-01-13 19:32 |  | 0.0625 | Idle | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32712613) |  | 3 / 5 | [] |  |  | MET.32712613 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 511 | 572178-01-1-002 | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32712634) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 13:53 | 1900-01-13 20:40 |  | 0.052083 | Idle | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32712634) |  | 3 / 5 | [] |  |  | MET.32712634 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 512 | 572179-01-1-001 | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712635) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 15:10 | 1900-01-13 19:23 |  | 0.125 | Idle | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712635) |  | 3 / 5 | [] |  |  | MET.32712635 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 513 | 572179-01-1-002 | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712598) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 22.Jul.2026 16:54 | 1900-01-15 17:39 |  | 0.0625 | Idle | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32712598) |  | 3 / 5 | [] |  |  | MET.32712598 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 525 | 711300-C1-1-001 | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356889) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 17.Jul.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356889) |  | 0 / 2 | [] |  |  | MET.28356889 | 09.Sep.2028 | 763 | 2028-09-09 | D
| 526 | 711300-C1-1-002 | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384391) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 17.Jul.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384391) |  | 0 / 2 | [] |  |  | MET.28384391 | 09.Sep.2028 | 763 | 2028-09-09 | D
| 537 | 712213-01-1-001 | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP (26290621) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.090278 | 28.Jul.2026 06:52 | 1900-01-10 03:41 |  | 1900-01-02 02:30 | Idle | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 7 / 8 | [] |  |  | MET.26290621 | 52636:58 | 7119:19 | 2028-07-08 | H
| 538 | 712213-01-1-002 | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP (26290681) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.090278 | 27.Jul.2026 15:57 | 1900-01-10 18:36 |  | 1900-01-01 05:30 | Idle | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 7 / 8 | [] |  |  | MET.26290681 | 52636:58 | 7119:19 | 2028-07-08 | H
| 541 | 72-00-00-27-0-SVA-001 | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28325809) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28325809) |  | 0 / 1 | [] |  |  | MET.28325809 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 542 | 72-00-00-27-0-SVA-002 | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28325798) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28325798) |  | 0 / 1 | [] |  |  | MET.28325798 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 543 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.034028 | 26.Jul.2026 16:00 | 1900-01-11 18:33 |  | 0.25694 | Idle | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) |  | 2 / 3 | [] |  |  | MET.19873954 | 49636:58 | 4119:19 | 2027-09-16 | H
| 544 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0069444 | 17.Jul.2026 22:00 | 0.034028 | 26.Jul.2026 13:39 | 1900-01-11 20:54 |  | 0.50694 | Idle | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) |  | 2 / 3 | [] |  |  | MET.19875040 | 49636:58 | 4119:19 | 2027-09-16 | H
| 549 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.059028 | 26.Jul.2026 16:02 | 1900-01-11 18:31 |  | 0.25694 | Idle | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) |  | 2 / 3 | [] |  |  | MET.28325884 | 49636:58 | 4119:19 | 2027-09-16 | H
| 550 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.059028 | 26.Jul.2026 16:03 | 1900-01-11 18:30 |  | 0.54861 | Idle | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) |  | 2 / 3 | [] |  |  | MET.28326044 | 49636:58 | 4119:19 | 2027-09-16 | H
| 551 | 783200-01-1-001 | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP (32712694) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.05 | 25.Jul.2026 15:23 | 1900-01-12 19:10 |  | 0.33333 | Idle | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 2 / 5 | [] |  |  | MET.32712694 | 20'400 | 4'086 | 2029-12-27 | C
| 552 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.05 | 25.Jul.2026 14:54 | 1900-01-12 19:39 |  | 0.32292 | Idle | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) |  | 2 / 5 | [] |  |  | MET.32712897 | 20'400 | 4'086 | 2029-12-27 | C
| 553 | 783209-01-1 | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32712662) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 14:30 | 1900-01-16 20:03 |  | 0.041667 | Idle | 0 | T: 9; O: 0; C: 9 | 78-32 |  | [] |  |  |  |  | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32712662) |  | 1 / 3 | [] |  |  | MET.32712662 | 26.Sep.2029 | 1145 | 2029-09-26 | D
| 582 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | TC/P |  |  |  | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) |  | 0 / 1 | [] |  |  | MET.28375011 | 23.Aug.2026 | 15 | 2026-08-23 | D
| 583 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) |  | 0 / 3 | [] |  |  | MET.32712914 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 584 | 282200-04-1 | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32712909) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10556 | 17.Jul.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 3; O: 0; C: 3 | 28-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32712909) |  | 0 / 3 | [] |  |  | MET.32712909 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 585 | 282400-01-1-001 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32712913) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP |  |  |  | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32712913) |  | 0 / 5 | [] |  |  | MET.32712913 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 586 | 282400-01-1-002 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32712915) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 17.Jul.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP |  |  |  | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32712915) |  | 0 / 6 | [] |  |  | MET.32712915 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 587 | 282400-02-1-001 | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712903) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712903) |  | 0 / 3 | [] |  |  | MET.32712903 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 588 | 282400-02-1-002 | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712916) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32712916) |  | 0 / 3 | [] |  |  | MET.32712916 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 589 | 344200-02-2 | 344200-02-2 (01) / RADIO ALTIMETER | 344200-02-2 (01) / RADIO ALTIMETER (32712908) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25903 | 17.Jul.2026 22:00 | 0.30069 | 29.Jul.2026 17:19 | 1900-01-08 17:14 |  | 0.041667 | Idle | 0 | T: 2; O: 0; C: 2 | 34-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 1 / 4 | [] |  |  | MET.32712908 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 590 | 344200-04-1 | 344200-04-1 (01) / RADIO ALTIMETER | 344200-04-1 (01) / RADIO ALTIMETER (32712907) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.42569 | 17.Jul.2026 22:00 | 0.38403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 344200-04-1 (01) / RADIO ALTIMETER (32712907) |  | 0 / 6 | [] |  |  | MET.32712907 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 591 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32712653) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 38-10 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  | AS PER T/Q: 740971 | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32712653) |  | 0 / 3 | [] |  |  | MET.32712653 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 592 | 383100-02-1 | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32712917) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12917 | 17.Jul.2026 22:00 | 0.10625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 38-31 |  | [] | JOB-SETUP, TC/P, CLOSE-UP |  |  |  | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32712917) |  | 0 / 3 | [] |  |  | MET.32712917 | 03.Apr.2028 | 604 | 2028-04-03 | D
| 598 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.14306 | 27.Jul.2026 02:07 | 1900-01-11 08:26 |  | 0.91667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) |  | 5 / 7 | [] |  |  | MET.32712911 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 603 | 05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW (32713058) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-11 |  | [] | TC/P |  |  |  | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW (32713058) |  | 0 / 1 | [] |  |  | MET.32713058 | 09.Aug.2027 | 366 | 2027-08-09 | D
| 604 | 12-21-11-01-0-SVA | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH (19231763) | On Demand Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.40625 | 17.Jul.2026 22:00 | 0.25139 | 17.Jul.2026 18:58 | 1900-01-20 15:35 |  | 0.5 | Idle | 0 | T: 0; O: 0; C: 0 | 12-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH (19231763) |  | 2 / 10 | [] |  |  | MET.19231763 |  |  | 1517606
| 608 | 322100-07-1 | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP (32713055) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">35</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.625 | 17.Jul.2026 22:00 | 0.48194 | 26.Jul.2026 02:10 | 1900-01-12 08:23 |  | 1900-01-03 11:46 | Idle | 0 | T: 2; O: 0; C: 2 | 32-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | OK TO INSTALL NLG LEG ASSY IPC 32-21-01-10 | 0 / 1 |  | 7 / 10 | [] |  |  | MET.32713055 | 20'000 | 3'686 | 2029-08-27 | C
| 610 | 521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP (32712993) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.077778 | 26.Jul.2026 12:00 | 1900-01-11 22:33 |  | 1899-12-31 10:30 | Idle | 0 | T: 10; O: 0; C: 10 | 25-62 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 7 / 10 | [] |  |  | MET.32712993 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 611 | 521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP (32713003) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.055556 | 17.Jul.2026 22:00 | 0.11319 | 27.Jul.2026 08:33 | 1900-01-11 02:00 |  | 0.6875 | Idle | 0 | T: 10; O: 0; C: 10 | 52-13 |  | [] | TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION |  |  |  | 0 / 2 |  | 7 / 10 | [] |  |  | MET.32713003 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 612 | 522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION (32713039) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.28125 | 03.Aug.2026 15:28 | 1900-01-03 19:05 |  | 0.40972 | Idle | 0 | T: 0; O: 0; C: 0 | 52-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 5 / 7 | [] |  |  | MET.32713039 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 613 | 523103-01-1 | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP (32713046) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15069 | 17.Jul.2026 22:00 | 0.10417 | 24.Jul.2026 07:10 | 1900-01-14 03:23 |  | 0.084028 | Idle | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 2 / 6 | [] |  |  | MET.32713046 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 614 | 523109-01-1 | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP (32713017) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.023611 | 24.Jul.2026 06:14 | 1900-01-14 04:19 |  | 0.16736 | Idle | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP (32713017) |  | 3 / 4 | [] |  |  | MET.32713017 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 615 | 523113-01-1 | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP (32713032) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10208 | 17.Jul.2026 22:00 | 0.11319 | 24.Jul.2026 06:57 | 1900-01-14 03:36 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 52-32 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 6 | [] |  |  | MET.32713032 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 616 | 523119-01-2 | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 17.Jul.2026 22:00 | 0.023611 | 24.Jul.2026 08:22 | 1900-01-14 02:11 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 52-32 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) |  | 3 / 4 | [] |  |  | MET.32713047 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 617 | 523303-01-1 | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP (32713027) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.047917 | 24.Jul.2026 07:07 | 1900-01-14 03:26 |  | 0.06875 | Idle | 0 | T: 0; O: 0; C: 0 | 52-33 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP (32713027) |  | 3 / 6 | [] |  |  | MET.32713027 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 619 | 532130-09-1 | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION (32712618) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11667 | 17.Jul.2026 22:00 | 0.10625 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION (32712618) |  | 0 / 6 | [] |  |  | MET.32712618 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 620 | 532130-29-1 | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION (32712912) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.14722 | 03.Aug.2026 14:03 | 1900-01-03 20:30 |  | 1900-01-02 09:55 | Idle | 0 | T: 9; O: 0; C: 9 | 53-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION (32712912) |  | 7 / 10 | [] |  |  | MET.32712912 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 621 | 532132-01-1 | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32713000) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.040278 | 17.Jul.2026 22:00 | 0.048611 | 24.Jul.2026 05:42 | 1900-01-14 04:51 |  | 0.084722 | Idle | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32713000) |  | 3 / 4 | [] |  |  | MET.32713000 | 50363:39 | 4846:00 | 2027-11-27 | H
| 623 | 532175-01-1 | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR (32713006) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20694 | 17.Jul.2026 22:00 | 0.18056 | 24.Jul.2026 06:15 | 1900-01-14 04:18 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR (32713006) |  | 3 / 12 | [] |  |  | MET.32713006 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 628 | 533152-01-7 | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.1875 | 25.Jul.2026 14:36 | 1900-01-12 19:57 |  | 0.33333 | Idle | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) |  | 2 / 9 | [] |  |  | MET.32713023 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 630 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25336763) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.43472 | 17.Jul.2026 22:00 | 0.5625 | 03.Aug.2026 05:02 | 1900-01-04 05:31 |  | 0.58333 | Idle | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, -- |  |  |  | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25336763) |  | 5 / 10 | [] |  |  | MET.25336763 | 52900:00 | 7382:21 | 2028-08-03 | H
| 632 | 534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (32712622) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.067361 | 17.Jul.2026 22:00 | 0.074306 | 27.Jul.2026 14:27 | 1900-01-10 20:06 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 3 / 3 |  | 2 / 7 | [] |  |  | MET.32712622 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 633 | 534150-01-1 | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION (25336879) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.13889 | 29.Jul.2026 04:06 | 1900-01-09 06:27 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 8 | [] |  |  | MET.25336879 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 634 | 534164-01-1 | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC (32712624) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045139 | 17.Jul.2026 22:00 | 0.060417 | 24.Jul.2026 06:40 | 1900-01-14 03:53 |  | 0.20833 | Idle | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC (32712624) |  | 3 / 8 | [] |  |  | MET.32712624 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 635 | 534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A (32450150) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25694 | 17.Jul.2026 22:00 | 0.25694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A (32450150) |  | 0 / 4 | [] |  |  | MET.32450150 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 636 | 534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 (32450149) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.14583 | 03.Aug.2026 04:40 | 1900-01-04 05:53 |  | 1899-12-31 | Idle | 0 | T: 3; O: 0; C: 3 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 (32450149) |  | 3 / 4 | [] |  |  | MET.32450149 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 639 | 545134-09-6-001 | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713052) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.032639 | 17.Jul.2026 22:00 | 0.053472 | 21.Jul.2026 14:29 | 1900-01-16 20:04 |  | 0.54861 | Idle | 0 | T: 5; O: 0; C: 5 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713052) |  | 3 / 4 | [] |  |  | MET.32713052 | 21.Jul.2028 | 713 | 2028-07-21 | D
| 640 | 545134-09-6-002 | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713051) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.032639 | 17.Jul.2026 22:00 | 0.053472 | 21.Jul.2026 14:51 | 1900-01-16 19:42 |  | 0.055556 | Idle | 0 | T: 5; O: 0; C: 5 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP (32713051) |  | 3 / 4 | [] |  |  | MET.32713051 | 21.Jul.2028 | 713 | 2028-07-21 | D
| 643 | 572001-01-1-001 | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP (32713002) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.084722 | 24.Jul.2026 14:57 | 1900-01-13 19:36 |  | 0.021528 | Idle | 0 | T: 5; O: 0; C: 5 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP (32713002) |  | 3 / 5 | [] |  |  | MET.32713002 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 644 | 572001-01-1-002 | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP (32713001) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0.084722 | 23.Jul.2026 15:01 | 1900-01-14 19:32 |  | 0.32292 | Idle | 0 | T: 5; O: 0; C: 5 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP (32713001) |  | 5 / 5 | [] |  |  | MET.32713001 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 645 | 572007-01-2-001 | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP (25336398) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.08125 | 24.Jul.2026 14:53 | 1900-01-13 19:40 |  | 0.022222 | Idle | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP (25336398) |  | 3 / 5 | [] |  |  | MET.25336398 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 646 | 572007-01-2-002 | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP (25336296) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.08125 | 23.Jul.2026 15:12 | 1900-01-14 19:21 |  | 0.34375 | Idle | 0 | T: 1; O: 0; C: 1 | 57-20 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP (25336296) |  | 3 / 5 | [] |  |  | MET.25336296 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 647 | 572020-01-1-001 | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP (28325976) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.50833 | 28.Jul.2026 09:22 | 1900-01-10 01:11 |  | 0.28472 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 5 / 6 | [] |  |  | MET.28325976 | 56800:00 | 11282:21 | 2029-08-22 | H
| 648 | 572020-01-1-002 | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP (28325981) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.50833 | 28.Jul.2026 09:20 | 1900-01-10 01:13 |  | 0.23958 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP (28325981) |  | 5 / 6 | [] |  |  | MET.28325981 | 56800:00 | 11282:21 | 2029-08-22 | H
| 649 | 572040-01-2-001 | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP (32713019) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0055556 | 17.Jul.2026 22:00 | 0.016667 | 28.Jul.2026 09:24 | 1900-01-10 01:09 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP (32713019) |  | 4 / 6 | [] |  |  | MET.32713019 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 650 | 572040-01-2-002 | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP (32713041) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0055556 | 17.Jul.2026 22:00 | 0.016667 | 28.Jul.2026 09:05 | 1900-01-10 01:28 |  | 0.28125 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 6 | [] |  |  | MET.32713041 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 655 | 572063-01-1-001 | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.067361 | 17.Jul.2026 22:00 | 0.077778 | 24.Jul.2026 17:22 | 1900-01-13 17:11 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) |  | 3 / 6 | [] |  |  | MET.32713040 | 22.Oct.2027 | 440 | 2027-10-22 | D
| 656 | 572063-01-1-002 | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP (32713044) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.067361 | 17.Jul.2026 22:00 | 0.077778 | 24.Jul.2026 05:16 | 1900-01-14 05:17 |  | 0.10417 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP (32713044) |  | 3 / 6 | [] |  |  | MET.32713044 | 22.Oct.2027 | 440 | 2027-10-22 | D
| 657 | 572066-01-1-001 | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712627) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 15:06 | 1900-01-13 19:27 |  | 0.0625 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712627) |  | 3 / 5 | [] |  |  | MET.32712627 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 658 | 572066-01-1-002 | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712612) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.090278 | 24.Jul.2026 13:33 | 1900-01-13 21:00 |  | 0.03125 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP (32712612) |  | 3 / 5 | [] |  |  | MET.32712612 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 664 | 572139-01-2-001 | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713042) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.040278 | 24.Jul.2026 07:26 | 1900-01-14 03:07 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 2 / 4 |  | 3 / 5 | [] |  |  | MET.32713042 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 665 | 572139-01-2-002 | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713021) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.040278 | 24.Jul.2026 07:26 | 1900-01-14 03:07 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP (32713021) |  | 3 / 5 | [] |  |  | MET.32713021 | 21.Oct.2027 | 439 | 2027-10-21 | D
| 666 | 32712996 | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP | 32712996 / 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712996) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 17.Jul.2026 22:00 | 0.047917 | 28.Jul.2026 07:26 | 1900-01-10 03:07 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 32712996 / 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712996) |  | 0 / 5 | [] |  |  | MET.32712996 | 19.Apr.2029 | 985 | 2029-04-19 | D
| 667 | 572140-01-2-002 | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP (32712997) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.047917 | 28.Jul.2026 07:16 | 1900-01-10 03:17 |  | 0.22917 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 3 / 4 |  | 3 / 5 | [] |  |  | MET.32712997 | 19.Apr.2029 | 985 | 2029-04-19 | D
| 707 | 29904504 | EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A | 29904504 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904504) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.64583 | 04.Aug.2026 02:05 | 1900-01-03 08:28 |  | 1900-01-01 19:00 | Idle | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  | EOD can be done at Line if not reach to C-CHK or Connectivity EOD can be done at Line if not reach to C-CHK or Connectivity | 29904504 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904504) |  | 0 / 10 | [] |  |  | ME.29904504 | 16.Feb.2027 | 192 | 2027-02-16 | D
| 709 | 20893203 | EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) | 20893203 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (20893203) | Document | PJED | <html><span style="font-weight: normal;">No part requests</span></html> | 0.38194 | 17.Jul.2026 22:00 | 0.34375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 20893203 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (20893203) |  | 0 / 9 | [] |  |  | ME.20893203 | 19'500 | 3'186 | 2029-03-30 | C
| 710 | 29715410 | EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO | 29715410 / EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO (29715410) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.26042 | 17.Jul.2026 22:00 | 0.17361 | 03.Aug.2026 10:52 | 1900-01-03 23:41 |  | 1900-01-01 12:05 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 17 | [] |  |  | ME.29715410 | 18.Dec.2027 | 497 | 2027-12-18 | D
| 711 | 30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) | Document | AD | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) |  | 0 / 4 | [] |  | 000 | ME.30970374 | 26.May.2029 | 1022 | 2029-05-26 | D
| 712 | 29411293 | EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411293 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411293) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">10</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">11</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.36458 | 17.Jul.2026 22:00 | 0.33333 | 07.Aug.2026 03:20 | 1899-12-31 07:13 |  | 1900-01-01 05:11 | Idle | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411293 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411293) |  | 0 / 6 | [] |  |  | ME.29411293 | 01.Oct.2029 | 1150 | 2029-10-01 | D
| 713 | 29411377 | EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411377 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411377) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">15</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.36458 | 17.Jul.2026 22:00 | 0.33333 | 06.Aug.2026 00:00 | 1900-01-01 10:33 |  | 1900-01-02 16:50 | Idle | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411377 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411377) |  | 0 / 6 | [] |  |  | ME.29411377 | 01.Oct.2029 | 1150 | 2029-10-01 | D
| 714 | 31889267 | EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66111 | 17.Jul.2026 22:00 | 0.6875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) |  | 0 / 12 | [] |  | 000 | ME.31889267 | 48000:00 | 2487:21 | 2027-04-10 | H
| 715 | 30839449 | EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON | 30839449 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839449) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-01 00:30 | 17.Jul.2026 22:00 | 1899-12-31 06:40 | 27.Jul.2026 15:24 | 1900-01-10 19:09 |  | 1900-01-01 21:55 | Idle | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | --, JOB-SETUP, JOB-SETUP, JOB-SETUP, --, --, --, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, CLOSE-UP, CLOSE-UP |  |  |  | 30839449 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839449) |  | 0 / 17 | [] |  |  | ME.30839449 | 01.Dec.2028 | 846 | 2028-12-01 | D
| 716 | 29500617 | EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | 29500617 / EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500617) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 28.Jul.2026 08:55 | 1900-01-10 01:38 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29500617 / EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500617) |  | 0 / 6 | [] |  |  | ME.29500617 | 28.Feb.2027 | 204 | 2027-02-28 | D
| 721 | 29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 06.Aug.2026 07:05 | 1900-01-01 03:28 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) |  | 0 / 6 | [] |  |  | ME.29155749 | 31.Dec.2026 | 145 | 2026-12-31 | D
| 723 | 23732996 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23732996 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23732996) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.53125 | 17.Jul.2026 22:00 | 0.51042 | 03.Aug.2026 11:48 | 1900-01-03 22:45 |  | 0.66667 | Idle | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23732996 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23732996) |  | 0 / 3 | [] |  | 000 | ME.23732996 | 23'965 | 3'600 | 2029-08-02 | C
| 724 | 23745496 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.53125 | 17.Jul.2026 22:00 | 0.51042 | 03.Aug.2026 15:00 | 1900-01-03 19:33 |  | 0.69097 | Idle | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) |  | 0 / 3 | [] |  | S32SRT731LH | ME.23745496 | 23'965 | 3'600 | 2029-08-02 | C
| 725 | 31990073 | EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED | 31990073 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (31990073) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">23</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-01 06:00 | 17.Jul.2026 22:00 | 1899-12-31 03:15 | 23.Jul.2026 09:59 | 1900-01-15 00:34 |  | 1900-01-03 21:02 | Idle | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | This modification EO can be done either in Line or Hanger Required nose jacking and nose gear swing | 31990073 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (31990073) |  | 0 / 10 | [] |  | 000 | ME.31990073 | 31.Dec.2027 | 510 | 2027-12-31 | D
| 726 | 27685448 | EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS | 27685448 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685448) | Document | CCHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.67708 | 17.Jul.2026 22:00 | 0.59375 | 28.Jul.2026 06:48 | 1900-01-10 03:45 |  | 1900-01-02 19:30 | Idle | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | PART WILL BE AVL AT EDD 26-AUG-2024 | 27685448 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685448) |  | 0 / 5 | [] |  |  | ME.27685448 | 01.Oct.2027 | 419 | 2027-10-01 | D
| 727 | 30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 30817926 / EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION (30817926) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">27</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">12</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-18 15:00 | 17.Jul.2026 22:00 | 1900-01-17 23:00 | 28.Jul.2026 01:56 | 1900-01-10 08:37 |  | 1899-12-31 13:21 | Idle | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 30817926 / EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION (30817926) |  | 0 / 42 | [] |  |  | ME.30817926 | 01.Apr.2028 | 602 | 2028-04-01 | D
| 728 | 31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | 31328631 / EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL (31328631) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-06 02:00 | 17.Jul.2026 22:00 | 1900-01-06 02:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 31328631 / EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL (31328631) |  | 0 / 5 | [] |  |  | ME.31328631 | 08.Aug.2026 | 0 | 2026-08-08 | D
| 729 | 29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | 29155915 / EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155915) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.96528 | 17.Jul.2026 22:00 | 0.79861 | 26.Jul.2026 12:23 | 1900-01-11 22:10 |  | 1900-01-02 | Idle | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29155915 / EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155915) |  | 0 / 14 | [] |  |  | ME.29155915 | 01.Sep.2027 | 389 | 2027-09-01 | D
| 730 | 29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.4375 | 26.Jul.2026 11:00 | 1900-01-11 23:33 |  | 1900-01-01 01:10 | Idle | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) |  | 0 / 8 | [] |  |  | ME.29156039 | 01.Sep.2027 | 389 | 2027-09-01 | D
| 731 | 29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.77083 | 17.Jul.2026 22:00 | 0.60417 | 27.Jul.2026 07:30 | 1900-01-11 03:03 |  | 1899-12-31 06:00 | Idle | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) |  | 0 / 9 | [] |  |  | ME.29156133 | 01.Sep.2027 | 389 | 2027-09-01 | D
| 732 | 29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 06.Aug.2026 17:21 | 1899-12-31 17:12 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) |  | 0 / 5 | [] |  |  | ME.29156195 | 01.Sep.2027 | 389 | 2027-09-01 | D
| 734 | 29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 04.Aug.2026 17:40 | 1900-01-02 16:53 |  | 0.71875 | Idle | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) |  | 0 / 5 | [] |  |  | ME.29156249 | 31.Dec.2026 | 145 | 2026-12-31 | D
| 735 | 15777417 | EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 15777417 / EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777417) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 17.Jul.2026 22:00 | 0.055556 | 03.Aug.2026 05:10 | 1900-01-04 05:23 |  | 0.18056 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777417 / EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777417) |  | 0 / 6 | [] |  |  | ME.15777417 | 20'000 | 3'686 | 2029-08-28 | C
| 736 | 15777631 | EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 15777631 / EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777631) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.097222 | 03.Aug.2026 06:00 | 1900-01-04 04:33 |  | 0.069444 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777631 / EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (15777631) |  | 0 / 6 | [] |  |  | ME.15777631 | 20'000 | 3'686 | 2029-08-28 | C
| 737 | 16152729 | EOD-320-53-00014-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL | 16152729 / EOD-320-53-00014-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL (16152729) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 17.Jul.2026 22:00 | 0.20833 | 03.Aug.2026 06:40 | 1900-01-04 03:53 |  | 0.13889 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | rev 4 - update priority | 16152729 / EOD-320-53-00014-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL (16152729) |  | 0 / 9 | [] |  |  | ME.16152729 | 19'800 | 3'486 | 2029-06-29 | C
| 738 | 16152761 | EOD-320-53-00015-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL | 16152761 / EOD-320-53-00015-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL (16152761) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 17.Jul.2026 22:00 | 0.20833 | 03.Aug.2026 08:10 | 1900-01-04 02:23 |  | 0.13889 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | rev 3 - update priority | 16152761 / EOD-320-53-00015-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL (16152761) |  | 0 / 9 | [] |  |  | ME.16152761 | 19'800 | 3'486 | 2029-06-29 | C
| 739 | 17837147 | EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- | 17837147 / EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- (17837147) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 01:00 | 17.Jul.2026 22:00 | 0.91667 | 27.Jul.2026 03:00 | 1900-01-11 07:33 |  | 0.61181 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 17837147 / EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- (17837147) |  | 0 / 8 | [] |  |  | ME.17837147 | 48000:00 | 2482:21 | 2027-04-09 | H
| 740 | 18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 18607800 / EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING (18607800) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-01 14:00 | 17.Jul.2026 22:00 | 1900-01-01 04:00 | 30.Jul.2026 02:54 | 1900-01-08 07:39 |  | 0.6875 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 18607800 / EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING (18607800) |  | 0 / 16 | [] |  |  | ME.18607800 | 48000:00 | 2482:21 | 2027-04-09 | H
| 741 | 29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 29441536 / EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441536) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 09:45 | 17.Jul.2026 22:00 | 1899-12-31 06:10 | 28.Jul.2026 05:00 | 1900-01-10 05:33 |  | 1900-01-01 09:09 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 29441536 / EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441536) |  | 0 / 12 | [] |  |  | ME.29441536 | 20'000 | 3'686 | 2029-08-28 | C
| 742 | 28479751 | EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 | 28479751 / EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 (28479751) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">14</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.82639 | 17.Jul.2026 22:00 | 0.72222 | 28.Jul.2026 03:00 | 1900-01-10 07:33 |  | 1900-01-01 23:20 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 28479751 / EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 (28479751) |  | 0 / 10 | [] |  |  | ME.28479751 | 56500:00 | 10982:21 | 2029-07-25 | H
| 743 | 31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | 31381248 / EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 (31381248) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 18:15 | 17.Jul.2026 22:00 | 1899-12-31 05:19 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | DO SIMULTANOUSLY WITH EO-320-53-00048-R00 | 31381248 / EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 (31381248) |  | 0 / 11 | [] |  |  | ME.31381248 | 07.Oct.2031 | 1886 | 2031-10-07 | D
| 744 | 29399531 | EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI | 29399531 / EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI (29399531) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1899-12-31 04:10 | 17.Jul.2026 22:00 | 1899-12-31 00:10 | 26.Jul.2026 03:00 | 1900-01-12 07:33 |  | 1900-01-15 12:41 | Idle | 0 | T: 0; O: 0; C: 0 | 55 |  | [] |  |  |  |  | 1 / 1 |  | 0 / 12 | [] |  |  | ME.29399531 | 22.Apr.2032 | 2084 | 2032-04-22 | D
| 745 | 31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31053001 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053001) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31053001 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053001) |  | 0 / 2 | [] |  | 000 | ME.31053001 | 22.Sep.2026 | 44d, 14h | 2026-09-22 | D
| 746 | 31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31053051 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053051) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31053051 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053051) |  | 0 / 2 | [] |  | 000 | ME.31053051 | 22.Sep.2026 | 44d, 14h | 2026-09-22 | D
| 747 | 15969127 | EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. | 15969127 / EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. (15969127) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">40</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1899-12-31 20:10 | 17.Jul.2026 22:00 | 1899-12-31 14:25 | 26.Jul.2026 03:00 | 1900-01-12 07:33 |  | 1900-01-01 13:32 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15969127 / EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. (15969127) |  | 0 / 19 | [] |  |  | ME.15969127 | 48000:00 | 2482:21 | 2027-04-09 | H
| 748 | 10897096 | EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION | 10897096 / EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION (10897096) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.52778 | 17.Jul.2026 22:00 | 0.45833 | 29.Jul.2026 05:20 | 1900-01-09 05:13 |  | 1900-01-04 15:45 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 10897096 / EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION (10897096) |  | 0 / 12 | [] |  |  | ME.10897096 | 20'000 | 3'686 | 2029-08-28 | C
| 750 | 31662556 | S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH | 31662556 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662556) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.11111 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] |  |  |  |  | 31662556 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662556) |  | 0 / 4 | [] |  |  | ME.31662556 | 30.Dec.2026 | 144 | 2026-12-30 | D
| 751 | 30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | 30936889 / S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM (30936889) | Document | CCHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.9375 | 17.Jul.2026 22:00 | 0.54167 | 22.Jul.2026 06:10 | 1900-01-16 04:23 |  | 0.68056 | Idle | 0 | T: 0; O: 0; C: 0 | 32-33 |  | [] | --, --, --, --, --, --, --, --, --, --, OPS/LK, --, --, --, CLOSE-UP |  |  |  | 0 / 7 |  | 0 / 15 | [] |  |  | ME.30936889 | 21.Aug.2028 | 744 | 2028-08-21 | D
| 753 | 20038778 | S51-R10008/A320 FLEET // DENT AND BUCKLE CHART | 20038778 / S51-R10008/A320 FLEET // DENT AND BUCKLE CHART (20038778) | Document | HNGR | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 09:30 | 17.Jul.2026 22:00 | 0.52083 | 18.Jul.2026 13:27 | 1900-01-19 21:06 |  | 0.055556 | Idle | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 8 / 9 |  | 0 / 10 | [] |  |  | ME.20038778 | 31.Dec.2026 | 145 | 2026-12-31 | D
| 754 | 31978429 | S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS | 31978429 / S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS (31978429) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.090278 | 17.Jul.2026 22:00 | 0.1875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 31978429 / S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS (31978429) |  | 0 / 4 | [] |  |  | ME.31978429 | 01.Aug.2026 | -7 | 2026-08-01 | D
| 755 | 31573583 | S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS | 31573583 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573583) | Document | CCHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31573583 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573583) |  | 0 / 7 | [] |  |  | ME.31573583 | 31.Dec.2028 | 876 | 2028-12-31 | D
| 756 | 32832482 | S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR | 32832482 / S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR (32832482) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 10:26 | 1900-01-19 00:07 |  | 0.055556 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 2 | [] |  |  | ME.32832482 | 16.Jun.2029 | 1043 | 2029-06-16 | D
| 757 | 29294848 | S73-D10063/ENGINE FUEL FILTER REPLACEMENT | 29294848 / S73-D10063/ENGINE FUEL FILTER REPLACEMENT (29294848) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18056 | 17.Jul.2026 22:00 | 0.090278 | 02.Aug.2026 06:36 | 1900-01-05 03:57 |  | 1899-12-31 15:35 | Idle | 0 | T: 0; O: 0; C: 0 | 73 |  | [] |  |  |  |  | 29294848 / S73-D10063/ENGINE FUEL FILTER REPLACEMENT (29294848) |  | 0 / 7 | [] |  | 00 | ME.29294848 | 45735:38 | 217:59 | 2026-08-29 | H
| 758 | 31958880 | REPLACE PN:3214-31 SN:151653 (BATTERY, EMERGENCY) INSTALLED AT: 12WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135210 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:12WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... | 31958880 / REPLACE PN:3214-31 SN:151653 (BATTERY, EMERGENCY) INSTALLED AT: 12WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135210 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:12WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958880) | Rotable Removal Obsolete | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958880 / REPLACE PN:3214-31 SN:151653 (BATTERY, EMERGENCY) INSTALLED AT: 12WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135210 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:12WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958880) |  | 1 / 1 | [] |  | 12WL | WO.31958880 | 18.Aug.2026 | 10 | 2026-08-18 | D
| 759 | 31958882 | REPLACE PN:3214-31 SN:151671 (BATTERY, EMERGENCY) INSTALLED AT: 10WL(10WL) INSTALLED IN PN:3214-62-10 SN:132048 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:10WL) (POS DESCR:10WL) INFO/TRIGGERED BY: 3214-31/151671 TS(EXECUTION/TESTING) BATTERY CAPACI... | 31958882 / REPLACE PN:3214-31 SN:151671 (BATTERY, EMERGENCY) INSTALLED AT: 10WL(10WL) INSTALLED IN PN:3214-62-10 SN:132048 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:10WL) (POS DESCR:10WL) INFO/TRIGGERED BY: 3214-31/151671 TS(EXECUTION/TESTING) BATTERY CAPACI... (31958882) | Rotable Removal Obsolete | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958882 / REPLACE PN:3214-31 SN:151671 (BATTERY, EMERGENCY) INSTALLED AT: 10WL(10WL) INSTALLED IN PN:3214-62-10 SN:132048 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:10WL) (POS DESCR:10WL) INFO/TRIGGERED BY: 3214-31/151671 TS(EXECUTION/TESTING) BATTERY CAPACI... (31958882) |  | 1 / 1 | [] |  | 10WL | WO.31958882 | 18.Aug.2026 | 10 | 2026-08-18 | D
| 760 | 31958881 | REPLACE PN:3214-31 SN:151674 (BATTERY, EMERGENCY) INSTALLED AT: 11WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135194 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:11WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... | 31958881 / REPLACE PN:3214-31 SN:151674 (BATTERY, EMERGENCY) INSTALLED AT: 11WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135194 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:11WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958881) | Rotable Removal Obsolete | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958881 / REPLACE PN:3214-31 SN:151674 (BATTERY, EMERGENCY) INSTALLED AT: 11WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135194 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:11WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958881) |  | 1 / 1 | [] |  | 11WL | WO.31958881 | 18.Aug.2026 | 10 | 2026-08-18 | D
| 761 | 31958879 | REPLACE PN:3214-31 SN:151687 (BATTERY, EMERGENCY) INSTALLED AT: 13WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135158 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:13WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... | 31958879 / REPLACE PN:3214-31 SN:151687 (BATTERY, EMERGENCY) INSTALLED AT: 13WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135158 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:13WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958879) | Rotable Removal Obsolete | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31958879 / REPLACE PN:3214-31 SN:151687 (BATTERY, EMERGENCY) INSTALLED AT: 13WL(ADDED BY TRANSFER-PROGRAM) INSTALLED IN PN:3214-62-10 SN:135158 (EPSU - EMERGENCY POWER SUPPLY UNIT) (POS:13WL) (POS DESCR:ADDED BY TRANSFER-PROGRAM) INFO/TRIGGERED BY: 3214-31/1... (31958879) |  | 1 / 1 | [] |  | 13WL | WO.31958879 | 18.Aug.2026 | 10 | 2026-08-18 | D
| 762 | 22959389 | REPLACE 47145-267/4527 (ACTUATOR-THS) | 22959389 / REPLACE 47145-267/4527 (ACTUATOR-THS) (22959389) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 22959389 / REPLACE 47145-267/4527 (ACTUATOR-THS) (22959389) |  | 0 / 1 | [] |  | 000 | ME.22959389 | 20'000 | 3'687 | 2029-08-29 | C
| 763 | 31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) | Replacement Event | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:28 | 1900-01-02 07:05 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) |  | 0 / 1 | [] |  | 100 | ME.31197928 | 31.Aug.2026 | 23 | 2026-08-31 | D
| 764 | 26290429 | 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:43 | 1900-01-10 15:50 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) |  | 0 / 3 | [] |  | 201 | ME.26290429 | 10.Sep.2028 | 764 | 2028-09-10 | D
| 765 | 28781470 | 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:38 | 1900-01-10 15:55 |  | 0.37847 | Idle | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) |  | 0 / 3 | [] |  | 101 | ME.28781470 | 22.Aug.2029 | 1110 | 2029-08-22 | D
| 766 | 28781472 | 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 30.Jul.2026 08:34 | 1900-01-08 01:59 |  | 0.29167 | Idle | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) |  | 0 / 3 | [] |  | 102 | ME.28781472 | 22.Aug.2029 | 1110 | 2029-08-22 | D
| 767 | 22574878 | 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:44 | 1900-01-10 15:49 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) |  | 0 / 3 | [] |  | 000 | ME.22574878 | 24.Feb.2027 | 200 | 2027-02-24 | D
| 768 | 23772081 | 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772081 / 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772081) | Part Requirement | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 23772081 / 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772081) |  | 0 / 3 | [] |  | 002 | ME.23772081 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 769 | 23772080 | 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) | Part Requirement | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) |  | 0 / 3 | [] |  | 001 | ME.23772080 | 21.Jun.2028 | 683 | 2028-06-21 | D
| 770 | 31045000 | CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING | 31045000 / CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING (31045000) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.20139 | 17.Jul.2026 22:00 | 0.10347 | 06.Aug.2026 10:11 | 1900-01-01 00:22 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 75 |  | [] |  |  |  |  | 31045000 / CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING (31045000) |  | 0 / 8 | [] |  | ENG100 | ME.31045000 | 31240:40 | 384:46 | 2026-09-14 | H
| 772 | 80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | 80944787 / PANEL 41C CEILING PANEL FOUND DAMAGE (80944787) | Workorder | PANT | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Oct.2025 06:06 | 1900-10-16 04:27 |  | 0.67361 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 80944787 / PANEL 41C CEILING PANEL FOUND DAMAGE (80944787) |  | 0 / 2 | [] |  |  | WO.80944787 | 21.Oct.2026 | 74 | 2026-10-21 | D
| 773 | 81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | 81002632 / AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR (81002632) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Apr.2026 01:29 | 1900-04-11 09:04 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 81002632 / AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR (81002632) |  | 0 / 1 | [] |  |  | WO.81002632 | 27.Apr.2027 | 262 | 2027-04-27 | D
| 774 | 94493475 | DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. | 94493475 / DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. (94493475) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 11.Jun.2026 23:28 | 1900-02-25 11:05 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493475 / DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. (94493475) |  | 0 / 1 | [] |  |  | WO.94493475 | 10.Oct.2026 | 63 | 2026-10-10 | D
| 775 | 94493476 | DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. | 94493476 / DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. (94493476) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 11.Jun.2026 23:31 | 1900-02-25 11:02 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493476 / DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. (94493476) |  | 0 / 1 | [] |  |  | WO.94493476 | 10.Oct.2026 | 63 | 2026-10-10 | D
| 776 | 94493487 | DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. | 94493487 / DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. (94493487) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Jun.2026 23:46 | 1900-02-23 10:47 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493487 / DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. (94493487) |  | 0 / 1 | [] |  |  | WO.94493487 | 11.Oct.2026 | 64 | 2026-10-11 | D
| 777 | 94493488 | DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. | 94493488 / DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. (94493488) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Jun.2026 23:51 | 1900-02-23 10:42 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493488 / DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. (94493488) |  | 0 / 1 | [] |  |  | WO.94493488 | 11.Oct.2026 | 64 | 2026-10-11 | D
| 778 | 94493489 | DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. | 94493489 / DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. (94493489) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 14.Jun.2026 00:04 | 1900-02-23 10:29 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94493489 / DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. (94493489) |  | 0 / 1 | [] |  |  | WO.94493489 | 11.Oct.2026 | 64 | 2026-10-11 | D
| 779 | 94734250 | WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING | 94734250 / WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING (94734250) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 15.May.2026 22:15 | 1900-03-24 12:18 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 94734250 / WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING (94734250) |  | 0 / 1 | [] |  |  | WO.94734250 | 11.Sep.2026 | 34 | 2026-09-11 | D
| 780 | 94740818 | BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 27.Apr.2026 10:57 | 1900-04-11 23:36 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) |  | 0 / 1 | [] |  |  | WO.94740818 | 25.Aug.2026 | 17 | 2026-08-25 | D
| 781 | 94799712 | DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED | 94799712 / DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED (94799712) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 02.Jun.2026 07:06 | 1900-03-07 03:27 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11-00 |  | [] |  |  |  |  | 94799712 / DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED (94799712) |  | 0 / 1 | [] |  |  | WO.94799712 | 30.Sep.2026 | 53 | 2026-09-30 | D
| 783 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (32924594) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE |  |  |  | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (32924594) |  | 0 / 1 | [] |  |  | JCA.32924594 |  |  | 1517606
| 784 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (32924593) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P |  |  |  | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (32924593) |  | 0 / 2 | [] |  |  | JCA.32924593 |  |  | 1517606
| 785 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (32924591) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE, ACFT RELEASE, -- |  |  |  | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (32924591) |  | 0 / 3 | [] |  |  | JCA.32924591 |  |  | 1517606
| 787 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (32924605) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.91667 | 17.Jul.2026 22:00 | 0.46528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (32924605) |  | 0 / 18 | [] |  |  | JCA.32924605 |  |  | 1517606
| 788 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P |  |  |  | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) |  | 0 / 1 | [] |  |  | JCA.32924631 |  |  | 1517606
| 789 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (32924630) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (32924630) |  | 0 / 3 | [] |  |  | JCA.32924630 |  |  | 1517606
| 790 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (32924632) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (32924632) |  | 0 / 1 | [] |  |  | JCA.32924632 |  |  | 1517606
| 791 | STJC-AREAS-FINAL-INSPECTION-03-GA-GO | AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (32924633) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (32924633) |  | 0 / 1 | [] |  |  | JCA.32924633 |  |  | 1517606
| 792 | STJC-AREAS-FINAL-INSPECTION-04-GA-GO | EMPENNAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (32924635) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (32924635) |  | 0 / 1 | [] |  |  | JCA.32924635 |  |  | 1517606
| 793 | STJC-AREAS-FINAL-INSPECTION-05-GA-GO | AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (32924636) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (32924636) |  | 0 / 1 | [] |  |  | JCA.32924636 |  |  | 1517606
| 794 | STJC-AREAS-FINAL-INSPECTION-06-GA-GO | L/H AND R/H WINGS FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (32924653) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (32924653) |  | 0 / 1 | [] |  |  | JCA.32924653 |  |  | 1517606
| 795 | STJC-AREAS-FINAL-INSPECTION-07-GA-GO | LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (32924652) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (32924652) |  | 0 / 1 | [] |  |  | JCA.32924652 |  |  | 1517606
| 796 | STJC-AREAS-FINAL-INSPECTION-08-GA-GO | ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (32924655) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (32924655) |  | 0 / 1 | [] |  |  | JCA.32924655 |  |  | 1517606
| 797 | STJC-AREAS-FINAL-INSPECTION-09-GA-GO | APU FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (32924654) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (32924654) |  | 0 / 1 | [] |  |  | JCA.32924654 |  |  | 1517606
| 798 | STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (32924658) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-11 |  | [] | ACFT RELEASE |  |  |  | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (32924658) |  | 0 / 1 | [] |  |  | JCA.32924658 |  |  | 1517606
| 799 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (32924657) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (32924657) |  | 0 / 4 | [] |  |  | JCA.32924657 |  |  | 1517606
| 800 | 32596938 | 22-70-00-01-0-A (03) / FMC DATA UPLOAD | 32596938 / 22-70-00-01-0-A (03) / FMC DATA UPLOAD (32596938) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 22-70 |  | [] | TC/P |  |  |  | 32596938 / 22-70-00-01-0-A (03) / FMC DATA UPLOAD (32596938) |  | 0 / 1 | [] |  |  | MET.32596938 | 01.Aug.2026 | -7 | 2026-08-01 | D
| 801 | 242000-21-1-001 | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION (32450186) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.086806 | 17.Jul.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 24-21 |  | [] | --, TC/P, -- |  |  |  | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION (32450186) |  | 0 / 3 | [] |  |  | MET.32450186 | 45566:21 | 48:42 | 2026-08-11 | H
| 803 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 381000-01-1 (3) / WATER TANK DISINFECTION (32626111) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 38-10 |  | [] | OPS/LK |  |  |  | 381000-01-1 (3) / WATER TANK DISINFECTION (32626111) |  | 0 / 1 | [] |  |  | MET.32626111 | 23.Sep.2026 | 46 | 2026-09-23 | D
| 804 | 32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 32840057 / DCC-32S (13) / DCC A32S DAILY CABIN CHECK (32840057) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">51</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.41667 | 29.Jul.2026 03:51 | 1900-01-09 06:42 |  | 1900-01-04 09:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, --, --, --, --, -- |  |  | This task is not required after the CRS of a higher-level letter check (A-Check, C-Check, 6Y or 12Y) | 10 / 15 |  | 0 / 9 | [] |  |  | MET.32840057 | 18.Jul.2026 | -20d, 10h | 2026-07-18 | D
| 810 | 32913243 | CCC-32S (05) / A32S CABIN CRITICAL CHECK | 32913243 / CCC-32S (05) / A32S CABIN CRITICAL CHECK (32913243) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.13194 | 17.Jul.2026 22:00 | 0.13194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, -- |  |  | To Remove step H. (Remove IFE CHECK as per T/Q: 692582) that Requestd by IFE ENGG H. IFE CONNECTIVITY CHECK 1. Performs a connectivity (satcom) test in accordance with THALES supplement as per AMM 44-31-01- 710-801. rectify as required. --------------------------------------------------------------------- ------------------------------------------ STEP D REVISED as per T/Q: 757461 -------------------------------------------------------- As per T/Q: 779111and 779112 andt T/Q;779113 T/Q: 779115 to add H. IFE CONNECTIVITY CHECK 1. CHECK THE FUNCTIONALITY OF THE CONNECTIVITY SYSTEM ONBOARD AS PER AIRBUS AMM 46-41-00-720-802-A. (if applicable)” 2. If the aircraft isequivalent to the Eclipse system, verify the following: A. CONFIRM The Ground Test and Reset switches are in the DISABLED position with the switch guards engaged. B. CONFIRM The Connectivity switch in the cockpit is pressed and fully seated. | 2 / 5 |  | 0 / 8 | [] |  |  | MET.32913243 | 18.Jul.2026 | -21d, 4h | 2026-07-18 | D
| 811 | 94844878 | O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS | 94844878 / O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS (94844878) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] |  |  |  |  | 94844878 / O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS (94844878) |  | 0 / 1 | [] |  |  | WO.94844878 | 18.Jul.2026 | -21d, 10h | 2026-07-18 | D
| 812 | 94844876 | L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 | 94844876 / L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 (94844876) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-00 |  | [] |  |  |  |  | 94844876 / L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 (94844876) |  | 0 / 1 | [] |  |  | WO.94844876 | 18.Jul.2026 | -21d, 9h | 2026-07-18 | D
| 815 | 32977685 | LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) |  | 0 / 1 | [] |  |  | WO.32977685 | 18.Jul.2026 | -20d, 19h | 2026-07-18 | D
| 816 | 32977864 | PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. | 32977864 / PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. (32977864) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 04:38 | 1900-01-08 05:55 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977864 / PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. (32977864) |  | 0 / 1 | [] |  |  | WO.32977864 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 817 | 32977871 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) |  | 0 / 1 | [] |  |  | WO.32977871 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 818 | 32977873 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) |  | 0 / 1 | [] |  |  | WO.32977873 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 821 | 32977882 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 07.Aug.2026 09:13 | 1899-12-31 01:20 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) |  | 0 / 1 | [] |  |  | WO.32977882 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 822 | 32977883 | PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:40 | 1900-01-19 06:53 |  | 1900-01-04 01:55 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) |  | 0 / 1 | [] |  |  | WO.32977883 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 823 | 32977884 | PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">10</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:50 | 1900-01-19 06:43 |  | 1900-01-01 12:15 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) |  | 0 / 1 | [] |  |  | WO.32977884 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 826 | 32977906 | PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 32977906 / PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977906) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977906 / PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977906) |  | 0 / 1 | [] |  |  | WO.32977906 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 827 | 32977907 | PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 04:01 | 1900-01-16 06:32 |  | 0.77222 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) |  | 0 / 1 | [] |  |  | WO.32977907 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 830 | 32977910 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 24.Jul.2026 13:34 | 1900-01-13 20:59 |  | 0.35417 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) |  | 0 / 1 | [] |  |  | WO.32977910 | 18.Jul.2026 | -20d, 16h | 2026-07-18 | D
| 834 | 32978238 | NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. | 32978238 / NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978238 / NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) |  | 0 / 1 | [] |  |  | WO.32978238 | 18.Jul.2026 | -20d, 12h | 2026-07-18 | D
| 840 | 32978254 | LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. | 32978254 / LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. (32978254) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 09:55 | 1900-01-05 00:38 |  | 0.58333 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978254 / LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. (32978254) |  | 0 / 1 | [] |  |  | WO.32978254 | 18.Jul.2026 | -20d, 11h | 2026-07-18 | D
| 841 | 32978259 | LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. | 32978259 / LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978259 / LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) |  | 0 / 1 | [] |  |  | WO.32978259 | 18.Jul.2026 | -20d, 11h | 2026-07-18 | D
| 847 | 32978282 | RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" | 32978282 / RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" (32978282) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 11:00 | 1900-01-16 23:33 |  | 0.65278 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978282 / RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" (32978282) |  | 0 / 3 | [] |  |  | WO.32978282 | 18.Jul.2026 | -20d, 11h | 2026-07-18 | D
| 851 | 32978507 | FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. | 32978507 / FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. (32978507) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 23.Jul.2026 05:00 | 1900-01-15 05:33 |  | 0.013889 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978507 / FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. (32978507) |  | 0 / 1 | [] |  |  | WO.32978507 | 19.Jul.2026 | -20d, 9h | 2026-07-19 | D
| 852 | 32978509 | FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. | 32978509 / FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. (32978509) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978509 / FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. (32978509) |  | 0 / 1 | [] |  |  | WO.32978509 | 19.Jul.2026 | -20d, 9h | 2026-07-19 | D
| 853 | 32978510 | FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 11:00 | 1900-01-18 23:33 |  | 1899-12-31 04:50 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) |  | 0 / 1 | [] |  |  | WO.32978510 | 19.Jul.2026 | -20d, 9h | 2026-07-19 | D
| 854 | 32978546 | FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 03:20 | 1900-01-10 07:13 |  | 1899-12-31 03:50 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) |  | 0 / 1 | [] |  |  | WO.32978546 | 19.Jul.2026 | -20d, 9h | 2026-07-19 | D
| 855 | 32978563 | FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 27.Jul.2026 02:00 | 1900-01-11 08:33 |  | 1900-01-01 05:40 | Idle | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) |  | 0 / 1 | [] |  |  | WO.32978563 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 861 | 32978585 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) |  | 0 / 1 | [] |  |  | WO.32978585 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 863 | 32978591 | FWD CARGO DOOR---AP--NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. | 32978591 / FWD CARGO DOOR---AP--NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. (32978591) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978591 / FWD CARGO DOOR---AP--NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. (32978591) |  | 0 / 1 | [] |  |  | WO.32978591 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 864 | 32978593 | FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT | 32978593 / FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT (32978593) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978593 / FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT (32978593) |  | 0 / 1 | [] |  |  | WO.32978593 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 866 | 32978626 | FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 05:37 | 1900-01-07 04:56 |  | 0.35417 | Idle | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) |  | 0 / 1 | [] |  |  | WO.32978626 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 867 | 32978634 | AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" | 32978634 / AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" (32978634) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 04:08 | 1900-01-16 06:25 |  | 0.013889 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978634 / AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" (32978634) |  | 0 / 1 | [] |  |  | WO.32978634 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 868 | 32978638 | AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" | 32978638 / AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" (32978638) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978638 / AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" (32978638) |  | 0 / 1 | [] |  |  | WO.32978638 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 869 | 32978643 | AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. | 32978643 / AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. (32978643) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978643 / AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. (32978643) |  | 0 / 1 | [] |  |  | WO.32978643 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 873 | 32978651 | AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. | 32978651 / AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978651 / AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) |  | 0 / 1 | [] |  |  | WO.32978651 | 19.Jul.2026 | -20d, 8h | 2026-07-19 | D
| 876 | 32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 32978879 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY (32978879) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978879 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY (32978879) |  | 0 / 1 | [] |  |  | WO.32978879 | 19.Jul.2026 | -20d, 5h | 2026-07-19 | D
| 886 | 32979256 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP LWR KICK SEAL WITH CUT 0.5 IN. | 32979256 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP LWR KICK SEAL WITH CUT 0.5 IN. (32979256) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979256 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP LWR KICK SEAL WITH CUT 0.5 IN. (32979256) |  | 0 / 1 | [] |  |  | WO.32979256 | 19.Jul.2026 | -20d, 4h | 2026-07-19 | D
| 888 | 32979304 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. | 32979304 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. (32979304) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 04:51 | 1900-01-05 05:42 |  | 1899-12-31 03:30 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979304 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. (32979304) |  | 0 / 1 | [] |  |  | WO.32979304 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 889 | 32979322 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN (32979322) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 17:00 | 1900-01-15 17:33 |  | 0.11111 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN (32979322) |  | 0 / 1 | [] |  |  | WO.32979322 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 890 | 32979401 | FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.20833 | 20.Jul.2026 19:00 | 1900-01-17 15:33 |  | 1900-01-01 23:30 | Idle | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) |  | 0 / 3 | [] |  |  | WO.32979401 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 891 | 32979406 | FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 20.Jul.2026 19:00 | 1900-01-17 15:33 |  | 1899-12-31 16:40 | Idle | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) |  | 0 / 3 | [] |  |  | WO.32979406 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 892 | 32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 32979530 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS (32979530) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 25.Jul.2026 11:28 | 1900-01-12 23:05 |  | 0.52083 | Idle | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] |  |  |  |  | 32979530 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS (32979530) |  | 0 / 1 | [] |  |  | WO.32979530 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 893 | 32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 32979557 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH (32979557) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] |  |  |  |  | 32979557 / FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH (32979557) |  | 0 / 1 | [] |  |  | WO.32979557 | 19.Jul.2026 | -20d, 3h | 2026-07-19 | D
| 894 | 32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 03:52 | 1900-01-01 06:41 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] |  |  |  |  | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) |  | 0 / 1 | [] |  |  | WO.32979661 | 19.Jul.2026 | -20d, 2h | 2026-07-19 | D
| 900 | 32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 04:16 | 1900-01-15 06:17 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) |  | 0 / 1 | [] |  |  | WO.32980022 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 901 | 32391506 | 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 | 02.Aug.2026 16:47 | 1900-01-04 17:46 |  | 0.069444 | Idle | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) |  | 0 / 3 | [] |  | 002 | ME.32391506 | 25.Jul.2026 | -14 | 2026-07-25 | D
| 902 | 32439904 | 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 | 02.Aug.2026 15:23 | 1900-01-04 19:10 |  | 0.55556 | Idle | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) |  | 0 / 3 | [] |  | 2522GM | ME.32439904 | 06.Oct.2026 | 59 | 2026-10-06 | D
| 903 | 32163655 | 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32163655 / 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163655) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 30.Jul.2026 17:02 | 1900-01-07 17:31 |  | 0.22917 | Idle | 0 | T: 1; O: 0; C: 1 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32163655 / 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163655) |  | 0 / 4 | [] |  | 100 | ME.32163655 | 1571:23 | 217:59 | 2026-08-29 | H
| 904 | 32163652 | 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32163652 / 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163652) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 30.Jul.2026 17:30 | 1900-01-07 17:03 |  | 0.33333 | Idle | 0 | T: 1; O: 0; C: 1 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32163652 / 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32163652) |  | 0 / 4 | [] |  | 002 | ME.32163652 | 38063:25 | 217:59 | 2026-08-29 | H
| 905 | 81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | 81172702 / IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 (81172702) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 03.Jul.2026 08:21 | 1900-02-04 02:12 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 44-26-00 |  | [] |  |  |  |  | 81172702 / IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 (81172702) |  | 0 / 1 | [] |  |  | WO.81172702 | 31.Oct.2026 | 84 | 2026-10-31 | D
| 906 | 94844831 | DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN | 94844831 / DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN (94844831) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:21 | 1900-01-26 02:12 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844831 / DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN (94844831) |  | 0 / 1 | [] |  |  | WO.94844831 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 907 | 94844832 | DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED | 94844832 / DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED (94844832) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:18 | 1900-01-26 02:15 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844832 / DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED (94844832) |  | 0 / 1 | [] |  |  | WO.94844832 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 908 | 94844833 | DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED | 94844833 / DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED (94844833) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 08:15 | 1900-01-26 02:18 |  | 0 | Idle | 0 | T: 0; O: 0; C: 0 | 11 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844833 / DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED (94844833) |  | 0 / 1 | [] |  |  | WO.94844833 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 909 | 94844834 | DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN | 94844834 / DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN (94844834) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:05 | 1900-01-26 03:28 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844834 / DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN (94844834) |  | 0 / 1 | [] |  |  | WO.94844834 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 910 | 94844835 | DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN | 94844835 / DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN (94844835) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:03 | 1900-01-26 03:30 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844835 / DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN (94844835) |  | 0 / 1 | [] |  |  | WO.94844835 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 911 | 94844836 | RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 07:49 | 1900-01-26 02:44 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) |  | 0 / 1 | [] |  |  | WO.94844836 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 912 | 94844837 | DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN | 94844837 / DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN (94844837) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Jul.2026 06:49 | 1900-01-26 03:44 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844837 / DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN (94844837) |  | 0 / 1 | [] |  |  | WO.94844837 | 09.Nov.2026 | 93 | 2026-11-09 | D
| 914 | 32850432 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) | Document | RON | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  |  | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) |  | 0 / 6 | [] |  |  | ME.32850432 | 06.Oct.2026 | 59 | 2026-10-06 | D
| 915 | 15777708 | EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | 15777708 / EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777708) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 17.Jul.2026 22:00 | 0.15278 | 29.Jul.2026 06:45 | 1900-01-09 03:48 |  | 0.4375 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | REVISED TO UPDATE WORKSTEP 5 TO MATCH REVISION NUMBER (02 INSTEAD OF 01) | 15777708 / EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777708) |  | 0 / 5 | [] |  |  | ME.15777708 | 22.Apr.2032 | 2084 | 2032-04-22 | D
| 916 | 15777769 | EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | 15777769 / EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777769) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19444 | 17.Jul.2026 22:00 | 0.16667 | 27.Jul.2026 09:00 | 1900-01-11 01:33 |  | 0.40972 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 15777769 / EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON (15777769) |  | 0 / 5 | [] |  |  | ME.15777769 | 22.Apr.2032 | 2084 | 2032-04-22 | D
| 917 | 28372303 | REPLACE DVE90-07/7369 (VALVE-SOLENOID) | 28372303 / REPLACE DVE90-07/7369 (VALVE-SOLENOID) (28372303) | Replacement Event | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-00 |  | [] |  |  |  |  | 28372303 / REPLACE DVE90-07/7369 (VALVE-SOLENOID) (28372303) |  | 0 / 1 | [] |  | 000 | ME.28372303 | 26.Sep.2026 | 49 | 2026-09-26 | D
| 919 | 32822269 | S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY | 32822269 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822269) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26 |  | [] |  |  |  |  | 32822269 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822269) |  | 0 / 2 | [] |  |  | ME.32822269 | 14.Dec.2026 | 128 | 2026-12-14 | D
| 920 | 32822529 | S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 06.Aug.2026 04:27 | 1900-01-01 06:06 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) |  | 0 / 2 | [] |  |  | ME.32822529 | 20.Jul.2026 | -19 | 2026-07-20 | D
| 922 | 30262642 | S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL | 30262642 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262642) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | If the part is S/D, please hold the plan and Inform Engineering . | 30262642 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262642) |  | 0 / 4 | [] |  |  | ME.30262642 | 03.Oct.2026 | 56 | 2026-10-03 | D
| 923 | 32800094 | S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK | 32800094 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800094) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 07:00 | 17.Jul.2026 22:00 | 1899-12-31 07:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | Please C/W. This ER is issued to perform Bleed Health Check on A320 CEO fleet EBAS system. Kindly schedule this task in the C-Check. | 32800094 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800094) |  | 0 / 18 | [] |  |  | ME.32800094 | 31.Dec.2029 | 1241 | 2029-12-31 | D
| 924 | 32872501 | S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) |  | 0 / 3 | [] |  |  | ME.32872501 | 21.Aug.2026 | 13 | 2026-08-21 | D
| 926 | 32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 32980026 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY (32980026) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980026 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY (32980026) |  | 0 / 1 | [] |  |  | WO.32980026 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 928 | 32980047 | LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) | 32980047 / LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) (32980047) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 14:30 | 1900-01-16 20:03 |  | 0.35417 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980047 / LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) (32980047) |  | 0 / 1 | [] |  |  | WO.32980047 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 929 | 32980064 | LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) | 32980064 / LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) (32980064) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 11:00 | 1900-01-16 23:33 |  | 0.6875 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980064 / LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) (32980064) |  | 0 / 1 | [] |  |  | WO.32980064 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 930 | 32980065 | LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 | 32980065 / LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 (32980065) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980065 / LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 (32980065) |  | 0 / 1 | [] |  |  | WO.32980065 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 931 | 32980071 | LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) |  | 0 / 1 | [] |  |  | WO.32980071 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 932 | 32980080 | LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) |  | 0 / 1 | [] |  |  | WO.32980080 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 937 | 32980104 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. | 32980104 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. (32980104) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980104 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. (32980104) |  | 0 / 1 | [] |  |  | WO.32980104 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 938 | 32980083 | LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) |  | 0 / 1 | [] |  |  | WO.32980083 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 939 | 32980111 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE | 32980111 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE (32980111) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 03:00 | 1900-01-16 07:33 |  | 0.30208 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980111 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE (32980111) |  | 0 / 1 | [] |  |  | WO.32980111 | 19.Jul.2026 | -20d, 1h | 2026-07-19 | D
| 941 | 32980118 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN | 32980118 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN (32980118) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 15:31 | 1900-01-02 19:02 |  | 0.57986 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980118 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN (32980118) |  | 0 / 1 | [] |  |  | WO.32980118 | 19.Jul.2026 | -20d, 59m | 2026-07-19 | D
| 943 | 44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK (32949267) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44-21 |  | [] |  |  |  |  | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK (32949267) |  | 0 / 1 | [] |  |  | MET.32949267 | 19.Jul.2026 | -20 | 2026-07-19 | D
| 944 | 32917899 | ISC/IN SERVCE CHECK_N | 32917899 / ISC/IN SERVCE CHECK_N (32917899) | Check | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 0 / 2 |  | 0 / 1 | [] |  |  | ME.32917899 | 19.Jul.2026 | -20d, 5h | 2026-07-19 | D
| 945 | 32420054 | W_N/WEEKLY CHECK | 32420054 / W_N/WEEKLY CHECK (32420054) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 32420054 / W_N/WEEKLY CHECK (32420054) |  | 0 / 1 | [] |  |  | ME.32420054 | 27.Jul.2026 | -12 | 2026-07-27 | D
| 947 | ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) (32917900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11806 | 17.Jul.2026 22:00 | 0.11806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12 |  | [] | TC/P, --, --, -- |  |  |  | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) (32917900) |  | 0 / 4 | [] |  |  | MET.32917900 | 19.Jul.2026 | -20d, 10h | 2026-07-19 | D
| 948 | WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | WEEKLY-32S (05) / WEEKLY 32S CHECK (32822769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.24653 | 17.Jul.2026 22:00 | 0.24653 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12 |  | [] | TC/P, --, --, --, --, --, --, -- |  |  |  | WEEKLY-32S (05) / WEEKLY 32S CHECK (32822769) |  | 0 / 8 | [] |  |  | MET.32822769 | 27.Jul.2026 | -12 | 2026-07-27 | D
| 949 | 32980140 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) |  | 0 / 1 | [] |  |  | WO.32980140 | 19.Jul.2026 | -20d, 56m | 2026-07-19 | D
| 950 | 32980164 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) |  | 0 / 1 | [] |  |  | WO.32980164 | 19.Jul.2026 | -20d, 53m | 2026-07-19 | D
| 953 | 32980186 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. | 32980186 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. (32980186) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980186 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. (32980186) |  | 0 / 1 | [] |  |  | WO.32980186 | 19.Jul.2026 | -20d, 47m | 2026-07-19 | D
| 954 | 32980176 | REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) |  | 0 / 1 | [] |  |  | WO.32980176 | 19.Jul.2026 | -20d, 51m | 2026-07-19 | D
| 955 | 32980920 | FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 04:40 | 1900-01-15 05:53 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) |  | 0 / 1 | [] |  |  | WO.32980920 | 19.Jul.2026 | -19d, 23h | 2026-07-19 | D
| 957 | 32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 32981683 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. (32981683) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981683 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. (32981683) |  | 0 / 1 | [] |  |  | WO.32981683 | 19.Jul.2026 | -19d, 21h | 2026-07-19 | D
| 960 | 32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) |  | 0 / 1 | [] |  |  | WO.32981726 | 19.Jul.2026 | -19d, 21h | 2026-07-19 | D
| 964 | 32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.625 | 17.Jul.2026 22:00 | 0.625 | 03.Aug.2026 11:56 | 1900-01-03 22:37 |  | 1899-12-31 08:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) |  | 0 / 1 | [] |  |  | WO.32981816 | 19.Jul.2026 | -19d, 20h | 2026-07-19 | D
| 966 | 32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 32982172 / AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY (32982172) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 08:50 | 1900-01-11 01:43 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982172 / AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY (32982172) |  | 0 / 1 | [] |  |  | WO.32982172 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 968 | 32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 32982194 / CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS (32982194) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 16:03 | 1900-01-17 18:30 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982194 / CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS (32982194) |  | 0 / 1 | [] |  |  | WO.32982194 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 969 | 32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 32982195 / S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED (32982195) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982195 / S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED (32982195) |  | 0 / 1 | [] |  |  | WO.32982195 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 970 | 32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 32982197 / CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS (32982197) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 14:54 | 1900-01-18 19:39 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982197 / CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS (32982197) |  | 0 / 1 | [] |  |  | WO.32982197 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 971 | 32982199 | RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 32982199 / RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982199) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 17:12 | 1900-01-18 17:21 |  | 0.0625 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982199 / RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982199) |  | 0 / 1 | [] |  |  | WO.32982199 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 972 | 32982200 | RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 32982200 / RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982200) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 17:00 | 1900-01-18 17:33 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982200 / RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982200) |  | 0 / 1 | [] |  |  | WO.32982200 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 973 | 32982202 | RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 32982202 / RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982202) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982202 / RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS (32982202) |  | 0 / 1 | [] |  |  | WO.32982202 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 974 | 32982203 | RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 32982203 / RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982203) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 16:39 | 1900-01-18 17:54 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32982203 / RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. (32982203) |  | 0 / 1 | [] |  |  | WO.32982203 | 19.Jul.2026 | -19d, 16h | 2026-07-19 | D
| 978 | 32983857 | PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 12:00 | 1900-01-14 22:33 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) |  | 0 / 1 | [] |  |  | WO.32983857 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 979 | 32983861 | PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) |  | 0 / 1 | [] |  |  | WO.32983861 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 984 | 32983896 | LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION | 32983896 / LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION (32983896) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32983896 / LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION (32983896) |  | 0 / 1 | [] |  |  | WO.32983896 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 987 | 32983929 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) |  | 0 / 1 | [] |  |  | WO.32983929 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 988 | 32983937 | PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. | 32983937 / PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. (32983937) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 20.Jul.2026 15:30 | 1900-01-17 19:03 |  | 0.020833 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983937 / PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. (32983937) |  | 0 / 1 | [] |  |  | WO.32983937 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 989 | 32983944 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. | 32983944 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. (32983944) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983944 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. (32983944) |  | 0 / 1 | [] |  |  | WO.32983944 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 991 | 32983948 | OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 05:25 | 1900-01-15 05:08 |  | 0.52083 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) |  | 0 / 1 | [] |  |  | WO.32983948 | 20.Jul.2026 | -19d, 3h | 2026-07-20 | D
| 992 | 32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 32983996 / CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. (32983996) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">15</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.35417 | 17.Jul.2026 22:00 | 0.11806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32983996 / CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. (32983996) |  | 0 / 1 | [] |  |  | WO.32983996 | 20.Jul.2026 | -19d, 2h | 2026-07-20 | D
| 996 | 32984174 | PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) |  | 0 / 1 | [] |  |  | WO.32984174 | 20.Jul.2026 | -19d, 2h | 2026-07-20 | D
| 997 | 32984360 | FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 09:34 | 1900-01-08 00:59 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) |  | 0 / 1 | [] |  |  | WO.32984360 | 20.Jul.2026 | -19d, 1h | 2026-07-20 | D
| 999 | 32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 32984263 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS (32984263) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 06:13 | 1900-01-16 04:20 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32984263 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS (32984263) |  | 0 / 1 | [] |  |  | WO.32984263 | 20.Jul.2026 | -19d, 1h | 2026-07-20 | D
| 1003 | 32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 32984585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS (32984585) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 01:43 | 1900-01-17 08:50 |  | 0.47917 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32984585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS (32984585) |  | 0 / 1 | [] |  |  | WO.32984585 | 20.Jul.2026 | -19d, 53m | 2026-07-20 | D
| 1004 | 32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 32984729 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. (32984729) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984729 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. (32984729) |  | 0 / 1 | [] |  |  | WO.32984729 | 20.Jul.2026 | -19d, 11m | 2026-07-20 | D
| 1005 | 32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 32984742 / CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. (32984742) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984742 / CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. (32984742) |  | 0 / 1 | [] |  |  | WO.32984742 | 20.Jul.2026 | -19d, 9m | 2026-07-20 | D
| 1006 | 32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 32984765 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. (32984765) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984765 / CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. (32984765) |  | 0 / 1 | [] |  |  | WO.32984765 | 20.Jul.2026 | -19d, 2m | 2026-07-20 | D
| 1007 | 32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) |  | 0 / 1 | [] |  |  | WO.32984781 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1008 | 32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) |  | 0 / 1 | [] |  |  | WO.32984766 | 20.Jul.2026 | -19d, 2m | 2026-07-20 | D
| 1010 | 32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) |  | 0 / 1 | [] |  |  | WO.32984820 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1011 | 32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) |  | 0 / 1 | [] |  |  | WO.32984829 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1012 | 32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 26.Jul.2026 20:20 | 1900-01-11 14:13 |  | 0.59722 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) |  | 0 / 1 | [] |  |  | WO.32984848 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1014 | 32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 32984906 / CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 (32984906) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 04:00 | 1900-01-17 06:33 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 38 |  | [] |  |  |  |  | 32984906 / CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 (32984906) |  | 0 / 1 | [] |  |  | WO.32984906 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1019 | 32984986 | AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) |  | 0 / 1 | [] |  |  | WO.32984986 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1021 | 32985000 | AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE | 32985000 / AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE (32985000) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985000 / AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE (32985000) |  | 0 / 1 | [] |  |  | WO.32985000 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1027 | 32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) |  | 0 / 1 | [] |  |  | WO.32985067 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1029 | 32985072 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:00 | 1900-01-13 04:33 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) |  | 0 / 1 | [] |  |  | WO.32985072 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1030 | 32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 32985083 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985083) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985083 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985083) |  | 0 / 1 | [] |  |  | WO.32985083 | 20.Jul.2026 | -18d, 23h | 2026-07-20 | D
| 1031 | 32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 32985088 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985088) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985088 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. (32985088) |  | 0 / 1 | [] |  |  | WO.32985088 | 20.Jul.2026 | -18d, 22h | 2026-07-20 | D
| 1036 | 32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 32985304 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985304) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985304 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985304) |  | 0 / 1 | [] |  |  | WO.32985304 | 20.Jul.2026 | -18d, 20h | 2026-07-20 | D
| 1038 | 32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 32985332 / CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY (32985332) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985332 / CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY (32985332) |  | 0 / 1 | [] |  |  | WO.32985332 | 20.Jul.2026 | -18d, 20h | 2026-07-20 | D
| 1045 | 32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 32985343 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY (32985343) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985343 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY (32985343) |  | 0 / 1 | [] |  |  | WO.32985343 | 20.Jul.2026 | -18d, 20h | 2026-07-20 | D
| 1049 | 32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 32985350 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985350) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985350 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT (32985350) |  | 0 / 1 | [] |  |  | WO.32985350 | 20.Jul.2026 | -18d, 20h | 2026-07-20 | D
| 1053 | 32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 32985354 / CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT (32985354) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985354 / CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT (32985354) |  | 0 / 1 | [] |  |  | WO.32985354 | 20.Jul.2026 | -18d, 20h | 2026-07-20 | D
| 1061 | 32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 32985832 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, (32985832) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] |  |  |  |  | 32985832 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, (32985832) |  | 0 / 1 | [] |  |  | WO.32985832 | 20.Jul.2026 | -18d, 16h | 2026-07-20 | D
| 1062 | 32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 32985833 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. (32985833) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-23 |  | [] |  |  |  |  | 32985833 / CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. (32985833) |  | 0 / 1 | [] |  |  | WO.32985833 | 20.Jul.2026 | -18d, 16h | 2026-07-20 | D
| 1063 | 32985836 | RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 27.Jul.2026 10:12 | 1900-01-11 00:21 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) |  | 0 / 1 | [] |  |  | WO.32985836 | 20.Jul.2026 | -18d, 15h | 2026-07-20 | D
| 1064 | 32985860 | L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 27.Jul.2026 10:13 | 1900-01-11 00:20 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) |  | 0 / 1 | [] |  |  | WO.32985860 | 20.Jul.2026 | -18d, 15h | 2026-07-20 | D
| 1075 | 32987066 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 32987066 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY (32987066) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32987066 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY (32987066) |  | 0 / 1 | [] |  |  | WO.32987066 | 21.Jul.2026 | -18d, 4h | 2026-07-21 | D
| 1077 | 32987097 | CABIN FLOOR PANELS - CAB -CALLBACK COCKPIT PANEL # 211FF AND CABIN FLOOR PANEL NO: 232WF, 241EF, 241KF, 241LF, 242FF, 242KF, AND 242LF REQUIRES REMOVAL FOR ACCESS. | 32987097 / CABIN FLOOR PANELS - CAB -CALLBACK COCKPIT PANEL # 211FF AND CABIN FLOOR PANEL NO: 232WF, 241EF, 241KF, 241LF, 242FF, 242KF, AND 242LF REQUIRES REMOVAL FOR ACCESS. (32987097) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 11:49 | 1900-01-15 22:44 |  | 1899-12-31 12:30 | Idle | 0 | T: 0; O: 0; C: 0 | 32-33 |  | [] |  |  |  |  | 32987097 / CABIN FLOOR PANELS - CAB -CALLBACK COCKPIT PANEL # 211FF AND CABIN FLOOR PANEL NO: 232WF, 241EF, 241KF, 241LF, 242FF, 242KF, AND 242LF REQUIRES REMOVAL FOR ACCESS. (32987097) |  | 0 / 1 | [] |  |  | WO.32987097 | 21.Jul.2026 | -18d, 4h | 2026-07-21 | D
| 1078 | 32987238 | LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. | 32987238 / LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. (32987238) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 16:54 | 1900-01-14 17:39 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32987238 / LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. (32987238) |  | 0 / 1 | [] |  |  | WO.32987238 | 21.Jul.2026 | -18d, 3h | 2026-07-21 | D
| 1082 | 94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | 94844868 / L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. (94844868) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 15.Jul.2026 17:19 | 1900-01-22 17:14 |  | 1899-12-31 11:00 | Idle | 0 | T: 0; O: 0; C: 0 | 52 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844868 / L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. (94844868) |  | 0 / 5 | [] |  |  | WO.94844868 | 16'513 | 199 | 2026-10-07 | C
| 1083 | 32968390 | S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) | 32968390 / S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) (32968390) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.024306 | 17.Jul.2026 22:00 | 0.017361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] |  |  |  |  | 32968390 / S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) (32968390) |  | 0 / 3 | [] |  |  | ME.32968390 | 15.Aug.2026 | 7 | 2026-08-15 | D
| 1084 | 32913240 | S28-R10083/A320,321 REPETITIVE FUEL SUMP AND DRAIN - WATER REMOVAL | 32913240 / S28-R10083/A320,321 REPETITIVE FUEL SUMP AND DRAIN - WATER REMOVAL (32913240) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 12:57 | 1900-01-15 21:36 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 28 |  | [] |  |  |  |  | 32913240 / S28-R10083/A320,321 REPETITIVE FUEL SUMP AND DRAIN - WATER REMOVAL (32913240) |  | 0 / 2 | [] |  |  | ME.32913240 | 19.Jul.2026 | -20 | 2026-07-19 | D
| 1085 | 32984296 | S34-R10187/A320/A321 - T2CAS - UPDATE OF TERRAIN DATABASE INTO VERSION 227 | 32984296 / S34-R10187/A320/A321 - T2CAS - UPDATE OF TERRAIN DATABASE INTO VERSION 227 (32984296) | Document | PJED | <html><span style="font-weight: normal;">No part requests</span></html> | 0.055556 | 17.Jul.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34 |  | [] |  |  |  |  | 32984296 / S34-R10187/A320/A321 - T2CAS - UPDATE OF TERRAIN DATABASE INTO VERSION 227 (32984296) |  | 0 / 3 | [] |  |  | ME.32984296 | 05.Aug.2026 | -3 | 2026-08-05 | D
| 1086 | 32974165 | S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 32974165 / S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE (32974165) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.010417 | 17.Jul.2026 22:00 | 0.010417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 32974165 / S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE (32974165) |  | 0 / 2 | [] |  |  | ME.32974165 | 27.Jul.2026 | -12 | 2026-07-27 | D
| 1100 | 32987976 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET IDENTIFICATION LABEL FOUND TORN AND NET STRIPS FOUND DETACHED. | 32987976 / PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET IDENTIFICATION LABEL FOUND TORN AND NET STRIPS FOUND DETACHED. (32987976) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32987976 / PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET IDENTIFICATION LABEL FOUND TORN AND NET STRIPS FOUND DETACHED. (32987976) |  | 0 / 1 | [] |  |  | WO.32987976 | 21.Jul.2026 | -18d, 2h | 2026-07-21 | D
| 1101 | 32987983 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET, IDENTIFICATION LABEL AND DIVIDER NET FOUND EXCESSIVE DIRTY WITH STAIN MARKS. | 32987983 / PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET, IDENTIFICATION LABEL AND DIVIDER NET FOUND EXCESSIVE DIRTY WITH STAIN MARKS. (32987983) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32987983 / PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET, IDENTIFICATION LABEL AND DIVIDER NET FOUND EXCESSIVE DIRTY WITH STAIN MARKS. (32987983) |  | 0 / 1 | [] |  |  | WO.32987983 | 21.Jul.2026 | -18d, 2h | 2026-07-21 | D
| 1106 | 32988202 | RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS | 32988202 / RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS (32988202) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-24 |  | [] |  |  |  |  | 32988202 / RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS (32988202) |  | 0 / 1 | [] |  | E27ACT325RH | WO.32988202 | 21.Jul.2026 | -18d, 1h | 2026-07-21 | D
| 1107 | 32988329 | PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ | 32988329 / PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ (32988329) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988329 / PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ (32988329) |  | 0 / 1 | [] |  |  | WO.32988329 | 21.Jul.2026 | -18d, 1h | 2026-07-21 | D
| 1108 | 32988444 | PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA | 32988444 / PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA (32988444) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988444 / PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA (32988444) |  | 0 / 1 | [] |  |  | WO.32988444 | 21.Jul.2026 | -18d, 55m | 2026-07-21 | D
| 1112 | 32988660 | PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS | 32988660 / PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS (32988660) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988660 / PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS (32988660) |  | 0 / 1 | [] |  |  | WO.32988660 | 21.Jul.2026 | -18d, 14m | 2026-07-21 | D
| 1113 | 32988687 | CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ | 32988687 / CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ (32988687) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988687 / CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ (32988687) |  | 0 / 1 | [] |  |  | WO.32988687 | 21.Jul.2026 | -18d, 10m | 2026-07-21 | D
| 1114 | 32988706 | CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED | 32988706 / CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED (32988706) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988706 / CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED (32988706) |  | 0 / 1 | [] |  |  | WO.32988706 | 21.Jul.2026 | -18d, 9m | 2026-07-21 | D
| 1115 | 32988779 | CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA | 32988779 / CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA (32988779) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 04.Aug.2026 12:29 | 1900-01-02 22:04 |  | 0.29167 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988779 / CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA (32988779) |  | 0 / 1 | [] |  |  | WO.32988779 | 21.Jul.2026 | -18d | 2026-07-21 | D
| 1116 | 32988786 | PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA | 32988786 / PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA (32988786) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988786 / PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA (32988786) |  | 0 / 1 | [] |  |  | WO.32988786 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1118 | 32988998 | PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. | 32988998 / PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. (32988998) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-18 |  | [] |  |  |  |  | 32988998 / PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. (32988998) |  | 0 / 1 | [] |  |  | WO.32988998 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1121 | 32988850 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY 8 EA AIR FLAP SEAL DETERIORATED. | 32988850 / CAB - NO CALLBACK - FWD GALLEY FWD GALLEY 8 EA AIR FLAP SEAL DETERIORATED. (32988850) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988850 / CAB - NO CALLBACK - FWD GALLEY FWD GALLEY 8 EA AIR FLAP SEAL DETERIORATED. (32988850) |  | 0 / 1 | [] |  |  | WO.32988850 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1122 | 32989105 | PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. | 32989105 / PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. (32989105) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 10:16 | 1900-01-08 00:17 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989105 / PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. (32989105) |  | 0 / 1 | [] |  |  | WO.32989105 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1123 | 32989125 | PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. | 32989125 / PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. (32989125) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 10:06 | 1900-01-08 00:27 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989125 / PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. (32989125) |  | 0 / 1 | [] |  |  | WO.32989125 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1124 | 32989133 | CAB - NO CALL BACK - GLLY G2 GALLEY SEVERAL RUB STRIP FADED | 32989133 / CAB - NO CALL BACK - GLLY G2 GALLEY SEVERAL RUB STRIP FADED (32989133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989133 / CAB - NO CALL BACK - GLLY G2 GALLEY SEVERAL RUB STRIP FADED (32989133) |  | 0 / 1 | [] |  |  | WO.32989133 | 21.Jul.2026 | -17d, 23h | 2026-07-21 | D
| 1126 | 32989457 | CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. | 32989457 / CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. (32989457) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:30 | 1900-01-15 06:03 |  | 0.10417 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989457 / CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. (32989457) |  | 0 / 1 | [] |  |  | WO.32989457 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1127 | 32989455 | CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP | 32989455 / CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP (32989455) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 32989455 / CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP (32989455) |  | 0 / 1 | [] |  |  | WO.32989455 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1128 | 32989472 | CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING | 32989472 / CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING (32989472) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 32989472 / CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING (32989472) |  | 0 / 1 | [] |  |  | WO.32989472 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1129 | 32989475 | AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. | 32989475 / AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. (32989475) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 07:37 | 1900-01-16 02:56 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989475 / AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. (32989475) |  | 0 / 1 | [] |  |  | WO.32989475 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1131 | 32989482 | CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT | 32989482 / CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT (32989482) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989482 / CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT (32989482) |  | 0 / 1 | [] |  |  | WO.32989482 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1132 | 32989491 | CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. | 32989491 / CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. (32989491) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989491 / CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. (32989491) |  | 0 / 1 | [] |  |  | WO.32989491 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1133 | 32989492 | CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT | 32989492 / CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT (32989492) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989492 / CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT (32989492) |  | 0 / 1 | [] |  |  | WO.32989492 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1134 | 32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 32989497 / CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED (32989497) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989497 / CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED (32989497) |  | 0 / 1 | [] |  |  | WO.32989497 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1135 | 32989529 | FWD GARGO COMPT=====FS=====NO CALL BACK FWD CARGO COMPARTMENT CEILING, SIDE WALL AND SLOPY AREA DIRTY WITH ACCUMULATED DUST | 32989529 / FWD GARGO COMPT=====FS=====NO CALL BACK FWD CARGO COMPARTMENT CEILING, SIDE WALL AND SLOPY AREA DIRTY WITH ACCUMULATED DUST (32989529) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989529 / FWD GARGO COMPT=====FS=====NO CALL BACK FWD CARGO COMPARTMENT CEILING, SIDE WALL AND SLOPY AREA DIRTY WITH ACCUMULATED DUST (32989529) |  | 0 / 1 | [] |  |  | WO.32989529 | 21.Jul.2026 | -17d, 20h | 2026-07-21 | D
| 1141 | 32989728 | CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING | 32989728 / CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING (32989728) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989728 / CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING (32989728) |  | 0 / 1 | [] |  |  | WO.32989728 | 21.Jul.2026 | -17d, 18h | 2026-07-21 | D
| 1142 | 32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 32989743 / CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING (32989743) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989743 / CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING (32989743) |  | 0 / 1 | [] |  |  | WO.32989743 | 21.Jul.2026 | -17d, 18h | 2026-07-21 | D
| 1144 | 32989797 | S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE | 32989797 / S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE (32989797) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 26.Jul.2026 20:00 | 1900-01-11 14:33 |  | 0.18056 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989797 / S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE (32989797) |  | 0 / 1 | [] |  |  | WO.32989797 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1145 | 32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 32989800 / CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING (32989800) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989800 / CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING (32989800) |  | 0 / 1 | [] |  |  | WO.32989800 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1146 | 32989825 | CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING | 32989825 / CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING (32989825) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989825 / CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING (32989825) |  | 0 / 1 | [] |  |  | WO.32989825 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1147 | 32989853 | CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER | 32989853 / CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER (32989853) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 23.Jul.2026 03:33 | 1900-01-15 07:00 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989853 / CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER (32989853) |  | 0 / 1 | [] |  |  | WO.32989853 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1149 | 32989860 | CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING | 32989860 / CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING (32989860) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989860 / CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING (32989860) |  | 0 / 1 | [] |  |  | WO.32989860 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1150 | 32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 32989874 / CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING (32989874) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989874 / CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING (32989874) |  | 0 / 1 | [] |  |  | WO.32989874 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1154 | 32989943 | CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. | 32989943 / CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. (32989943) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989943 / CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. (32989943) |  | 0 / 1 | [] |  |  | WO.32989943 | 21.Jul.2026 | -17d, 17h | 2026-07-21 | D
| 1156 | 32989952 | CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. | 32989952 / CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. (32989952) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989952 / CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. (32989952) |  | 0 / 1 | [] |  |  | WO.32989952 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1158 | 32989962 | #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 32989962 / #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32989962) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 11:00 | 1900-01-15 23:33 |  | 0.41667 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989962 / #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32989962) |  | 0 / 1 | [] |  | #2 ENG | WO.32989962 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1160 | 32989963 | #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. | 32989963 / #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. (32989963) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 13:30 | 1900-01-13 21:03 |  | 0.25 | Idle | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989963 / #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. (32989963) |  | 0 / 1 | [] |  | #2 ENG | WO.32989963 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1163 | 32989966 | #2 ENG - FAN FR ASSY - HMU LINES CLAMPS - AP - RII #2 ENG FAN FRAME ASSEMBLY AT 06:00 O`CLOCK POSTION FOUND HYDROMECHANICAL UNIT (HMU) SOV FUEL LINES (ROD AND HEAD LINES) CLAMPS CORRODED . | 32989966 / #2 ENG - FAN FR ASSY - HMU LINES CLAMPS - AP - RII #2 ENG FAN FRAME ASSEMBLY AT 06:00 O`CLOCK POSTION FOUND HYDROMECHANICAL UNIT (HMU) SOV FUEL LINES (ROD AND HEAD LINES) CLAMPS CORRODED . (32989966) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 24-92 |  | [] |  |  |  |  | 32989966 / #2 ENG - FAN FR ASSY - HMU LINES CLAMPS - AP - RII #2 ENG FAN FRAME ASSEMBLY AT 06:00 O`CLOCK POSTION FOUND HYDROMECHANICAL UNIT (HMU) SOV FUEL LINES (ROD AND HEAD LINES) CLAMPS CORRODED . (32989966) |  | 0 / 1 | [] |  | #2 ENG | WO.32989966 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1164 | 32989967 | #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. | 32989967 / #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. (32989967) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 24-92 |  | [] |  |  |  |  | 32989967 / #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. (32989967) |  | 0 / 1 | [] |  | #2 ENG | WO.32989967 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1165 | 32989971 | #2 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #2 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. | 32989971 / #2 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #2 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (32989971) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 08:40 | 1900-01-11 01:53 |  | 0.0069444 | Idle | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32989971 / #2 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #2 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (32989971) |  | 0 / 1 | [] |  | #2 ENG | WO.32989971 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1166 | 32989973 | #2 ENG - R/H T/REV - HCU - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FWD FACE FOUND HYDRAULIC CONTROL UNIT (HCU) LEAKING . | 32989973 / #2 ENG - R/H T/REV - HCU - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FWD FACE FOUND HYDRAULIC CONTROL UNIT (HCU) LEAKING . (32989973) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989973 / #2 ENG - R/H T/REV - HCU - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FWD FACE FOUND HYDRAULIC CONTROL UNIT (HCU) LEAKING . (32989973) |  | 0 / 1 | [] |  | #2 ENG | WO.32989973 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1169 | 32989982 | #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... | 32989982 / #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... (32989982) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 17:00 | 1900-01-10 17:33 |  | 0.052083 | Idle | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989982 / #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... (32989982) |  | 0 / 1 | [] |  | #2 ENG | WO.32989982 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1170 | 32989993 | #2 ENG - L/H TREV - THERMAL BLANKET - SM - RII #2 ENG L/H THRUST REVERSER INNER SIDE FOUND THERMAL BLANKET TORN ( T/REV CHAFFING AGAINST T495 THERMOCOUPLE HARNESS AT 08:00 OCLOCK POSITION) DISTANCE TO NEAREST EDGE :- 2.5 INCH. DIM:- L= 2.31 INCH.... | 32989993 / #2 ENG - L/H TREV - THERMAL BLANKET - SM - RII #2 ENG L/H THRUST REVERSER INNER SIDE FOUND THERMAL BLANKET TORN ( T/REV CHAFFING AGAINST T495 THERMOCOUPLE HARNESS AT 08:00 OCLOCK POSITION) DISTANCE TO NEAREST EDGE :- 2.5 INCH. DIM:- L= 2.31 INCH.... (32989993) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 18:15 | 1900-01-10 16:18 |  | 0.010417 | Idle | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989993 / #2 ENG - L/H TREV - THERMAL BLANKET - SM - RII #2 ENG L/H THRUST REVERSER INNER SIDE FOUND THERMAL BLANKET TORN ( T/REV CHAFFING AGAINST T495 THERMOCOUPLE HARNESS AT 08:00 OCLOCK POSITION) DISTANCE TO NEAREST EDGE :- 2.5 INCH. DIM:- L= 2.31 INCH.... (32989993) |  | 0 / 1 | [] |  | #2 ENG | WO.32989993 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1171 | 32989995 | RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. | 32989995 / RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. (32989995) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 03:41 | 1900-01-16 06:52 |  | 1899-12-31 11:30 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989995 / RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. (32989995) |  | 0 / 1 | [] |  |  | WO.32989995 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1172 | 32989994 | #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... | 32989994 / #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... (32989994) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 11:00 | 1900-01-10 23:33 |  | 0.083333 | Idle | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989994 / #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... (32989994) |  | 0 / 1 | [] |  | #2 ENG | WO.32989994 | 21.Jul.2026 | -17d, 16h | 2026-07-21 | D
| 1174 | 32990008 | CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS | 32990008 / CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS (32990008) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] |  |  |  |  | 32990008 / CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS (32990008) |  | 0 / 1 | [] |  |  | WO.32990008 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1175 | 32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL | 32990007 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL (32990007) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990007 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL (32990007) |  | 0 / 1 | [] |  |  | WO.32990007 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1176 | 32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 32990011 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L (32990011) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990011 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L (32990011) |  | 0 / 1 | [] |  |  | WO.32990011 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1177 | 32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 32990012 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C (32990012) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990012 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C (32990012) |  | 0 / 1 | [] |  |  | WO.32990012 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1178 | 32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 32990013 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C (32990013) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990013 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C (32990013) |  | 0 / 1 | [] |  |  | WO.32990013 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1179 | 32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B | 32990020 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B (32990020) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990020 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B (32990020) |  | 0 / 1 | [] |  |  | WO.32990020 | 21.Jul.2026 | -17d, 15h | 2026-07-21 | D
| 1186 | 32990048 | #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... | 32990048 / #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... (32990048) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 05:00 | 1900-01-11 05:33 |  | 0.125 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990048 / #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... (32990048) |  | 0 / 1 | [] |  | #1 ENG | WO.32990048 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1187 | 32990053 | #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... | 32990053 / #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... (32990053) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 08:00 | 1900-01-11 02:33 |  | 0.55486 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990053 / #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... (32990053) |  | 0 / 1 | [] |  | #1 ENG | WO.32990053 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1188 | 32990054 | #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... | 32990054 / #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... (32990054) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 11:00 | 1900-01-15 23:33 |  | 0.41667 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990054 / #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... (32990054) |  | 0 / 1 | [] |  | #1 ENG | WO.32990054 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1189 | 32990067 | #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 32990067 / #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32990067) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 15:00 | 1900-01-15 19:33 |  | 0.74306 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990067 / #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32990067) |  | 0 / 1 | [] |  | #1 ENG | WO.32990067 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1191 | 32990169 | #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. | 32990169 / #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. (32990169) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 04:22 | 1900-01-07 06:11 |  | 0.125 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990169 / #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. (32990169) |  | 0 / 1 | [] |  | #1 ENG | WO.32990169 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1192 | 32990170 | #1 ENG - R/H FAN COWL - PRESS DR - AP - RII #1 ENG R/H FAN COWL INNER SIDE FOUND PRESSURE RELIEF DOOR UPPER AND LOWER SPRING LOADED ARMS HINGES RUSTED AND UPPER SPRING LOADED ARM LANYARD FWD END CHAFFED-OFF AND SPRING LOADED ARM END GOUGED. | 32990170 / #1 ENG - R/H FAN COWL - PRESS DR - AP - RII #1 ENG R/H FAN COWL INNER SIDE FOUND PRESSURE RELIEF DOOR UPPER AND LOWER SPRING LOADED ARMS HINGES RUSTED AND UPPER SPRING LOADED ARM LANYARD FWD END CHAFFED-OFF AND SPRING LOADED ARM END GOUGED. (32990170) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990170 / #1 ENG - R/H FAN COWL - PRESS DR - AP - RII #1 ENG R/H FAN COWL INNER SIDE FOUND PRESSURE RELIEF DOOR UPPER AND LOWER SPRING LOADED ARMS HINGES RUSTED AND UPPER SPRING LOADED ARM LANYARD FWD END CHAFFED-OFF AND SPRING LOADED ARM END GOUGED. (32990170) |  | 0 / 1 | [] |  | #1 ENG | WO.32990170 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1193 | 32990171 | #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... | 32990171 / #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... (32990171) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 09:31 | 1900-01-10 01:02 |  | 0.013889 | Idle | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990171 / #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... (32990171) |  | 0 / 1 | [] |  | #1 ENG | WO.32990171 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1195 | 32990192 | #1 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #1 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (R/H T/REV TEFLON SEAL DETACHED FROM UPPER AND LOWER SIDE). | 32990192 / #1 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #1 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (R/H T/REV TEFLON SEAL DETACHED FROM UPPER AND LOWER SIDE). (32990192) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 08:30 | 1900-01-11 02:03 |  | 0.013889 | Idle | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32990192 / #1 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #1 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (R/H T/REV TEFLON SEAL DETACHED FROM UPPER AND LOWER SIDE). (32990192) |  | 0 / 1 | [] |  | #1 ENG | WO.32990192 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1196 | 32990196 | #1 ENG - L/H T/REV - LOWER BLOCKER DR - AP - NO CALL BACK #1 ENG L/H THRUST REVERSER FOUND LOWER BLOCKER DOOR ACTUATOR WITH HEAVY LEAK AT ROD END. | 32990196 / #1 ENG - L/H T/REV - LOWER BLOCKER DR - AP - NO CALL BACK #1 ENG L/H THRUST REVERSER FOUND LOWER BLOCKER DOOR ACTUATOR WITH HEAVY LEAK AT ROD END. (32990196) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.0625 | 01.Aug.2026 05:45 | 1900-01-06 04:48 |  | 0.041667 | Idle | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32990196 / #1 ENG - L/H T/REV - LOWER BLOCKER DR - AP - NO CALL BACK #1 ENG L/H THRUST REVERSER FOUND LOWER BLOCKER DOOR ACTUATOR WITH HEAVY LEAK AT ROD END. (32990196) |  | 0 / 1 | [] |  | #1 ENG | WO.32990196 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1198 | 32990219 | #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... | 32990219 / #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... (32990219) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 15:00 | 1900-01-10 19:33 |  | 0.083333 | Idle | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32990219 / #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... (32990219) |  | 0 / 1 | [] |  | #1 ENG | WO.32990219 | 21.Jul.2026 | -17d, 14h | 2026-07-21 | D
| 1199 | 32991206 | CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA | 32991206 / CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA (32991206) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 02.Aug.2026 12:06 | 1900-01-04 22:27 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32991206 / CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA (32991206) |  | 0 / 1 | [] |  |  | WO.32991206 | 22.Jul.2026 | -17d, 4h | 2026-07-22 | D
| 1200 | 32991276 | AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. | 32991276 / AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. (32991276) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:33 | 1900-01-16 03:00 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991276 / AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. (32991276) |  | 0 / 1 | [] |  |  | WO.32991276 | 22.Jul.2026 | -17d, 4h | 2026-07-22 | D
| 1201 | 32991499 | PNT - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. | 32991499 / PNT - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. (32991499) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991499 / PNT - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. (32991499) |  | 0 / 1 | [] |  |  | WO.32991499 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1202 | 32991511 | CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | 32991511 / CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. (32991511) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991511 / CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. (32991511) |  | 0 / 1 | [] |  |  | WO.32991511 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1204 | 32991518 | FINDING (NRC) TASKCARD ZL-531-02-1-001 (01) LH WING AP-- NO CALLBACK LH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT. | 32991518 / FINDING (NRC) TASKCARD ZL-531-02-1-001 (01) LH WING AP-- NO CALLBACK LH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT. (32991518) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 09:26 | 1900-01-08 01:07 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991518 / FINDING (NRC) TASKCARD ZL-531-02-1-001 (01) LH WING AP-- NO CALLBACK LH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT. (32991518) |  | 0 / 1 | [] |  |  | WO.32991518 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1205 | 32991527 | CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP | 32991527 / CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP (32991527) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991527 / CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP (32991527) |  | 0 / 1 | [] |  |  | WO.32991527 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1206 | 32991534 | PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. | 32991534 / PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. (32991534) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991534 / PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. (32991534) |  | 0 / 1 | [] |  |  | WO.32991534 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1207 | 32991563 | RH WING -- FT REFER TO TC # 572020-01-1-002, 572040-01-2-002, 572139-01-2-002, 572140-01-2-002 AND 572161-01-11-002 REQUIRE TO REMOVE RH WING FUEL TANK ACCESS PANELS - 640AB, 640BB , 640CB, 640DB, 640EB, 640FB, 640GB - 640HB, 640JB, 640KB, 640LB... | 32991563 / RH WING -- FT REFER TO TC # 572020-01-1-002, 572040-01-2-002, 572139-01-2-002, 572140-01-2-002 AND 572161-01-11-002 REQUIRE TO REMOVE RH WING FUEL TANK ACCESS PANELS - 640AB, 640BB , 640CB, 640DB, 640EB, 640FB, 640GB - 640HB, 640JB, 640KB, 640LB... (32991563) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 05:30 | 1900-01-16 05:03 |  | 1900-01-04 23:19 | Idle | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  |  | 32991563 / RH WING -- FT REFER TO TC # 572020-01-1-002, 572040-01-2-002, 572139-01-2-002, 572140-01-2-002 AND 572161-01-11-002 REQUIRE TO REMOVE RH WING FUEL TANK ACCESS PANELS - 640AB, 640BB , 640CB, 640DB, 640EB, 640FB, 640GB - 640HB, 640JB, 640KB, 640LB... (32991563) |  | 0 / 15 | [] |  |  | WO.32991563 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1209 | 32991584 | LH WING -- FT REFER TO TC # 572020-01-1-001, 572040-01-2-001, 572139-01-2-001, 572140-01-2-001 AND 572161-01-11-001 REQUIRE TO REMOVE LH WING FUEL TANK ACCESS PANELS - 540AB, 540BB , 540CB, 540DB, 540EB, 540FB, 540GB - 540HB, 540JB, 540KB, 540LB... | 32991584 / LH WING -- FT REFER TO TC # 572020-01-1-001, 572040-01-2-001, 572139-01-2-001, 572140-01-2-001 AND 572161-01-11-001 REQUIRE TO REMOVE LH WING FUEL TANK ACCESS PANELS - 540AB, 540BB , 540CB, 540DB, 540EB, 540FB, 540GB - 540HB, 540JB, 540KB, 540LB... (32991584) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:19 | 1900-01-16 04:14 |  | 1900-01-03 14:35 | Idle | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  |  | 32991584 / LH WING -- FT REFER TO TC # 572020-01-1-001, 572040-01-2-001, 572139-01-2-001, 572140-01-2-001 AND 572161-01-11-001 REQUIRE TO REMOVE LH WING FUEL TANK ACCESS PANELS - 540AB, 540BB , 540CB, 540DB, 540EB, 540FB, 540GB - 540HB, 540JB, 540KB, 540LB... (32991584) |  | 0 / 15 | [] |  |  | WO.32991584 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1210 | 32991594 | FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--NO C/B RH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT . | 32991594 / FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--NO C/B RH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT . (32991594) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 07:19 | 1900-01-10 03:14 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991594 / FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--NO C/B RH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT . (32991594) |  | 0 / 1 | [] |  |  | WO.32991594 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1211 | 32991646 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. | 32991646 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. (32991646) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:45 | 1900-01-16 02:48 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32991646 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. (32991646) |  | 0 / 1 | [] |  |  | WO.32991646 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1212 | 32991651 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. | 32991651 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. (32991651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:48 | 1900-01-16 02:45 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32991651 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. (32991651) |  | 0 / 1 | [] |  |  | WO.32991651 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1213 | 32991622 | FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--CALLBACK FLAP TRACK NO#2 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 32991622 / FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--CALLBACK FLAP TRACK NO#2 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991622) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991622 / FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--CALLBACK FLAP TRACK NO#2 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991622) |  | 0 / 1 | [] |  |  | WO.32991622 | 22.Jul.2026 | -17d, 3h | 2026-07-22 | D
| 1214 | 32991955 | FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP--NO CALLBACK RH WING FLAP TRACK NO#3 AFT BONDING WIRE WITH CUT . | 32991955 / FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP--NO CALLBACK RH WING FLAP TRACK NO#3 AFT BONDING WIRE WITH CUT . (32991955) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 09:10 | 1900-01-08 01:23 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991955 / FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP--NO CALLBACK RH WING FLAP TRACK NO#3 AFT BONDING WIRE WITH CUT . (32991955) |  | 0 / 1 | [] |  |  | WO.32991955 | 22.Jul.2026 | -17d, 2h | 2026-07-22 | D
| 1215 | 32991957 | FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP-- CALLBACK FLAP TRACK NO#3 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 32991957 / FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP-- CALLBACK FLAP TRACK NO#3 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991957) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991957 / FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP-- CALLBACK FLAP TRACK NO#3 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991957) |  | 0 / 1 | [] |  |  | WO.32991957 | 22.Jul.2026 | -17d, 2h | 2026-07-22 | D
| 1216 | 32991972 | FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK FLAP TRACK NO#4 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 32991972 / FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK FLAP TRACK NO#4 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991972) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991972 / FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK FLAP TRACK NO#4 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. (32991972) |  | 0 / 1 | [] |  |  | WO.32991972 | 22.Jul.2026 | -17d, 1h | 2026-07-22 | D
| 1217 | 32991973 | FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK RH WING FLAP TRACK NO#4 AFT BONDING WIRE WITH CUT . | 32991973 / FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK RH WING FLAP TRACK NO#4 AFT BONDING WIRE WITH CUT . (32991973) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 09:18 | 1900-01-08 01:15 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32991973 / FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK RH WING FLAP TRACK NO#4 AFT BONDING WIRE WITH CUT . (32991973) |  | 0 / 1 | [] |  |  | WO.32991973 | 22.Jul.2026 | -17d, 1h | 2026-07-22 | D
| 1218 | 32992461 | MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. | 32992461 / MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. (32992461) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 03:30 | 1900-01-15 07:03 |  | 0.27778 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992461 / MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. (32992461) |  | 0 / 1 | [] |  |  | WO.32992461 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1219 | 32992488 | CAB - CALL BACK - AFT GLLY AFT GALLEY REQUIRE REMOVAL FOR ACCESS | 32992488 / CAB - CALL BACK - AFT GLLY AFT GALLEY REQUIRE REMOVAL FOR ACCESS (32992488) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 10:21 | 1900-01-16 00:12 |  | 1899-12-31 21:30 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32992488 / CAB - CALL BACK - AFT GLLY AFT GALLEY REQUIRE REMOVAL FOR ACCESS (32992488) |  | 0 / 1 | [] |  |  | WO.32992488 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1220 | 32992489 | CAB - CALLBACK - G1 GALLEY G1 GALLEY REQUIRE REMOVAL FOR ACCESS. | 32992489 / CAB - CALLBACK - G1 GALLEY G1 GALLEY REQUIRE REMOVAL FOR ACCESS. (32992489) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 18:47 | 1900-01-15 15:46 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992489 / CAB - CALLBACK - G1 GALLEY G1 GALLEY REQUIRE REMOVAL FOR ACCESS. (32992489) |  | 0 / 1 | [] |  |  | WO.32992489 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1221 | 32992493 | CAB - CALLBACK - LAV A "LAVATORY A" REQUIRE REMOVAL FOR ACCESS. | 32992493 / CAB - CALLBACK - LAV A "LAVATORY A" REQUIRE REMOVAL FOR ACCESS. (32992493) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 00:51 | 1900-01-10 09:42 |  | 1899-12-31 08:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992493 / CAB - CALLBACK - LAV A "LAVATORY A" REQUIRE REMOVAL FOR ACCESS. (32992493) |  | 0 / 1 | [] |  |  | WO.32992493 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1222 | 32992492 | CAB - CALL BACK - LAV E LAVATORY "E" REQUIRE REMOVAL FOR ACCESS | 32992492 / CAB - CALL BACK - LAV E LAVATORY "E" REQUIRE REMOVAL FOR ACCESS (32992492) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:56 | 1900-01-14 22:37 |  | 1899-12-31 08:30 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32992492 / CAB - CALL BACK - LAV E LAVATORY "E" REQUIRE REMOVAL FOR ACCESS (32992492) |  | 0 / 1 | [] |  |  | WO.32992492 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1223 | 32992500 | CAB - CALL BACK - LAV D LAVATORY "D" REQUIRE REMOVAL FOR ACCESS | 32992500 / CAB - CALL BACK - LAV D LAVATORY "D" REQUIRE REMOVAL FOR ACCESS (32992500) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 15:40 | 1900-01-14 18:53 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32992500 / CAB - CALL BACK - LAV D LAVATORY "D" REQUIRE REMOVAL FOR ACCESS (32992500) |  | 0 / 1 | [] |  |  | WO.32992500 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1224 | 32992517 | CAB - CALLBACK - STOWAGE C1 "STOWAGE C1" REQUIRE REMOVAL FOR ACCESS. | 32992517 / CAB - CALLBACK - STOWAGE C1 "STOWAGE C1" REQUIRE REMOVAL FOR ACCESS. (32992517) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:30 | 1900-01-15 06:03 |  | 0.39583 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992517 / CAB - CALLBACK - STOWAGE C1 "STOWAGE C1" REQUIRE REMOVAL FOR ACCESS. (32992517) |  | 0 / 1 | [] |  |  | WO.32992517 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1225 | 32992509 | CAB - CALL BACK- SEAT SEATS FROM 39LH TO 44 LH AND 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS | 32992509 / CAB - CALL BACK- SEAT SEATS FROM 39LH TO 44 LH AND 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS (32992509) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 11:57 | 1900-01-15 22:36 |  | 1899-12-31 02:00 | Idle | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32992509 / CAB - CALL BACK- SEAT SEATS FROM 39LH TO 44 LH AND 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS (32992509) |  | 0 / 1 | [] |  |  | WO.32992509 | 22.Jul.2026 | -16d, 23h | 2026-07-22 | D
| 1227 | 32992699 | CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING | 32992699 / CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING (32992699) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992699 / CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING (32992699) |  | 0 / 1 | [] |  |  | WO.32992699 | 22.Jul.2026 | -16d, 21h | 2026-07-22 | D
| 1228 | 32992702 | CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING | 32992702 / CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING (32992702) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992702 / CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING (32992702) |  | 0 / 1 | [] |  |  | WO.32992702 | 22.Jul.2026 | -16d, 21h | 2026-07-22 | D
| 1229 | 32992708 | CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING | 32992708 / CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING (32992708) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992708 / CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING (32992708) |  | 0 / 1 | [] |  |  | WO.32992708 | 22.Jul.2026 | -16d, 21h | 2026-07-22 | D
| 1230 | 32992709 | CAB - NO CALLBACK - LAV D LAV D THRESHOLD SCREW MISSING | 32992709 / CAB - NO CALLBACK - LAV D LAV D THRESHOLD SCREW MISSING (32992709) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992709 / CAB - NO CALLBACK - LAV D LAV D THRESHOLD SCREW MISSING (32992709) |  | 0 / 1 | [] |  |  | WO.32992709 | 22.Jul.2026 | -16d, 21h | 2026-07-22 | D
| 1231 | 32992712 | CAB - NO CALLBACK - LAV D LAV D TOILET SHROUD NOT SECURED | 32992712 / CAB - NO CALLBACK - LAV D LAV D TOILET SHROUD NOT SECURED (32992712) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992712 / CAB - NO CALLBACK - LAV D LAV D TOILET SHROUD NOT SECURED (32992712) |  | 0 / 1 | [] |  |  | WO.32992712 | 22.Jul.2026 | -16d, 20h | 2026-07-22 | D
| 1232 | 32992717 | CAB - NO CALLBACK - LAV D LAV D TOILET SEAT COVER BROKEN | 32992717 / CAB - NO CALLBACK - LAV D LAV D TOILET SEAT COVER BROKEN (32992717) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992717 / CAB - NO CALLBACK - LAV D LAV D TOILET SEAT COVER BROKEN (32992717) |  | 0 / 1 | [] |  |  | WO.32992717 | 22.Jul.2026 | -16d, 20h | 2026-07-22 | D
| 1233 | 32992719 | CAB - NO CALLBACK - LAV D LAV D DOOR LOCK LABLE FADED | 32992719 / CAB - NO CALLBACK - LAV D LAV D DOOR LOCK LABLE FADED (32992719) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992719 / CAB - NO CALLBACK - LAV D LAV D DOOR LOCK LABLE FADED (32992719) |  | 0 / 1 | [] |  |  | WO.32992719 | 22.Jul.2026 | -16d, 20h | 2026-07-22 | D
| 1234 | 32992731 | CAB - RII - SEAT REMOVAL FOR ACCESS SEAT 5JL REQUIRE REMOVAL FOR ACCESS | 32992731 / CAB - RII - SEAT REMOVAL FOR ACCESS SEAT 5JL REQUIRE REMOVAL FOR ACCESS (32992731) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:00 | 1900-01-15 03:33 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992731 / CAB - RII - SEAT REMOVAL FOR ACCESS SEAT 5JL REQUIRE REMOVAL FOR ACCESS (32992731) |  | 0 / 1 | [] |  |  | WO.32992731 | 22.Jul.2026 | -16d, 20h | 2026-07-22 | D
| 1235 | 32992738 | CAB - NO CALL BACK - COFFEE MAKER AFT GALLEY COFFEE MAKER NO.1 STENCIL | 32992738 / CAB - NO CALL BACK - COFFEE MAKER AFT GALLEY COFFEE MAKER NO.1 STENCIL (32992738) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992738 / CAB - NO CALL BACK - COFFEE MAKER AFT GALLEY COFFEE MAKER NO.1 STENCIL (32992738) |  | 0 / 1 | [] |  |  | WO.32992738 | 22.Jul.2026 | -16d, 20h | 2026-07-22 | D
| 1250 | 32994149 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOODTRAYS ARE NOT ADJUSTABLE. | 32994149 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOODTRAYS ARE NOT ADJUSTABLE. (32994149) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 29.Jul.2026 03:52 | 1900-01-09 06:41 |  | 0.33333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-25 |  | [] |  |  |  |  | 32994149 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOODTRAYS ARE NOT ADJUSTABLE. (32994149) |  | 0 / 1 | [] |  |  | WO.32994149 | 23.Jul.2026 | -16d, 5h | 2026-07-23 | D
| 1254 | 32994746 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 32994746 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32994746) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 26.Jul.2026 14:32 | 1900-01-11 20:01 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994746 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32994746) |  | 0 / 1 | [] |  |  | WO.32994746 | 23.Jul.2026 | -16d, 3h | 2026-07-23 | D
| 1261 | 32996054 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--CAB RH EMERGENCY EXIT HATCH DOOR WITH DOOR SEAL WORN AT LOWER EDGE | 32996054 / FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--CAB RH EMERGENCY EXIT HATCH DOOR WITH DOOR SEAL WORN AT LOWER EDGE (32996054) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32996054 / FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--CAB RH EMERGENCY EXIT HATCH DOOR WITH DOOR SEAL WORN AT LOWER EDGE (32996054) |  | 0 / 1 | [] |  |  | WO.32996054 | 23.Jul.2026 | -15d, 22h | 2026-07-23 | D
| 1262 | 32996073 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--SM RH FWD EMERGENCY EXIT HATCH DOOR CUTOUT WITH ABRAISION AT LOWER EDGE L=80 MM W=10 MM | 32996073 / FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--SM RH FWD EMERGENCY EXIT HATCH DOOR CUTOUT WITH ABRAISION AT LOWER EDGE L=80 MM W=10 MM (32996073) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 10:01 | 1900-01-10 00:32 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32996073 / FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--SM RH FWD EMERGENCY EXIT HATCH DOOR CUTOUT WITH ABRAISION AT LOWER EDGE L=80 MM W=10 MM (32996073) |  | 0 / 1 | [] |  |  | WO.32996073 | 23.Jul.2026 | -15d, 22h | 2026-07-23 | D
| 1263 | 32996598 | FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) | 32996598 / FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) (32996598) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 26.Jul.2026 04:10 | 1900-01-12 06:23 |  | 1899-12-31 14:20 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32996598 / FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) (32996598) |  | 0 / 4 | [] |  |  | WO.32996598 | 23.Jul.2026 | -15d, 20h | 2026-07-23 | D
| 1266 | 32996751 | L/H WING REFUEL DEFUEL COUPLING===AP==RII L/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING. | 32996751 / L/H WING REFUEL DEFUEL COUPLING===AP==RII L/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING. (32996751) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 16:21 | 1900-01-06 18:12 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 28-25 |  | [] |  |  |  |  | 32996751 / L/H WING REFUEL DEFUEL COUPLING===AP==RII L/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING. (32996751) |  | 0 / 1 | [] |  |  | WO.32996751 | 23.Jul.2026 | -15d, 19h | 2026-07-23 | D
| 1269 | 32997085 | APU BLEED DUCT=====AP======NO CALL BACK APU BLEED DUCT CHECK VLV SPRING BROKEN | 32997085 / APU BLEED DUCT=====AP======NO CALL BACK APU BLEED DUCT CHECK VLV SPRING BROKEN (32997085) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 14:01 | 1900-01-07 20:32 |  | 0.10486 | Idle | 0 | T: 0; O: 0; C: 0 | 36-12 |  | [] |  |  |  |  | 32997085 / APU BLEED DUCT=====AP======NO CALL BACK APU BLEED DUCT CHECK VLV SPRING BROKEN (32997085) |  | 0 / 1 | [] |  |  | WO.32997085 | 23.Jul.2026 | -15d, 15h | 2026-07-23 | D
| 1270 | 32998086 | RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. | 32998086 / RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. (32998086) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 08:50 | 1900-01-08 01:43 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] |  |  |  |  | 32998086 / RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. (32998086) |  | 0 / 1 | [] |  |  | WO.32998086 | 24.Jul.2026 | -15d, 3h | 2026-07-24 | D
| 1271 | 32998113 | GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . | 32998113 / GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . (32998113) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.27083 | 24.Jul.2026 01:57 | 1900-01-14 08:36 |  | 0.54167 | Idle | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 32998113 / GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . (32998113) |  | 0 / 1 | [] |  |  | WO.32998113 | 24.Jul.2026 | -15d, 3h | 2026-07-24 | D
| 1272 | 32998140 | ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. | 32998140 / ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. (32998140) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 24.Jul.2026 02:01 | 1900-01-14 08:32 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 32998140 / ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. (32998140) |  | 0 / 1 | [] |  |  | WO.32998140 | 24.Jul.2026 | -15d, 3h | 2026-07-24 | D
| 1273 | 32998206 | FINDING (NRC) TASKCARD 532181-02-1 (0) / ITEM-1 REF TO SEQ 489 INSPECTION AREA BETWEEN FR 34-35 AND STRG 38LH-38RH REQUIRE OPEN UP AND CLEANING FOR INSPECTION | 32998206 / FINDING (NRC) TASKCARD 532181-02-1 (0) / ITEM-1 REF TO SEQ 489 INSPECTION AREA BETWEEN FR 34-35 AND STRG 38LH-38RH REQUIRE OPEN UP AND CLEANING FOR INSPECTION (32998206) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 14:00 | 17.Jul.2026 22:00 | 0.27083 | 26.Jul.2026 04:37 | 1900-01-12 05:56 |  | 1899-12-31 05:00 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 32998206 / FINDING (NRC) TASKCARD 532181-02-1 (0) / ITEM-1 REF TO SEQ 489 INSPECTION AREA BETWEEN FR 34-35 AND STRG 38LH-38RH REQUIRE OPEN UP AND CLEANING FOR INSPECTION (32998206) |  | 0 / 1 | [] |  |  | WO.32998206 | 24.Jul.2026 | -15d, 2h | 2026-07-24 | D
| 1274 | 32998241 | FINDING (NRC) TASKCARD 532137-03-1 (1) / ITEM ONE SM--RII FWD CARGO DOOR CUTOUTS BOTH FWD AND AFT LOWER CUTOUTS AT FRAMES FR24A AND FR28 WITH BOTH FITTINGS MISSING FASTNERS (2EA PER FITTING) | 32998241 / FINDING (NRC) TASKCARD 532137-03-1 (1) / ITEM ONE SM--RII FWD CARGO DOOR CUTOUTS BOTH FWD AND AFT LOWER CUTOUTS AT FRAMES FR24A AND FR28 WITH BOTH FITTINGS MISSING FASTNERS (2EA PER FITTING) (32998241) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 04:30 | 1900-01-10 06:03 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] |  |  |  |  | 32998241 / FINDING (NRC) TASKCARD 532137-03-1 (1) / ITEM ONE SM--RII FWD CARGO DOOR CUTOUTS BOTH FWD AND AFT LOWER CUTOUTS AT FRAMES FR24A AND FR28 WITH BOTH FITTINGS MISSING FASTNERS (2EA PER FITTING) (32998241) |  | 0 / 1 | [] |  |  | WO.32998241 | 24.Jul.2026 | -15d, 2h | 2026-07-24 | D
| 1278 | 33000741 | FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . | 33000741 / FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . (33000741) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:14 | 1900-01-13 04:19 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 11-00 |  | [] |  |  |  |  | 33000741 / FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . (33000741) |  | 0 / 1 | [] |  |  | WO.33000741 | 25.Jul.2026 | -14d, 2h | 2026-07-25 | D
| 1280 | 33000799 | AP---CALLBACK---AFT BULKHEAD REMOVE REAR PRESSURE BULKHEAD COVER FOR INSPECTION | 33000799 / AP---CALLBACK---AFT BULKHEAD REMOVE REAR PRESSURE BULKHEAD COVER FOR INSPECTION (33000799) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 07:53 | 1900-01-13 02:40 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 53-51 |  | [] |  |  |  |  | 33000799 / AP---CALLBACK---AFT BULKHEAD REMOVE REAR PRESSURE BULKHEAD COVER FOR INSPECTION (33000799) |  | 0 / 1 | [] |  |  | WO.33000799 | 25.Jul.2026 | -14d, 1h | 2026-07-25 | D
| 1281 | 33001011 | L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF | 33001011 / L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF (33001011) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.375 | 17.Jul.2026 22:00 | 0.1875 | 25.Jul.2026 08:26 | 1900-01-13 02:07 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33001011 / L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF (33001011) |  | 0 / 1 | [] |  |  | WO.33001011 | 25.Jul.2026 | -13d, 23h | 2026-07-25 | D
| 1282 | 33001198 | AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT | 33001198 / AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT (33001198) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 08:37 | 1900-01-08 01:56 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 33001198 / AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT (33001198) |  | 0 / 1 | [] |  |  | WO.33001198 | 25.Jul.2026 | -13d, 19h | 2026-07-25 | D
| 1286 | 33002727 | AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 OUTBOARD EDGE SEAL CUT OFF | 33002727 / AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 OUTBOARD EDGE SEAL CUT OFF (33002727) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33002727 / AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 OUTBOARD EDGE SEAL CUT OFF (33002727) |  | 0 / 1 | [] |  |  | WO.33002727 | 26.Jul.2026 | -13d, 4h | 2026-07-26 | D
| 1289 | 33002784 | PNT - NO CALLBACK - OSBD OSB DOORS AT 1AC, 4AC, 5AC, 4JL, 5JL OSB DOORS REQUIRE PAINT (7 EA). | 33002784 / PNT - NO CALLBACK - OSBD OSB DOORS AT 1AC, 4AC, 5AC, 4JL, 5JL OSB DOORS REQUIRE PAINT (7 EA). (33002784) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 28.Jul.2026 02:34 | 1900-01-10 07:59 |  | 0.95833 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33002784 / PNT - NO CALLBACK - OSBD OSB DOORS AT 1AC, 4AC, 5AC, 4JL, 5JL OSB DOORS REQUIRE PAINT (7 EA). (33002784) |  | 0 / 1 | [] |  |  | WO.33002784 | 26.Jul.2026 | -13d, 3h | 2026-07-26 | D
| 1291 | 33003253 | FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 4 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 33003253 / FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 4 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33003253) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 17:59 | 1900-01-07 16:34 |  | 0.0625 | Idle | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] |  |  |  |  | 33003253 / FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 4 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33003253) |  | 0 / 1 | [] |  |  | WO.33003253 | 26.Jul.2026 | -13d, 2h | 2026-07-26 | D
| 1293 | 33003278 | AP---RII---RH WING SLAT 4 RH WING SLAT 4 INBOARD TRACK LOWER PLATE ATTACHMENT CRACKED | 33003278 / AP---RII---RH WING SLAT 4 RH WING SLAT 4 INBOARD TRACK LOWER PLATE ATTACHMENT CRACKED (33003278) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] |  |  |  |  | 33003278 / AP---RII---RH WING SLAT 4 RH WING SLAT 4 INBOARD TRACK LOWER PLATE ATTACHMENT CRACKED (33003278) |  | 0 / 1 | [] |  |  | WO.33003278 | 26.Jul.2026 | -13d, 2h | 2026-07-26 | D
| 1295 | 33003366 | FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 5 INNER RUBBER SEAL TORN 1 EA | 33003366 / FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 5 INNER RUBBER SEAL TORN 1 EA (33003366) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] |  |  |  |  | 33003366 / FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 5 INNER RUBBER SEAL TORN 1 EA (33003366) |  | 0 / 1 | [] |  |  | WO.33003366 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1296 | 33003374 | FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 33003374 / FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33003374) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] |  |  |  |  | 33003374 / FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33003374) |  | 0 / 1 | [] |  |  | WO.33003374 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1297 | 33007153 | FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 33007153 / FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33007153) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 18:03 | 1900-01-07 16:30 |  | 0.052083 | Idle | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33007153 / FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33007153) |  | 0 / 1 | [] |  |  | WO.33007153 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1298 | 33007155 | FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 INNER RUBBER SEAL TORN 1 EA AT SLAT INNER INBOARD SIDE | 33007155 / FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 INNER RUBBER SEAL TORN 1 EA AT SLAT INNER INBOARD SIDE (33007155) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33007155 / FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 INNER RUBBER SEAL TORN 1 EA AT SLAT INNER INBOARD SIDE (33007155) |  | 0 / 1 | [] |  |  | WO.33007155 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1299 | 33007178 | FINDING (NRC) TASKCARD 574305-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 2 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 33007178 / FINDING (NRC) TASKCARD 574305-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 2 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33007178) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] |  |  |  |  | 33007178 / FINDING (NRC) TASKCARD 574305-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 2 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA (33007178) |  | 0 / 1 | [] |  |  | WO.33007178 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1301 | 33007347 | FINDING (NRC) TASKCARD 574405-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 INNER RUBBER SEAL TORN 1 EA | 33007347 / FINDING (NRC) TASKCARD 574405-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 INNER RUBBER SEAL TORN 1 EA (33007347) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] |  |  |  |  | 33007347 / FINDING (NRC) TASKCARD 574405-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 INNER RUBBER SEAL TORN 1 EA (33007347) |  | 0 / 1 | [] |  |  | WO.33007347 | 26.Jul.2026 | -13d, 1h | 2026-07-26 | D
| 1304 | 33012238 | UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... | 33012238 / UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... (33012238) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 28.Jul.2026 03:00 | 1900-01-10 07:33 |  | 1900-01-01 13:05 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33012238 / UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... (33012238) |  | 0 / 2 | [] |  |  | WO.33012238 | 26.Jul.2026 | -12d, 17h | 2026-07-26 | D
| 1308 | 33013430 | L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN | 33013430 / L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN (33013430) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 10:11 | 1900-01-10 00:22 |  | 0.0013889 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33013430 / L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN (33013430) |  | 0 / 1 | [] |  |  | WO.33013430 | 26.Jul.2026 | -12d, 16h | 2026-07-26 | D
| 1310 | 33013470 | L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. | 33013470 / L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. (33013470) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 29.Jul.2026 18:39 | 1900-01-08 15:54 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] |  |  |  |  | 33013470 / L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. (33013470) |  | 0 / 1 | [] |  |  | WO.33013470 | 26.Jul.2026 | -12d, 16h | 2026-07-26 | D
| 1314 | 33013562 | ENG NO#01=====SM=====RII ENG NO#01 LH THR/REV NEAR THE FWD MOST HINGE ADJACENT STRUCTURE WITH BULGE ASSOCIATED WITH DELAMINATION DIMENSION AS FOLLOWS LENGTH = 3.5" WIDTH = 3" | 33013562 / ENG NO#01=====SM=====RII ENG NO#01 LH THR/REV NEAR THE FWD MOST HINGE ADJACENT STRUCTURE WITH BULGE ASSOCIATED WITH DELAMINATION DIMENSION AS FOLLOWS LENGTH = 3.5" WIDTH = 3" (33013562) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-01 | 17.Jul.2026 22:00 | 0.5 | 28.Jul.2026 09:51 | 1900-01-10 00:42 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] |  |  |  |  | 33013562 / ENG NO#01=====SM=====RII ENG NO#01 LH THR/REV NEAR THE FWD MOST HINGE ADJACENT STRUCTURE WITH BULGE ASSOCIATED WITH DELAMINATION DIMENSION AS FOLLOWS LENGTH = 3.5" WIDTH = 3" (33013562) |  | 0 / 1 | [] |  |  | WO.33013562 | 26.Jul.2026 | -12d, 15h | 2026-07-26 | D
| 1315 | 33014957 | RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES | 33014957 / RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES (33014957) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 34-42 |  | [] |  |  |  |  | 33014957 / RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES (33014957) |  | 0 / 1 | [] |  |  | WO.33014957 | 27.Jul.2026 | -12d, 4h | 2026-07-27 | D
| 1316 | 33015570 | CAB - RII - COCKPIT CAPTAIN SEAT INERTIA REEL FAILED TO RETRACT PROPERLY. | 33015570 / CAB - RII - COCKPIT CAPTAIN SEAT INERTIA REEL FAILED TO RETRACT PROPERLY. (33015570) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33015570 / CAB - RII - COCKPIT CAPTAIN SEAT INERTIA REEL FAILED TO RETRACT PROPERLY. (33015570) |  | 0 / 1 | [] |  |  | WO.33015570 | 27.Jul.2026 | -12d, 3h | 2026-07-27 | D
| 1317 | 33017436 | CAB - NO CALL BACK - CURTAIN RAIL FWD GALLEY CURTAIN RAIL DEFORMED | 33017436 / CAB - NO CALL BACK - CURTAIN RAIL FWD GALLEY CURTAIN RAIL DEFORMED (33017436) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33017436 / CAB - NO CALL BACK - CURTAIN RAIL FWD GALLEY CURTAIN RAIL DEFORMED (33017436) |  | 0 / 1 | [] |  |  | WO.33017436 | 27.Jul.2026 | -12d, 3h | 2026-07-27 | D
| 1319 | 33017650 | FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED | 33017650 / FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED (33017650) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:30 | 1900-01-08 05:03 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 33017650 / FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED (33017650) |  | 0 / 1 | [] |  |  | WO.33017650 | 27.Jul.2026 | -12d, 2h | 2026-07-27 | D
| 1320 | 33018932 | CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) | 33018932 / CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) (33018932) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-10 |  | [] |  |  |  |  | 33018932 / CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) (33018932) |  | 0 / 1 | [] |  |  | WO.33018932 | 27.Jul.2026 | -12d, 1h | 2026-07-27 | D
| 1321 | 33019264 | ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 | 33019264 / ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 (33019264) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 07:20 | 1900-01-11 03:13 |  | 0.25 | Idle | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] |  |  |  |  | 33019264 / ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 (33019264) |  | 0 / 1 | [] |  |  | WO.33019264 | 27.Jul.2026 | -12d, 22m | 2026-07-27 | D
| 1322 | 33019321 | SM---RII---NLG ERROSION FOUND ON RH NOSE GEAR SWIVEL BEARING BUSHING | 33019321 / SM---RII---NLG ERROSION FOUND ON RH NOSE GEAR SWIVEL BEARING BUSHING (33019321) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 04:05 | 1900-01-09 06:28 |  | 1899-12-31 14:00 | Idle | 0 | T: 0; O: 0; C: 0 | 32-21 |  | [] |  |  |  |  | 33019321 / SM---RII---NLG ERROSION FOUND ON RH NOSE GEAR SWIVEL BEARING BUSHING (33019321) |  | 0 / 1 | [] |  |  | WO.33019321 | 27.Jul.2026 | -12d, 13m | 2026-07-27 | D
| 1323 | 33019327 | ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 | 33019327 / ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 (33019327) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 07:26 | 1900-01-11 03:07 |  | 0.25 | Idle | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] |  |  |  |  | 33019327 / ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 (33019327) |  | 0 / 1 | [] |  |  | WO.33019327 | 27.Jul.2026 | -12d, 11m | 2026-07-27 | D
| 1324 | 33019384 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 | 33019384 / ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 (33019384) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 07:33 | 1900-01-11 03:00 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] |  |  |  |  | 33019384 / ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 (33019384) |  | 0 / 1 | [] |  |  | WO.33019384 | 27.Jul.2026 | -12d, 4m | 2026-07-27 | D
| 1325 | 33019437 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE L/H RQE REMOVEVAL FOR ACCESS PN / D30665-709 SN/ M14410 | 33019437 / ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE L/H RQE REMOVEVAL FOR ACCESS PN / D30665-709 SN/ M14410 (33019437) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 07:37 | 1900-01-11 02:56 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] |  |  |  |  | 33019437 / ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE L/H RQE REMOVEVAL FOR ACCESS PN / D30665-709 SN/ M14410 (33019437) |  | 0 / 1 | [] |  |  | WO.33019437 | 27.Jul.2026 | -11d, 23h | 2026-07-27 | D
| 1328 | 33014940 | S71-R10397/HZ-ASD ENG.2 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 33014940 / S71-R10397/HZ-ASD ENG.2 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33014940) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.14583 | 02.Aug.2026 03:00 | 1900-01-05 07:33 |  | 1899-12-31 17:35 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 3 | [] |  | 000 | ME.33014940 | 05.Aug.2026 | -3 | 2026-08-05 | D
| 1329 | 33014947 | S71-R10398/HZ-ASD ENG.1 REPLACEMENT OF LH FAN COWL AFT EDGE PROTECTORS | 33014947 / S71-R10398/HZ-ASD ENG.1 REPLACEMENT OF LH FAN COWL AFT EDGE PROTECTORS (33014947) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.22917 | 05.Aug.2026 03:00 | 1900-01-02 07:33 |  | 0.86111 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 3 | [] |  | 000 | ME.33014947 | 06.Aug.2026 | -2 | 2026-08-06 | D
| 1331 | 95001843 | ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 | 95001843 / ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 (95001843) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 27.Jul.2026 14:02 | 1900-01-10 20:31 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 21-00 |  | [] |  |  |  |  | 95001843 / ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 (95001843) |  | 0 / 1 | [] |  |  | WO.95001843 | 27.Jul.2026 | -11d, 18h | 2026-07-27 | D
| 1334 | 33020727 | CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . | 33020727 / CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . (33020727) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:40 | 1900-01-08 04:53 |  | 0.0069444 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020727 / CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . (33020727) |  | 0 / 1 | [] |  |  | WO.33020727 | 27.Jul.2026 | -11d, 15h | 2026-07-27 | D
| 1335 | 33020728 | AFT CGO COMPT=====AP=====RII AFT CGO COMPT FWD LEFT HAND SIDE APU DUCT CLAMP INSTALLATION ADJACENT AREA INSULATION BLANKETS WITH BURN MARKS (SIGN OF LEAK) | 33020728 / AFT CGO COMPT=====AP=====RII AFT CGO COMPT FWD LEFT HAND SIDE APU DUCT CLAMP INSTALLATION ADJACENT AREA INSULATION BLANKETS WITH BURN MARKS (SIGN OF LEAK) (33020728) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] |  |  |  |  | 33020728 / AFT CGO COMPT=====AP=====RII AFT CGO COMPT FWD LEFT HAND SIDE APU DUCT CLAMP INSTALLATION ADJACENT AREA INSULATION BLANKETS WITH BURN MARKS (SIGN OF LEAK) (33020728) |  | 0 / 1 | [] |  |  | WO.33020728 | 27.Jul.2026 | -11d, 15h | 2026-07-27 | D
| 1336 | 33020729 | CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... | 33020729 / CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... (33020729) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 11:35 | 1900-01-09 22:58 |  | 0.32639 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020729 / CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... (33020729) |  | 0 / 1 | [] |  |  | WO.33020729 | 27.Jul.2026 | -11d, 15h | 2026-07-27 | D
| 1337 | 33020731 | CAB - FLOOR STRUC - SEAT TRACK (Y-765) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-765) FWD OF FR41 WITH GOUGE AT UPPER FLANGE OF SEAT TRACK . DIM:- L=0.78 INCH. ,W=0.15 INCH.... | 33020731 / CAB - FLOOR STRUC - SEAT TRACK (Y-765) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-765) FWD OF FR41 WITH GOUGE AT UPPER FLANGE OF SEAT TRACK . DIM:- L=0.78 INCH. ,W=0.15 INCH.... (33020731) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 13:05 | 1900-01-09 21:28 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020731 / CAB - FLOOR STRUC - SEAT TRACK (Y-765) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-765) FWD OF FR41 WITH GOUGE AT UPPER FLANGE OF SEAT TRACK . DIM:- L=0.78 INCH. ,W=0.15 INCH.... (33020731) |  | 0 / 1 | [] |  |  | WO.33020731 | 27.Jul.2026 | -11d, 15h | 2026-07-27 | D
| 1338 | 33020734 | CAB - UNDER FLOOR - CAB - CALL BACK CABIN FROM FR 43 TO FR46 FOUND UNDER FLOOR STRUCTURE WITH MISSING CIC APPLICATION AND FROM FR36 TO FR46 FOUND UNDER FLOOR STRUCTURE , AIR CONDITIONING DUCT , LINES DUSTY AND WITH EXCESSIVE LINT ACCUMULATION. | 33020734 / CAB - UNDER FLOOR - CAB - CALL BACK CABIN FROM FR 43 TO FR46 FOUND UNDER FLOOR STRUCTURE WITH MISSING CIC APPLICATION AND FROM FR36 TO FR46 FOUND UNDER FLOOR STRUCTURE , AIR CONDITIONING DUCT , LINES DUSTY AND WITH EXCESSIVE LINT ACCUMULATION. (33020734) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 14:20 | 1900-01-03 20:13 |  | 0.10069 | Idle | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020734 / CAB - UNDER FLOOR - CAB - CALL BACK CABIN FROM FR 43 TO FR46 FOUND UNDER FLOOR STRUCTURE WITH MISSING CIC APPLICATION AND FROM FR36 TO FR46 FOUND UNDER FLOOR STRUCTURE , AIR CONDITIONING DUCT , LINES DUSTY AND WITH EXCESSIVE LINT ACCUMULATION. (33020734) |  | 0 / 1 | [] |  |  | WO.33020734 | 27.Jul.2026 | -11d, 15h | 2026-07-27 | D
| 1339 | 33021722 | MACHINEST - NO CALL BACK - OVEN G1 GALLEY OVEN COMP. 104 SCREWS FROZEN | 33021722 / MACHINEST - NO CALL BACK - OVEN G1 GALLEY OVEN COMP. 104 SCREWS FROZEN (33021722) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33021722 / MACHINEST - NO CALL BACK - OVEN G1 GALLEY OVEN COMP. 104 SCREWS FROZEN (33021722) |  | 0 / 1 | [] |  |  | WO.33021722 | 28.Jul.2026 | -11d, 4h | 2026-07-28 | D
| 1340 | 33021799 | EMERGENCY EXIT HATCH - CABIN - NO CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL | 33021799 / EMERGENCY EXIT HATCH - CABIN - NO CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL (33021799) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 13:58 | 1900-01-09 20:35 |  | 0.16667 | Idle | 0 | T: 0; O: 0; C: 0 | 53-00-00 |  | [] |  |  |  |  | 33021799 / EMERGENCY EXIT HATCH - CABIN - NO CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL (33021799) |  | 0 / 1 | [] |  |  | WO.33021799 | 28.Jul.2026 | -11d, 4h | 2026-07-28 | D
| 1342 | 33022670 | CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING | 33022670 / CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING (33022670) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022670 / CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING (33022670) |  | 0 / 1 | [] |  |  | WO.33022670 | 28.Jul.2026 | -11d, 4h | 2026-07-28 | D
| 1343 | 33022800 | CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. | 33022800 / CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. (33022800) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] |  |  |  |  | 33022800 / CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. (33022800) |  | 0 / 1 | [] |  |  | WO.33022800 | 28.Jul.2026 | -11d, 3h | 2026-07-28 | D
| 1344 | 33022853 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP | 33022853 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP (33022853) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022853 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP (33022853) |  | 0 / 1 | [] |  |  | WO.33022853 | 28.Jul.2026 | -11d, 3h | 2026-07-28 | D
| 1345 | 33022868 | CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. | 33022868 / CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. (33022868) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33022868 / CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. (33022868) |  | 0 / 1 | [] |  |  | WO.33022868 | 28.Jul.2026 | -11d, 3h | 2026-07-28 | D
| 1349 | 33022983 | CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. | 33022983 / CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. (33022983) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022983 / CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. (33022983) |  | 0 / 1 | [] |  |  | WO.33022983 | 28.Jul.2026 | -11d, 2h | 2026-07-28 | D
| 1353 | 33023666 | CAB - RII - COCKPIT FLIGHT DECK FIRST OFFICER SEAT HARNESS DETERIORATED. | 33023666 / CAB - RII - COCKPIT FLIGHT DECK FIRST OFFICER SEAT HARNESS DETERIORATED. (33023666) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33023666 / CAB - RII - COCKPIT FLIGHT DECK FIRST OFFICER SEAT HARNESS DETERIORATED. (33023666) |  | 0 / 1 | [] |  |  | WO.33023666 | 28.Jul.2026 | -11d, 1h | 2026-07-28 | D
| 1356 | 33023803 | CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. | 33023803 / CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. (33023803) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 04:02 | 1900-01-01 06:31 |  | 0.5 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023803 / CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. (33023803) |  | 0 / 1 | [] |  |  | WO.33023803 | 28.Jul.2026 | -11d, 1h | 2026-07-28 | D
| 1357 | 33023820 | CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED | 33023820 / CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED (33023820) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023820 / CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED (33023820) |  | 0 / 1 | [] |  |  | WO.33023820 | 28.Jul.2026 | -11d, 1h | 2026-07-28 | D
| 1358 | 33023837 | CAB - NO CALL BACK - GALLEY FWD GALLEY (G1,G2) SIDE TURN CATCH FADED | 33023837 / CAB - NO CALL BACK - GALLEY FWD GALLEY (G1,G2) SIDE TURN CATCH FADED (33023837) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33023837 / CAB - NO CALL BACK - GALLEY FWD GALLEY (G1,G2) SIDE TURN CATCH FADED (33023837) |  | 0 / 1 | [] |  |  | WO.33023837 | 28.Jul.2026 | -11d, 1h | 2026-07-28 | D
| 1360 | 33025667 | CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE | 33025667 / CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE (33025667) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 15:10 | 0.80764 |  | 0.1875 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33025667 / CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE (33025667) |  | 0 / 1 | [] |  |  | WO.33025667 | 28.Jul.2026 | -10d, 18h | 2026-07-28 | D
| 1361 | 33025672 | ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 | 33025672 / ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 (33025672) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 33025672 / ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 (33025672) |  | 0 / 1 | [] |  |  | WO.33025672 | 28.Jul.2026 | -10d, 18h | 2026-07-28 | D
| 1365 | 33025894 | LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN | 33025894 / LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN (33025894) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 04:21 | 1900-01-09 06:12 |  | 0.70139 | Idle | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025894 / LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN (33025894) |  | 0 / 1 | [] |  |  | WO.33025894 | 28.Jul.2026 | -10d, 15h | 2026-07-28 | D
| 1368 | 33027334 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT | 33027334 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT (33027334) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 11:02 | 1900-01-07 23:31 |  | 1899-12-31 02:30 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027334 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT (33027334) |  | 0 / 1 | [] |  |  | WO.33027334 | 29.Jul.2026 | -10d, 3h | 2026-07-29 | D
| 1369 | 33027336 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 | 33027336 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 (33027336) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 06:50 | 1900-01-08 03:43 |  | 0.61806 | Idle | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027336 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 (33027336) |  | 0 / 1 | [] |  |  | WO.33027336 | 29.Jul.2026 | -10d, 3h | 2026-07-29 | D
| 1372 | 33028124 | BROKEN PLENUM LH&RH-AP-N0-CALLBACK DURING INSPECTION FOUND LH & RH PACKS PLENUM CHAMBERS DELAMINATED OUT OF LIMITS | 33028124 / BROKEN PLENUM LH&RH-AP-N0-CALLBACK DURING INSPECTION FOUND LH & RH PACKS PLENUM CHAMBERS DELAMINATED OUT OF LIMITS (33028124) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 08:32 | 1900-01-09 02:01 |  | 0.41667 | Idle | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] |  |  |  |  | 33028124 / BROKEN PLENUM LH&RH-AP-N0-CALLBACK DURING INSPECTION FOUND LH & RH PACKS PLENUM CHAMBERS DELAMINATED OUT OF LIMITS (33028124) |  | 0 / 1 | [] |  |  | WO.33028124 | 29.Jul.2026 | -10d, 1h | 2026-07-29 | D
| 1373 | 33028166 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY AIR CHILLER COVER PANEL GRILLE DEFORMED. | 33028166 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY AIR CHILLER COVER PANEL GRILLE DEFORMED. (33028166) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33028166 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY AIR CHILLER COVER PANEL GRILLE DEFORMED. (33028166) |  | 0 / 1 | [] |  |  | WO.33028166 | 29.Jul.2026 | -10d, 1h | 2026-07-29 | D
| 1376 | 33028349 | AP---CALLBACK---REAR AVN COMP REAR AVN COMPARTMENT UNDER INSULATION AND FLOOR AREA REQUIRE CIC | 33028349 / AP---CALLBACK---REAR AVN COMP REAR AVN COMPARTMENT UNDER INSULATION AND FLOOR AREA REQUIRE CIC (33028349) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33028349 / AP---CALLBACK---REAR AVN COMP REAR AVN COMPARTMENT UNDER INSULATION AND FLOOR AREA REQUIRE CIC (33028349) |  | 0 / 1 | [] |  |  | WO.33028349 | 29.Jul.2026 | -10d, 30m | 2026-07-29 | D
| 1377 | 33028466 | CAB - CALLBACK - G2 GALLEY G2 GALLEY REQUIRE REMOVAL FOR ACCESS. | 33028466 / CAB - CALLBACK - G2 GALLEY G2 GALLEY REQUIRE REMOVAL FOR ACCESS. (33028466) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 04:00 | 1900-01-09 06:33 |  | 0.8125 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33028466 / CAB - CALLBACK - G2 GALLEY G2 GALLEY REQUIRE REMOVAL FOR ACCESS. (33028466) |  | 0 / 1 | [] |  |  | WO.33028466 | 29.Jul.2026 | -9d, 23h | 2026-07-29 | D
| 1378 | 33028471 | CAB - RII - B/C SEATS ALL B/C SEATS REQUIRE REMOVAL FOR ACCESS. | 33028471 / CAB - RII - B/C SEATS ALL B/C SEATS REQUIRE REMOVAL FOR ACCESS. (33028471) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 04:00 | 1900-01-09 06:33 |  | 1899-12-31 02:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33028471 / CAB - RII - B/C SEATS ALL B/C SEATS REQUIRE REMOVAL FOR ACCESS. (33028471) |  | 0 / 1 | [] |  |  | WO.33028471 | 29.Jul.2026 | -9d, 23h | 2026-07-29 | D
| 1379 | 33028546 | CAB - NO CALLBACK - G/C AREA G/C AREA 9 EA SIDEWALLS WINDOW FRAME FOUND BROKEN. | 33028546 / CAB - NO CALLBACK - G/C AREA G/C AREA 9 EA SIDEWALLS WINDOW FRAME FOUND BROKEN. (33028546) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">10</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33028546 / CAB - NO CALLBACK - G/C AREA G/C AREA 9 EA SIDEWALLS WINDOW FRAME FOUND BROKEN. (33028546) |  | 0 / 1 | [] |  |  | WO.33028546 | 29.Jul.2026 | -9d, 23h | 2026-07-29 | D
| 1380 | 33028549 | PNT - NO CALL BACK - GALLEY FWD (G1) GALLEY PAINT PEELED OFF BETWEEN COMP. 104 AND 105. | 33028549 / PNT - NO CALL BACK - GALLEY FWD (G1) GALLEY PAINT PEELED OFF BETWEEN COMP. 104 AND 105. (33028549) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33028549 / PNT - NO CALL BACK - GALLEY FWD (G1) GALLEY PAINT PEELED OFF BETWEEN COMP. 104 AND 105. (33028549) |  | 0 / 1 | [] |  |  | WO.33028549 | 29.Jul.2026 | -9d, 23h | 2026-07-29 | D
| 1381 | 33028590 | FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF | 33028590 / FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF (33028590) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 17.Jul.2026 22:00 | 0.41667 | 31.Jul.2026 02:20 | 1900-01-07 08:13 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] |  |  |  |  | 33028590 / FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF (33028590) |  | 0 / 1 | [] |  |  | WO.33028590 | 29.Jul.2026 | -9d, 22h | 2026-07-29 | D
| 1385 | 33029239 | FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... | 33029239 / FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... (33029239) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">16</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:50 | 1900-01-08 04:43 |  | 1899-12-31 16:40 | Idle | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33029239 / FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... (33029239) |  | 0 / 1 | [] |  |  | WO.33029239 | 29.Jul.2026 | -9d, 16h | 2026-07-29 | D
| 1387 | 33030770 | SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE | 33030770 / SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE (33030770) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 03.Aug.2026 04:30 | 1900-01-04 06:03 |  | 1900-01-01 00:47 | Idle | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33030770 / SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE (33030770) |  | 0 / 3 | [] |  |  | WO.33030770 | 30.Jul.2026 | -9d, 2h | 2026-07-30 | D
| 1388 | 33030877 | AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 TRACK 3 UPPER SURROUNDING SEAL TORN | 33030877 / AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 TRACK 3 UPPER SURROUNDING SEAL TORN (33030877) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33030877 / AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 TRACK 3 UPPER SURROUNDING SEAL TORN (33030877) |  | 0 / 1 | [] |  |  | WO.33030877 | 30.Jul.2026 | -9d, 1h | 2026-07-30 | D
| 1389 | 33030906 | CTR TANK FUEL PNL----FT----RII REFER TO TC # 571192-19-1 AND 571192-09-1 REQUIRE TO REMOVE CENTER FUEL TANK ACCESS PANEL 148AZ | 33030906 / CTR TANK FUEL PNL----FT----RII REFER TO TC # 571192-19-1 AND 571192-09-1 REQUIRE TO REMOVE CENTER FUEL TANK ACCESS PANEL 148AZ (33030906) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 04:09 | 1900-01-04 06:24 |  | 0.83819 | Idle | 0 | T: 2; O: 0; C: 2 | 28 |  | [] |  |  |  |  | 33030906 / CTR TANK FUEL PNL----FT----RII REFER TO TC # 571192-19-1 AND 571192-09-1 REQUIRE TO REMOVE CENTER FUEL TANK ACCESS PANEL 148AZ (33030906) |  | 0 / 1 | [] |  |  | WO.33030906 | 30.Jul.2026 | -9d, 1h | 2026-07-30 | D
| 1390 | 33032675 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY ICE DRAWER LOWER TRIM DETACHED. | 33032675 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY ICE DRAWER LOWER TRIM DETACHED. (33032675) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33032675 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY ICE DRAWER LOWER TRIM DETACHED. (33032675) |  | 0 / 1 | [] |  |  | WO.33032675 | 30.Jul.2026 | -8d, 22h | 2026-07-30 | D
| 1391 | 33032681 | FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM | 33032681 / FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM (33032681) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 02.Aug.2026 06:44 | 1900-01-05 03:49 |  | 1899-12-31 04:55 | Idle | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 33032681 / FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM (33032681) |  | 0 / 2 | [] |  |  | WO.33032681 | 30.Jul.2026 | -8d, 22h | 2026-07-30 | D
| 1393 | 33035902 | VHS BROKEN VHS AT SEAT 1A BROKEN | 33035902 / VHS BROKEN VHS AT SEAT 1A BROKEN (33035902) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 33035902 / VHS BROKEN VHS AT SEAT 1A BROKEN (33035902) |  | 0 / 1 | [] |  |  | WO.33035902 | 31.Jul.2026 | -7d, 10h | 2026-07-31 | D
| 1394 | 33035907 | VHS BROKEN VHS AT SEAT 1L BROKEN | 33035907 / VHS BROKEN VHS AT SEAT 1L BROKEN (33035907) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 33035907 / VHS BROKEN VHS AT SEAT 1L BROKEN (33035907) |  | 0 / 1 | [] |  |  | WO.33035907 | 01.Aug.2026 | -7d, 10h | 2026-08-01 | D
| 1395 | 33036878 | ENG#1 HPV FUNCTIONAL CHECK FAILED -- AP -- RII ENG#1 HPV DURING HEALTH CHECK TEST FOUND HPV STUCK TO CLOSED POSITION, REQUIRE R/R. | 33036878 / ENG#1 HPV FUNCTIONAL CHECK FAILED -- AP -- RII ENG#1 HPV DURING HEALTH CHECK TEST FOUND HPV STUCK TO CLOSED POSITION, REQUIRE R/R. (33036878) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 02.Aug.2026 09:10 | 1900-01-05 01:23 |  | 1899-12-31 01:30 | Idle | 0 | T: 0; O: 0; C: 0 | 36-11-00 |  | [] |  |  |  |  | 33036878 / ENG#1 HPV FUNCTIONAL CHECK FAILED -- AP -- RII ENG#1 HPV DURING HEALTH CHECK TEST FOUND HPV STUCK TO CLOSED POSITION, REQUIRE R/R. (33036878) |  | 0 / 1 | [] |  | #1 ENG | WO.33036878 | 01.Aug.2026 | -7d, 56m | 2026-08-01 | D
| 1396 | 33037808 | LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK | 33037808 / LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK (33037808) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 01.Aug.2026 09:07 | 1900-01-06 01:26 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33037808 / LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK (33037808) |  | 0 / 1 | [] |  |  | WO.33037808 | 01.Aug.2026 | -6d, 19h | 2026-08-01 | D
| 1397 | 33037811 | RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK | 33037811 / RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK (33037811) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 01.Aug.2026 09:04 | 1900-01-06 01:29 |  | 0.27083 | Idle | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33037811 / RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK (33037811) |  | 0 / 1 | [] |  |  | WO.33037811 | 01.Aug.2026 | -6d, 19h | 2026-08-01 | D
| 1398 | 33037962 | ENGINE #1 LH FAN COWL.....AP..RII REFER TO WO# 33014947. ENGINE #1 LH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR | 33037962 / ENGINE #1 LH FAN COWL.....AP..RII REFER TO WO# 33014947. ENGINE #1 LH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037962) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.16667 | 01.Aug.2026 16:29 | 1900-01-05 18:04 |  | 0.19167 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33037962 / ENGINE #1 LH FAN COWL.....AP..RII REFER TO WO# 33014947. ENGINE #1 LH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037962) |  | 0 / 1 | [] |  |  | WO.33037962 | 01.Aug.2026 | -6d, 16h | 2026-08-01 | D
| 1399 | 33037966 | ENGINE #1 RH FAN COWL.....AP...RII REFER TO WO# 33014938. ENGINE #1 RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR | 33037966 / ENGINE #1 RH FAN COWL.....AP...RII REFER TO WO# 33014938. ENGINE #1 RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037966) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.16667 | 01.Aug.2026 16:35 | 1900-01-05 17:58 |  | 0.17917 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33037966 / ENGINE #1 RH FAN COWL.....AP...RII REFER TO WO# 33014938. ENGINE #1 RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037966) |  | 0 / 1 | [] |  |  | WO.33037966 | 01.Aug.2026 | -6d, 16h | 2026-08-01 | D
| 1400 | 33037967 | ENGINE #2 RH FAN COWL.....AP....RII REFER TO WO# 33014940. ENGINE # RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR | 33037967 / ENGINE #2 RH FAN COWL.....AP....RII REFER TO WO# 33014940. ENGINE # RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037967) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 17.Jul.2026 22:00 | 0.16667 | 01.Aug.2026 17:38 | 1900-01-05 16:55 |  | 0.19167 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33037967 / ENGINE #2 RH FAN COWL.....AP....RII REFER TO WO# 33014940. ENGINE # RH FAN COWL REQ REMOVAL FOR STRUCTURE REPAIR (33037967) |  | 0 / 1 | [] |  |  | WO.33037967 | 01.Aug.2026 | -6d, 16h | 2026-08-01 | D
| 1401 | 33040155 | S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 33040155 / S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33040155) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.14583 | 05.Aug.2026 03:00 | 1900-01-02 07:33 |  | 1899-12-31 00:30 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33040155 / S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33040155) |  | 0 / 3 | [] |  | 000 | ME.33040155 | 05.Aug.2026 | -3 | 2026-08-05 | D
| 1405 | 33043802 | TASKCARD 531166-01-2 (2) / ITEM-1---SM---CALL BACK--- R1 DOOR-CUTOUT LOWER-CORNERS ON FWD AND AFT FOUND SURFACE CORROSION. | 33043802 / TASKCARD 531166-01-2 (2) / ITEM-1---SM---CALL BACK--- R1 DOOR-CUTOUT LOWER-CORNERS ON FWD AND AFT FOUND SURFACE CORROSION. (33043802) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 05:33 | 1900-01-02 05:00 |  | 0.090278 | Idle | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33043802 / TASKCARD 531166-01-2 (2) / ITEM-1---SM---CALL BACK--- R1 DOOR-CUTOUT LOWER-CORNERS ON FWD AND AFT FOUND SURFACE CORROSION. (33043802) |  | 0 / 3 | [] |  |  | WO.33043802 | 03.Aug.2026 | -5d, 3h | 2026-08-03 | D
| 1406 | 571192-09-1 | 571192-09-1 (0) / CENTER WING BOX | 571192-09-1 (0) / CENTER WING BOX (33044425) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | As per response in T/Q:843420 and airbus response in Dosseeier #81845619. to add Advance AMM. | 571192-09-1 (0) / CENTER WING BOX (33044425) |  | 0 / 3 | [] |  |  | MET.33044425 | 21.Jul.2028 | 713 | 2028-07-21 | D
| 1407 | 571192-19-1 | 571192-19-1 (0) / CENTER WING BOX | 571192-19-1 (0) / CENTER WING BOX (33044444) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 2; O: 0; C: 2 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | As per T/Q: 843444 and airbus response Dossier TA# 81845708. | 571192-19-1 (0) / CENTER WING BOX (33044444) |  | 0 / 3 | [] |  |  | MET.33044444 | 21.Jul.2028 | 713 | 2028-07-21 | D
| 1408 | 33045441 | VERTICAL MEMBER ASSEMBLIES FR24- AP-RII FWD CARGO VERTICAL MEMBER ASSEMBLIES AT FRAME 24 (LOC : Y-765, Y-254, Y254, Y765) FOUND DVI EVALUATION OUT OF LIMITS | 33045441 / VERTICAL MEMBER ASSEMBLIES FR24- AP-RII FWD CARGO VERTICAL MEMBER ASSEMBLIES AT FRAME 24 (LOC : Y-765, Y-254, Y254, Y765) FOUND DVI EVALUATION OUT OF LIMITS (33045441) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.20833 | 17.Jul.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33045441 / VERTICAL MEMBER ASSEMBLIES FR24- AP-RII FWD CARGO VERTICAL MEMBER ASSEMBLIES AT FRAME 24 (LOC : Y-765, Y-254, Y254, Y765) FOUND DVI EVALUATION OUT OF LIMITS (33045441) |  | 0 / 1 | [] |  |  | WO.33045441 | 03.Aug.2026 | -4d, 16h | 2026-08-03 | D
| 1409 | 33045500 | CAB - CALL BACK - RH AFT EXIT DOOR RH AFT EXIT DOOR INNER SIDE AROUND WINDOW FRAME BROKEN | 33045500 / CAB - CALL BACK - RH AFT EXIT DOOR RH AFT EXIT DOOR INNER SIDE AROUND WINDOW FRAME BROKEN (33045500) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33045500 / CAB - CALL BACK - RH AFT EXIT DOOR RH AFT EXIT DOOR INNER SIDE AROUND WINDOW FRAME BROKEN (33045500) |  | 0 / 1 | [] |  |  | WO.33045500 | 03.Aug.2026 | -4d, 15h | 2026-08-03 | D
| 1410 | 95001845 | ROB TQ REF. # 845597 ENG # 2 THRUST REVERSER HCU P/N : TY2013-11 S/N # 8888 REQ. ROB TO SVC AS 75 | 95001845 / ROB TQ REF. # 845597 ENG # 2 THRUST REVERSER HCU P/N : TY2013-11 S/N # 8888 REQ. ROB TO SVC AS 75 (95001845) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">12</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 04:46 | 1900-01-03 05:47 |  | 1900-01-01 06:00 | Idle | 0 | T: 0; O: 0; C: 0 | 70-00 |  | [] |  |  |  |  | 95001845 / ROB TQ REF. # 845597 ENG # 2 THRUST REVERSER HCU P/N : TY2013-11 S/N # 8888 REQ. ROB TO SVC AS 75 (95001845) |  | 0 / 1 | [] |  |  | WO.95001845 | 04.Aug.2026 | -4d, 4h | 2026-08-04 | D
| 1416 | 33057946 | SIDEWALL - NO CALL BACK - TEDLER SIDEWALL 5AC TEDLER CHIPPED OFF | 33057946 / SIDEWALL - NO CALL BACK - TEDLER SIDEWALL 5AC TEDLER CHIPPED OFF (33057946) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 02:00 | 1900-01-02 08:33 |  | 1899-12-31 02:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33057946 / SIDEWALL - NO CALL BACK - TEDLER SIDEWALL 5AC TEDLER CHIPPED OFF (33057946) |  | 0 / 1 | [] |  |  | WO.33057946 | 05.Aug.2026 | -3d, 8m | 2026-08-05 | D
| 1417 | 33058259 | GALLEY ..... CAB...... NO CALL BACK GALLEY DOOR 210 TEDLAR DAMMAGED | 33058259 / GALLEY ..... CAB...... NO CALL BACK GALLEY DOOR 210 TEDLAR DAMMAGED (33058259) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 05.Aug.2026 02:00 | 1900-01-02 08:33 |  | 1899-12-31 02:00 | Idle | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33058259 / GALLEY ..... CAB...... NO CALL BACK GALLEY DOOR 210 TEDLAR DAMMAGED (33058259) |  | 0 / 1 | [] |  |  | WO.33058259 | 05.Aug.2026 | -2d, 22h | 2026-08-05 | D
| 1418 | 33058303 | FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED | 33058303 / FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED (33058303) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 05.Aug.2026 02:00 | 1900-01-02 08:33 |  | 0.54167 | Idle | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33058303 / FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED (33058303) |  | 0 / 1 | [] |  |  | WO.33058303 | 05.Aug.2026 | -2d, 22h | 2026-08-05 | D
| 1419 | 33058312 | CAB- AFT WALL .... NO ....CALL BACK AFT WALL OF 44 JKL TEDLAR DAMMAGED | 33058312 / CAB- AFT WALL .... NO ....CALL BACK AFT WALL OF 44 JKL TEDLAR DAMMAGED (33058312) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 05.Aug.2026 02:00 | 1900-01-02 08:33 |  | 0.54167 | Idle | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33058312 / CAB- AFT WALL .... NO ....CALL BACK AFT WALL OF 44 JKL TEDLAR DAMMAGED (33058312) |  | 0 / 1 | [] |  |  | WO.33058312 | 05.Aug.2026 | -2d, 22h | 2026-08-05 | D
| 1421 | 33060680 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED | 33060680 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED (33060680) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33060680 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED (33060680) |  | 0 / 1 | [] |  |  | WO.33060680 | 05.Aug.2026 | -2d, 14h | 2026-08-05 | D
| 1423 | 33062059 | PNT - NO CALLBACK - SEATS DURING CKPT CHK FOUND SIDE OF CAP. AND F/O SEATS PAINT CHIPPED | 33062059 / PNT - NO CALLBACK - SEATS DURING CKPT CHK FOUND SIDE OF CAP. AND F/O SEATS PAINT CHIPPED (33062059) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 05:23 | 1899-12-31 05:10 |  | 0.3125 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062059 / PNT - NO CALLBACK - SEATS DURING CKPT CHK FOUND SIDE OF CAP. AND F/O SEATS PAINT CHIPPED (33062059) |  | 0 / 1 | [] |  |  | WO.33062059 | 06.Aug.2026 | -2d, 3h | 2026-08-06 | D
| 1424 | 33062121 | PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED | 33062121 / PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED (33062121) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:00 | 1899-12-31 04:33 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062121 / PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED (33062121) |  | 0 / 1 | [] |  |  | WO.33062121 | 06.Aug.2026 | -2d, 3h | 2026-08-06 | D
| 1425 | 33062156 | PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED | 33062156 / PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED (33062156) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:00 | 1899-12-31 04:33 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062156 / PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED (33062156) |  | 0 / 1 | [] |  |  | WO.33062156 | 06.Aug.2026 | -2d, 3h | 2026-08-06 | D
| 1426 | 33062169 | PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED | 33062169 / PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED (33062169) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:35 | 1899-12-31 03:58 |  | 0.14583 | Idle | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062169 / PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED (33062169) |  | 0 / 1 | [] |  |  | WO.33062169 | 06.Aug.2026 | -2d, 3h | 2026-08-06 | D
| 1427 | 95001846 | ROB REF TO TQ # 846298 VHS ROBBED TO SVC AS55 P/N # RD-FA5117-01 S/N#H597712 | 95001846 / ROB REF TO TQ # 846298 VHS ROBBED TO SVC AS55 P/N # RD-FA5117-01 S/N#H597712 (95001846) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 07:00 | 1900-01-02 03:33 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 95001846 / ROB REF TO TQ # 846298 VHS ROBBED TO SVC AS55 P/N # RD-FA5117-01 S/N#H597712 (95001846) |  | 0 / 1 | [] |  |  | WO.95001846 | 05.Aug.2026 | -3d, 2h | 2026-08-05 | D
| 1428 | 33067651 | LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. | 33067651 / LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. (33067651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-00 |  | [] |  |  |  |  | 33067651 / LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. (33067651) |  | 0 / 1 | [] |  |  | WO.33067651 | 06.Aug.2026 | -1d, 23h | 2026-08-06 | D
| 1429 | 95001847 | ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 | 95001847 / ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 (95001847) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 13:00 | 1899-12-31 21:33 |  | 0.125 | Idle | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 95001847 / ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 (95001847) |  | 0 / 1 | [] |  |  | WO.95001847 | 06.Aug.2026 | -1d, 20h | 2026-08-06 | D
| 1430 | 33069516 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED | 33069516 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED (33069516) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 11:20 | 1899-12-31 23:13 |  | 0.35417 | Idle | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33069516 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED (33069516) |  | 0 / 1 | [] |  |  | WO.33069516 | 06.Aug.2026 | -1d, 18h | 2026-08-06 | D
| 1431 | 33069524 | CAB - NO CALLBACK -AFT GALLEY AFT GALLEY 1 EA AIR FLAP SEALTORN. | 33069524 / CAB - NO CALLBACK -AFT GALLEY AFT GALLEY 1 EA AIR FLAP SEALTORN. (33069524) | Finding WO | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33069524 / CAB - NO CALLBACK -AFT GALLEY AFT GALLEY 1 EA AIR FLAP SEALTORN. (33069524) |  | 0 / 1 | [] |  |  | WO.33069524 | 06.Aug.2026 | -1d, 18h | 2026-08-06 | D
| 1432 | 33073741 | CAB - NO CALLBACK - F/A SEAT L1 INBOARD F/A SEAT LOWER AND UPPER RUBSTRIP DEFORMED. | 33073741 / CAB - NO CALLBACK - F/A SEAT L1 INBOARD F/A SEAT LOWER AND UPPER RUBSTRIP DEFORMED. (33073741) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 08.Aug.2026 06:30 | 0.16875 |  | 0.10417 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33073741 / CAB - NO CALLBACK - F/A SEAT L1 INBOARD F/A SEAT LOWER AND UPPER RUBSTRIP DEFORMED. (33073741) |  | 0 / 1 | [] |  |  | WO.33073741 | 08.Aug.2026 | -1h, 29m | 2026-08-08 | D
| 1433 | 33073939 | FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-254 WITH SURFACE CORROSION | 33073939 / FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-254 WITH SURFACE CORROSION (33073939) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33073939 / FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-254 WITH SURFACE CORROSION (33073939) |  | 0 / 1 | [] |  |  | WO.33073939 | 08.Aug.2026 | -24m | 2026-08-08 | D