## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Due at | To Go | Expected | Dimension
| 1 | 31909295 | A_N (A_N10)/A_N-CHECK | 31909295 / A_N (A_N10)/A_N-CHECK (31909295) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31909295 / A_N (A_N10)/A_N-CHECK (31909295) |  | 0 / 1 | [] |  |  | ME.31909295 | 37508:14 | 309:36 | 2026-10-05 | H
| 2 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32721995) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK (32721995) |  | 0 / 2 | [] |  |  | MET.32721995 | 17.May.2027 | 259 | 2027-05-17 | D
| 3 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29291084) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 11-11 |  | [] | PRE INSP |  |  |  | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK (29291084) |  | 0 / 1 | [] |  |  | MET.29291084 | 37508:14 | 309:36 | 2026-10-05 | H
| 4 | 212141-01-1 | 212141-01-1 (3) / RECIRCULATION FILTER REPLACEMENT | 212141-01-1 (3) / RECIRCULATION FILTER REPLACEMENT (32722023) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-21 |  | [] | TC/P |  |  |  | 212141-01-1 (3) / RECIRCULATION FILTER REPLACEMENT (32722023) |  | 0 / 1 | [] |  |  | MET.32722023 | 40650:09 | 3451:31 | 2027-10-15 | H
| 5 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32722040) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-23 |  | [] | TC/P, TC/P |  |  |  | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32722040) |  | 0 / 2 | [] |  |  | MET.32722040 | 37508:14 | 309:36 | 2026-10-05 | H
| 6 | 212600-02-1 | 212600-02-1 (5) / OVERRIDE FUNCTION (BLOWER AND EXTRACT) OPC | 212600-02-1 (5) / OVERRIDE FUNCTION (BLOWER AND EXTRACT) OPC (32722051) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-02-1 (5) / OVERRIDE FUNCTION (BLOWER AND EXTRACT) OPC (32722051) |  | 0 / 1 | [] |  |  | MET.32722051 | 29.Jun.2028 | 668 | 2028-06-29 | D
| 7 | 212600-11-1 | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32722021) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R (32722021) |  | 0 / 4 | [] |  |  | MET.32722021 | 37508:14 | 309:36 | 2026-10-05 | H
| 8 | 23-71-00-00-A | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING (32722034) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] |  |  |  |  | 23-71-00-00-A (01) / CVR DATA DOWNLOADING ON WING (32722034) |  | 0 / 5 | [] |  |  | MET.32722034 | 07.Mar.2027 | 188 | 2027-03-07 | D
| 9 | 237100-01-1 | 237100-01-1 (02) / COCKPIT VOICE RECORDER OPC | 237100-01-1 (02) / COCKPIT VOICE RECORDER OPC (25495527) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-13 |  | [] | PRE HGR |  |  |  | 237100-01-1 (02) / COCKPIT VOICE RECORDER OPC (25495527) |  | 0 / 1 | [] |  |  | MET.25495527 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 10 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32722027) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-41 |  | [] | OPS/LK |  |  |  | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32722027) |  | 0 / 1 | [] |  |  | MET.32722027 | 37508:14 | 309:36 | 2026-10-05 | H
| 11 | 242100-01-1-001 | 242100-01-1-001 (01) / NO.1 ENG (QAD)ADAPTER TENSION BOLT | 242100-01-1-001 (01) / NO.1 ENG (QAD)ADAPTER TENSION BOLT (25495632) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.040972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-21 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 242100-01-1-001 (01) / NO.1 ENG (QAD)ADAPTER TENSION BOLT (25495632) |  | 0 / 4 | [] |  |  | MET.25495632 | 38050:09 | 851:31 | 2026-12-09 | H
| 12 | 242100-01-1-002 | 242100-01-1-002 (01) / NO.2 ENG (QAD)ADAPTER TENSION BOLT | 242100-01-1-002 (01) / NO.2 ENG (QAD)ADAPTER TENSION BOLT (25470465) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.040972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-21 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 242100-01-1-002 (01) / NO.2 ENG (QAD)ADAPTER TENSION BOLT (25470465) |  | 0 / 4 | [] |  |  | MET.25470465 | 38050:09 | 851:31 | 2026-12-09 | H
| 13 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32722014) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-28 |  | [] | OPS/LK |  |  |  | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32722014) |  | 0 / 1 | [] |  |  | MET.32722014 | 37508:14 | 309:36 | 2026-10-05 | H
| 14 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32722037) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-38 |  | [] | OPS/LK |  |  |  | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32722037) |  | 0 / 1 | [] |  |  | MET.32722037 | 37508:14 | 309:36 | 2026-10-05 | H
| 15 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 25-10-00-00-SVA (00) / COCKPIT CHECK (31510236) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28472 | 04.Sep.2026 22:00 | 0.28472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-10-00-00-SVA (00) / COCKPIT CHECK (31510236) |  | 0 / 15 | [] |  |  | MET.31510236 | 37508:14 | 309:36 | 2026-10-05 | H
| 16 | 25-11-00-07-0-SVA-001 | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION (32722032) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-07-0-SVA-001 (04) / FOURTH OCCUPANT SEAT LUBRICATION (32722032) |  | 0 / 1 | [] |  |  | MET.32722032 | 37650:09 | 451:31 | 2026-10-22 | H
| 17 | 25-11-00-19-0-SVA | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION (32722039) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-19-0-SVA (02) / THIRD OCCUPANT SEAT LUBRICATION (32722039) |  | 0 / 1 | [] |  |  | MET.32722039 | 37900:09 | 701:31 | 2026-11-21 | H
| 18 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32722042) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.45139 | 04.Sep.2026 22:00 | 0.45139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP (32722042) |  | 0 / 22 | [] |  |  | MET.32722042 | 37508:14 | 309:36 | 2026-10-05 | H
| 19 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32722001) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25347 | 04.Sep.2026 22:00 | 0.25347 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP (32722001) |  | 0 / 13 | [] |  |  | MET.32722001 | 37508:14 | 309:36 | 2026-10-05 | H
| 20 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32722043) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 04.Sep.2026 22:00 | 0.28819 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP (32722043) |  | 0 / 16 | [] |  |  | MET.32722043 | 37508:14 | 309:36 | 2026-10-05 | H
| 21 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32722017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11458 | 04.Sep.2026 22:00 | 0.11458 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP (32722017) |  | 0 / 6 | [] |  |  | MET.32722017 | 37508:14 | 309:36 | 2026-10-05 | H
| 22 | 25-26-00-03-0-SVA | 25-26-00-03-0-SVA (04) / PASS COMPT CURTAIN RAILS INSPECTION | 25-26-00-03-0-SVA (04) / PASS COMPT CURTAIN RAILS INSPECTION (32722007) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-26 |  | [] | PRE INSP |  |  |  | 25-26-00-03-0-SVA (04) / PASS COMPT CURTAIN RAILS INSPECTION (32722007) |  | 0 / 1 | [] |  |  | MET.32722007 | 37650:09 | 451:31 | 2026-10-22 | H
| 23 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32722047) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-26 |  | [] | TC/P |  |  |  | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT (32722047) |  | 0 / 1 | [] |  |  | MET.32722047 | 37508:14 | 309:36 | 2026-10-05 | H
| 24 | 25-28-00-03-0-SVA-003 | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R (31764964) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | PRE INSP |  |  |  | 25-28-00-03-0-SVA-003 (05) / HZ-ASH TO ASW AISLE CARPETS R/R (31764964) |  | 0 / 1 | [] |  |  | MET.31764964 | 37508:14 | 309:36 | 2026-10-05 | H
| 25 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29291052) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] | PRE INSP |  |  |  | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC (29291052) |  | 0 / 1 | [] |  |  | MET.29291052 | 37508:14 | 309:36 | 2026-10-05 | H
| 26 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 25-32-00-00-SVA (01) / GALLEY CHECK (32721818) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.28819 | 04.Sep.2026 22:00 | 0.28819 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-32-00-00-SVA (01) / GALLEY CHECK (32721818) |  | 0 / 16 | [] |  |  | MET.32721818 | 37508:14 | 309:36 | 2026-10-05 | H
| 27 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 25-40-00-00-SVA (01) / LAV CHECK (32721822) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30903 | 04.Sep.2026 22:00 | 0.30903 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  | AS PR T/Q685629 | 25-40-00-00-SVA (01) / LAV CHECK (32721822) |  | 0 / 18 | [] |  |  | MET.32721822 | 37508:14 | 309:36 | 2026-10-05 | H
| 28 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29291075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] | PRE INSP |  |  |  | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29291075) |  | 0 / 1 | [] |  |  | MET.29291075 | 37508:14 | 309:36 | 2026-10-05 | H
| 29 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29291049) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  |  | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29291049) |  | 0 / 1 | [] |  |  | MET.29291049 | 37508:14 | 309:36 | 2026-10-05 | H
| 30 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32722050) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  | As per requested by CONF ENGG in T/Q CONF ENGG 805450. | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32722050) |  | 0 / 1 | [] |  |  | MET.32722050 | 16.Nov.2026 | 77 | 2026-11-16 | D
| 31 | 252100-04-1 | 252100-04-1 (04) / INFLATABLE RESTRAINT SYSTEM-ELECTRONICS MODULE ASS.(EMA) BATTERY R/R | 252100-04-1 (04) / INFLATABLE RESTRAINT SYSTEM-ELECTRONICS MODULE ASS.(EMA) BATTERY R/R (32722054) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P |  |  |  | 252100-04-1 (04) / INFLATABLE RESTRAINT SYSTEM-ELECTRONICS MODULE ASS.(EMA) BATTERY R/R (32722054) |  | 0 / 1 | [] |  |  | MET.32722054 | 37508:14 | 309:36 | 2026-10-05 | H
| 32 | 252100-05-1 | 252100-05-1 (05) / INFLATABLE RESTRAINT SYS-GAS STORAGE AND SQUIB VALIDITY CHECK | 252100-05-1 (05) / INFLATABLE RESTRAINT SYS-GAS STORAGE AND SQUIB VALIDITY CHECK (32722029) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.68611 | 04.Sep.2026 22:00 | 0.68611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | PRE INSP |  |  |  | 252100-05-1 (05) / INFLATABLE RESTRAINT SYS-GAS STORAGE AND SQUIB VALIDITY CHECK (32722029) |  | 0 / 1 | [] |  |  | MET.32722029 | 37508:14 | 309:36 | 2026-10-05 | H
| 33 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 253400-01-1. (03) / GALLEY COOLING CLEANING (32721999) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013889 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 253400-01-1. (03) / GALLEY COOLING CLEANING (32721999) |  | 0 / 2 | [] |  |  | MET.32721999 | 38008:14 | 809:36 | 2026-12-04 | H
| 34 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32722013) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-34 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING (32722013) |  | 0 / 8 | [] |  |  | MET.32722013 | 37508:14 | 309:36 | 2026-10-05 | H
| 35 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP (32722006) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP (32722006) |  | 0 / 1 | [] |  |  | MET.32722006 | 37508:14 | 309:36 | 2026-10-05 | H
| 36 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32722060) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32722060) |  | 0 / 1 | [] |  |  | MET.32722060 | 37508:14 | 309:36 | 2026-10-05 | H
| 37 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32721817) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-62 |  | [] | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK |  |  |  | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32721817) |  | 0 / 4 | [] |  |  | MET.32721817 | 29'769 | 583 | 2026-11-19 | C
| 38 | 256600-02-1 | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK (29290983) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-66 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 256600-02-1 (02) / SUPPLEMENTAL LIFE/RAFT PRES CHK (29290983) |  | 0 / 3 | [] |  |  | MET.29290983 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 39 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32722009) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-12 |  | [] | OPS/LK |  |  |  | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32722009) |  | 0 / 1 | [] |  |  | MET.32722009 | 37508:14 | 309:36 | 2026-10-05 | H
| 40 | 261300-01-1 | 261300-01-1 (4) / APU FIRE AND OVERHEAT DETECTION OPC | 261300-01-1 (4) / APU FIRE AND OVERHEAT DETECTION OPC (32722020) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-13 |  | [] | OPS/LK |  |  |  | 261300-01-1 (4) / APU FIRE AND OVERHEAT DETECTION OPC (32722020) |  | 0 / 1 | [] |  |  | MET.32722020 | 37650:09 | 451:31 | 2026-10-22 | H
| 41 | 261600-03-1 | 261600-03-1 (3) / CGO`S SMOKE DETECTION OPS CHK | 261600-03-1 (3) / CGO`S SMOKE DETECTION OPS CHK (32722000) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-16 |  | [] | OPS/LK |  |  |  | 261600-03-1 (3) / CGO`S SMOKE DETECTION OPS CHK (32722000) |  | 0 / 1 | [] |  |  | MET.32722000 | 37650:09 | 451:31 | 2026-10-22 | H
| 42 | 261600-04-1 | 261600-04-1 (4) / CGO SMOKE DETECTION OPS CHK | 261600-04-1 (4) / CGO SMOKE DETECTION OPS CHK (31509606) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-16 |  | [] | OPS/LK |  |  |  | 261600-04-1 (4) / CGO SMOKE DETECTION OPS CHK (31509606) |  | 0 / 1 | [] |  |  | MET.31509606 | 37650:09 | 451:31 | 2026-10-22 | H
| 43 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32478480) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32478480) |  | 0 / 3 | [] |  |  | MET.32478480 | 37508:14 | 309:36 | 2026-10-05 | H
| 44 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32478490) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32478490) |  | 0 / 3 | [] |  |  | MET.32478490 | 37508:14 | 309:36 | 2026-10-05 | H
| 45 | 262441-01-1 | 262441-01-1 (3) / PORT FIRE EXT PRESS GAUGE CHK | 262441-01-1 (3) / PORT FIRE EXT PRESS GAUGE CHK (32722059) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-24 |  | [] | PRE INSP |  |  |  | 262441-01-1 (3) / PORT FIRE EXT PRESS GAUGE CHK (32722059) |  | 0 / 1 | [] |  |  | MET.32722059 | 37650:09 | 451:31 | 2026-10-22 | H
| 46 | 27-92-00-01-SVA | 27-92-00-01-SVA (02) / CAPTAIN AND FIRST OFFICER RADIO PTT SWITCH REPLACEMENT | 27-92-00-01-SVA (02) / CAPTAIN AND FIRST OFFICER RADIO PTT SWITCH REPLACEMENT (28379426) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 | 24.Jan.2026 22:20 | 1900-08-05 13:43 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, CLEAN-UP, OPS/LK |  |  | part sd, to be assign later ( should not takes more than 6 hours as per A/check) | 27-92-00-01-SVA (02) / CAPTAIN AND FIRST OFFICER RADIO PTT SWITCH REPLACEMENT (28379426) |  | 0 / 3 | [] |  |  | MET.28379426 | 30'403 | 1'217 | 2027-02-15 | C
| 47 | 273400-01-1 | 273400-01-1 (3) / ELEV DAMPING MEASUREMENT OPS TEST | 273400-01-1 (3) / ELEV DAMPING MEASUREMENT OPS TEST (32722003) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-96 |  | [] | OPS/LK |  |  |  | 273400-01-1 (3) / ELEV DAMPING MEASUREMENT OPS TEST (32722003) |  | 0 / 1 | [] |  |  | MET.32722003 | 40650:09 | 3451:31 | 2027-10-15 | H
| 48 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32722057) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK |  |  |  | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32722057) |  | 0 / 1 | [] |  |  | MET.32722057 | 37708:14 | 509:36 | 2026-10-29 | H
| 49 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32722041) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32722041) |  | 0 / 1 | [] |  |  | MET.32722041 | 38108:14 | 909:36 | 2026-12-16 | H
| 50 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32722004) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.58333 | 04.Sep.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32722004) |  | 0 / 6 | [] |  |  | MET.32722004 | 17.Mar.2027 | 198 | 2027-03-17 | D
| 51 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32722048) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 04.Sep.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32722048) |  | 0 / 2 | [] |  |  | MET.32722048 | 30'459 | 1'273 | 2027-02-23 | C
| 52 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32722031) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 04.Sep.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32722031) |  | 0 / 2 | [] |  |  | MET.32722031 | 30'459 | 1'273 | 2027-02-23 | C
| 53 | 276400-01-1-001 | 276400-01-1-001 (02) / L/H SPOILER AND HYDR ACTUATION LUBR | 276400-01-1-001 (02) / L/H SPOILER AND HYDR ACTUATION LUBR (32722028) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.049306 | 04.Sep.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 276400-01-1-001 (02) / L/H SPOILER AND HYDR ACTUATION LUBR (32722028) |  | 0 / 1 | [] |  |  | MET.32722028 | 37650:09 | 451:31 | 2026-10-22 | H
| 54 | 276400-01-1-002 | 276400-01-1-002 (02) / R/H SPOILER AND HYDR ACTUATION LUBR | 276400-01-1-002 (02) / R/H SPOILER AND HYDR ACTUATION LUBR (32722033) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.049306 | 04.Sep.2026 22:00 | 0.024306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 276400-01-1-002 (02) / R/H SPOILER AND HYDR ACTUATION LUBR (32722033) |  | 0 / 1 | [] |  |  | MET.32722033 | 37650:09 | 451:31 | 2026-10-22 | H
| 55 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 281100-02-1 (3) / TANKS WATER DRAIN (32722026) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | OPS/LK |  |  |  | 281100-02-1 (3) / TANKS WATER DRAIN (32722026) |  | 0 / 1 | [] |  |  | MET.32722026 | 37508:14 | 309:36 | 2026-10-05 | H
| 56 | 281100-05-1 | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32722022) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS (32722022) |  | 0 / 3 | [] |  |  | MET.32722022 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 57 | 281100-06-1 | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32722015) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES (32722015) |  | 0 / 2 | [] |  |  | MET.32722015 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 58 | 281200-01-1-001 | 281200-01-1-001 (04) / L/H WING SURGE TANK BURST DISC INSP | 281200-01-1-001 (04) / L/H WING SURGE TANK BURST DISC INSP (32722058) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 281200-01-1-001 (04) / L/H WING SURGE TANK BURST DISC INSP (32722058) |  | 0 / 3 | [] |  |  | MET.32722058 | 37650:09 | 451:31 | 2026-10-22 | H
| 59 | 281200-01-1-002 | 281200-01-1-002 (04) / R/H WING SURGE TANK BURST DISC INSP | 281200-01-1-002 (04) / R/H WING SURGE TANK BURST DISC INSP (32722046) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 281200-01-1-002 (04) / R/H WING SURGE TANK BURST DISC INSP (32722046) |  | 0 / 3 | [] |  |  | MET.32722046 | 37650:09 | 451:31 | 2026-10-22 | H
| 60 | 290000-05-1 | 290000-05-1 (6) / HYDRAULIC SYSTEM FILTERS CLOGGING INDICATORS CHECK | 290000-05-1 (6) / HYDRAULIC SYSTEM FILTERS CLOGGING INDICATORS CHECK (32721998) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 290000-05-1 (6) / HYDRAULIC SYSTEM FILTERS CLOGGING INDICATORS CHECK (32721998) |  | 0 / 1 | [] |  |  | MET.32721998 | 37650:09 | 451:31 | 2026-10-22 | H
| 61 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32722025) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | TC/P |  |  |  | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32722025) |  | 0 / 1 | [] |  |  | MET.32722025 | 37508:14 | 309:36 | 2026-10-05 | H
| 62 | 291000-05-1 | 291000-05-1 (2) / MAIN HYDRAULIC POWER SERVICING | 291000-05-1 (2) / MAIN HYDRAULIC POWER SERVICING (32722038) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-14 |  | [] | TC/P |  |  |  | 291000-05-1 (2) / MAIN HYDRAULIC POWER SERVICING (32722038) |  | 0 / 1 | [] |  |  | MET.32722038 | 37900:09 | 701:31 | 2026-11-21 | H
| 63 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32722052) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-27 |  | [] | TC/P |  |  |  | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32722052) |  | 0 / 1 | [] |  |  | MET.32722052 | 38008:14 | 809:36 | 2026-12-04 | H
| 64 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29291011) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-63 |  | [] | CLEAN-UP |  |  |  | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29291011) |  | 0 / 1 | [] |  |  | MET.29291011 | 38008:14 | 809:36 | 2026-12-04 | H
| 65 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32722010) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-30 |  | [] | PRE HGR |  |  |  | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32722010) |  | 0 / 1 | [] |  |  | MET.32722010 | 37508:14 | 309:36 | 2026-10-05 | H
| 66 | 32-47-00-SVA | 32-47-00-SVA (00) / BRAKE TEMPRETURE SENSOR CLEANING | 32-47-00-SVA (00) / BRAKE TEMPRETURE SENSOR CLEANING (25495763) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-47 |  | [] | JOB-SETUP, TC/P, --, CLOSE-UP, CLOSE-UP |  |  |  | 32-47-00-SVA (00) / BRAKE TEMPRETURE SENSOR CLEANING (25495763) |  | 0 / 5 | [] |  |  | MET.25495763 | 37650:09 | 451:31 | 2026-10-22 | H
| 67 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32722011) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32722011) |  | 0 / 1 | [] |  |  | MET.32722011 | 37508:14 | 309:36 | 2026-10-05 | H
| 68 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT (32722045) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT (32722045) |  | 0 / 1 | [] |  |  | MET.32722045 | 37508:14 | 309:36 | 2026-10-05 | H
| 69 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT (32722002) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 04.Sep.2026 22:00 | 0.0048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT (32722002) |  | 0 / 1 | [] |  |  | MET.32722002 | 37508:14 | 309:36 | 2026-10-05 | H
| 70 | 323000-19-1 | 323000-19-1 (4) / (LG) EXT AND RETR COMPNENTS INSP | 323000-19-1 (4) / (LG) EXT AND RETR COMPNENTS INSP (32722024) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.21944 | 04.Sep.2026 22:00 | 0.21944 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 323000-19-1 (4) / (LG) EXT AND RETR COMPNENTS INSP (32722024) |  | 0 / 7 | [] |  |  | MET.32722024 | 37650:09 | 451:31 | 2026-10-22 | H
| 71 | 331400-01-1 | 331400-01-1 (3) / ANNUNCIATOR LIGHTS OPERATIONAL CHECK | 331400-01-1 (3) / ANNUNCIATOR LIGHTS OPERATIONAL CHECK (32722056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 33-14 |  | [] | OPS/LK |  |  |  | 331400-01-1 (3) / ANNUNCIATOR LIGHTS OPERATIONAL CHECK (32722056) |  | 0 / 1 | [] |  |  | MET.32722056 | 37650:09 | 451:31 | 2026-10-22 | H
| 72 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32722012) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | CLEAN-UP |  |  |  | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32722012) |  | 0 / 1 | [] |  |  | MET.32722012 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 73 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32722008) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 04.Sep.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32722008) |  | 0 / 3 | [] |  |  | MET.32722008 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 74 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 353000-05-1 (5) / CABIN PBE INSP (32722019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 353000-05-1 (5) / CABIN PBE INSP (32722019) |  | 0 / 3 | [] |  |  | MET.32722019 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 75 | 36-11-00-SVA-02-001 | 36-11-00-SVA-02-001 (01) / NO. 1 ENGINE BLEED AIR SYSTEM (EBAS) HEALTH CHECK PREVENTEN MAINTENANCE PROGRAM | 36-11-00-SVA-02-001 (01) / NO. 1 ENGINE BLEED AIR SYSTEM (EBAS) HEALTH CHECK PREVENTEN MAINTENANCE PROGRAM (31510167) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34028 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] | JOB-SETUP, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 36-11-00-SVA-02-001 (01) / NO. 1 ENGINE BLEED AIR SYSTEM (EBAS) HEALTH CHECK PREVENTEN MAINTENANCE PROGRAM (31510167) |  | 0 / 6 | [] |  |  | MET.31510167 | 40444:05 | 3245:27 | 2027-09-20 | H
| 76 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29291009) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 04.Sep.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29291009) |  | 0 / 7 | [] |  |  | MET.29291009 | 29'659 | 473 | 2026-11-04 | C
| 77 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29291060) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 04.Sep.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29291060) |  | 0 / 7 | [] |  |  | MET.29291060 | 37508:14 | 309:36 | 2026-10-05 | H
| 78 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32721821) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-10 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  | AS PER T/Q: 740971 | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM (32721821) |  | 0 / 3 | [] |  |  | MET.32721821 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 79 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32722044) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-32 |  | [] | CLEAN-UP, CLEAN-UP, CLEAN-UP |  |  |  | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING (32722044) |  | 0 / 3 | [] |  |  | MET.32722044 | 38008:14 | 809:36 | 2026-12-04 | H
| 80 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31510223) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 04.Sep.2026 22:00 | 0.076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31510223) |  | 0 / 3 | [] |  |  | MET.31510223 | 37508:14 | 309:36 | 2026-10-05 | H
| 81 | 491200-B2-1 | 491200-B2-1 (04) / GVI OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY. | 491200-B2-1 (04) / GVI OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY. (32722030) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.066667 | 04.Sep.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 49-12 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 491200-B2-1 (04) / GVI OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY. (32722030) |  | 0 / 4 | [] |  |  | MET.32722030 | 30'845 | 1'659 | 2027-04-18 | C
| 82 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29290988) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | JOB-SETUP, --, --, -- |  |  | TQ: 792422 | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29290988) |  | 0 / 4 | [] |  |  | MET.29290988 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 83 | 52-32-00-01-0-SVA | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29290996) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.055556 | 04.Sep.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | CLEAN-UP, TC/P, TC/P, --, JOB-CLOSEUP |  |  |  | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING (29290996) |  | 0 / 5 | [] |  |  | MET.29290996 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 84 | 523000-01-1-001 | 523000-01-1-001 (03) / FORWARD CARGO DOOR LUBRICATION | 523000-01-1-001 (03) / FORWARD CARGO DOOR LUBRICATION (32722018) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523000-01-1-001 (03) / FORWARD CARGO DOOR LUBRICATION (32722018) |  | 0 / 6 | [] |  |  | MET.32722018 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 85 | 523000-01-1-002 | 523000-01-1-002 (03) / AFT CARGO DOOR LUBRICATION | 523000-01-1-002 (03) / AFT CARGO DOOR LUBRICATION (32722055) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 523000-01-1-002 (03) / AFT CARGO DOOR LUBRICATION (32722055) |  | 0 / 6 | [] |  |  | MET.32722055 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 86 | 523000-03-1-001 | 523000-03-1-001 (03) / FWD CARGO DOOR HANDLE LUBRICATION | 523000-03-1-001 (03) / FWD CARGO DOOR HANDLE LUBRICATION (32722053) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.015972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 523000-03-1-001 (03) / FWD CARGO DOOR HANDLE LUBRICATION (32722053) |  | 0 / 5 | [] |  |  | MET.32722053 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 87 | 523000-03-1-002 | 523000-03-1-002 (03) / AFT CARGO DOOR HANDLE LUBRICATION | 523000-03-1-002 (03) / AFT CARGO DOOR HANDLE LUBRICATION (32722016) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.015972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 523000-03-1-002 (03) / AFT CARGO DOOR HANDLE LUBRICATION (32722016) |  | 0 / 5 | [] |  |  | MET.32722016 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 88 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32722049) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32722049) |  | 0 / 3 | [] |  |  | MET.32722049 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 89 | 533154-05-1-A | 533154-05-1-A (03) / MLG ACT FITTINGS KEEL BEAM INSP | 533154-05-1-A (03) / MLG ACT FITTINGS KEEL BEAM INSP (28388283) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">20</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 01:40 | 04.Sep.2026 22:00 | 0.73611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, JOB-SETUP, --, X-RAY / NDT, INSPECTION, --, --, --, --, --, --, --, -- |  |  |  | 533154-05-1-A (03) / MLG ACT FITTINGS KEEL BEAM INSP (28388283) |  | 0 / 13 | [] |  |  | MET.28388283 | 30'264 | 1'078 | 2027-01-27 | C
| 90 | 31674595 | EOD-321-53-00065-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL | 31674595 / EOD-321-53-00065-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL (31674595) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">11</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 04:30 | 04.Sep.2026 22:00 | 0.97222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31674595 / EOD-321-53-00065-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL (31674595) |  | 0 / 19 | [] |  |  | ME.31674595 | 30'909 | 1'723 | 2027-04-26 | C
| 91 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29291089) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14583 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29291089) |  | 0 / 4 | [] |  |  | MET.29291089 | 37508:14 | 309:36 | 2026-10-05 | H
| 92 | 561000-02-1 | 561000-02-1 (01) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS. | 561000-02-1 (01) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS. (32721996) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 561000-02-1 (01) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS. (32721996) |  | 0 / 1 | [] |  |  | MET.32721996 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 93 | 711300-C2-1-001 | 711300-C2-1-001 (02) / NO. 1 ENG FAN COWL LOCKING DEVICE INSP | 711300-C2-1-001 (02) / NO. 1 ENG FAN COWL LOCKING DEVICE INSP (25439539) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 711300-C2-1-001 (02) / NO. 1 ENG FAN COWL LOCKING DEVICE INSP (25439539) |  | 0 / 4 | [] |  |  | MET.25439539 | 30'014 | 828 | 2026-12-23 | C
| 94 | 711300-C2-1-002 | 711300-C2-1-002 (02) / NO. 2 ENG FAN COWL LOCKING DEVICE INSP | 711300-C2-1-002 (02) / NO. 2 ENG FAN COWL LOCKING DEVICE INSP (25495693) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 711300-C2-1-002 (02) / NO. 2 ENG FAN COWL LOCKING DEVICE INSP (25495693) |  | 0 / 4 | [] |  |  | MET.25495693 | 30'014 | 828 | 2026-12-23 | C
| 95 | 72-00-00-01-0-SVA-001 | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29291014) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 04.Sep.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH (29291014) |  | 0 / 11 | [] |  |  | MET.29291014 | 38008:14 | 809:36 | 2026-12-04 | H
| 96 | 72-00-00-01-0-SVA-002 | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29291013) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 04.Sep.2026 22:00 | 0.40972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72-00 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH (29291013) |  | 0 / 11 | [] |  |  | MET.29291013 | 38008:14 | 809:36 | 2026-12-04 | H
| 97 | 722000-C1-1-001 | 722000-C1-1-001 (04) / NO. 1 ENGINE INLET FAN SECTION INSP | 722000-C1-1-001 (04) / NO. 1 ENGINE INLET FAN SECTION INSP (25133141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72-20 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 722000-C1-1-001 (04) / NO. 1 ENGINE INLET FAN SECTION INSP (25133141) |  | 0 / 3 | [] |  |  | MET.25133141 | 30'014 | 828 | 2026-12-23 | C
| 98 | 722000-C1-1-002 | 722000-C1-1-002 (04) / NO. 2 ENGINE INLET FAN SECTION INSP | 722000-C1-1-002 (04) / NO. 2 ENGINE INLET FAN SECTION INSP (25133140) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72-23 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 722000-C1-1-002 (04) / NO. 2 ENGINE INLET FAN SECTION INSP (25133140) |  | 0 / 3 | [] |  |  | MET.25133140 | 30'014 | 828 | 2026-12-23 | C
| 99 | 792000-C8-1-001 | 792000-C8-1-001 (03) / NO. 1 ENGINE EMCD CHECK | 792000-C8-1-001 (03) / NO. 1 ENGINE EMCD CHECK (28394722) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 79-00 |  | [] | OPS/LK |  |  |  | 792000-C8-1-001 (03) / NO. 1 ENGINE EMCD CHECK (28394722) |  | 0 / 1 | [] |  |  | MET.28394722 | 37650:09 | 451:31 | 2026-10-22 | H
| 100 | 792000-C8-1-002 | 792000-C8-1-002 (03) / NO. 2 ENGINE EMCD CHECK | 792000-C8-1-002 (03) / NO. 2 ENGINE EMCD CHECK (28358178) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 79-00 |  | [] | OPS/LK |  |  |  | 792000-C8-1-002 (03) / NO. 2 ENGINE EMCD CHECK (28358178) |  | 0 / 1 | [] |  |  | MET.28358178 | 37650:09 | 451:31 | 2026-10-22 | H
| 101 | 801110-C1-1-001 | 801110-C1-1-001 (03) / NO. 1 ENGINE STARTER CHIP DETECTOR | 801110-C1-1-001 (03) / NO. 1 ENGINE STARTER CHIP DETECTOR (28358433) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.06875 | 04.Sep.2026 22:00 | 0.06875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 80-11 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | step 3 added by P/P Mohammed said m Basaif ENGG sent mail as folowing: MPD TASK 801110-C1-1 Reference to TASKs 801110-C1-1-001 and 801110-C1-1-002, the Work Template requires amend as follows: Step 1: No change (keep as is) Step 2: (amend as follows) Take pictures of the magnetic plug probe, and particles Carefully examine and record the maximum size of the particles and decide the serviceability of the starter accordingly Record the added oil quantity. Issue work order to: Attach the pictures of the magnetic plug probe The record of particles maximum size The record of added oil quantity | 801110-C1-1-001 (03) / NO. 1 ENGINE STARTER CHIP DETECTOR (28358433) |  | 0 / 3 | [] |  |  | MET.28358433 | 37650:09 | 451:31 | 2026-10-22 | H
| 102 | 801110-C1-1-002 | 801110-C1-1-002 (03) / NO. 2 ENGINE STARTER CHIP DETECTOR | 801110-C1-1-002 (03) / NO. 2 ENGINE STARTER CHIP DETECTOR (28358548) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.06875 | 04.Sep.2026 22:00 | 0.06875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 80-11 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | step 3 added by P/P Mohammed said m Basaif ENGG sent mail as folowing: MPD TASK 801110-C1-1 Reference to TASKs 801110-C1-1-001 and 801110-C1-1-002, the Work Template requires amend as follows: Step 1: No change (keep as is) Step 2: (amend as follows) Take pictures of the magnetic plug probe, and particles Carefully examine and record the maximum size of the particles and decide the serviceability of the starter accordingly Record the added oil quantity. Issue work order to: Attach the pictures of the magnetic plug probe The record of particles maximum size The record of added oil quantity | 801110-C1-1-002 (03) / NO. 2 ENGINE STARTER CHIP DETECTOR (28358548) |  | 0 / 3 | [] |  |  | MET.28358548 | 37650:09 | 451:31 | 2026-10-22 | H
| 103 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29291008) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29291008) |  | 0 / 3 | [] |  |  | MET.29291008 | 37708:14 | 509:36 | 2026-10-29 | H
| 104 | 801110-C3-1-002 | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29291007) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT (29291007) |  | 0 / 3 | [] |  |  | MET.29291007 | 37708:14 | 509:36 | 2026-10-29 | H
| 105 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29290982) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23611 | 04.Sep.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29290982) |  | 0 / 2 | [] |  |  | MET.29290982 | 38008:14 | 809:36 | 2026-12-04 | H
| 106 | ZL-147-02-1 | ZL-147-02-1 (03) / MLG-WELL AND HYD COMP. ZONAL INSP | ZL-147-02-1 (03) / MLG-WELL AND HYD COMP. ZONAL INSP (32722036) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-147-02-1 (03) / MLG-WELL AND HYD COMP. ZONAL INSP (32722036) |  | 0 / 1 | [] |  |  | MET.32722036 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 107 | ZL-400-02-1-001 | ZL-400-02-1-001 (02) / NO. 1 ENG NACELLES AND PYLONS INSP | ZL-400-02-1-001 (02) / NO. 1 ENG NACELLES AND PYLONS INSP (25428046) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-400-02-1-001 (02) / NO. 1 ENG NACELLES AND PYLONS INSP (25428046) |  | 0 / 1 | [] |  |  | MET.25428046 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 108 | ZL-400-02-1-002 | ZL-400-02-1-002 (02) / NO. 2 ENG NACELLES AND PYLONS INSP | ZL-400-02-1-002 (02) / NO. 2 ENG NACELLES AND PYLONS INSP (25495582) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-400-02-1-002 (02) / NO. 2 ENG NACELLES AND PYLONS INSP (25495582) |  | 0 / 1 | [] |  |  | MET.25495582 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 109 | ZL-711-01-1 | ZL-711-01-1 (03) / NLG AND NOSE GEAR DOORS ZONAL INSP | ZL-711-01-1 (03) / NLG AND NOSE GEAR DOORS ZONAL INSP (32721990) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP |  |  |  | ZL-711-01-1 (03) / NLG AND NOSE GEAR DOORS ZONAL INSP (32721990) |  | 0 / 1 | [] |  |  | MET.32721990 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 110 | ZL-731-01-1 | ZL-731-01-1 (03) / MAIN LANDING GEAR ZONAL INSPECTION | ZL-731-01-1 (03) / MAIN LANDING GEAR ZONAL INSPECTION (32722061) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP, PRE INSP |  |  |  | ZL-731-01-1 (03) / MAIN LANDING GEAR ZONAL INSPECTION (32722061) |  | 0 / 2 | [] |  |  | MET.32722061 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 111 | 31956352 | C_N (C_N07)/C-CHECK | 31956352 / C_N (C_N07)/C-CHECK (31956352) | Check | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31956352 / C_N (C_N07)/C-CHECK (31956352) |  | 0 / 1 | [] |  |  | ME.31956352 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 113 | 08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32721815) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-01 17:00 | 04.Sep.2026 22:00 | 0.83333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 08-10 |  | [] | WT&BAL |  |  |  | 08-10-00-01-0-A (02) / WIGHT & BALANCE (32721815) |  | 0 / 1 | [] |  |  | MET.32721815 | 18.Oct.2028 | 779 | 2028-10-18 | D
| 114 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32721863) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32721863) |  | 0 / 1 | [] |  |  | MET.32721863 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 115 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390046) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 04.Sep.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390046) |  | 0 / 3 | [] |  |  | MET.28390046 | 19.Dec.2027 | 475 | 2027-12-19 | D
| 116 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349999) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 04.Sep.2026 22:00 | 0.0375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349999) |  | 0 / 3 | [] |  |  | MET.28349999 | 19.Dec.2027 | 475 | 2027-12-19 | D
| 117 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32721877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 04.Sep.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32721877) |  | 0 / 3 | [] |  |  | MET.32721877 | 19.Dec.2027 | 475 | 2027-12-19 | D
| 118 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32721871) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022222 | 04.Sep.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32721871) |  | 0 / 3 | [] |  |  | MET.32721871 | 19.Dec.2027 | 475 | 2027-12-19 | D
| 119 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32721886) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32721886) |  | 0 / 1 | [] |  |  | MET.32721886 | 40988:17 | 3789:39 | 2027-11-24 | H
| 120 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32721880) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32721880) |  | 0 / 1 | [] |  |  | MET.32721880 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 121 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32721957) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32721957) |  | 0 / 1 | [] |  |  | MET.32721957 | 40988:17 | 3789:39 | 2027-11-24 | H
| 122 | 213100-02-1 | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32721879) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC (32721879) |  | 0 / 1 | [] |  |  | MET.32721879 | 40988:17 | 3789:39 | 2027-11-24 | H
| 123 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32721838) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 04.Sep.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-61 |  | [] | PRE HGR |  |  |  | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32721838) |  | 0 / 1 | [] |  |  | MET.32721838 | 40988:17 | 3789:39 | 2027-11-24 | H
| 124 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32721950) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14653 | 04.Sep.2026 22:00 | 0.12222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32721950) |  | 0 / 5 | [] |  |  | MET.32721950 | 40988:17 | 3789:39 | 2027-11-24 | H
| 125 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32721903) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.10972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-63 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK |  |  |  | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32721903) |  | 0 / 5 | [] |  |  | MET.32721903 | 40988:17 | 3789:39 | 2027-11-24 | H
| 126 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19890175) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-73 |  | [] | OPS/LK |  |  |  | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19890175) |  | 0 / 1 | [] |  |  | MET.19890175 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 127 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32721855) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.014583 | 04.Sep.2026 22:00 | 0.011806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32721855) |  | 0 / 3 | [] |  |  | MET.32721855 | 17.Sep.2026 | 17 | 2026-09-17 | D
| 128 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32721835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-22 |  | [] | OPS/LK |  |  |  | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32721835) |  | 0 / 1 | [] |  |  | MET.32721835 | 40988:17 | 3789:39 | 2027-11-24 | H
| 129 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32721856) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-25 |  | [] | OPS/LK |  |  |  | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32721856) |  | 0 / 1 | [] |  |  | MET.32721856 | 40988:17 | 3789:39 | 2027-11-24 | H
| 130 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 243000-13-1 (01) / DC GENERATION (32721833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-13-1 (01) / DC GENERATION (32721833) |  | 0 / 3 | [] |  |  | MET.32721833 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 131 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 243000-14-1 (01) / DC GENERATION (32721828) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0020833 | 04.Sep.2026 22:00 | 0.043056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-30 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-14-1 (01) / DC GENERATION (32721828) |  | 0 / 3 | [] |  |  | MET.32721828 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 132 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32721860) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 04.Sep.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-32 |  | [] | OPS/LK |  |  |  | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32721860) |  | 0 / 1 | [] |  |  | MET.32721860 | 40988:17 | 3789:39 | 2027-11-24 | H
| 133 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32721935) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 04.Sep.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 24-34 |  | [] | OPS/LK |  |  |  | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32721935) |  | 0 / 1 | [] |  |  | MET.32721935 | 40988:17 | 3789:39 | 2027-11-24 | H
| 134 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019483) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] |  |  |  |  | 25-11-00-03-0-SVA-001 (03) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019483) |  | 0 / 2 | [] |  |  | MET.33019483 | 25.Sep.2029 | 1121 | 2029-09-25 | D
| 135 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32721841) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | INSPECTION, -- |  |  |  | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT (32721841) |  | 0 / 2 | [] |  |  | MET.32721841 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 136 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32721894) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P, TC/P |  |  |  | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT (32721894) |  | 0 / 2 | [] |  |  | MET.32721894 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 137 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019482) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | PRE INSP, -- |  |  |  | 25-11-00-17-0-SVA-002 (04) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (33019482) |  | 0 / 2 | [] |  |  | MET.33019482 | 25.Sep.2029 | 1121 | 2029-09-25 | D
| 138 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT (33113081) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P |  |  |  | 25-28-00-04-0-SVA-002 (04) / COCKPIT COMPARTMENT CARPETS REPLCMNT (33113081) |  | 0 / 1 | [] |  |  | MET.33113081 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 139 | 25-28-00-04-0-SVA-004 | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R (28342269) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 12:00 | 04.Sep.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P, TC/P, TC/P, TC/P, -- |  |  |  | 25-28-00-04-0-SVA-004 (01) / A321 (HZ-ASH TO ASW) CARPETS&MATS R/R (28342269) |  | 0 / 5 | [] |  |  | MET.28342269 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 140 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 25-SVA-01 (01) / COCKPIT CHECK (32721918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14583 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-01 (01) / COCKPIT CHECK (32721918) |  | 0 / 17 | [] |  |  | MET.32721918 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 141 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32721948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.69444 | 04.Sep.2026 22:00 | 0.69444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK (32721948) |  | 0 / 21 | [] |  |  | MET.32721948 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 142 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 25-SVA-05 (01) / G/C SEAT REFRESH (32721941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.75 | 04.Sep.2026 22:00 | 0.75 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | As per T/Q: 759627 adding step 14 | 25-SVA-05 (01) / G/C SEAT REFRESH (32721941) |  | 0 / 14 | [] |  |  | MET.32721941 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 143 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 25-SVA-06 (01) / GALLEY REFRESH (32721969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-06 (01) / GALLEY REFRESH (32721969) |  | 0 / 1 | [] |  |  | MET.32721969 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 144 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 25-SVA-07 (01) / LAV REFRESH (32721846) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-07 (01) / LAV REFRESH (32721846) |  | 0 / 1 | [] |  |  | MET.32721846 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 145 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32721914) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP (32721914) |  | 0 / 1 | [] |  |  | MET.32721914 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 146 | 252100-01-0-SVA | 252100-01-0-SVA (04) / GUEST CLASS (G/C) PAX SEAT RECLINE AT EMRGENCY EXIT INSPECTION | 252100-01-0-SVA (04) / GUEST CLASS (G/C) PAX SEAT RECLINE AT EMRGENCY EXIT INSPECTION (32721824) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | PRE INSP |  |  |  | 252100-01-0-SVA (04) / GUEST CLASS (G/C) PAX SEAT RECLINE AT EMRGENCY EXIT INSPECTION (32721824) |  | 0 / 1 | [] |  |  | MET.32721824 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 147 | 252100-01-0-SVA-003 | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT (23589458) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">13</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-02 | 04.Sep.2026 22:00 | 0.5 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  | as REQ in T/Q: 791821. | 252100-01-0-SVA-003 (02) / PASSENGER SEAT COVERS REPLACEMENT (23589458) |  | 0 / 2 | [] |  |  | MET.23589458 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 148 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32721974) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P |  |  | As per T/Q: 791828 from INT ENGG PN has been updated. | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C (32721974) |  | 0 / 2 | [] |  |  | MET.32721974 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 149 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32721823) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.625 | 04.Sep.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C (32721823) |  | 0 / 4 | [] |  |  | MET.32721823 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 150 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32721840) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 04.Sep.2026 22:00 | 0.1375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | PRE INSP |  |  |  | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32721840) |  | 0 / 1 | [] |  |  | MET.32721840 | 40988:17 | 3789:39 | 2027-11-24 | H
| 151 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31957733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | OPS/LK |  |  |  | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31957733) |  | 0 / 1 | [] |  |  | MET.31957733 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 152 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31957744) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.052083 | 04.Sep.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31957744) |  | 0 / 4 | [] |  |  | MET.31957744 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 153 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28342303) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.13542 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP |  |  |  | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION (28342303) |  | 0 / 4 | [] |  |  | MET.28342303 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 154 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32721936) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-15 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP |  |  |  | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32721936) |  | 0 / 5 | [] |  |  | MET.32721936 | 46988:17 | 9789:39 | 2029-11-09 | H
| 155 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32721963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32721963) |  | 0 / 1 | [] |  |  | MET.32721963 | 40988:17 | 3789:39 | 2027-11-24 | H
| 156 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32721921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32721921) |  | 0 / 1 | [] |  |  | MET.32721921 | 40988:17 | 3789:39 | 2027-11-24 | H
| 157 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32721831) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.036806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32721831) |  | 0 / 4 | [] |  |  | MET.32721831 | 43988:17 | 6789:39 | 2028-11-16 | H
| 158 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32721884) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32721884) |  | 0 / 1 | [] |  |  | MET.32721884 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 159 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32721869) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-14 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32721869) |  | 0 / 3 | [] |  |  | MET.32721869 | 41308:07 | 4109:29 | 2028-01-01 | H
| 160 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (25480713) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] | JOB-SETUP, --, -- |  |  |  | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (25480713) |  | 0 / 3 | [] |  |  | MET.25480713 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 161 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (25467798) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] | TC/P |  |  |  | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (25467798) |  | 0 / 1 | [] |  |  | MET.25467798 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 162 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28342416) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28342416) |  | 0 / 8 | [] |  |  | MET.28342416 | 46988:17 | 9789:39 | 2029-11-09 | H
| 163 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31509654) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-34 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31509654) |  | 0 / 4 | [] |  |  | MET.31509654 | 47650:09 | 10451:31 | 2030-01-27 | H
| 164 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32721906) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-41 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32721906) |  | 0 / 3 | [] |  |  | MET.32721906 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 165 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32721908) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 04.Sep.2026 22:00 | 0.00625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | INSPECTION, INSPECTION |  |  |  | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32721908) |  | 0 / 2 | [] |  |  | MET.32721908 | 40988:17 | 3789:39 | 2027-11-24 | H
| 166 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32721895) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 04.Sep.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | P/N: Changed from "MIL-PRF-680.TYPEI" TO "PD680" as requestd in T/Q:584726 T/Q: 581544 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32721895) |  | 0 / 3 | [] |  |  | MET.32721895 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 167 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32721937) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | PRE INSP |  |  |  | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32721937) |  | 0 / 1 | [] |  |  | MET.32721937 | 40988:17 | 3789:39 | 2027-11-24 | H
| 168 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32721897) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32721897) |  | 0 / 2 | [] |  |  | MET.32721897 | 40988:17 | 3789:39 | 2027-11-24 | H
| 169 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32721944) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 04.Sep.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | TC/P, TC/P |  |  |  | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32721944) |  | 0 / 2 | [] |  |  | MET.32721944 | 46988:17 | 9789:39 | 2029-11-09 | H
| 170 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32721949) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.029861 | 04.Sep.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK |  |  |  | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32721949) |  | 0 / 1 | [] |  |  | MET.32721949 | 43988:17 | 6789:39 | 2028-11-16 | H
| 171 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32721951) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32721951) |  | 0 / 3 | [] |  |  | MET.32721951 | 40988:17 | 3789:39 | 2027-11-24 | H
| 172 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32721961) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32721961) |  | 0 / 3 | [] |  |  | MET.32721961 | 40988:17 | 3789:39 | 2027-11-24 | H
| 173 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32721926) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32721926) |  | 0 / 3 | [] |  |  | MET.32721926 | 40988:17 | 3789:39 | 2027-11-24 | H
| 174 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32721907) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.075 | 04.Sep.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32721907) |  | 0 / 3 | [] |  |  | MET.32721907 | 40988:17 | 3789:39 | 2027-11-24 | H
| 175 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32721825) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.075 | 04.Sep.2026 22:00 | 0.075 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32721825) |  | 0 / 3 | [] |  |  | MET.32721825 | 40988:17 | 3789:39 | 2027-11-24 | H
| 176 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32721959) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 04.Sep.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32721959) |  | 0 / 4 | [] |  |  | MET.32721959 | 40988:17 | 3789:39 | 2027-11-24 | H
| 177 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32721943) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 04.Sep.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32721943) |  | 0 / 4 | [] |  |  | MET.32721943 | 40988:17 | 3789:39 | 2027-11-24 | H
| 178 | 275451-01-1 | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32721826) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT (32721826) |  | 0 / 4 | [] |  |  | MET.32721826 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 179 | 278100-03-1 | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32721859) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-81 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC (32721859) |  | 0 / 3 | [] |  |  | MET.32721859 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 180 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32721956) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32721956) |  | 0 / 3 | [] |  |  | MET.32721956 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 181 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32721905) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32721905) |  | 0 / 3 | [] |  |  | MET.32721905 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 182 | 278451-01-1 | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32721942) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT (32721942) |  | 0 / 4 | [] |  |  | MET.32721942 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 183 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32721887) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 04.Sep.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32721887) |  | 0 / 1 | [] |  |  | MET.32721887 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 184 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32721868) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 04.Sep.2026 22:00 | 0.0034722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32721868) |  | 0 / 1 | [] |  |  | MET.32721868 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 185 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP (32721947) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP (32721947) |  | 0 / 3 | [] |  |  | MET.32721947 | 40988:17 | 3789:39 | 2027-11-24 | H
| 186 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32721965) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32721965) |  | 0 / 3 | [] |  |  | MET.32721965 | 40988:17 | 3789:39 | 2027-11-24 | H
| 187 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28342234) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-23 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28342234) |  | 0 / 3 | [] |  |  | MET.28342234 | 40988:17 | 3789:39 | 2027-11-24 | H
| 188 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32721946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32721946) |  | 0 / 3 | [] |  |  | MET.32721946 | 30'743 | 1'557 | 2027-04-03 | C
| 189 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32721902) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32721902) |  | 0 / 3 | [] |  |  | MET.32721902 | 30'743 | 1'557 | 2027-04-03 | C
| 190 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32721847) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32721847) |  | 0 / 1 | [] |  |  | MET.32721847 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 191 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32721889) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32721889) |  | 0 / 1 | [] |  |  | MET.32721889 | 40988:17 | 3789:39 | 2027-11-24 | H
| 192 | 291000-20-1 | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32721834) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 04.Sep.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS (32721834) |  | 0 / 1 | [] |  |  | MET.32721834 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 193 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32721929) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.022917 | 04.Sep.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | OPS/LK |  |  |  | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32721929) |  | 0 / 1 | [] |  |  | MET.32721929 | 17.Sep.2026 | 17 | 2026-09-17 | D
| 194 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32721858) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32721858) |  | 0 / 3 | [] |  |  | MET.32721858 | 40988:17 | 3789:39 | 2027-11-24 | H
| 195 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32721913) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29-34 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32721913) |  | 0 / 3 | [] |  |  | MET.32721913 | 40988:17 | 3789:39 | 2027-11-24 | H
| 196 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (25480536) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (25480536) |  | 0 / 3 | [] |  |  | MET.25480536 | 40988:17 | 3789:39 | 2027-11-24 | H
| 197 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (25480556) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.022222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (25480556) |  | 0 / 3 | [] |  |  | MET.25480556 | 40988:17 | 3789:39 | 2027-11-24 | H
| 198 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32721954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 04.Sep.2026 22:00 | 0.01875 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 30-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32721954) |  | 0 / 3 | [] |  |  | MET.32721954 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 199 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32721882) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 04.Sep.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32721882) |  | 0 / 1 | [] |  |  | MET.32721882 | 01.Nov.2026 | 62 | 2026-11-01 | D
| 200 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32721927) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32721927) |  | 0 / 1 | [] |  |  | MET.32721927 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 201 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32721890) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32721890) |  | 0 / 1 | [] |  |  | MET.32721890 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 202 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32721845) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | OPS/LK |  |  |  | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32721845) |  | 0 / 1 | [] |  |  | MET.32721845 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 203 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32721836) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 04.Sep.2026 22:00 | 0.0083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32721836) |  | 0 / 1 | [] |  |  | MET.32721836 | 40988:17 | 3789:39 | 2027-11-24 | H
| 204 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32721925) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32721925) |  | 0 / 1 | [] |  |  | MET.32721925 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 205 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32721866) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-61 |  | [] | OPS/LK |  |  |  | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32721866) |  | 0 / 1 | [] |  |  | MET.32721866 | 40988:17 | 3789:39 | 2027-11-24 | H
| 206 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32721893) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 04.Sep.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32721893) |  | 0 / 1 | [] |  |  | MET.32721893 | 31'743 | 2'557 | 2027-08-20 | C
| 207 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32721962) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 04.Sep.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32721962) |  | 0 / 1 | [] |  |  | MET.32721962 | 31'743 | 2'557 | 2027-08-20 | C
| 208 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28342202) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.37153 | 04.Sep.2026 22:00 | 0.32292 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | JOB-SETUP, TC/P, TC/P, CLOSE-UP |  |  |  | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28342202) |  | 0 / 4 | [] |  |  | MET.28342202 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 209 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32721867) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42153 | 04.Sep.2026 22:00 | 0.21042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | OPS/LK |  |  |  | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32721867) |  | 0 / 1 | [] |  |  | MET.32721867 | 30'743 | 1'557 | 2027-04-03 | C
| 210 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32721915) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 04.Sep.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-41 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32721915) |  | 0 / 3 | [] |  |  | MET.32721915 | 30'743 | 1'557 | 2027-04-03 | C
| 211 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32721938) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-43 |  | [] | OPS/LK |  |  |  | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32721938) |  | 0 / 1 | [] |  |  | MET.32721938 | 40988:17 | 3789:39 | 2027-11-24 | H
| 212 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 34-55-00-03-A (04) / VOR SYSTEM TEST (32721881) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 34-55-00-03-A (04) / VOR SYSTEM TEST (32721881) |  | 0 / 3 | [] |  |  | MET.32721881 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 213 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32721861) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32721861) |  | 0 / 1 | [] |  |  | MET.32721861 | 40988:17 | 3789:39 | 2027-11-24 | H
| 214 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32721837) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32721837) |  | 0 / 4 | [] |  |  | MET.32721837 | 40988:17 | 3789:39 | 2027-11-24 | H
| 215 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32721829) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.03125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32721829) |  | 0 / 3 | [] |  |  | MET.32721829 | 40988:17 | 3789:39 | 2027-11-24 | H
| 216 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28342161) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-48 |  | [] | TC/P |  |  |  | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28342161) |  | 0 / 1 | [] |  |  | MET.28342161 | 40988:17 | 3789:39 | 2027-11-24 | H
| 217 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32721924) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | OPS/LK |  |  |  | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32721924) |  | 0 / 1 | [] |  |  | MET.32721924 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 218 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32721888) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 04.Sep.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32721888) |  | 0 / 3 | [] |  |  | MET.32721888 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 219 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28342158) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.21528 | 04.Sep.2026 22:00 | 0.13194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, TC/P, --, JOB-CLOSEUP, -- |  |  | As requested in T/Q: 737585 by ENGG CONFIGRATION. | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS (28342158) |  | 0 / 5 | [] |  |  | MET.28342158 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 220 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28342488) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.09375 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-64 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | as per MGR Mial ear @Jinoy Jose, Thanks for the email. As discussed further, the referenced task cards will be revised to change the replacement interval from 6 months to 02 months prior to expiry. Dear @Mohammed A Albukhari, Refer email below. As discussed, please revised the text for following tasks to change the replacement interval from 6 months to 2 month prior to expiry. Remaining instructions (2 & 3 ) will be deleted from the task as well. MP Task Number Title PBE replacement interval 333 353250-01-1-SVA CABIN ATTENDANTS PORTABLE BREATHING EQUIPMENT (PBE) PERIODIC CHECK FOR EXPIRATION 6 Months 773 25-180-00-SVA PROTECTIVE BREATHING EQUIPMENT (PBE) EXPIRATION DATE CHECK 6 Months 787 25-060-00-01-SVA SMOK HOODS PERIODIC CHECK FOR EXPIRATION 6 Months 32S 353000-06-1-SVA PROTECT. BREATHING EQPT (CKPT & CABIN) PERIODIC CHECK FOR EXPIRATION 6 Months Regards, Muhammad Noor Manager, Maintenance Program E-mail: MONOOR@saudia.com Office: +966126867409 Maintenance Program, JED, SA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28342488) |  | 0 / 3 | [] |  |  | MET.28342488 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 221 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32721953) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32721953) |  | 0 / 3 | [] |  |  | MET.32721953 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 222 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25479970) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25479970) |  | 0 / 3 | [] |  |  | MET.25479970 | 25.Sep.2028 | 756 | 2028-09-25 | D
| 223 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25480037) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.0076389 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25480037) |  | 0 / 3 | [] |  |  | MET.25480037 | 25.Sep.2028 | 756 | 2028-09-25 | D
| 224 | 361100-SVA-01 | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT (28342472) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59028 | 04.Sep.2026 22:00 | 0.22917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT (28342472) |  | 0 / 10 | [] |  |  | MET.28342472 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 225 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32721917) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32721917) |  | 0 / 3 | [] |  |  | MET.32721917 | 50988:17 | 13789:39 | 2031-03-01 | H
| 226 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32721928) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32721928) |  | 0 / 3 | [] |  |  | MET.32721928 | 50988:17 | 13789:39 | 2031-03-01 | H
| 227 | 361251-01-3 | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP (32721960) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 04.Sep.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-12 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP (32721960) |  | 0 / 7 | [] |  |  | MET.32721960 | 41988:17 | 4789:39 | 2028-03-22 | H
| 228 | 383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32721827) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.41667 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-31 |  | [] | CLEAN-UP |  |  |  | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING (32721827) |  | 0 / 1 | [] |  |  | MET.32721827 | 40988:17 | 3789:39 | 2027-11-24 | H
| 229 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31957747) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12986 | 04.Sep.2026 22:00 | 0.12986 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 49-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31957747) |  | 0 / 3 | [] |  |  | MET.31957747 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 230 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31957748) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.011806 | 04.Sep.2026 22:00 | 0.011806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 49-16 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31957748) |  | 0 / 3 | [] |  |  | MET.31957748 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 231 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32721931) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 49-81 |  | [] | INSPECTION |  |  |  | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32721931) |  | 0 / 1 | [] |  |  | MET.32721931 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 232 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342232) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342232) |  | 0 / 4 | [] |  |  | MET.28342232 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 233 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32721891) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.029167 | 04.Sep.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | Revised to respond T/Q:560580 (SAEI production) | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK (32721891) |  | 0 / 9 | [] |  |  | MET.32721891 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 234 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342455) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342455) |  | 0 / 4 | [] |  |  | MET.28342455 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 235 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342305) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342305) |  | 0 / 4 | [] |  |  | MET.28342305 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 236 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32721901) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.040278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK (32721901) |  | 0 / 9 | [] |  |  | MET.32721901 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 237 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32721832) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK (32721832) |  | 0 / 9 | [] |  |  | MET.32721832 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 238 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32721923) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK (32721923) |  | 0 / 9 | [] |  |  | MET.32721923 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 239 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32721958) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.042361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32721958) |  | 0 / 9 | [] |  |  | MET.32721958 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 240 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342204) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20833 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342204) |  | 0 / 4 | [] |  |  | MET.28342204 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 241 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32721904) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32721904) |  | 0 / 4 | [] |  |  | MET.32721904 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 242 | 522200-01-1 | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK (28342424) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 522200-01-1 (04) / EMERGENCY EXIT DOORS OPS CHK (28342424) |  | 0 / 4 | [] |  |  | MET.28342424 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 243 | 522200-01-SVA | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342155) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-01-SVA (01) / FWD LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342155) |  | 0 / 4 | [] |  |  | MET.28342155 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 244 | 522200-02-1 | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK (28342452) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.055556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 522200-02-1 (02) / EMER DOORS ARMED POSITION OPS CHK (28342452) |  | 0 / 4 | [] |  |  | MET.28342452 | 40988:17 | 3789:39 | 2027-11-24 | H
| 245 | 522200-02-SVA | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342206) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-02-SVA (01) / FWD RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342206) |  | 0 / 4 | [] |  |  | MET.28342206 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 246 | 522200-03-SVA | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342280) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-03-SVA (01) / AFT LH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342280) |  | 0 / 4 | [] |  |  | MET.28342280 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 247 | 522200-04-1 | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP (28365333) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 522200-04-1 (04) / EMER DOOR DAMPER & EMER CLY INSP (28365333) |  | 0 / 4 | [] |  |  | MET.28365333 | 45878:57 | 8680:19 | 2029-06-29 | H
| 248 | 522200-04-SVA | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342476) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18056 | 04.Sep.2026 22:00 | 0.11111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52 |  | [] |  |  |  |  | 522200-04-SVA (01) / AFT RH EMERGENCY DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28342476) |  | 0 / 4 | [] |  |  | MET.28342476 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 249 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32721930) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32721930) |  | 0 / 1 | [] |  |  | MET.32721930 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 250 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32721900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-71 |  | [] | OPS/LK |  |  |  | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32721900) |  | 0 / 1 | [] |  |  | MET.32721900 | 40988:17 | 3789:39 | 2027-11-24 | H
| 251 | 527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32721844) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32721844) |  | 0 / 4 | [] |  |  | MET.32721844 | 25.Jan.2027 | 147 | 2027-01-25 | D
| 252 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32721952) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32721952) |  | 0 / 3 | [] |  |  | MET.32721952 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 253 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32721872) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.017361 | 04.Sep.2026 22:00 | 0.017361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32721872) |  | 0 / 3 | [] |  |  | MET.32721872 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 254 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32721932) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32721932) |  | 0 / 3 | [] |  |  | MET.32721932 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 255 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32721916) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.097222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32721916) |  | 0 / 3 | [] |  |  | MET.32721916 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 256 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32721966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-19 |  | [] | OPS/LK |  |  |  | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32721966) |  | 0 / 1 | [] |  |  | MET.32721966 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 257 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 531900-10-1 (1) / FUSELAGE DRAINAGE (32721870) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531900-10-1 (1) / FUSELAGE DRAINAGE (32721870) |  | 0 / 3 | [] |  |  | MET.32721870 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 258 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32721964) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 04.Sep.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | PRE INSP, PRE INSP |  |  |  | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32721964) |  | 0 / 2 | [] |  |  | MET.32721964 | 34'243 | 5'057 | 2028-08-02 | C
| 259 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 532176-01-1 (0) / FORWARD FUSELAGE (32478475) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16806 | 04.Sep.2026 22:00 | 0.16806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 532176-01-1 (0) / FORWARD FUSELAGE (32478475) |  | 0 / 3 | [] |  |  | MET.32478475 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 260 | 532181-03-1 | 532181-03-1 (0) / FORWARD FUSELAGE | 532181-03-1 (0) / FORWARD FUSELAGE (32478503) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 532181-03-1 (0) / FORWARD FUSELAGE (32478503) |  | 0 / 3 | [] |  |  | MET.32478503 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 261 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32721899) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-39 |  | [] | OPS/LK |  |  |  | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32721899) |  | 0 / 1 | [] |  |  | MET.32721899 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 262 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32721820) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32721820) |  | 0 / 3 | [] |  |  | MET.32721820 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 263 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32478567) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11875 | 04.Sep.2026 22:00 | 0.097917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32478567) |  | 0 / 5 | [] |  |  | MET.32478567 | 28.Apr.2029 | 971 | 2029-04-28 | D
| 264 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 534307-03-1 (0) / REAR FUSELAGE (32478504) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534307-03-1 (0) / REAR FUSELAGE (32478504) |  | 0 / 3 | [] |  |  | MET.32478504 | 20.Apr.2029 | 963 | 2029-04-20 | D
| 265 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 534308-02-1 (0) / REAR FUSELAGE (32478496) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 13:31 | 04.Sep.2026 22:00 | 1899-12-31 13:31 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534308-02-1 (0) / REAR FUSELAGE (32478496) |  | 0 / 4 | [] |  |  | MET.32478496 | 20.Apr.2029 | 963 | 2029-04-20 | D
| 266 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 535900-01-1 (3) / FUSELAGE DRAINAGE (32721934) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0041667 | 04.Sep.2026 22:00 | 0.0041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-01-1 (3) / FUSELAGE DRAINAGE (32721934) |  | 0 / 1 | [] |  |  | MET.32721934 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 267 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32721830) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32721830) |  | 0 / 1 | [] |  |  | MET.32721830 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 268 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (25423214) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (25423214) |  | 0 / 3 | [] |  |  | MET.25423214 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 269 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (25420379) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.013889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (25420379) |  | 0 / 3 | [] |  |  | MET.25420379 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 270 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (25479306) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 04.Sep.2026 22:00 | 0.095833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (25479306) |  | 0 / 3 | [] |  |  | MET.25479306 | 40988:17 | 3789:39 | 2027-11-24 | H
| 271 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (25477625) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 04.Sep.2026 22:00 | 0.095833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (25477625) |  | 0 / 3 | [] |  |  | MET.25477625 | 40988:17 | 3789:39 | 2027-11-24 | H
| 272 | 545000-05-1-001 | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621808) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 04.Sep.2026 22:00 | 0.70833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP (23621808) |  | 0 / 4 | [] |  |  | MET.23621808 | 40988:17 | 3789:39 | 2027-11-24 | H
| 273 | 545000-05-1-002 | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642825) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.73333 | 04.Sep.2026 22:00 | 0.70833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP (23642825) |  | 0 / 4 | [] |  |  | MET.23642825 | 40988:17 | 3789:39 | 2027-11-24 | H
| 274 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19990774) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 04.Sep.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19990774) |  | 0 / 3 | [] |  |  | MET.19990774 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 275 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19891418) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 04.Sep.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19891418) |  | 0 / 3 | [] |  |  | MET.19891418 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 276 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32721873) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32721873) |  | 0 / 1 | [] |  |  | MET.32721873 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 277 | 572178-01-1-001 | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32478373) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP (32478373) |  | 0 / 5 | [] |  |  | MET.32478373 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 278 | 572178-01-1-002 | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32478378) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP (32478378) |  | 0 / 5 | [] |  |  | MET.32478378 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 279 | 572179-01-1-001 | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32478382) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32478382) |  | 0 / 5 | [] |  |  | MET.32478382 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 280 | 572179-01-1-002 | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32478384) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP (32478384) |  | 0 / 5 | [] |  |  | MET.32478384 | 27.Sep.2029 | 1123 | 2029-09-27 | D
| 281 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (25477719) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (25477719) |  | 0 / 1 | [] |  |  | MET.25477719 | 40988:17 | 3789:39 | 2027-11-24 | H
| 282 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19890730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19890730) |  | 0 / 1 | [] |  |  | MET.19890730 | 40988:17 | 3789:39 | 2027-11-24 | H
| 283 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28342147) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 04.Sep.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | OPEN-UP, INSPECTION, CLOSE-UP |  |  |  | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28342147) |  | 0 / 3 | [] |  |  | MET.28342147 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 284 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28342251) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 04.Sep.2026 22:00 | 0.070833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28342251) |  | 0 / 3 | [] |  |  | MET.28342251 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 285 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (25477392) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (25477392) |  | 0 / 3 | [] |  |  | MET.25477392 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 286 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19891163) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.045833 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19891163) |  | 0 / 3 | [] |  |  | MET.19891163 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 287 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28342261) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | INSPECTION |  |  |  | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28342261) |  | 0 / 1 | [] |  |  | MET.28342261 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 288 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28342273) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | INSPECTION |  |  |  | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28342273) |  | 0 / 1 | [] |  |  | MET.28342273 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 289 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (25479176) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 04.Sep.2026 22:00 | 0.065278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (25479176) |  | 0 / 3 | [] |  |  | MET.25479176 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 290 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (25444265) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 04.Sep.2026 22:00 | 0.065278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (25444265) |  | 0 / 3 | [] |  |  | MET.25444265 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 291 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627447) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] |  |  |  |  | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627447) |  | 0 / 1 | [] |  |  | MET.23627447 | 30'243 | 1'057 | 2027-01-24 | C
| 292 | 711300-C1-1-001 | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 04.Sep.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION (28356946) |  | 0 / 2 | [] |  |  | MET.28356946 | 16.May.2029 | 989 | 2029-05-16 | D
| 293 | 711300-C1-1-002 | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384401) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.049306 | 04.Sep.2026 22:00 | 0.049306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-13 |  | [] | OPS/LK, OPS/LK |  |  |  | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION (28384401) |  | 0 / 2 | [] |  |  | MET.28384401 | 16.May.2029 | 989 | 2029-05-16 | D
| 294 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28342434) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10625 | 04.Sep.2026 22:00 | 0.052778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28342434) |  | 0 / 3 | [] |  |  | MET.28342434 | 30'243 | 1'057 | 2027-01-24 | C
| 295 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28342433) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.10625 | 04.Sep.2026 22:00 | 0.052778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28342433) |  | 0 / 3 | [] |  |  | MET.28342433 | 30'243 | 1'057 | 2027-01-24 | C
| 296 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28342439) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28342439) |  | 0 / 3 | [] |  |  | MET.28342439 | 30'243 | 1'057 | 2027-01-24 | C
| 297 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28342438) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28342438) |  | 0 / 3 | [] |  |  | MET.28342438 | 30'243 | 1'057 | 2027-01-24 | C
| 298 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28342437) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28342437) |  | 0 / 1 | [] |  |  | MET.28342437 | 30'243 | 1'057 | 2027-01-24 | C
| 299 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28342443) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28342443) |  | 0 / 1 | [] |  |  | MET.28342443 | 30'243 | 1'057 | 2027-01-24 | C
| 300 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (25437881) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (25437881) |  | 0 / 3 | [] |  |  | MET.25437881 | 30'243 | 1'057 | 2027-01-24 | C
| 301 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (25479006) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.038889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (25479006) |  | 0 / 3 | [] |  |  | MET.25479006 | 30'243 | 1'057 | 2027-01-24 | C
| 302 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (25426517) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 04.Sep.2026 22:00 | 0.10556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (25426517) |  | 0 / 3 | [] |  |  | MET.25426517 | 30'243 | 1'057 | 2027-01-24 | C
| 303 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (25478211) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 04.Sep.2026 22:00 | 0.10556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (25478211) |  | 0 / 3 | [] |  |  | MET.25478211 | 30'243 | 1'057 | 2027-01-24 | C
| 304 | 712213-01-1-001 | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP (25425499) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.14653 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP (25425499) |  | 0 / 8 | [] |  |  | MET.25425499 | 30'243 | 1'057 | 2027-01-24 | C
| 305 | 712213-01-1-002 | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP (25478196) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.14653 | 04.Sep.2026 22:00 | 0.090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP (25478196) |  | 0 / 8 | [] |  |  | MET.25478196 | 30'243 | 1'057 | 2027-01-24 | C
| 306 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28342477) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  | As per T/Q: 841758 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28342477) |  | 0 / 1 | [] |  |  | MET.28342477 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 307 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28342165) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28342165) |  | 0 / 1 | [] |  |  | MET.28342165 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 308 | 72-00-00-27-0-SVA-001 | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28342229) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK (28342229) |  | 0 / 1 | [] |  |  | MET.28342229 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 309 | 72-00-00-27-0-SVA-002 | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28342218) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK (28342218) |  | 0 / 1 | [] |  |  | MET.28342218 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 310 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19890151) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.040972 | 04.Sep.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19890151) |  | 0 / 3 | [] |  |  | MET.19890151 | 40988:17 | 3789:39 | 2027-11-24 | H
| 311 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19891043) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.040972 | 04.Sep.2026 22:00 | 0.034028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19891043) |  | 0 / 3 | [] |  |  | MET.19891043 | 40988:17 | 3789:39 | 2027-11-24 | H
| 312 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (25480102) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (25480102) |  | 0 / 3 | [] |  |  | MET.25480102 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 313 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (25478089) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.029167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (25478089) |  | 0 / 3 | [] |  |  | MET.25478089 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 314 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (25479266) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (25479266) |  | 0 / 3 | [] |  |  | MET.25479266 | 30'743 | 1'557 | 2027-04-03 | C
| 315 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19891153) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19891153) |  | 0 / 3 | [] |  |  | MET.19891153 | 30'743 | 1'557 | 2027-04-03 | C
| 316 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28342304) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 04.Sep.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28342304) |  | 0 / 3 | [] |  |  | MET.28342304 | 40988:17 | 3789:39 | 2027-11-24 | H
| 317 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28342469) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 04.Sep.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28342469) |  | 0 / 3 | [] |  |  | MET.28342469 | 40988:17 | 3789:39 | 2027-11-24 | H
| 318 | 783200-01-1-001 | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP (32721875) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP (32721875) |  | 0 / 5 | [] |  |  | MET.32721875 | 30'243 | 1'057 | 2027-01-24 | C
| 319 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32721862) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32721862) |  | 0 / 5 | [] |  |  | MET.32721862 | 30'243 | 1'057 | 2027-01-24 | C
| 320 | 783209-01-1 | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32721970) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-32 |  | [] |  |  |  |  | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. (32721970) |  | 0 / 3 | [] |  |  | MET.32721970 | 30'243 | 1'057 | 2027-01-24 | C
| 321 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP (32721909) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.51944 | 04.Sep.2026 22:00 | 0.51944 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP (32721909) |  | 0 / 1 | [] |  |  | MET.32721909 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 322 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP (32721922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP (32721922) |  | 0 / 1 | [] |  |  | MET.32721922 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 323 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32721955) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32721955) |  | 0 / 1 | [] |  |  | MET.32721955 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 324 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP (32721857) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP (32721857) |  | 0 / 1 | [] |  |  | MET.32721857 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 325 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32721945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32721945) |  | 0 / 1 | [] |  |  | MET.32721945 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 326 | ZL-171-01-1 | ZL-171-01-1 (05) / AFT CABIN UNDERFLOOR COMPART INSP | ZL-171-01-1 (05) / AFT CABIN UNDERFLOOR COMPART INSP (32721864) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.22639 | 04.Sep.2026 22:00 | 0.13611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | --, PRE INSP, --, -- |  |  |  | ZL-171-01-1 (05) / AFT CABIN UNDERFLOOR COMPART INSP (32721864) |  | 0 / 4 | [] |  |  | MET.32721864 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 327 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32721898) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32721898) |  | 0 / 1 | [] |  |  | MET.32721898 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 328 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) (32721842) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) (32721842) |  | 0 / 1 | [] |  |  | MET.32721842 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 329 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32721885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32721885) |  | 0 / 1 | [] |  |  | MET.32721885 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 330 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32721854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 04.Sep.2026 22:00 | 0.015972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32721854) |  | 0 / 1 | [] |  | #1 | MET.32721854 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 331 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32721971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 04.Sep.2026 22:00 | 0.015972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32721971) |  | 0 / 1 | [] |  | #1 | MET.32721971 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 332 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32721940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32721940) |  | 0 / 1 | [] |  |  | MET.32721940 | 18.Dec.2027 | 474 | 2027-12-18 | D
| 333 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE (32721892) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE (32721892) |  | 0 / 1 | [] |  |  | MET.32721892 | 18.Dec.2027 | 474 | 2027-12-18 | D
| 334 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28342298) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.022917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28342298) |  | 0 / 3 | [] |  |  | MET.28342298 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 335 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28342209) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.030556 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28342209) |  | 0 / 3 | [] |  |  | MET.28342209 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 336 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32721972) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32721972) |  | 0 / 1 | [] |  |  | MET.32721972 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 337 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32721878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32721878) |  | 0 / 1 | [] |  |  | MET.32721878 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 338 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32721968) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32721968) |  | 0 / 1 | [] |  |  | MET.32721968 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 339 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32721920) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32721920) |  | 0 / 1 | [] |  |  | MET.32721920 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 340 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP (32721883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 04.Sep.2026 22:00 | 0.058333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP (32721883) |  | 0 / 1 | [] |  |  | MET.32721883 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 341 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP (32721874) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 04.Sep.2026 22:00 | 0.058333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP (32721874) |  | 0 / 1 | [] |  |  | MET.32721874 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 342 | ZL-537-01-2-001 | ZL-537-01-2-001 (03) / L/H FLAP TAB HINGE AND FAIRING NO.3A | ZL-537-01-2-001 (03) / L/H FLAP TAB HINGE AND FAIRING NO.3A (32721843) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-537-01-2-001 (03) / L/H FLAP TAB HINGE AND FAIRING NO.3A (32721843) |  | 0 / 1 | [] |  |  | MET.32721843 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 343 | ZL-537-01-2-002 | ZL-537-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING NO.3A | ZL-537-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING NO.3A (32721911) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-537-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING NO.3A (32721911) |  | 0 / 1 | [] |  |  | MET.32721911 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 344 | ZL-539-01-2-001 | ZL-539-01-2-001 (04) / L/H FLAP TAB HINGE AND FAIRING | ZL-539-01-2-001 (04) / L/H FLAP TAB HINGE AND FAIRING (32721939) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-539-01-2-001 (04) / L/H FLAP TAB HINGE AND FAIRING (32721939) |  | 0 / 1 | [] |  |  | MET.32721939 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 345 | ZL-539-01-2-002 | ZL-539-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING | ZL-539-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING (32721912) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038194 | 04.Sep.2026 22:00 | 0.038194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-539-01-2-002 (04) / R/H FLAP TAB HINGE AND FAIRING (32721912) |  | 0 / 1 | [] |  |  | MET.32721912 | 25.Sep.2027 | 390 | 2027-09-25 | D
| 346 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32721919) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 04.Sep.2026 22:00 | 0.058333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32721919) |  | 0 / 1 | [] |  |  | MET.32721919 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 347 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32721933) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 04.Sep.2026 22:00 | 0.058333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32721933) |  | 0 / 1 | [] |  |  | MET.32721933 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 348 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION (32721848) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP, PRE INSP |  |  |  | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION (32721848) |  | 0 / 2 | [] |  |  | MET.32721848 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 349 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP (32721896) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP (32721896) |  | 0 / 1 | [] |  |  | MET.32721896 | 18.Dec.2027 | 474 | 2027-12-18 | D
| 350 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP (32721910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP (32721910) |  | 0 / 1 | [] |  |  | MET.32721910 | 18.Dec.2027 | 474 | 2027-12-18 | D
| 351 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP (32721967) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP (32721967) |  | 0 / 1 | [] |  |  | MET.32721967 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 352 | ZL-833-04-1 | ZL-833-04-1 (05) / FWD AND AFT EMERGENCY EXITS INSP | ZL-833-04-1 (05) / FWD AND AFT EMERGENCY EXITS INSP (32721865) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-833-04-1 (05) / FWD AND AFT EMERGENCY EXITS INSP (32721865) |  | 0 / 1 | [] |  |  | MET.32721865 | 25.Sep.2026 | 25 | 2026-09-25 | D
| 353 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 25-SVA-03 (01) / B/C SEAT REFRESH (32722075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42361 | 04.Sep.2026 22:00 | 0.42361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  | T/Q 685607 | 25-SVA-03 (01) / B/C SEAT REFRESH (32722075) |  | 0 / 19 | [] |  |  | MET.32722075 | 05.Feb.2028 | 523 | 2028-02-05 | D
| 356 | 272100-04-1 | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25382789) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-26 |  | [] | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK (25382789) |  | 0 / 4 | [] |  |  | MET.25382789 | 45695:53 | 8497:15 | 2029-06-08 | H
| 357 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375076) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] | TC/P |  |  |  | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375076) |  | 0 / 1 | [] |  |  | MET.28375076 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 358 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32721986) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32721986) |  | 0 / 3 | [] |  |  | MET.32721986 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 359 | 282200-04-1 | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32722069) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10556 | 04.Sep.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE (32722069) |  | 0 / 3 | [] |  |  | MET.32722069 | 14.Sep.2026 | 14 | 2026-09-14 | D
| 360 | 282400-01-1-001 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32721973) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.034722 | 04.Sep.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-24 |  | [] | JOB-SETUP, OPS/LK, TC/P, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  | As Req in T/Q: 845050 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC (32721973) |  | 0 / 6 | [] |  |  | MET.32721973 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 361 | 282400-01-1-002 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32721989) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.011111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP |  |  | T/Q 841621 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC (32721989) |  | 0 / 5 | [] |  |  | MET.32721989 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 362 | 282400-02-1-001 | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32721982) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32721982) |  | 0 / 3 | [] |  |  | MET.32721982 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 363 | 282400-02-1-002 | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32721983) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 28-24 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS (32721983) |  | 0 / 3 | [] |  |  | MET.32721983 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 364 | 291000-15-1 | 291000-15-1 (4) / ANALYZE HYD FLUID FOR PARTICLE, WATER & ACIDITY CONTAMINATION | 291000-15-1 (4) / ANALYZE HYD FLUID FOR PARTICLE, WATER & ACIDITY CONTAMINATION (32721984) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-32 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 291000-15-1 (4) / ANALYZE HYD FLUID FOR PARTICLE, WATER & ACIDITY CONTAMINATION (32721984) |  | 0 / 5 | [] |  |  | MET.32721984 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 365 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32721992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 04.Sep.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32721992) |  | 0 / 3 | [] |  |  | MET.32721992 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 366 | 345200-01-1-A | 345200-01-1-A (05) / ALTITUDE REPORTING FUNCTIONAL TEST | 345200-01-1-A (05) / ALTITUDE REPORTING FUNCTIONAL TEST (32721985) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | OPS/LK |  |  |  | 345200-01-1-A (05) / ALTITUDE REPORTING FUNCTIONAL TEST (32721985) |  | 0 / 1 | [] |  |  | MET.32721985 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 367 | 345200-03-1-A | 345200-03-1-A (05) / ATC MODE “S” TRANSP FUC CHK | 345200-03-1-A (05) / ATC MODE “S” TRANSP FUC CHK (32721981) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.01875 | 04.Sep.2026 22:00 | 0.0069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | OPS/LK |  |  |  | 345200-03-1-A (05) / ATC MODE “S” TRANSP FUC CHK (32721981) |  | 0 / 1 | [] |  |  | MET.32721981 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 368 | 383100-02-1 | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32721979) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.12917 | 04.Sep.2026 22:00 | 0.10625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-31 |  | [] | JOB-SETUP, TC/P, CLOSE-UP |  |  |  | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY (32721979) |  | 0 / 3 | [] |  |  | MET.32721979 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 369 | 383100-05-1 | 383100-05-1 (5) / VACUUM TOILET SYSTEM INSPECTION | 383100-05-1 (5) / VACUUM TOILET SYSTEM INSPECTION (32721816) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 383100-05-1 (5) / VACUUM TOILET SYSTEM INSPECTION (32721816) |  | 0 / 3 | [] |  |  | MET.32721816 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 370 | 470000-01-1 | 470000-01-1 (03) / D-ULPA FILTER ELEMENT REPLACEMENT | 470000-01-1 (03) / D-ULPA FILTER ELEMENT REPLACEMENT (25416078) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.06875 | 04.Sep.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 47-10 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 470000-01-1 (03) / D-ULPA FILTER ELEMENT REPLACEMENT (25416078) |  | 0 / 5 | [] |  |  | MET.25416078 | 37648:11 | 449:33 | 2026-10-22 | H
| 371 | 493000-B1-1 | 493000-B1-1 (03) / DISCARD FUEL INLET FILTER ELEMENT | 493000-B1-1 (03) / DISCARD FUEL INLET FILTER ELEMENT (32721977) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 49-30-00 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 493000-B1-1 (03) / DISCARD FUEL INLET FILTER ELEMENT (32721977) |  | 0 / 3 | [] |  |  | MET.32721977 | 41055:09 | 3856:31 | 2027-12-02 | H
| 372 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32721988) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32721988) |  | 0 / 1 | [] |  |  | MET.32721988 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 373 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32721980) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32721980) |  | 0 / 1 | [] |  |  | MET.32721980 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 374 | 522200-03-1 | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR (28377189) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td><td><img alt="" src="amos-resource://Icons/warningsmall.png" border="0" /></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 522200-03-1 (03) / EMERG EXIT DOOR EXT CNTRL HNDL LUBR (28377189) |  | 0 / 1 | [] |  |  | MET.28377189 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 375 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32721975) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32721975) |  | 0 / 1 | [] |  |  | MET.32721975 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 376 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32722072) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.15 | 04.Sep.2026 22:00 | 0.14306 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32722072) |  | 0 / 7 | [] |  |  | MET.32722072 | 17.Sep.2026 | 17 | 2026-09-17 | D
| 377 | 534141-01-5 | 534141-01-5 (04) / WATER SERVICE PANEL CUTOUT INSP | 534141-01-5 (04) / WATER SERVICE PANEL CUTOUT INSP (25383779) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.013194 | 04.Sep.2026 22:00 | 0.013194 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 534141-01-5 (04) / WATER SERVICE PANEL CUTOUT INSP (25383779) |  | 0 / 2 | [] |  |  | MET.25383779 | 37'500 | 8'314 | 2029-10-28 | C
| 378 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28342346) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.30069 | 04.Sep.2026 22:00 | 0.30069 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28342346) |  | 0 / 4 | [] |  |  | MET.28342346 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 379 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP (32721976) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP (32721976) |  | 0 / 1 | [] |  |  | MET.32721976 | 18.Dec.2026 | 109 | 2026-12-18 | D
| 380 | ZL-193-02-1 | ZL-193-02-1 (0) / UPPER WING FAIRING SLIDE STOWAGE | ZL-193-02-1 (0) / UPPER WING FAIRING SLIDE STOWAGE (28342345) | Block Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.42569 | 04.Sep.2026 22:00 | 0.38403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | ZL-193-02-1 (0) / UPPER WING FAIRING SLIDE STOWAGE (28342345) |  | 0 / 6 | [] |  |  | MET.28342345 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 381 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR (32721978) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP, PRE INSP |  |  |  | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR (32721978) |  | 0 / 2 | [] |  |  | MET.32721978 | 19.Dec.2026 | 110 | 2026-12-19 | D
| 383 | 32-10-00-01-0-SVA | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (31375689) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-12 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (31375689) |  | 0 / 3 | [] |  |  | MET.31375689 | 24.Oct.2026 | 54 | 2026-10-24 | D
| 385 | 352142-01-1 | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS (32722073) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1875 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-21 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 352142-01-1 (7) / DISCARD CHEMICAL OXYGEN GENERATORS (32722073) |  | 0 / 3 | [] |  |  | MET.32722073 | 10.Feb.2027 | 163 | 2027-02-10 | D
| 386 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 381000-01-1 (3) / WATER TANK DISINFECTION (32626072) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 04.Sep.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 38-10 |  | [] | OPS/LK |  |  |  | 381000-01-1 (3) / WATER TANK DISINFECTION (32626072) |  | 0 / 1 | [] |  |  | MET.32626072 | 13.Oct.2026 | 43 | 2026-10-13 | D
| 387 | 523108-01-1 | 523108-01-1 (02) / FWD CGO DOOR FTNG EXTERNAL AREA INSP | 523108-01-1 (02) / FWD CGO DOOR FTNG EXTERNAL AREA INSP (32722063) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523108-01-1 (02) / FWD CGO DOOR FTNG EXTERNAL AREA INSP (32722063) |  | 0 / 4 | [] |  |  | MET.32722063 | 37'243 | 8'057 | 2029-09-22 | C
| 388 | 523118-01-2 | 523118-01-2 (02) / AFT CGO DOOR FTNG EXTERNAL AREA INSP | 523118-01-2 (02) / AFT CGO DOOR FTNG EXTERNAL AREA INSP (32722065) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.023611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523118-01-2 (02) / AFT CGO DOOR FTNG EXTERNAL AREA INSP (32722065) |  | 0 / 4 | [] |  |  | MET.32722065 | 37'243 | 8'057 | 2029-09-22 | C
| 389 | 528223-01-1 | 528223-01-1 (2) / NLG AFT DOOR AFT FITTINGS INSPECTION | 528223-01-1 (2) / NLG AFT DOOR AFT FITTINGS INSPECTION (32722070) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.030556 | 04.Sep.2026 22:00 | 0.015278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 52-82 |  | [] | INSPECTION |  |  |  | 528223-01-1 (2) / NLG AFT DOOR AFT FITTINGS INSPECTION (32722070) |  | 0 / 1 | [] |  |  | MET.32722070 | 30'243 | 1'057 | 2027-01-24 | C
| 390 | 531101-02-1 | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH (31575944) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.059028 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531101-02-1 (03) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT, INTERCOSTALS FITTINGS N°7 BETWEEN FR15-16 & FR20-21, LH/RH (31575944) |  | 0 / 10 | [] |  |  | MET.31575944 | 32'743 | 3'557 | 2028-01-06 | C
| 391 | 531101-04-1 | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH (31575943) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.72083 | 04.Sep.2026 22:00 | 0.39444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 531101-04-1 (02) / SDI (ENDOSCOPE) OF FWD PAX/CREW DOOR CUTOUT,INTERCOSTALS FITTINGS NO.1 BETWEEN FR15-16 & FR20-21,LH/RH (31575943) |  | 0 / 10 | [] |  |  | MET.31575943 | 32'743 | 3'557 | 2028-01-06 | C
| 392 | 531111-02-1 | 531111-02-1 (4) / AVIONICS DOORS SURROUND INSPECTION | 531111-02-1 (4) / AVIONICS DOORS SURROUND INSPECTION (32721819) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION |  |  |  | 531111-02-1 (4) / AVIONICS DOORS SURROUND INSPECTION (32721819) |  | 0 / 2 | [] |  |  | MET.32721819 | 35'943 | 6'757 | 2029-03-26 | C
| 393 | 531113-03-1 | 531113-03-1 (00) / FUSELAGE SKIN ATTACHMENT | 531113-03-1 (00) / FUSELAGE SKIN ATTACHMENT (31486316) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 04.Sep.2026 22:00 | 0.025 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531113-03-1 (00) / FUSELAGE SKIN ATTACHMENT (31486316) |  | 0 / 3 | [] |  |  | MET.31486316 | 36'500 | 7'314 | 2029-06-11 | C
| 394 | 531124-01-1 | 531124-01-1 (04) / FR20 SPLICE STRUCTURE LWR STGR INSP | 531124-01-1 (04) / FR20 SPLICE STRUCTURE LWR STGR INSP (25471528) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.054861 | 04.Sep.2026 22:00 | 0.044444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 531124-01-1 (04) / FR20 SPLICE STRUCTURE LWR STGR INSP (25471528) |  | 0 / 2 | [] |  |  | MET.25471528 | 30'643 | 1'457 | 2027-03-21 | C
| 395 | 531131-02-1 | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP (32722079) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.19792 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, X-RAY / NDT, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531131-02-1 (2) / WINDSHIELD CTR POST UPPER ATTACHMENT INSP (32722079) |  | 0 / 8 | [] |  |  | MET.32722079 | 35'343 | 6'157 | 2029-01-01 | C
| 396 | 531135-03-1 | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH (32722081) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.875 | 04.Sep.2026 22:00 | 0.52083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 531135-03-1 (1) / SPECIAL DETAILED INSPECTION (ROTO) OF WINDSHIELD SIDE POST AT FR 4, UPPER ATTACHMENT, INTERNAL SIDE, LH/RH (32722081) |  | 0 / 11 | [] |  |  | MET.32722081 | 33'743 | 4'557 | 2028-05-24 | C
| 397 | 531153-04-1 | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH (25434854) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.62153 | 04.Sep.2026 22:00 | 0.42014 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, --, JOB-CLOSEUP, JOB-CLOSEUP |  |  | T/Q: 846599 --------------------------------------------------------------------- ------------------------------------------------------------ mail has been sent from production to remove INSP SCOPE from STEP 11. Greetings ,, Ref. To the below email , Need your assistance on WORKSTEP No. 11 Kindly remove INSP Scop from the mentioned work step as LAVATORY OK TO INSTALL Is not required. Regards, Alaa Fageeh Designee Supervisor, Aircraft Maintenance Heavy Maint Cabin Narrow Body A321/A320 Tel:+966 12-2729001 ¦ Extn:77772 Email:A.Fageeh@saudiatechnic.com PO Box 167 - Jeddah 21231 - Saudi Arabia | 531153-04-1 (00) / SPECIAL DETAILED INSPECTION (HFEC) OF DOOR FR 16, LH/RH (25434854) |  | 0 / 12 | [] |  |  | MET.25434854 | 34'043 | 4'857 | 2028-07-05 | C
| 398 | 531155-04-1 | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH (25524033) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25347 | 04.Sep.2026 22:00 | 0.20139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-CLOSEUP |  |  |  | 531155-04-1 (00) / SDI (HFEC) OF DOOR FR 20, BETWEEN LINTEL & INTERCOSTAL 6, EXCEPT DOUBLE JOGGLE AREA, LH/RH (25524033) |  | 0 / 12 | [] |  |  | MET.25524033 | 34'043 | 4'857 | 2028-07-05 | C
| 399 | 531184-04-1 | 531184-04-1 (1) / FWD PRESSURE BULKHEAD VERTICAL POSTS | 531184-04-1 (1) / FWD PRESSURE BULKHEAD VERTICAL POSTS (32721997) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.033333 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 531184-04-1 (1) / FWD PRESSURE BULKHEAD VERTICAL POSTS (32721997) |  | 0 / 5 | [] |  |  | MET.32721997 | 01.Nov.2027 | 427 | 2027-11-01 | D
| 400 | 532107-01-1 | 532107-01-1 (02) / CABIN FLOOR BEAMS, INTERNAL STRUCTURE | 532107-01-1 (02) / CABIN FLOOR BEAMS, INTERNAL STRUCTURE (28342393) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.097222 | 04.Sep.2026 22:00 | 0.086806 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] |  |  |  |  | 532107-01-1 (02) / CABIN FLOOR BEAMS, INTERNAL STRUCTURE (28342393) |  | 0 / 6 | [] |  |  | MET.28342393 | 36'300 | 7'114 | 2029-05-14 | C
| 401 | 532130-39-1 | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION (32721991) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22222 | 04.Sep.2026 22:00 | 0.22014 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | To remove panles T/Q: 851220 Dear Concerned, The requested action has been completed. The Work Template has been revised in accordance with AMM 53-21-00-220-827-A. Access panels 231FF, 231NF, 231TF, 231YF, 232FF, 232PF, 232UF, and 232YF have been removed from the access requirements, and only Access Door 831 remains applicable for task accomplishment. The Work Template revision has been reviewed, approved, and activated. Production action is required to discard any printed copies of the previous Work Template revision and reprint/use the latest activated revision for task accomplishment. Regards, MPDC | 532130-39-1 (01) / ANTI-CRASH ROD JUNCTION (32721991) |  | 0 / 13 | [] |  |  | MET.32721991 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 402 | 532132-01-1 | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32722071) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.081944 | 04.Sep.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP (32722071) |  | 0 / 4 | [] |  |  | MET.32722071 | 32'043 | 2'857 | 2027-10-01 | C
| 403 | 532164-01-6 | 532164-01-6 (03) / FUS STRINGER 23 TO CROWN CENTERLINE | 532164-01-6 (03) / FUS STRINGER 23 TO CROWN CENTERLINE (32722062) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.47569 | 04.Sep.2026 22:00 | 0.2375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-21 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 532164-01-6 (03) / FUS STRINGER 23 TO CROWN CENTERLINE (32722062) |  | 0 / 2 | [] |  |  | MET.32722062 | 30'000 | 814 | 2026-12-21 | C
| 404 | 533111-01-2 | 533111-01-2 (04) / PRESS DEK MEMBRANES LWR SURFACE INSP | 533111-01-2 (04) / PRESS DEK MEMBRANES LWR SURFACE INSP (25534555) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 04.Sep.2026 22:00 | 0.1375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 533111-01-2 (04) / PRESS DEK MEMBRANES LWR SURFACE INSP (25534555) |  | 0 / 2 | [] |  |  | MET.25534555 | 33'643 | 4'457 | 2028-05-10 | C
| 405 | 533141-01-2 | 533141-01-2 (04) / FUS SKIN BETWEEN FR35.8 & FR36 INSP | 533141-01-2 (04) / FUS SKIN BETWEEN FR35.8 & FR36 INSP (32722082) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 533141-01-2 (04) / FUS SKIN BETWEEN FR35.8 & FR36 INSP (32722082) |  | 0 / 4 | [] |  |  | MET.32722082 | 32'543 | 3'357 | 2027-12-09 | C
| 406 | 533144-01-1 | 533144-01-1 (01) / PRESS FLOOR FR42 TO FR46 FRAME ATTCH | 533144-01-1 (01) / PRESS FLOOR FR42 TO FR46 FRAME ATTCH (25512469) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10972 | 04.Sep.2026 22:00 | 0.094444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533144-01-1 (01) / PRESS FLOOR FR42 TO FR46 FRAME ATTCH (25512469) |  | 0 / 6 | [] |  |  | MET.25512469 | 35'543 | 6'357 | 2029-01-29 | C
| 407 | 533183-01-1-001 | 533183-01-1-001 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, LH | 533183-01-1-001 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, LH (28342493) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 533183-01-1-001 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, LH (28342493) |  | 0 / 3 | [] |  |  | MET.28342493 | 33'900 | 4'714 | 2028-06-15 | C
| 408 | 533183-01-1-002 | 533183-01-1-002 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, RH | 533183-01-1-002 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, RH (28342265) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 533183-01-1-002 (00) / DETAILED INSPECTION OF FORWARD PRESSURE BULKHEAD LOWER FLANGE AT FR 35 (A318/A319/A320) OR AT FR 35.8 (A321), BETWEEN STRINGER 37 AND STRINGER 38, INTERNAL SIDE, RH (28342265) |  | 0 / 3 | [] |  |  | MET.28342265 | 33'900 | 4'714 | 2028-06-15 | C
| 409 | 533188-01-2 | 533188-01-2 (02) / PRESS BLKHD AFT FACE LOWER PART INSP | 533188-01-2 (02) / PRESS BLKHD AFT FACE LOWER PART INSP (32722077) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 04.Sep.2026 22:00 | 0.054861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | INSPECTION |  |  |  | 533188-01-2 (02) / PRESS BLKHD AFT FACE LOWER PART INSP (32722077) |  | 0 / 1 | [] |  |  | MET.32722077 | 31'143 | 1'957 | 2027-05-29 | C
| 410 | 534108-01-2 | 534108-01-2 (3) / FUSELAGE EXTERNAL SURFACE INSPECTION | 534108-01-2 (3) / FUSELAGE EXTERNAL SURFACE INSPECTION (32722068) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 04.Sep.2026 22:00 | 0.045833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | PRE INSP, PRE INSP |  |  |  | 534108-01-2 (3) / FUSELAGE EXTERNAL SURFACE INSPECTION (32722068) |  | 0 / 2 | [] |  |  | MET.32722068 | 30'000 | 814 | 2026-12-21 | C
| 411 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25450096) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.68542 | 04.Sep.2026 22:00 | 0.5625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, -- |  |  |  | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP (25450096) |  | 0 / 10 | [] |  |  | MET.25450096 | 32'843 | 3'657 | 2028-01-20 | C
| 412 | 534124-01-3 | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP (31486331) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.077778 | 04.Sep.2026 22:00 | 0.077778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | As REQ per T/C: 850864. | 534124-01-3 (5) / PAX/CREW DR CUTOUT UPR CORN NDT INSP (31486331) |  | 0 / 8 | [] |  |  | MET.31486331 | 01.Nov.2027 | 427 | 2027-11-01 | D
| 413 | 534126-01-3 | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP (25383414) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11875 | 04.Sep.2026 22:00 | 0.10833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | CLEAN-UP, INSPECTION, X-RAY / NDT |  |  |  | 534126-01-3 (04) / FUSELAGE AT WASTE SVC PANEL NDT INSP (25383414) |  | 0 / 3 | [] |  |  | MET.25383414 | 35'100 | 5'914 | 2028-11-29 | C
| 414 | 534127-01-3 | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP (25402520) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534127-01-3 (05) / FUSE BETWEEN STGR4 & STGR5 NDT INSP (25402520) |  | 0 / 8 | [] |  |  | MET.25402520 | 33'843 | 4'657 | 2028-06-07 | C
| 415 | 534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 534135-02-1 (0) / REAR FUSELAGE (32478491) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027778 | 04.Sep.2026 22:00 | 0.027778 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534135-02-1 (0) / REAR FUSELAGE (32478491) |  | 0 / 3 | [] |  |  | MET.32478491 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 416 | 534163-01-1 | 534163-01-1 (3) / AFT CRGO DOOR ACTUA ATTACH BRKT INSP | 534163-01-1 (3) / AFT CRGO DOOR ACTUA ATTACH BRKT INSP (32722083) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 534163-01-1 (3) / AFT CRGO DOOR ACTUA ATTACH BRKT INSP (32722083) |  | 0 / 3 | [] |  |  | MET.32722083 | 32'243 | 3'057 | 2027-10-29 | C
| 417 | 534172-01-4 | 534172-01-4 (04) / BULK CARGO DOOR CUTOUT SEALING PROFILE | 534172-01-4 (04) / BULK CARGO DOOR CUTOUT SEALING PROFILE (32722067) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0090278 | 04.Sep.2026 22:00 | 0.0090278 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | CLEAN-UP, INSPECTION, INSPECTION |  |  |  | 534172-01-4 (04) / BULK CARGO DOOR CUTOUT SEALING PROFILE (32722067) |  | 0 / 3 | [] |  |  | MET.32722067 | 37'243 | 8'057 | 2029-09-22 | C
| 418 | 534189-02-1 | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER (25383649) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.058333 | 04.Sep.2026 22:00 | 0.053472 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 534189-02-1 (00) / SDI (ROTO) OF DOOR STOP FITTING FASTENER HOLES IN FR 47.2A AND FR 47.4 AT STRINGER 13 AND AT STRINGER (25383649) |  | 0 / 5 | [] |  |  | MET.25383649 | 36'000 | 6'814 | 2029-04-03 | C
| 419 | 535163-01-1 | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP (28342398) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.4125 | 04.Sep.2026 22:00 | 0.4125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-51 |  | [] | CLEAN-UP, INSPECTION, X-RAY / NDT |  |  |  | 535163-01-1 (02) / LWR FLANGES OF FR72 & FR74 NDT INSP (28342398) |  | 0 / 3 | [] |  |  | MET.28342398 | 37'300 | 8'114 | 2029-09-30 | C
| 420 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32722078) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.050694 | 04.Sep.2026 22:00 | 0.047917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32722078) |  | 0 / 4 | [] |  |  | MET.32722078 | 31'243 | 2'057 | 2027-06-12 | C
| 421 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32722080) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.038889 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32722080) |  | 0 / 4 | [] |  |  | MET.32722080 | 31'243 | 2'057 | 2027-06-12 | C
| 422 | 572007-01-4-001 | 572007-01-4-001 (04) / L/H OUTER WING REAR SPAR AFT FACE | 572007-01-4-001 (04) / L/H OUTER WING REAR SPAR AFT FACE (25473704) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-4-001 (04) / L/H OUTER WING REAR SPAR AFT FACE (25473704) |  | 0 / 5 | [] |  |  | MET.25473704 | 33'943 | 4'757 | 2028-06-21 | C
| 423 | 572007-01-4-002 | 572007-01-4-002 (04) / R/H OUTER WING REAR SPAR AFT FACE | 572007-01-4-002 (04) / R/H OUTER WING REAR SPAR AFT FACE (25445741) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.084722 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572007-01-4-002 (04) / R/H OUTER WING REAR SPAR AFT FACE (25445741) |  | 0 / 5 | [] |  |  | MET.25445741 | 33'943 | 4'757 | 2028-06-21 | C
| 424 | 572011-01-4-001 | 572011-01-4-001 (02) / LH OUTER WNG REAR SPAR FWD FACE INSP | 572011-01-4-001 (02) / LH OUTER WNG REAR SPAR FWD FACE INSP (25580778) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 04.Sep.2026 22:00 | 0.17639 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572011-01-4-001 (02) / LH OUTER WNG REAR SPAR FWD FACE INSP (25580778) |  | 0 / 5 | [] |  |  | MET.25580778 | 33'243 | 4'057 | 2028-03-16 | C
| 425 | 572011-01-4-002 | 572011-01-4-002 (01) / RH OUTER WNG REAR SPAR FWD FACE INSP | 572011-01-4-002 (01) / RH OUTER WNG REAR SPAR FWD FACE INSP (25523672) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.18333 | 04.Sep.2026 22:00 | 0.17639 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572011-01-4-002 (01) / RH OUTER WNG REAR SPAR FWD FACE INSP (25523672) |  | 0 / 5 | [] |  |  | MET.25523672 | 33'243 | 4'057 | 2028-03-16 | C
| 426 | 572012-01-2-001 | 572012-01-2-001 (03) / L/H WING TOP SKIN UPPER SURFACE INSP | 572012-01-2-001 (03) / L/H WING TOP SKIN UPPER SURFACE INSP (25478500) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572012-01-2-001 (03) / L/H WING TOP SKIN UPPER SURFACE INSP (25478500) |  | 0 / 4 | [] |  |  | MET.25478500 | 36'143 | 6'957 | 2029-04-22 | C
| 427 | 572012-01-2-002 | 572012-01-2-002 (03) / R/H WING TOP SKIN UPPER SURFACE INSP | 572012-01-2-002 (03) / R/H WING TOP SKIN UPPER SURFACE INSP (19333670) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572012-01-2-002 (03) / R/H WING TOP SKIN UPPER SURFACE INSP (19333670) |  | 0 / 4 | [] |  |  | MET.19333670 | 36'143 | 6'957 | 2029-04-22 | C
| 428 | 572020-01-6-001 | 572020-01-6-001 (01) / L/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-6-001 (01) / L/H WING TOP SKIN RIB 1 AND 8 INSP (25516310) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.55 | 04.Sep.2026 22:00 | 0.50833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572020-01-6-001 (01) / L/H WING TOP SKIN RIB 1 AND 8 INSP (25516310) |  | 0 / 6 | [] |  |  | MET.25516310 | 34'743 | 5'557 | 2028-10-10 | C
| 429 | 572020-01-6-002 | 572020-01-6-002 (01) / R/H WING TOP SKIN RIB 1 AND 8 INSP | 572020-01-6-002 (01) / R/H WING TOP SKIN RIB 1 AND 8 INSP (25469838) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.55 | 04.Sep.2026 22:00 | 0.52222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572020-01-6-002 (01) / R/H WING TOP SKIN RIB 1 AND 8 INSP (25469838) |  | 0 / 6 | [] |  |  | MET.25469838 | 34'743 | 5'557 | 2028-10-10 | C
| 430 | 572032-01-2-001 | 572032-01-2-001 (01) / L/H WNG BOTTOM SKIN/REAR SPAR INSP | 572032-01-2-001 (01) / L/H WNG BOTTOM SKIN/REAR SPAR INSP (25494787) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572032-01-2-001 (01) / L/H WNG BOTTOM SKIN/REAR SPAR INSP (25494787) |  | 0 / 4 | [] |  |  | MET.25494787 | 29'543 | 357 | 2026-10-19 | C
| 431 | 572032-01-2-002 | 572032-01-2-002 (01) / R/H WNG BOTTOM SKIN/REAR SPAR INSP | 572032-01-2-002 (01) / R/H WNG BOTTOM SKIN/REAR SPAR INSP (25494808) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572032-01-2-002 (01) / R/H WNG BOTTOM SKIN/REAR SPAR INSP (25494808) |  | 0 / 4 | [] |  |  | MET.25494808 | 29'543 | 357 | 2026-10-19 | C
| 432 | 572034-01-3-001 | 572034-01-3-001 (01) / L/H WING BOTOM SKIN LDG PLATE INSP | 572034-01-3-001 (01) / L/H WING BOTOM SKIN LDG PLATE INSP (25531669) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572034-01-3-001 (01) / L/H WING BOTOM SKIN LDG PLATE INSP (25531669) |  | 0 / 4 | [] |  |  | MET.25531669 | 32'943 | 3'757 | 2028-02-03 | C
| 433 | 572034-01-3-002 | 572034-01-3-002 (01) / R/H WING BOTOM SKIN LDG PLATE INSP | 572034-01-3-002 (01) / R/H WING BOTOM SKIN LDG PLATE INSP (25448956) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572034-01-3-002 (01) / R/H WING BOTOM SKIN LDG PLATE INSP (25448956) |  | 0 / 4 | [] |  |  | MET.25448956 | 32'943 | 3'757 | 2028-02-03 | C
| 434 | 572036-01-3-001 | 572036-01-3-001 (02) / L/H WING BOTOM SKIN FLAP TRAK2 INSP | 572036-01-3-001 (02) / L/H WING BOTOM SKIN FLAP TRAK2 INSP (19281322) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572036-01-3-001 (02) / L/H WING BOTOM SKIN FLAP TRAK2 INSP (19281322) |  | 0 / 4 | [] |  |  | MET.19281322 | 35'800 | 6'614 | 2029-03-06 | C
| 435 | 572036-01-3-002 | 572036-01-3-002 (03) / R/H WING BOTOM SKIN FLAP TRAK2 INSP | 572036-01-3-002 (03) / R/H WING BOTOM SKIN FLAP TRAK2 INSP (19281296) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572036-01-3-002 (03) / R/H WING BOTOM SKIN FLAP TRAK2 INSP (19281296) |  | 0 / 4 | [] |  |  | MET.19281296 | 35'800 | 6'614 | 2029-03-06 | C
| 436 | 572038-01-2-001 | 572038-01-2-001 (01) / L-OUTER WNG BOTTOM SKIN RUNOUTS INSP | 572038-01-2-001 (01) / L-OUTER WNG BOTTOM SKIN RUNOUTS INSP (25495005) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.063889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572038-01-2-001 (01) / L-OUTER WNG BOTTOM SKIN RUNOUTS INSP (25495005) |  | 0 / 4 | [] |  |  | MET.25495005 | 30'092 | 906 | 2027-01-03 | C
| 437 | 572038-01-2-002 | 572038-01-2-002 (01) / R-OUTER WNG BOTTOM SKIN RUNOUTS INSP | 572038-01-2-002 (01) / R-OUTER WNG BOTTOM SKIN RUNOUTS INSP (25429077) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.063889 | 04.Sep.2026 22:00 | 0.063889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | --, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572038-01-2-002 (01) / R-OUTER WNG BOTTOM SKIN RUNOUTS INSP (25429077) |  | 0 / 4 | [] |  |  | MET.25429077 | 30'092 | 906 | 2027-01-03 | C
| 438 | 572042-01-4-001 | 572042-01-4-001 (01) / L/H WNG BOTTOM SKIN LWR SURFACE INSP | 572042-01-4-001 (01) / L/H WNG BOTTOM SKIN LWR SURFACE INSP (25494965) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572042-01-4-001 (01) / L/H WNG BOTTOM SKIN LWR SURFACE INSP (25494965) |  | 0 / 4 | [] |  |  | MET.25494965 | 29'992 | 806 | 2026-12-20 | C
| 439 | 572042-01-4-002 | 572042-01-4-002 (01) / R/H WNG BOTTOM SKIN LWR SURFACE INSP | 572042-01-4-002 (01) / R/H WNG BOTTOM SKIN LWR SURFACE INSP (25401297) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.027083 | 04.Sep.2026 22:00 | 0.027083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572042-01-4-002 (01) / R/H WNG BOTTOM SKIN LWR SURFACE INSP (25401297) |  | 0 / 4 | [] |  |  | MET.25401297 | 29'992 | 806 | 2026-12-20 | C
| 440 | 572053-01-3-001 | 572053-01-3-001 (01) / L/H WING BOTOM SKIN STRINGERS INSP | 572053-01-3-001 (01) / L/H WING BOTOM SKIN STRINGERS INSP (25445926) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.070139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572053-01-3-001 (01) / L/H WING BOTOM SKIN STRINGERS INSP (25445926) |  | 0 / 9 | [] |  |  | MET.25445926 | 35'043 | 5'857 | 2028-11-21 | C
| 441 | 572053-01-3-002 | 572053-01-3-002 (01) / R/H WING BOTOM SKIN STRINGERS INSP | 572053-01-3-002 (01) / R/H WING BOTOM SKIN STRINGERS INSP (25395708) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.070139 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572053-01-3-002 (01) / R/H WING BOTOM SKIN STRINGERS INSP (25395708) |  | 0 / 9 | [] |  |  | MET.25395708 | 35'043 | 5'857 | 2028-11-21 | C
| 442 | 572111-01-3-001 | 572111-01-3-001 (03) / LH WING REAR SPAR AFT FACE INSP | 572111-01-3-001 (03) / LH WING REAR SPAR AFT FACE INSP (32722066) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-3-001 (03) / LH WING REAR SPAR AFT FACE INSP (32722066) |  | 0 / 4 | [] |  |  | MET.32722066 | 36'743 | 7'557 | 2029-07-15 | C
| 443 | 572111-01-3-002 | 572111-01-3-002 (03) / RH WING REAR SPAR AFT FACE INSP | 572111-01-3-002 (03) / RH WING REAR SPAR AFT FACE INSP (32722064) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-3-002 (03) / RH WING REAR SPAR AFT FACE INSP (32722064) |  | 0 / 4 | [] |  |  | MET.32722064 | 36'743 | 7'557 | 2029-07-15 | C
| 444 | 572115-01-3-001 | 572115-01-3-001 (02) / L-OUTER WING REAR SPAR FWD FACE INSP | 572115-01-3-001 (02) / L-OUTER WING REAR SPAR FWD FACE INSP (25383063) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.060417 | 04.Sep.2026 22:00 | 0.056944 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572115-01-3-001 (02) / L-OUTER WING REAR SPAR FWD FACE INSP (25383063) |  | 0 / 5 | [] |  |  | MET.25383063 | 35'600 | 6'414 | 2029-02-06 | C
| 445 | 572115-01-3-002 | 572115-01-3-002 (02) / R-OUTER WING REAR SPAR FWD FACE INSP | 572115-01-3-002 (02) / R-OUTER WING REAR SPAR FWD FACE INSP (25383680) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.060417 | 04.Sep.2026 22:00 | 0.056944 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572115-01-3-002 (02) / R-OUTER WING REAR SPAR FWD FACE INSP (25383680) |  | 0 / 5 | [] |  |  | MET.25383680 | 35'600 | 6'414 | 2029-02-06 | C
| 446 | 572150-01-4-001 | 572150-01-4-001 (01) / L/W BOTOM SKIN JOINTS RIB 11-13 INSP | 572150-01-4-001 (01) / L/W BOTOM SKIN JOINTS RIB 11-13 INSP (19492905) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572150-01-4-001 (01) / L/W BOTOM SKIN JOINTS RIB 11-13 INSP (19492905) |  | 0 / 4 | [] |  |  | MET.19492905 | 32'143 | 2'957 | 2027-10-15 | C
| 447 | 572150-01-4-002 | 572150-01-4-002 (01) / R/W BOTOM SKIN JOINTS RIB 11-13 INSP | 572150-01-4-002 (01) / R/W BOTOM SKIN JOINTS RIB 11-13 INSP (19492932) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572150-01-4-002 (01) / R/W BOTOM SKIN JOINTS RIB 11-13 INSP (19492932) |  | 0 / 4 | [] |  |  | MET.19492932 | 32'143 | 2'957 | 2027-10-15 | C
| 448 | 572157-01-8 | 572157-01-8 (0) / OUTER WING BOTTOM SKIN RUNOUT | 572157-01-8 (0) / OUTER WING BOTTOM SKIN RUNOUT (28342348) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.42569 | 04.Sep.2026 22:00 | 0.38403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572157-01-8 (0) / OUTER WING BOTTOM SKIN RUNOUT (28342348) |  | 0 / 6 | [] |  |  | MET.28342348 | 35'800 | 6'614 | 2029-03-06 | C
| 449 | 575159-01-2-001 | 575159-01-2-001 (01) / L/H WING BOTOM SKIN/REAR SPAR INSP | 575159-01-2-001 (01) / L/H WING BOTOM SKIN/REAR SPAR INSP (25444761) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575159-01-2-001 (01) / L/H WING BOTOM SKIN/REAR SPAR INSP (25444761) |  | 0 / 4 | [] |  |  | MET.25444761 | 30'543 | 1'357 | 2027-03-07 | C
| 450 | 575159-01-2-002 | 575159-01-2-002 (01) / R/H WING BOTOM SKIN/REAR SPAR INSP | 575159-01-2-002 (01) / R/H WING BOTOM SKIN/REAR SPAR INSP (25410465) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575159-01-2-002 (01) / R/H WING BOTOM SKIN/REAR SPAR INSP (25410465) |  | 0 / 4 | [] |  |  | MET.25410465 | 30'543 | 1'357 | 2027-03-07 | C
| 451 | 575160-01-3-001 | 575160-01-3-001 (01) / LH T/E BOTTOM SKN REAR SPAR NDT INSP | 575160-01-3-001 (01) / LH T/E BOTTOM SKN REAR SPAR NDT INSP (25495041) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 575160-01-3-001 (01) / LH T/E BOTTOM SKN REAR SPAR NDT INSP (25495041) |  | 0 / 6 | [] |  |  | MET.25495041 | 34'643 | 5'457 | 2028-09-26 | C
| 452 | 575160-01-3-002 | 575160-01-3-002 (01) / RH T/E BOTTOM SKN REAR SPAR NDT INSP | 575160-01-3-002 (01) / RH T/E BOTTOM SKN REAR SPAR NDT INSP (25495052) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.22917 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 575160-01-3-002 (01) / RH T/E BOTTOM SKN REAR SPAR NDT INSP (25495052) |  | 0 / 6 | [] |  |  | MET.25495052 | 34'643 | 5'457 | 2028-09-26 | C
| 453 | 575161-01-2-001 | 575161-01-2-001 (01) / L/H WING T/E BOTTOM SKIN INSPECTION | 575161-01-2-001 (01) / L/H WING T/E BOTTOM SKIN INSPECTION (25495053) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 575161-01-2-001 (01) / L/H WING T/E BOTTOM SKIN INSPECTION (25495053) |  | 0 / 3 | [] |  |  | MET.25495053 | 29'992 | 806 | 2026-12-20 | C
| 454 | 575161-01-2-002 | 575161-01-2-002 (01) / R/H WING T/E BOTTOM SKIN INSPECTION | 575161-01-2-002 (01) / R/H WING T/E BOTTOM SKIN INSPECTION (25495046) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.018056 | 04.Sep.2026 22:00 | 0.018056 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 575161-01-2-002 (01) / R/H WING T/E BOTTOM SKIN INSPECTION (25495046) |  | 0 / 3 | [] |  |  | MET.25495046 | 29'992 | 806 | 2026-12-20 | C
| 455 | 575164-01-4-001 | 575164-01-4-001 (01) / LH WNG BOTOM SKN FLAP TRK 2 NDT INSP | 575164-01-4-001 (01) / LH WNG BOTOM SKN FLAP TRK 2 NDT INSP (25494963) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.275 | 04.Sep.2026 22:00 | 0.25417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, X-RAY / NDT, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 575164-01-4-001 (01) / LH WNG BOTOM SKN FLAP TRK 2 NDT INSP (25494963) |  | 0 / 6 | [] |  |  | MET.25494963 | 29'892 | 706 | 2026-12-06 | C
| 456 | 575164-01-4-002 | 575164-01-4-002 (01) / RH WNG BOTOM SKN FLAP TRK 2 NDT INSP | 575164-01-4-002 (01) / RH WNG BOTOM SKN FLAP TRK 2 NDT INSP (25419465) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.275 | 04.Sep.2026 22:00 | 0.25417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, X-RAY / NDT, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 575164-01-4-002 (01) / RH WNG BOTOM SKN FLAP TRK 2 NDT INSP (25419465) |  | 0 / 6 | [] |  |  | MET.25419465 | 29'892 | 706 | 2026-12-06 | C
| 457 | 575165-01-2-001 | 575165-01-2-001 (02) / LH WING BOTTOM SKIN &FLAP2 FAIR INSP | 575165-01-2-001 (02) / LH WING BOTTOM SKIN &FLAP2 FAIR INSP (25383239) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575165-01-2-001 (02) / LH WING BOTTOM SKIN &FLAP2 FAIR INSP (25383239) |  | 0 / 4 | [] |  |  | MET.25383239 | 35'400 | 6'214 | 2029-01-09 | C
| 458 | 575165-01-2-002 | 575165-01-2-002 (02) / RH WING BOTTOM SKIN &FLAP2 FAIR INSP | 575165-01-2-002 (02) / RH WING BOTTOM SKIN &FLAP2 FAIR INSP (25383838) | Single Running Taskcard | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.036111 | 04.Sep.2026 22:00 | 0.036111 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575165-01-2-002 (02) / RH WING BOTTOM SKIN &FLAP2 FAIR INSP (25383838) |  | 0 / 4 | [] |  |  | MET.25383838 | 35'400 | 6'214 | 2029-01-09 | C
| 459 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (25383783) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.19444 | 04.Sep.2026 22:00 | 0.19444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-30 |  | [] |  |  |  |  | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (25383783) |  | 0 / 3 | [] |  |  | MET.25383783 | 45000:00 | 7801:22 | 2029-03-17 | H
| 460 | 32855789 | DENT ON NOSE FWD FUSELAGE SKIN (0) / DENT ON NOSE FWD FUSELAGE SKIN | 32855789 / DENT ON NOSE FWD FUSELAGE SKIN (0) / DENT ON NOSE FWD FUSELAGE SKIN (32855789) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32855789 / DENT ON NOSE FWD FUSELAGE SKIN (0) / DENT ON NOSE FWD FUSELAGE SKIN (32855789) |  | 0 / 2 | [] |  |  | MET.32855789 | 36'184 | 6'998 | 2029-04-28 | C
| 461 | 31905893 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | 31905893 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905893) | Single Running Taskcard | RI | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | 31905893 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905893) |  | 0 / 2 | [] |  |  | MET.31905893 | 01.Oct.2026 | 31 | 2026-10-01 | D
| 462 | 29290772 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 29290772 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29290772) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 29290772 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29290772) |  | 0 / 1 | [] |  |  | ME.29290772 | 37508:14 | 309:36 | 2026-10-05 | H
| 463 | 32345888 | EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 | 32345888 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345888) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 04.Sep.2026 22:00 | 0.22222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 32345888 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345888) |  | 0 / 5 | [] |  |  | ME.32345888 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 464 | 29904516 | EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A | 29904516 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904516) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.66667 | 04.Sep.2026 22:00 | 0.64583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  | EOD can be done at Line if not reach to C-CHK or Connectivity | 29904516 / EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A (29904516) |  | 0 / 10 | [] |  |  | ME.29904516 | 16.Feb.2027 | 169 | 2027-02-16 | D
| 465 | 32850444 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | 32850444 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850444) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  |  | 32850444 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850444) |  | 0 / 6 | [] |  |  | ME.32850444 | 06.Oct.2026 | 36 | 2026-10-06 | D
| 466 | 29749810 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | 29749810 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749810) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.52083 | 04.Sep.2026 22:00 | 0.52083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 29749810 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749810) |  | 0 / 11 | [] |  |  | ME.29749810 | 31.Dec.2027 | 487 | 2027-12-31 | D
| 467 | 27900248 | EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) | 27900248 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (27900248) | Document | PJED | <html><span style="font-weight: normal;">No part requests</span></html> | 0.38194 | 04.Sep.2026 22:00 | 0.34375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 27900248 / EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) (27900248) |  | 0 / 9 | [] |  |  | ME.27900248 | 29'385 | 199 | 2026-09-27 | C
| 468 | 29715422 | EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO | 29715422 / EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO (29715422) | Document | CCHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.26042 | 04.Sep.2026 22:00 | 0.17361 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 29715422 / EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO (29715422) |  | 0 / 17 | [] |  |  | ME.29715422 | 18.Dec.2027 | 474 | 2027-12-18 | D
| 469 | 30970369 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 30970369 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970369) | Document | AD | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 30970369 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970369) |  | 0 / 4 | [] |  | 000 | ME.30970369 | 26.May.2029 | 999 | 2029-05-26 | D
| 470 | 29411321 | EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411321 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411321) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">21</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.36458 | 04.Sep.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411321 / EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411321) |  | 0 / 6 | [] |  |  | ME.29411321 | 01.Oct.2029 | 1127 | 2029-10-01 | D
| 471 | 29411395 | EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | 29411395 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411395) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">21</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.36458 | 04.Sep.2026 22:00 | 0.33333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] | --, --, --, --, --, CLOSE-UP |  |  |  | 29411395 / EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA (29411395) |  | 0 / 6 | [] |  |  | ME.29411395 | 01.Oct.2029 | 1127 | 2029-10-01 | D
| 472 | 30839461 | EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON | 30839461 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839461) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-01 00:30 | 04.Sep.2026 22:00 | 1899-12-31 06:40 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | --, JOB-SETUP, JOB-SETUP, JOB-SETUP, --, --, --, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, CLOSE-UP, CLOSE-UP |  |  |  | 30839461 / EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON (30839461) |  | 0 / 17 | [] |  |  | ME.30839461 | 01.Dec.2028 | 823 | 2028-12-01 | D
| 473 | 23733290 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23733290 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23733290) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.53125 | 04.Sep.2026 22:00 | 0.51042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23733290 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23733290) |  | 0 / 3 | [] |  | 000 | ME.23733290 | 26'449 | 790 | 2026-12-18 | C
| 474 | 23733519 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23733519 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23733519) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.53125 | 04.Sep.2026 22:00 | 0.51042 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23733519 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23733519) |  | 0 / 3 | [] |  | 000 | ME.23733519 | 26'449 | 790 | 2026-12-18 | C
| 475 | 27076192 | EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED | 27076192 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (27076192) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">20</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-01 06:00 | 04.Sep.2026 22:00 | 1899-12-31 03:15 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | This modification EO can be done either in Line or Hanger Required nose jacking and nose gear swing | 27076192 / EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED (27076192) |  | 0 / 10 | [] |  | 000 | ME.27076192 | 31.Dec.2027 | 487 | 2027-12-31 | D
| 476 | 27685460 | EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS | 27685460 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685460) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.67708 | 04.Sep.2026 22:00 | 0.59375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | PART WILL BE AVL AT EDD 26-AUG-2024 | 27685460 / EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS (27685460) |  | 0 / 5 | [] |  |  | ME.27685460 | 01.Oct.2027 | 396 | 2027-10-01 | D
| 477 | 31427159 | EOD-320-53-00004-R00/AD-A320/21 - FUSELAGE - BELLY FAIRING AND KEEL BEAM SIDE PANEL | 31427159 / EOD-320-53-00004-R00/AD-A320/21 - FUSELAGE - BELLY FAIRING AND KEEL BEAM SIDE PANEL (31427159) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">12</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-04 10:00 | 04.Sep.2026 22:00 | 1900-01-05 20:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31427159 / EOD-320-53-00004-R00/AD-A320/21 - FUSELAGE - BELLY FAIRING AND KEEL BEAM SIDE PANEL (31427159) |  | 0 / 10 | [] |  |  | ME.31427159 | 32'691 | 3'505 | 2027-12-30 | C
| 478 | 30919336 | EOD-320-54-00004-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION | 30919336 / EOD-320-54-00004-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION (30919336) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.093056 | 04.Sep.2026 22:00 | 0.075694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  |  | 30919336 / EOD-320-54-00004-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION (30919336) |  | 0 / 10 | [] |  |  | ME.30919336 | 24.Jan.2027 | 146 | 2027-01-24 | D
| 479 | 30988801 | EOD-320-54-00005-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION | 30988801 / EOD-320-54-00005-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION (30988801) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.1 | 04.Sep.2026 22:00 | 0.079167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  | UNNECESSARY TO PERFORM EOD-320-54-00004 WITHIN SAME LAYOVER. NOTE The Remarks is subject to Post-MOD NUT Availability. | 30988801 / EOD-320-54-00005-R00/AD-ATA 57-A320-WING-PYLON SPIGOT FITTING-SLEEVE MIGRATION (30988801) |  | 0 / 11 | [] |  |  | ME.30988801 | 01.Sep.2029 | 1097 | 2029-09-01 | D
| 480 | 30481986 | EOD-321-31-00003-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | 30481986 / EOD-321-31-00003-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30481986) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.13889 | 04.Sep.2026 22:00 | 0.13889 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30481986 / EOD-321-31-00003-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30481986) |  | 0 / 6 | [] |  |  | ME.30481986 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 481 | 29500744 | EOD-321-31-00004-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | 29500744 / EOD-321-31-00004-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500744) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.25 | 04.Sep.2026 22:00 | 0.25 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29500744 / EOD-321-31-00004-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO (29500744) |  | 0 / 6 | [] |  |  | ME.29500744 | 30.Aug.2027 | 364 | 2027-08-30 | D
| 482 | 30481439 | EOD-321-31-00005-R00/A321 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | 30481439 / EOD-321-31-00005-R00/A321 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481439) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.20486 | 04.Sep.2026 22:00 | 0.20486 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30481439 / EOD-321-31-00005-R00/A321 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481439) |  | 0 / 6 | [] |  |  | ME.30481439 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 483 | 29155544 | EOD-321-31-00006-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | 29155544 / EOD-321-31-00006-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155544) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 04.Sep.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155544 / EOD-321-31-00006-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155544) |  | 0 / 6 | [] |  |  | ME.29155544 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 484 | 29155673 | EOD-321-31-00008-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 29155673 / EOD-321-31-00008-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155673) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 04.Sep.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155673 / EOD-321-31-00008-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155673) |  | 0 / 6 | [] |  |  | ME.29155673 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 485 | 29155762 | EOD-321-31-00009-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 29155762 / EOD-321-31-00009-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (29155762) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155762 / EOD-321-31-00009-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (29155762) |  | 0 / 6 | [] |  |  | ME.29155762 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 486 | 31476915 | EOD-321-44-00007-R00/ECLIPSE CONNECTIVITY MODIFICATION | 31476915 / EOD-321-44-00007-R00/ECLIPSE CONNECTIVITY MODIFICATION (31476915) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">27</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-18 12:00 | 04.Sep.2026 22:00 | 1900-01-17 20:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 31476915 / EOD-321-44-00007-R00/ECLIPSE CONNECTIVITY MODIFICATION (31476915) |  | 0 / 42 | [] |  |  | ME.31476915 | 31.Dec.2026 | 122 | 2026-12-31 | D
| 487 | 30695758 | EOD-321-44-00018-R00/DE-MOD TAQNIA SYSTEM REMOVAL | 30695758 / EOD-321-44-00018-R00/DE-MOD TAQNIA SYSTEM REMOVAL (30695758) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-06 02:00 | 04.Sep.2026 22:00 | 1900-01-06 02:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 44 |  | [] |  |  |  |  | 30695758 / EOD-321-44-00018-R00/DE-MOD TAQNIA SYSTEM REMOVAL (30695758) |  | 0 / 5 | [] |  |  | ME.30695758 | 01.Feb.2027 | 154 | 2027-02-01 | D
| 488 | 29155928 | EOD-321-46-00003-R00/INSTALL FOMAX SYSTEM PROVISIONS | 29155928 / EOD-321-46-00003-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155928) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.96528 | 04.Sep.2026 22:00 | 0.79861 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29155928 / EOD-321-46-00003-R00/INSTALL FOMAX SYSTEM PROVISIONS (29155928) |  | 0 / 14 | [] |  |  | ME.29155928 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 489 | 29155985 | EOD-321-46-00004-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 29155985 / EOD-321-46-00004-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29155985) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.75 | 04.Sep.2026 22:00 | 0.4375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29155985 / EOD-321-46-00004-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29155985) |  | 0 / 8 | [] |  |  | ME.29155985 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 490 | 29156055 | EOD-321-46-00005-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 29156055 / EOD-321-46-00005-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156055) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.77083 | 04.Sep.2026 22:00 | 0.60417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156055 / EOD-321-46-00005-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156055) |  | 0 / 9 | [] |  |  | ME.29156055 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 491 | 29156154 | EOD-321-46-00006-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 29156154 / EOD-321-46-00006-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156154) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.10417 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156154 / EOD-321-46-00006-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156154) |  | 0 / 5 | [] |  |  | ME.29156154 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 492 | 29157086 | EOD-321-46-00007-R00/FOMAX 4 ACTIVATION | 29157086 / EOD-321-46-00007-R00/FOMAX 4 ACTIVATION (29157086) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.16667 | 04.Sep.2026 22:00 | 0.14583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29157086 / EOD-321-46-00007-R00/FOMAX 4 ACTIVATION (29157086) |  | 0 / 8 | [] |  |  | ME.29157086 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 493 | 29156207 | EOD-321-46-00008-R00/ACTIVATE FOMAX OPTION 1 | 29156207 / EOD-321-46-00008-R00/ACTIVATE FOMAX OPTION 1 (29156207) | Document | C | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156207 / EOD-321-46-00008-R00/ACTIVATE FOMAX OPTION 1 (29156207) |  | 0 / 5 | [] |  |  | ME.29156207 | 29.Feb.2028 | 547 | 2028-02-29 | D
| 494 | 14811451 | EOD-321-53-00010-R00/AD-INSPECTION OF THE DOOR STOP FITTING HOLES ON DOOR STOP | 14811451 / EOD-321-53-00010-R00/AD-INSPECTION OF THE DOOR STOP FITTING HOLES ON DOOR STOP (14811451) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">8</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 10:30 | 04.Sep.2026 22:00 | 1899-12-31 07:20 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 14811451 / EOD-321-53-00010-R00/AD-INSPECTION OF THE DOOR STOP FITTING HOLES ON DOOR STOP (14811451) |  | 0 / 13 | [] |  |  | ME.14811451 | 30'000 | 814 | 2026-12-21 | C
| 495 | 18029146 | EOD-321-53-00015-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 18029146 / EOD-321-53-00015-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (18029146) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | Revision 6 - update priority | 18029146 / EOD-321-53-00015-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (18029146) |  | 0 / 6 | [] |  |  | ME.18029146 | 34'032 | 4'846 | 2028-07-03 | C
| 496 | 18029255 | EOD-321-53-00016-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 18029255 / EOD-321-53-00016-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (18029255) | Document | AD | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.076389 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 18029255 / EOD-321-53-00016-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME (18029255) |  | 0 / 6 | [] |  |  | ME.18029255 | 34'032 | 4'846 | 2028-07-03 | C
| 497 | 21624440 | EOD-321-53-00021-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME | 21624440 / EOD-321-53-00021-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME (21624440) | Document | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | Revision 3 - update priority | 21624440 / EOD-321-53-00021-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME (21624440) |  | 0 / 9 | [] |  |  | ME.21624440 | 33'076 | 3'890 | 2028-02-21 | C
| 498 | 21624433 | EOD-321-53-00022-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME | 21624433 / EOD-321-53-00022-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME (21624433) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.34722 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | Revision 4 - update priority | 21624433 / EOD-321-53-00022-R00/AD-INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME (21624433) |  | 0 / 9 | [] |  |  | ME.21624433 | 33'076 | 3'890 | 2028-02-21 | C
| 499 | 17693475 | EOD-321-53-00023-R00/AD-FUSELAGE - WINDSHIELD CENTRAL LOWER NODE - INSPECTION OF WINDSHIELD | 17693475 / EOD-321-53-00023-R00/AD-FUSELAGE - WINDSHIELD CENTRAL LOWER NODE - INSPECTION OF WINDSHIELD (17693475) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 01:05 | 04.Sep.2026 22:00 | 1899-12-31 23:05 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 17693475 / EOD-321-53-00023-R00/AD-FUSELAGE - WINDSHIELD CENTRAL LOWER NODE - INSPECTION OF WINDSHIELD (17693475) |  | 0 / 10 | [] |  |  | ME.17693475 | 30'600 | 1'414 | 2027-03-15 | C
| 500 | 27749648 | EOD-321-53-00040-R01/AD-FUSELAGE - MAIN STRUCTURE - REINFORCE FITTING AT TORSION | 27749648 / EOD-321-53-00040-R01/AD-FUSELAGE - MAIN STRUCTURE - REINFORCE FITTING AT TORSION (27749648) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">11</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-02 02:40 | 04.Sep.2026 22:00 | 1899-12-31 21:40 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | Rev 3 - update priority | 27749648 / EOD-321-53-00040-R01/AD-FUSELAGE - MAIN STRUCTURE - REINFORCE FITTING AT TORSION (27749648) |  | 0 / 14 | [] |  |  | ME.27749648 | 03.Apr.2027 | 215 | 2027-04-03 | D
| 501 | 29441783 | EOD-321-53-00041-R01/AD-321- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 29441783 / EOD-321-53-00041-R01/AD-321- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441783) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 09:45 | 04.Sep.2026 22:00 | 1899-12-31 06:10 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | update priority | 29441783 / EOD-321-53-00041-R01/AD-321- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 (29441783) |  | 0 / 12 | [] |  |  | ME.29441783 | 35'276 | 6'090 | 2028-12-23 | C
| 502 | 31458795 | EOD-321-53-00043-R00/FWD FUSELAGE-HOLES FR 35.3 LHS UNDER SLIDEBOX INSPECTION - AFTER RDAS | 31458795 / EOD-321-53-00043-R00/FWD FUSELAGE-HOLES FR 35.3 LHS UNDER SLIDEBOX INSPECTION - AFTER RDAS (31458795) | Document | C | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 04.Sep.2026 22:00 | 0.014583 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53-10-02 |  | [] |  |  |  |  | 31458795 / EOD-321-53-00043-R00/FWD FUSELAGE-HOLES FR 35.3 LHS UNDER SLIDEBOX INSPECTION - AFTER RDAS (31458795) |  | 0 / 5 | [] |  |  | ME.31458795 | 31'396 | 2'210 | 2027-07-03 | C
| 503 | 27655459 | EOD-321-53-00044-R00/FWD FUSELAGE-HOLES FR 35.3 RHS UNDER SLIDEBOX INSPECTION - AFTER RDAS | 27655459 / EOD-321-53-00044-R00/FWD FUSELAGE-HOLES FR 35.3 RHS UNDER SLIDEBOX INSPECTION - AFTER RDAS (27655459) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | RELATED AMOS WO# 92093641 | 27655459 / EOD-321-53-00044-R00/FWD FUSELAGE-HOLES FR 35.3 RHS UNDER SLIDEBOX INSPECTION - AFTER RDAS (27655459) |  | 0 / 2 | [] |  |  | ME.27655459 | 32'651 | 3'465 | 2027-12-24 | C
| 504 | 28479630 | EOD-321-53-00063-R00/AD-FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION | 28479630 / EOD-321-53-00063-R00/AD-FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION (28479630) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">11</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.82639 | 04.Sep.2026 22:00 | 0.72222 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  | Revision 2- update priority | 28479630 / EOD-321-53-00063-R00/AD-FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION (28479630) |  | 0 / 10 | [] |  |  | ME.28479630 | 33'400 | 4'214 | 2028-04-06 | C
| 505 | 29399482 | EOD-321-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI | 29399482 / EOD-321-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI (29399482) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 04:10 | 04.Sep.2026 22:00 | 1899-12-31 00:10 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 55 |  | [] |  |  |  | Prequisites: Perform ED S55-D10005 to check the overplay on Rudder, prior perform this EOD. NOTE This EOD is on-conditional depends by the result of ED S55-D10005 | 29399482 / EOD-321-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI (29399482) |  | 0 / 12 | [] |  |  | ME.29399482 | 22.Apr.2032 | 2061 | 2032-04-22 | D
| 506 | 24388868 | EOD-321-57-00003-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND | 24388868 / EOD-321-57-00003-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND (24388868) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.43056 | 04.Sep.2026 22:00 | 0.19792 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  | DO CONCURRENT WITH EOD-321-57-00004-R00 | 24388868 / EOD-321-57-00003-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND (24388868) |  | 0 / 7 | [] |  |  | ME.24388868 | 31'000 | 1'814 | 2027-05-09 | C
| 507 | 24388883 | EOD-321-57-00004-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND | 24388883 / EOD-321-57-00004-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND (24388883) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">9</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.14236 | 04.Sep.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 57 |  | [] |  |  |  | DO CONCURRENT WITH EOD-321-57-00003-R00 | 24388883 / EOD-321-57-00004-R00/AD-WINGS - INSPECTION OF CENTER WING BOX (CWB) REAR LOWER SPAR AND (24388883) |  | 0 / 7 | [] |  |  | ME.24388883 | 31'000 | 1'814 | 2027-05-09 | C
| 508 | 24373163 | EOD-321-92-00001-R00/AD-ELECTRIC AND ELECTRONIC COMMON INSTALLATION - | 24373163 / EOD-321-92-00001-R00/AD-ELECTRIC AND ELECTRONIC COMMON INSTALLATION - (24373163) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">21</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1900-01-02 22:30 | 04.Sep.2026 22:00 | 1900-01-01 04:30 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 92 |  | [] |  |  |  |  | 24373163 / EOD-321-92-00001-R00/AD-ELECTRIC AND ELECTRONIC COMMON INSTALLATION - (24373163) |  | 0 / 15 | [] |  |  | ME.24373163 | 30'000 | 814 | 2026-12-21 | C
| 509 | 31053084 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31053084 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053084) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31053084 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31053084) |  | 0 / 2 | [] |  | 000 | ME.31053084 | 22.Sep.2026 | 21d, 12h | 2026-09-22 | D
| 510 | 31600187 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31600187 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31600187) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31600187 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31600187) |  | 0 / 2 | [] |  | 000 | ME.31600187 | 22.Sep.2026 | 21d, 12h | 2026-09-22 | D
| 511 | 31909581 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 31909581 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31909581) | Document | RON | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 31909581 / EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE (31909581) |  | 0 / 2 | [] |  | 000 | ME.31909581 | 22.Sep.2026 | 21d, 12h | 2026-09-22 | D
| 512 | 31902844 | EOD-A32S-31-00002-R00/A32S-SDAC - SHIELD TEMPERATURE DATA PROVIDER WIRES FROM HYDRAULIC TANK | 31902844 / EOD-A32S-31-00002-R00/A32S-SDAC - SHIELD TEMPERATURE DATA PROVIDER WIRES FROM HYDRAULIC TANK (31902844) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 11:10 | 04.Sep.2026 22:00 | 0.81944 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 31902844 / EOD-A32S-31-00002-R00/A32S-SDAC - SHIELD TEMPERATURE DATA PROVIDER WIRES FROM HYDRAULIC TANK (31902844) |  | 0 / 9 | [] |  |  | ME.31902844 | 28.Jan.2029 | 881 | 2029-01-28 | D
| 513 | 9547732 | EOD-A32S-53-00016-R02/AD-FUSELAGE-INSPECTION AT CROSSBEAM SPLICING FR16/20 LHS/RHS | 9547732 / EOD-A32S-53-00016-R02/AD-FUSELAGE-INSPECTION AT CROSSBEAM SPLICING FR16/20 LHS/RHS (9547732) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">15</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 08:15 | 04.Sep.2026 22:00 | 1899-12-31 14:15 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 9547732 / EOD-A32S-53-00016-R02/AD-FUSELAGE-INSPECTION AT CROSSBEAM SPLICING FR16/20 LHS/RHS (9547732) |  | 0 / 27 | [] |  |  | ME.9547732 | 31'200 | 2'014 | 2027-06-06 | C
| 514 | 29463721 | EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION | 29463721 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463721) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59722 | 04.Sep.2026 22:00 | 0.50694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78 |  | [] |  |  |  |  | 29463721 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463721) |  | 0 / 13 | [] |  | S78RVR415LHN1 | ME.29463721 | 26.Sep.2028 | 757 | 2028-09-26 | D
| 515 | 29463725 | EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION | 29463725 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463725) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59722 | 04.Sep.2026 22:00 | 0.50694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78 |  | [] |  |  |  |  | 29463725 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463725) |  | 0 / 13 | [] |  | S78RVR415RHN1 | ME.29463725 | 26.Sep.2028 | 757 | 2028-09-26 | D
| 516 | 29463731 | EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION | 29463731 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463731) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">6</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59722 | 04.Sep.2026 22:00 | 0.50694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78 |  | [] |  |  |  |  | 29463731 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463731) |  | 0 / 13 | [] |  | S78RVR416LHN2 | ME.29463731 | 26.Sep.2028 | 757 | 2028-09-26 | D
| 517 | 29463744 | EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION | 29463744 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463744) | Document | PJED | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.59722 | 04.Sep.2026 22:00 | 0.50694 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78 |  | [] |  |  |  |  | 29463744 / EOD-A32S-78-00001-R00/AD-2016-0076 THRUST REVERSER - 3/9 O`CLOCK PIVOT FITTING INSPECTION (29463744) |  | 0 / 13 | [] |  | S78RVR416RHN2 | ME.29463744 | 26.Sep.2028 | 757 | 2028-09-26 | D
| 518 | 32822281 | S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY | 32822281 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822281) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26 |  | [] |  |  |  |  | 32822281 / S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY (32822281) |  | 0 / 2 | [] |  |  | ME.32822281 | 14.Dec.2026 | 105 | 2026-12-14 | D
| 519 | 27309216 | S27-R10030/HZ-ASP // PERMANENT REPAIR OF BRACKET | 27309216 / S27-R10030/HZ-ASP // PERMANENT REPAIR OF BRACKET (27309216) | Document | C | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.125 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 27309216 / S27-R10030/HZ-ASP // PERMANENT REPAIR OF BRACKET (27309216) |  | 0 / 2 | [] |  |  | ME.27309216 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 520 | 30693123 | S29-R10062/INSPECTION OF HYDRAULIC HOSE/TUBE ASSEMBLIES AND CLAMPS ENGINE SIDE | 30693123 / S29-R10062/INSPECTION OF HYDRAULIC HOSE/TUBE ASSEMBLIES AND CLAMPS ENGINE SIDE (30693123) | Document | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.39583 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] |  |  |  |  | 30693123 / S29-R10062/INSPECTION OF HYDRAULIC HOSE/TUBE ASSEMBLIES AND CLAMPS ENGINE SIDE (30693123) |  | 0 / 3 | [] |  |  | ME.30693123 | 23.Dec.2026 | 114 | 2026-12-23 | D
| 521 | 31662568 | S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH | 31662568 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662568) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.11111 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 29 |  | [] |  |  |  |  | 31662568 / S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH (31662568) |  | 0 / 4 | [] |  |  | ME.31662568 | 30.Dec.2026 | 121 | 2026-12-30 | D
| 522 | 30206003 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | 30206003 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30206003) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.0625 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] | INSPECTION |  |  |  | 30206003 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30206003) |  | 0 / 1 | [] |  |  | ME.30206003 | 17.Nov.2026 | 78 | 2026-11-17 | D
| 523 | 30262871 | S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL | 30262871 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262871) | Document | ACHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.0625 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | If the part is S/D, please hold the plan and Inform Engineering . | 30262871 / S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL (30262871) |  | 0 / 4 | [] |  |  | ME.30262871 | 05.Sep.2026 | 5 | 2026-09-05 | D
| 524 | 30936901 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | 30936901 / S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM (30936901) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.9375 | 04.Sep.2026 22:00 | 0.54167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 32-33 |  | [] | --, --, --, --, --, --, --, --, --, --, OPS/LK, --, --, --, CLOSE-UP |  |  |  | 30936901 / S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM (30936901) |  | 0 / 15 | [] |  |  | ME.30936901 | 21.Aug.2028 | 721 | 2028-08-21 | D
| 525 | 32070182 | S35-D10066/A320/21 - PBE SERIAL NUMBER VERIFICATION. | 32070182 / S35-D10066/A320/21 - PBE SERIAL NUMBER VERIFICATION. (32070182) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.048611 | 04.Sep.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35 |  | [] |  |  |  |  | 32070182 / S35-D10066/A320/21 - PBE SERIAL NUMBER VERIFICATION. (32070182) |  | 0 / 2 | [] |  |  | ME.32070182 | 09.Sep.2026 | 9 | 2026-09-09 | D
| 526 | 30423787 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | 30423787 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30423787) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 30423787 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30423787) |  | 0 / 3 | [] |  |  | ME.30423787 | 37508:14 | 309:36 | 2026-10-05 | H
| 527 | 32800105 | S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK | 32800105 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800105) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 1899-12-31 07:00 | 04.Sep.2026 22:00 | 1899-12-31 07:00 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  | Please C/W. This ER is issued to perform Bleed Health Check on A320 CEO fleet EBAS system. Kindly schedule this task in the C-Check. | 32800105 / S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK (32800105) |  | 0 / 18 | [] |  |  | ME.32800105 | 31.Dec.2029 | 1218 | 2029-12-31 | D
| 528 | 32316646 | S51-R10016/A320 // DENT AND BUCKLE CHART UPDATE | 32316646 / S51-R10016/A320 // DENT AND BUCKLE CHART UPDATE (32316646) | Document | C | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 17:30 | 04.Sep.2026 22:00 | 0.69444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32316646 / S51-R10016/A320 // DENT AND BUCKLE CHART UPDATE (32316646) |  | 0 / 11 | [] |  |  | ME.32316646 | 05.Sep.2026 | 5 | 2026-09-05 | D
| 529 | 31573595 | S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS | 31573595 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573595) | Document | CCHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 04.Sep.2026 22:00 | 0.10417 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 31573595 / S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS (31573595) |  | 0 / 7 | [] |  |  | ME.31573595 | 31.Dec.2028 | 853 | 2028-12-31 | D
| 530 | 26291307 | S53-R10354/HZ-ASP // CRACK INDICATION AT SIDE POST FR4 UPPER ATTACHMENT | 26291307 / S53-R10354/HZ-ASP // CRACK INDICATION AT SIDE POST FR4 UPPER ATTACHMENT (26291307) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 26291307 / S53-R10354/HZ-ASP // CRACK INDICATION AT SIDE POST FR4 UPPER ATTACHMENT (26291307) |  | 0 / 2 | [] |  |  | ME.26291307 | 33'751 | 4'565 | 2028-05-25 | C
| 531 | 26292805 | S53-R10360/HZ-ASP // CRACK / REWORK IND AT DOUBLER JOGGLE AREA FR 16 RH & LH | 26292805 / S53-R10360/HZ-ASP // CRACK / REWORK IND AT DOUBLER JOGGLE AREA FR 16 RH & LH (26292805) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 04.Sep.2026 22:00 | 0.16667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 26292805 / S53-R10360/HZ-ASP // CRACK / REWORK IND AT DOUBLER JOGGLE AREA FR 16 RH & LH (26292805) |  | 0 / 3 | [] |  |  | ME.26292805 | 29'543 | 357 | 2026-10-19 | C
| 532 | 27655946 | S53-R10576/HZ-ASP // HEAVY MECH DAMAGE FOUND AT FR 35.3LH | 27655946 / S53-R10576/HZ-ASP // HEAVY MECH DAMAGE FOUND AT FR 35.3LH (27655946) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 27655946 / S53-R10576/HZ-ASP // HEAVY MECH DAMAGE FOUND AT FR 35.3LH (27655946) |  | 0 / 2 | [] |  |  | ME.27655946 | 30'351 | 1'165 | 2027-02-08 | C
| 533 | 32240396 | S55-D10005/A320 - RUDDER ATTACH FITTINGS INSPECTION | 32240396 / S55-D10005/A320 - RUDDER ATTACH FITTINGS INSPECTION (32240396) | Document | CCHK | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.28125 | 04.Sep.2026 22:00 | 0.22917 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 55 |  | [] |  |  |  |  | 32240396 / S55-D10005/A320 - RUDDER ATTACH FITTINGS INSPECTION (32240396) |  | 0 / 2 | [] |  |  | ME.32240396 | 16.Jan.2027 | 138 | 2027-01-16 | D
| 534 | 32832500 | S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR | 32832500 / S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR (32832500) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 32832500 / S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR (32832500) |  | 0 / 2 | [] |  |  | ME.32832500 | 16.Jun.2029 | 1020 | 2029-06-16 | D
| 535 | 27936373 | REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) | 27936373 / REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) (27936373) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 27936373 / REPLACE 4323100-01-6622/N14101241023296 (3000/3075 OVEN SERIES) (27936373) |  | 0 / 1 | [] |  | 004 | ME.27936373 | 36118:45 | 492:45 | 2026-10-27 | H
| 536 | 27946863 | REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) | 27946863 / REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) (27946863) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 27946863 / REPLACE 4323100-01-6622/N16070192AA0676 (3000/3075 OVEN SERIES) (27946863) |  | 0 / 1 | [] |  | 005 | ME.27946863 | 26585:13 | 509:39 | 2026-10-29 | H
| 537 | 28372304 | REPLACE DVE90-07/6953 (VALVE-SOLENOID) | 28372304 / REPLACE DVE90-07/6953 (VALVE-SOLENOID) (28372304) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35-00 |  | [] |  |  |  |  | 28372304 / REPLACE DVE90-07/6953 (VALVE-SOLENOID) (28372304) |  | 0 / 1 | [] |  | 000 | ME.28372304 | 04.Sep.2026 | 4 | 2026-09-04 | D
| 538 | 31871488 | REPLACE PPC1100-00/74293 (CARGO,SMOKE DETECTOR) | 31871488 / REPLACE PPC1100-00/74293 (CARGO,SMOKE DETECTOR) (31871488) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31871488 / REPLACE PPC1100-00/74293 (CARGO,SMOKE DETECTOR) (31871488) |  | 0 / 1 | [] |  | 10WH | ME.31871488 | 18000:00 | 736:54 | 2026-11-25 | H
| 539 | 31871490 | REPLACE PPC1100-00/74546 (CARGO,SMOKE DETECTOR) | 31871490 / REPLACE PPC1100-00/74546 (CARGO,SMOKE DETECTOR) (31871490) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 04.Sep.2026 22:00 | 0 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31871490 / REPLACE PPC1100-00/74546 (CARGO,SMOKE DETECTOR) (31871490) |  | 0 / 1 | [] |  | 9WH | ME.31871490 | 18000:00 | 736:54 | 2026-11-25 | H
| 540 | 22579023 | REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) | 22579023 / REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) (22579023) | Replacement Event | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 25-63-05 |  | [] |  |  |  |  | 22579023 / REPLACE S1823502-05/TM0000238322 (EMERGENCY LOCATOR TRANSMITTR) (22579023) |  | 0 / 1 | [] |  | 001 | ME.22579023 | 17.Dec.2026 | 108 | 2026-12-17 | D
| 541 | 32963988 | 114122014/CH1205722 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32963988 / 114122014/CH1205722 LB(LUBRICATION) / LUB OF MLG AND DOORS (32963988) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.083333 | 04.Sep.2026 22:00 | 0.048611 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32963988 / 114122014/CH1205722 LB(LUBRICATION) / LUB OF MLG AND DOORS (32963988) |  | 0 / 3 | [] |  | 001 | ME.32963988 | 13.Sep.2026 | 13 | 2026-09-13 | D
| 542 | 22001396 | 34100005-1/74611D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 22001396 / 34100005-1/74611D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22001396) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 04.Sep.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 22001396 / 34100005-1/74611D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22001396) |  | 0 / 3 | [] |  | 202 | ME.22001396 | 07.Dec.2026 | 98 | 2026-12-07 | D
| 543 | 22574802 | 34100005-1/E1812D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 22574802 / 34100005-1/E1812D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574802) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.072917 | 04.Sep.2026 22:00 | 0.052083 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 22574802 / 34100005-1/E1812D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574802) |  | 0 / 3 | [] |  | 201 | ME.22574802 | 24.Feb.2027 | 177 | 2027-02-24 | D
| 544 | 32354827 | 342B050000/18943 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32354827 / 342B050000/18943 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32354827) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32354827 / 342B050000/18943 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32354827) |  | 0 / 4 | [] |  | 002 | ME.32354827 | 22137:06 | 309:36 | 2026-10-05 | H
| 545 | 32354830 | 342B050000/18947 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 32354830 / 342B050000/18947 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32354830) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.091667 | 04.Sep.2026 22:00 | 0.091667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 32354830 / 342B050000/18947 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL (32354830) |  | 0 / 4 | [] |  | 001 | ME.32354830 | 21023:30 | 309:36 | 2026-10-05 | H
| 546 | 27433594 | 642-3801-533/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT | 27433594 / 642-3801-533/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27433594) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">3</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.033333 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 27433594 / 642-3801-533/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27433594) |  | 0 / 3 | [] |  | S78RVR415LHN1 | ME.27433594 | 40988:17 | 3789:39 | 2027-11-24 | H
| 547 | 27433595 | 642-3801-533/11094001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT | 27433595 / 642-3801-533/11094001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27433595) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.033333 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 27433595 / 642-3801-533/11094001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27433595) |  | 0 / 3 | [] |  | S78RVR415RHN1 | ME.27433595 | 40988:17 | 3789:39 | 2027-11-24 | H
| 548 | 27446107 | 642-3802-535/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT | 27446107 / 642-3802-535/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27446107) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.033333 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 27446107 / 642-3802-535/11093001 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27446107) |  | 0 / 3 | [] |  | S78RVR416LHN2 | ME.27446107 | 40988:17 | 3789:39 | 2027-11-24 | H
| 549 | 27446108 | 642-3802-535/13830003 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT | 27446108 / 642-3802-535/13830003 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27446108) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.033333 | 04.Sep.2026 22:00 | 0.033333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 27446108 / 642-3802-535/13830003 IN(INSPECTION) / GVI OF ACTUATOR ROD END ATTACHMENT (27446108) |  | 0 / 3 | [] |  | S78RVR416RHN2 | ME.27446108 | 22933:07 | 3789:39 | 2027-11-24 | H
| 550 | 26275155 | 9024-15704-03/21210348 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 26275155 / 9024-15704-03/21210348 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (26275155) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.086806 | 04.Sep.2026 22:00 | 0.065972 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 26275155 / 9024-15704-03/21210348 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (26275155) |  | 0 / 3 | [] |  | 002 | ME.26275155 | 01.Dec.2027 | 457 | 2027-12-01 | D
| 551 | 31702603 | CFM56-5B3/3/645426 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 31702603 / CFM56-5B3/3/645426 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (31702603) | Part Requirement | 1 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.56667 | 04.Sep.2026 22:00 | 0.33403 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP |  |  |  | 31702603 / CFM56-5B3/3/645426 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (31702603) |  | 0 / 7 | [] |  | ENG200 | ME.31702603 | 21'681 | 282 | 2026-10-08 | C
| 552 | 31345003 | MXP801-11/SE133391 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB | 31345003 / MXP801-11/SE133391 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31345003) | Part Requirement | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35 |  | [] | JOB-SETUP, -- |  |  |  | 31345003 / MXP801-11/SE133391 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31345003) |  | 0 / 2 | [] |  | 000 | ME.31345003 | 1'102 | 66 | 2026-11-05 | ID
| 553 | 31344997 | MXP801-11/SE38062 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB | 31344997 / MXP801-11/SE38062 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31344997) | Part Requirement | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35 |  | [] | JOB-SETUP, -- |  |  |  | 31344997 / MXP801-11/SE38062 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31344997) |  | 0 / 2 | [] |  | 001 | ME.31344997 | 5'597 | 66 | 2026-11-05 | ID
| 554 | 31344999 | MXP801-11/SE38500 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB | 31344999 / MXP801-11/SE38500 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31344999) | Part Requirement | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35 |  | [] | JOB-SETUP, -- |  |  |  | 31344999 / MXP801-11/SE38500 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31344999) |  | 0 / 2 | [] |  | 000 | ME.31344999 | 5'587 | 66 | 2026-11-05 | ID
| 555 | 31345001 | MXP801-11/SE99764 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB | 31345001 / MXP801-11/SE99764 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31345001) | Part Requirement | LINE | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">5</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.069444 | 04.Sep.2026 22:00 | 0.069444 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 35 |  | [] | JOB-SETUP, -- |  |  |  | 31345001 / MXP801-11/SE99764 LB(LUBRICATION) / OXY STOWAGE BOX CLN & LUB (31345001) |  | 0 / 2 | [] |  | 000 | ME.31345001 | 2'888 | 66 | 2026-11-05 | ID
| 556 | 81077674 | SEAT 1L RECLINE LEVER IS MISSING OPEN BY CREW | 81077674 / SEAT 1L RECLINE LEVER IS MISSING OPEN BY CREW (81077674) | Workorder | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">2</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 0 | 04.Sep.2026 22:00 | 0 | 08.Jul.2026 22:26 | 1900-02-21 13:37 |  | 0.041667 | Idle | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 81077674 / SEAT 1L RECLINE LEVER IS MISSING OPEN BY CREW (81077674) |  | 0 / 1 | [] |  |  | WO.81077674 | 05.Nov.2026 | 66 | 2026-11-05 | D
| 557 | 93616258 | SEAT CABLES DAMAGE[C-CHK]. SEAT TO SEAT CABLES DAMAGED AS FOLLOWS: 1L/H BLACK CABLE P/N: 178319-1600; 30-42L/H BLUE CABLE P/N: 182336-438; 41-42L/H, 50-51L/H, 51-52R/H BLUE CABLES P/N: 182276-1400. REPLACEMENT REQUIRED IAW AMM 25-21-61-04 REV 58. | 93616258 / SEAT CABLES DAMAGE[C-CHK]. SEAT TO SEAT CABLES DAMAGED AS FOLLOWS: 1L/H BLACK CABLE P/N: 178319-1600; 30-42L/H BLUE CABLE P/N: 182336-438; 41-42L/H, 50-51L/H, 51-52R/H BLUE CABLES P/N: 182276-1400. REPLACEMENT REQUIRED IAW AMM 25-21-61-04 REV 58. (93616258) | Workorder | M | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">4</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0 | 04.Sep.2026 22:00 | 0 | 24.Sep.2023 08:05 | 1902-12-07 03:58 |  | 0.00069444 | Idle | 0 | T: 0; O: 0; C: 0 | 25-21 | Approved | [] |  | 5001256324 |  |  | 93616258 / SEAT CABLES DAMAGE[C-CHK]. SEAT TO SEAT CABLES DAMAGED AS FOLLOWS: 1L/H BLACK CABLE P/N: 178319-1600; 30-42L/H BLUE CABLE P/N: 182336-438; 41-42L/H, 50-51L/H, 51-52R/H BLUE CABLES P/N: 182276-1400. REPLACEMENT REQUIRED IAW AMM 25-21-61-04 REV 58. (93616258) |  | 0 / 1 | [] |  |  | WO.93616258 | 27.Sep.2026 | 27 | 2026-09-27 | D
| 558 | 94134879 | FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR[5000 FC]. FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR PLZ CHECK | 94134879 / FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR[5000 FC]. FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR PLZ CHECK (94134879) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 04.Sep.2026 22:00 | 0.33333 | 02.Jan.2025 19:22 | 1901-08-27 16:41 |  | 0.625 | Idle | 0 | T: 0; O: 0; C: 0 | 53-00-01 | Approved | [] |  |  |  |  | 94134879 / FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR[5000 FC]. FOUND DENT / SCRATCH R/H SIDE OF L2 DOOR PLZ CHECK (94134879) |  | 0 / 2 | [] |  |  | WO.94134879 | 30'709 | 1'523 | 2027-03-30 | C
| 559 | 94154134 | DENT ON L/H FWD FUSELAGE[10000FH/5000FC]. DURING ARR WAC FOUND DENT ON L/H FWD FUSELAGE | 94154134 / DENT ON L/H FWD FUSELAGE[10000FH/5000FC]. DURING ARR WAC FOUND DENT ON L/H FWD FUSELAGE (94154134) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 04.Sep.2026 22:00 | 0.33333 | 31.Jan.2025 12:44 | 1901-07-29 23:19 |  | 0.375 | Idle | 0 | T: 0; O: 0; C: 0 | 53 | Approved | [] |  |  |  |  | 94154134 / DENT ON L/H FWD FUSELAGE[10000FH/5000FC]. DURING ARR WAC FOUND DENT ON L/H FWD FUSELAGE (94154134) |  | 0 / 1 | [] |  |  | WO.94154134 | 30'867 | 1'681 | 2027-04-21 | C
| 560 | 94200818 | REF. TO W/O: 29984684 DURING W/A FOUND BLEND OUT WITH SCRATCH L4 AFT BTWN FR68 TO 69 AND STG 18L - 19L. | 94200818 / REF. TO W/O: 29984684 DURING W/A FOUND BLEND OUT WITH SCRATCH L4 AFT BTWN FR68 TO 69 AND STG 18L - 19L. (94200818) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 | 02.Mar.2025 23:17 | 1901-06-29 12:46 |  | 0.083333 | Idle | 0 | T: 0; O: 0; C: 0 | 53 | WO transferred Engineering Appr | [] |  |  |  |  | 94200818 / REF. TO W/O: 29984684 DURING W/A FOUND BLEND OUT WITH SCRATCH L4 AFT BTWN FR68 TO 69 AND STG 18L - 19L. (94200818) |  | 0 / 1 | [] |  |  | WO.94200818 | 30'992 | 1'806 | 2027-05-08 | C
| 561 | 94267513 | BIRD STRIKE INITIAL EVALUATION FOUND RH WING SLAT # 2 HAS DENT MEASURE L=2.7" W=1.0" D=0.008" DIST. TO NEAREST RIVET 2.2" REQD FINAL EVALUATION- RII AMO-001 REF WO 94267511 | 94267513 / BIRD STRIKE INITIAL EVALUATION FOUND RH WING SLAT # 2 HAS DENT MEASURE L=2.7" W=1.0" D=0.008" DIST. TO NEAREST RIVET 2.2" REQD FINAL EVALUATION- RII AMO-001 REF WO 94267511 (94267513) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 | 06.Aug.2025 01:46 | 1901-01-24 10:17 |  | 0.29167 | Idle | 0 | T: 0; O: 0; C: 0 | 05 |  | [] |  |  |  |  | 94267513 / BIRD STRIKE INITIAL EVALUATION FOUND RH WING SLAT # 2 HAS DENT MEASURE L=2.7" W=1.0" D=0.008" DIST. TO NEAREST RIVET 2.2" REQD FINAL EVALUATION- RII AMO-001 REF WO 94267511 (94267513) |  | 0 / 2 | [] |  |  | WO.94267513 | 31'924 | 2'738 | 2027-09-14 | C
| 562 | 94663602 | REF WO 94663595 BIRD STRIKE INITAL EVALUATION FOR DENT FOUND AFTER BIRD STRIKE UNDER CAPTAIN WINDSHIELD AS FOLLOW DIM L=3" AND W=3" DEP =0.04 FR3 FWD OF STA4330 AND STGR18 NEAREST FASTENRS =0.71" | 94663602 / REF WO 94663595 BIRD STRIKE INITAL EVALUATION FOR DENT FOUND AFTER BIRD STRIKE UNDER CAPTAIN WINDSHIELD AS FOLLOW DIM L=3" AND W=3" DEP =0.04 FR3 FWD OF STA4330 AND STGR18 NEAREST FASTENRS =0.71" (94663602) | Workorder | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 04.Sep.2026 22:00 | 0 | 14.Nov.2025 04:06 | 1900-10-16 07:57 |  | 0.20833 | Idle | 0 | T: 0; O: 0; C: 0 | 05 | WO transferred Engineering Appr | [] |  |  |  |  | 94663602 / REF WO 94663595 BIRD STRIKE INITAL EVALUATION FOR DENT FOUND AFTER BIRD STRIKE UNDER CAPTAIN WINDSHIELD AS FOLLOW DIM L=3" AND W=3" DEP =0.04 FR3 FWD OF STA4330 AND STGR18 NEAREST FASTENRS =0.71" (94663602) |  | 0 / 1 | [] |  |  | WO.94663602 | 32'560 | 3'374 | 2027-12-12 | C
| 563 | 94667477 | RH HORZ STAB O/B REF TO WO. 94667476 COND INSP C/W FOUND RH HORZ STABLZ OUT BORD FARING WITH DENT. DIM= L=2.6" IN W=1.5" IN D=0.13" IN NE=4" IN NF=3.4" IN A=4.2" IN | 94667477 / RH HORZ STAB O/B REF TO WO. 94667476 COND INSP C/W FOUND RH HORZ STABLZ OUT BORD FARING WITH DENT. DIM= L=2.6" IN W=1.5" IN D=0.13" IN NE=4" IN NF=3.4" IN A=4.2" IN (94667477) | Workorder | 3 | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Partly dropped" src="amos-resource://Icons/part_partly_dropped.png" border="0" /></div></td></tr></table></html> | 1900-01-02 19:22 | 04.Sep.2026 22:00 | 1900-01-02 19:22 | 02.Dec.2025 07:31 | 1900-09-28 04:32 |  | 1900-01-03 07:22 | Idle | 0 | T: 0; O: 0; C: 0 | 27 | WO transferred Engineering Appr | [] |  |  |  |  | 94667477 / RH HORZ STAB O/B REF TO WO. 94667476 COND INSP C/W FOUND RH HORZ STABLZ OUT BORD FARING WITH DENT. DIM= L=2.6" IN W=1.5" IN D=0.13" IN NE=4" IN NF=3.4" IN A=4.2" IN (94667477) |  | 0 / 6 | [] |  |  | WO.94667477 | 32'191 | 3'005 | 2027-10-22 | C
| 564 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (33019434) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.375 | 04.Sep.2026 22:00 | 0.375 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (33019434) |  | 0 / 9 | [] |  |  | JCA.33019434 |  |  | 1517606
| 565 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (33019436) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE |  |  |  | STJC-20-00-00-03-GA-GO / TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE (33019436) |  | 0 / 1 | [] |  |  | JCA.33019436 |  |  | 1517606
| 566 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (33019435) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P |  |  |  | STJC-20-00-00-04-GA-SV / AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT (33019435) |  | 0 / 2 | [] |  |  | JCA.33019435 |  |  | 1517606
| 567 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (33019433) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.20833 | 04.Sep.2026 22:00 | 0.20833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | ACFT RELEASE, ACFT RELEASE, -- |  |  |  | STJC-20-00-00-05-GA-SV / AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK (33019433) |  | 0 / 3 | [] |  |  | JCA.33019433 |  |  | 1517606
| 568 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (33019440) | Jobcard | N | <html><table><tr><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #C1F47A;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFF7B;color: #000000;"><span style="font-size: 8px;">1</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FAB30A;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #F4867F;color: #000000;"><span style="font-size: 8px;">7</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #EAEAEA;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;background: #FFFFFF;color: #000000;"><span style="font-size: 8px;">0</span></div></td><td style="padding: 0px 0px 0px 0px;"><div style="border-style: solid;margin: 0px 0px 0px 0px;width: 15px;height: 8px;text-align: center;border-width: 1px;border-color: #000000;"><img alt="Issued" src="amos-resource://Icons/empty.gif" border="0" /></div></td></tr></table></html> | 0.54167 | 04.Sep.2026 22:00 | 0.37847 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (33019440) |  | 0 / 20 | [] |  |  | JCA.33019440 |  |  | 1517606
| 569 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (33019439) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.91667 | 04.Sep.2026 22:00 | 0.46528 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | STJC-20-00-00-07-A32S-SV / HEAVEY CHECK DE-HANGARING PREPARATION (33019439) |  | 0 / 18 | [] |  |  | JCA.33019439 |  |  | 1517606
| 570 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (33019441) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P |  |  |  | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (33019441) |  | 0 / 1 | [] |  |  | JCA.33019441 |  |  | 1517606
| 571 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (33019438) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 04.Sep.2026 22:00 | 0.125 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-01-GA-GO / AIRCRAFT FINAL INSPECTION (33019438) |  | 0 / 3 | [] |  |  | JCA.33019438 |  |  | 1517606
| 572 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (33019460) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-02-GA-GO / COCKPIT AND PAX CABIN FINAL INSPECTION (33019460) |  | 0 / 1 | [] |  |  | JCA.33019460 |  |  | 1517606
| 573 | STJC-AREAS-FINAL-INSPECTION-03-GA-GO | AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (33019461) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-03-GA-GO / AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION (33019461) |  | 0 / 1 | [] |  |  | JCA.33019461 |  |  | 1517606
| 574 | STJC-AREAS-FINAL-INSPECTION-04-GA-GO | EMPENNAGE FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (33019462) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-04-GA-GO / EMPENNAGE FINAL INSPECTION (33019462) |  | 0 / 1 | [] |  |  | JCA.33019462 |  |  | 1517606
| 575 | STJC-AREAS-FINAL-INSPECTION-05-GA-GO | AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (33019463) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-05-GA-GO / AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION (33019463) |  | 0 / 1 | [] |  |  | JCA.33019463 |  |  | 1517606
| 576 | STJC-AREAS-FINAL-INSPECTION-06-GA-GO | L/H AND R/H WINGS FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (33019480) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-06-GA-GO / L/H AND R/H WINGS FINAL INSPECTION (33019480) |  | 0 / 1 | [] |  |  | JCA.33019480 |  |  | 1517606
| 577 | STJC-AREAS-FINAL-INSPECTION-07-GA-GO | LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (33019478) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-07-GA-GO / LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) (33019478) |  | 0 / 1 | [] |  |  | JCA.33019478 |  |  | 1517606
| 578 | STJC-AREAS-FINAL-INSPECTION-08-GA-GO | ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (33019479) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 04.Sep.2026 22:00 | 0.083333 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-08-GA-GO / ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) (33019479) |  | 0 / 1 | [] |  |  | JCA.33019479 |  |  | 1517606
| 579 | STJC-AREAS-FINAL-INSPECTION-09-GA-GO | APU FINAL INSPECTION | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (33019475) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 04.Sep.2026 22:00 | 0.041667 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP |  |  |  | STJC-AREAS-FINAL-INSPECTION-09-GA-GO / APU FINAL INSPECTION (33019475) |  | 0 / 1 | [] |  |  | JCA.33019475 |  |  | 1517606
| 580 | STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (33019477) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 04.Sep.2026 22:00 | 0.020833 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-11 |  | [] | ACFT RELEASE |  |  |  | STJC-CRS-GA-SV / CERTIFICATE OF RELEASE TO SERVICE (CRS) (33019477) |  | 0 / 1 | [] |  |  | JCA.33019477 |  |  | 1517606
| 581 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (33019476) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29167 | 04.Sep.2026 22:00 | 0.29167 |  | 0 |  | 0 | Not Started | 0 | T: 0; O: 0; C: 0 | 05-00 |  | [] | FINAL INSP, FINAL INSP, FINAL INSP, FINAL INSP |  |  |  | STJC-RTS-03-A32S-SV / AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK (33019476) |  | 0 / 4 | [] |  |  | JCA.33019476 |  |  | 1517606