## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Closed By | Closed Date | Closing Status
| 2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18472 | 17.Jul.2026 22:00 | 0.10139 | 23.Jul.2026 15:22 | 0.16181 |  | 0.51042 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | OPS/LK, OPS/LK |  |  |  | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) |  | 2 / 2 | [] |  |  | MET.32712972 | 13008286 | 2026-07-26 | Performed
| 3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB (32712946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:45 | 0.12708 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712946 | 13008286 | 2026-07-23 | Performed
| 4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:47 | 0.12569 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) |  | 1 / 1 | [] |  |  | MET.32712992 | 13008286 | 2026-07-23 | Performed
| 5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB (32712973) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 21.Jul.2026 10:27 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712973 | 13003390 | 2026-07-21 | Performed
| 6 | 200121-01-1 | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 01.Aug.2026 16:31 | 0.084028 |  | 0.5 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | TC/P, TC/P |  |  |  | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING (32712986) |  | 2 / 2 | [] |  |  | MET.32712986 | 40000930 | 2026-08-02 | Performed
| 7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 24.Jul.2026 07:52 | 0.0625 |  | 0.125 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) |  | 1 / 1 | [] |  |  | MET.32712948 | 13008286 | 2026-07-26 | Performed
| 8 | 200121-04-1 | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.052778 | 17.Jul.2026 22:00 | 0.045833 | 30.Jul.2026 16:03 | 0.083333 |  | 0.16667 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP (32712952) |  | 1 / 1 | [] |  |  | MET.32712952 | 13008286 | 2026-08-02 | Performed
| 9 | 200125-01-1 | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 30.Jul.2026 06:06 | 0.25 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING (32712957) |  | 1 / 1 | [] |  |  | MET.32712957 | 40000930 | 2026-08-02 | Performed
| 10 | 200125-05-1 | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP (32712921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.4125 | 17.Jul.2026 22:00 | 0.4125 | 19.Jul.2026 07:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 3 / 6 |  | 1 / 1 | [] |  |  | MET.32712921 | 13008286 | 2026-07-20 | Performed
| 12 | 200127-02-1 | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 01.Aug.2026 16:29 | 0.083333 |  | 0.25 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | CLEAN-UP |  |  |  | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING (32712975) |  | 1 / 1 | [] |  |  | MET.32712975 | 40000930 | 2026-08-02 | Performed
| 13 | 200127-05-1 | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION (32712929) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 26.Jul.2026 17:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | TC/P |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712929 | 13008286 | 2026-07-27 | Performed
| 14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34792 | 17.Jul.2026 22:00 | 0.34792 | 22.Jul.2026 12:42 | 0.041667 |  | 0.041667 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | INSPECTION |  |  |  | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) |  | 1 / 1 | [] |  |  | MET.32712935 | 13008286 | 2026-07-23 | Performed
| 17 | 200137-01-1 | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:04 | 17.Jul.2026 22:00 | 1899-12-31 11:24 | 24.Jul.2026 19:00 | 1900-01-02 11:59 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING (32712985) |  | 3 / 3 | [] |  |  | MET.32712985 | 40000930 | 2026-07-28 | Performed
| 21 | 200161-01-1 | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 09:26 | 17.Jul.2026 22:00 | 1899-12-31 00:31 | 24.Jul.2026 17:39 | 1900-01-02 13:21 |  | 0.625 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING (25336758) |  | 3 / 3 | [] |  |  | MET.25336758 | 40000930 | 2026-07-28 | Performed
| 22 | 200191-01-1 | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING (28325963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 30.Jul.2026 08:08 | 0.16736 |  | 0.33333 | Closed | 0 | T: 16; O: 0; C: 16 | 24-92 |  | [] | PWR-OFF |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.28325963 | 40000930 | 2026-08-02 | Performed
| 23 | 200211-02-1 | 200211-02-1 (01) / COCKPIT WIRING CLEANING | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23819 | 17.Jul.2026 22:00 | 0.11875 | 02.Aug.2026 06:54 | 0.16736 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | PWR-OFF |  |  |  | 200211-02-1 (01) / COCKPIT WIRING CLEANING (25336264) |  | 1 / 1 | [] |  |  | MET.25336264 | 40000929 | 2026-08-03 | Performed
| 24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.15486 | 21.Jul.2026 12:38 | 0.92361 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) |  | 3 / 3 | [] |  |  | MET.32712990 | 13003390 | 2026-07-22 | Performed
| 27 | 200315-01-1 | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 11:11 | 0.020833 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | INSPECTION |  |  |  | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) |  | 1 / 1 | [] |  |  | MET.32712977 | 13003390 | 2026-07-20 | Performed
| 28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 15:27 | 1899-12-31 15:16 |  | 0.23958 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) |  | 3 / 3 | [] |  |  | MET.25335922 | 13009981 | 2026-07-23 | Performed
| 29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:51 | 1899-12-31 15:54 |  | 0.097222 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) |  | 3 / 3 | [] |  |  | MET.25336676 | 13009981 | 2026-07-23 | Performed
| 30 | 212100-03-1 | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 02.Aug.2026 04:34 | 0.11667 |  | 0.375 | Closed | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION (32450171) |  | 3 / 3 | [] |  |  | MET.32450171 | 13008286 | 2026-08-02 | Performed
| 31 | 212600-09-1 | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 28.Jul.2026 14:17 | 0.16736 |  | 0.33333 | Closed | 0 | T: 2; O: 0; C: 2 | 21-26 |  | [] | CLEAN-UP |  |  |  | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING (32712967) |  | 1 / 1 | [] |  |  | MET.32712967 | 13008286 | 2026-07-29 | Performed
| 33 | 25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 09.Aug.2026 07:19 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] | TC/P |  |  |  | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R (32713056) |  | 1 / 1 | [] |  |  | MET.32713056 | 13009981 | 2026-08-12 | Performed
| 37 | 256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP (32712971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 | 20.Jul.2026 08:31 | 0.11597 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 1 / 1 |  | 5 / 5 | [] |  |  | MET.32712971 | 13003390 | 2026-07-20 | Performed
| 38 | 262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:18 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) |  | 1 / 1 | [] |  |  | MET.32712927 | 13008286 | 2026-07-20 | Performed
| 39 | 272100-13-1 | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 31.Jul.2026 13:07 | 1899-12-31 19:22 |  | 0.16667 | Closed | 0 | T: 4; O: 0; C: 4 | 27 |  | [] |  |  |  |  | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL (32450169) |  | 3 / 3 | [] |  |  | MET.32450169 | 13008286 | 2026-08-02 | Performed
| 40 | 281800-02-1 | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 06:04 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 28-18 |  | [] | INSPECTION |  |  |  | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) |  | 1 / 1 | [] |  |  | MET.32712944 | 13003390 | 2026-07-20 | Performed
| 41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP (32712932) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 08:02 | 0.11458 |  | 0.1875 | Closed | 0 | T: 3; O: 0; C: 3 | 28-18 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712932 | 13003390 | 2026-07-21 | Performed
| 46 | 341300-13-1 | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST (32712926) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.03125 | 05.Aug.2026 01:06 | 0.16736 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST (32712926) |  | 3 / 3 | [] |  |  | MET.32712926 | 13008286 | 2026-08-05 | Performed
| 47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0069444 | 23.Jul.2026 13:22 | 0.27153 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) |  | 3 / 3 | [] |  |  | MET.32712942 | 13008286 | 2026-07-26 | Performed
| 48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 13:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) |  | 3 / 3 | [] |  |  | MET.32712978 | 13003390 | 2026-07-23 | Performed
| 49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 08:00 | 0.93194 |  | 0.11111 | Closed | 0 | T: 4; O: 0; C: 4 | 52-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) |  | 3 / 3 | [] |  |  | MET.32712931 | 13009981 | 2026-07-23 | Performed
| 50 | 530000-01-1 | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 25.Jul.2026 19:12 | 1900-01-07 12:19 |  | 0.40625 | Closed | 0 | T: 0; O: 0; C: 0 | 53-00 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP (32712941) |  | 3 / 3 | [] |  |  | MET.32712941 | 13003390 | 2026-08-03 | Performed
| 51 | 531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP (32712625) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 26.Jul.2026 04:38 | 1900-01-02 02:27 |  | 0.10486 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | CLEAN-UP, INSPECTION, INSPECTION |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712625 | 13003390 | 2026-07-29 | Performed
| 58 | 532137-03-1 | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION (32712609) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.066667 | 17.Jul.2026 22:00 | 0.054861 | 24.Jul.2026 05:30 | 1899-12-31 10:23 |  | 0.1875 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | JOB-SETUP, INSPECTION, CLOSE-UP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712609 | 13008286 | 2026-07-26 | Performed
| 60 | 534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS (32712709) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.03125 | 17.Jul.2026 22:00 | 0.03125 | 26.Jul.2026 04:29 | 1900-01-02 00:17 |  | 0.09375 | Closed | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712709 | 40000929 | 2026-07-30 | Performed
| 61 | 534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.23819 | 17.Jul.2026 22:00 | 0.19653 | 28.Jul.2026 05:03 | 1900-01-20 04:30 |  | 1899-12-31 16:31 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | task should be deleted per MP EMAIL ON 11-AUG-26 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP (31498197) |  | 5 / 5 | [] |  |  | MET.31498197 | 13008286 | 2026-08-20 | Performed
| 63 | 534148-01-1 | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP (31497923) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.56319 | 17.Jul.2026 22:00 | 0.47986 | 25.Jul.2026 19:00 | 1900-01-20 15:05 |  | 0.42014 | Closed | 0 | T: 45; O: 0; C: 45 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 7 / 7 |  | 5 / 5 | [] |  |  | MET.31497923 | 13008286 | 2026-08-16 | Performed
| 64 | 534159-02-1 | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 20.Jul.2026 18:52 | 1900-01-02 15:20 |  | 0.3125 | Closed | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. (32712636) |  | 3 / 3 | [] |  |  | MET.32712636 | 13008286 | 2026-07-26 | Performed
| 65 | 534171-02-1 | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 24.Jul.2026 07:05 | 0.52361 |  | 0.14653 | Closed | 0 | T: 3; O: 0; C: 3 | 53-41 |  | [] |  |  |  |  | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS (32712610) |  | 3 / 3 | [] |  |  | MET.32712610 | 13008286 | 2026-07-26 | Performed
| 67 | 534301-01-1 | 534301-01-1 (0) / REAR FUSELAGE | 534301-01-1 (0) / REAR FUSELAGE (32450153) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 06:51 | 1899-12-31 09:03 |  | 0.22986 | Closed | 0 | T: 3; O: 0; C: 3 | 53-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534301-01-1 (0) / REAR FUSELAGE (32450153) |  | 4 / 4 | [] |  |  | MET.32450153 | 13008286 | 2026-07-26 | Performed
| 69 | 551020-01-1 | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.072917 | 24.Jul.2026 06:03 | 1900-01-15 11:50 |  | 0.41319 | Closed | 0 | T: 16; O: 0; C: 16 | 55-16 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP (32712717) |  | 5 / 5 | [] |  |  | MET.32712717 | 13003081 | 2026-08-09 | Performed
| 70 | 552002-01-1 | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.072917 | 24.Jul.2026 07:00 | 1900-01-15 10:54 |  | 0.37153 | Closed | 0 | T: 16; O: 0; C: 16 | 55-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP (32712602) |  | 5 / 5 | [] |  |  | MET.32712602 | 13003081 | 2026-08-09 | Performed
| 72 | 553005-01-1 | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015972 | 23.Jul.2026 12:30 | 1900-01-16 05:25 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP (32712648) |  | 5 / 5 | [] |  |  | MET.32712648 | 13003081 | 2026-08-09 | Performed
| 73 | 553006-01-2 | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.011111 | 23.Jul.2026 13:30 | 1900-01-16 04:25 |  | 0.35417 | Closed | 0 | T: 4; O: 0; C: 4 | 55-30 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION (32712614) |  | 5 / 5 | [] |  |  | MET.32712614 | 13003081 | 2026-08-09 | Performed
| 74 | 554003-01-1 | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION (25336894) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.069444 | 03.Jul.2026 19:23 | 1900-01-29 12:51 |  | 0.47917 | Closed | 0 | T: 8; O: 0; C: 8 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION (25336894) |  | 5 / 5 | [] |  |  | MET.25336894 | 40000930 | 2026-08-04 | Performed
| 75 | 554005-01-1 | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 | 23.Jul.2026 12:30 | 1900-01-16 05:26 |  | 0.26042 | Closed | 0 | T: 2; O: 0; C: 2 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP (32712638) |  | 5 / 5 | [] |  |  | MET.32712638 | 13003081 | 2026-08-09 | Performed
| 76 | 554006-01-1 | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP (32712637) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.011111 | 23.Jul.2026 13:30 | 1900-01-16 04:26 |  | 0.32292 | Closed | 0 | T: 3; O: 0; C: 3 | 55-40 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 5 / 5 | [] |  |  | MET.32712637 | 13003081 | 2026-08-09 | Performed
| 77 | 554008-01-1 | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP (32712641) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.15625 | 17.Jul.2026 22:00 | 0.077778 | 21.Jul.2026 19:22 | 1900-01-12 19:43 |  | 1899-12-31 08:30 | Closed | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP (32712641) |  | 5 / 5 | [] |  |  | MET.32712641 | 13003390 | 2026-08-04 | Performed
| 78 | 554009-01-1 | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP (32712621) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.30208 | 17.Jul.2026 22:00 | 0.15069 | 21.Jul.2026 19:22 | 1900-01-11 16:56 |  | 1899-12-31 10:30 | Closed | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP |  |  |  | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP (32712621) |  | 5 / 5 | [] |  |  | MET.32712621 | 40000930 | 2026-08-04 | Performed
| 82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 21.Jul.2026 17:28 | 0.69722 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) |  | 3 / 3 | [] |  |  | MET.25335733 | 13009981 | 2026-07-23 | Performed
| 83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.011806 | 21.Jul.2026 17:29 | 0.67431 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) |  | 3 / 3 | [] |  |  | MET.25336621 | 13009981 | 2026-07-23 | Performed
| 86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 17:25 | 0.67847 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) |  | 4 / 4 | [] |  |  | MET.32712633 | 13009981 | 2026-07-23 | Performed
| 87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 17:27 | 0.67639 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) |  | 4 / 4 | [] |  |  | MET.32712611 | 13009981 | 2026-07-23 | Performed
| 88 | 572161-01-11-001 | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP (32450259) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 28.Jul.2026 06:11 | 1900-01-14 00:29 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | PNLS 540HB, 540JB, 540KB, 540LB,540MB, 540NB, 540PB, 540QB, 540RB, 550AB, 550CB, 550DB, 560AB OK GIVEN BY INSP 726 REF WO # 32991584 | 1 / 1 |  | 6 / 6 | [] |  |  | MET.32450259 | 13008286 | 2026-08-12 | Performed
| 89 | 572161-01-11-002 | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP (32450258) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 28.Jul.2026 06:13 | 1900-01-14 00:16 |  | 0.64583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | PNLS 640HB, 640JB, 640KB, 640LB,640MB, 640NB, 640PB, 640QB, 640RB, 650AB, 650CB, 650DB, 660AB OK GIVEN BY INSP 726 REF WO # 32991563 | 1 / 1 |  | 6 / 6 | [] |  |  | MET.32450258 | 13008286 | 2026-08-12 | Performed
| 90 | 572651-01-2-001 | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:44 | 1899-12-31 05:07 |  | 0.072917 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP (32712646) |  | 4 / 4 | [] |  |  | MET.32712646 | 13008286 | 2026-07-26 | Performed
| 91 | 572651-01-2-002 | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 13:05 | 1899-12-31 06:49 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING (32712601) |  | 4 / 4 | [] |  |  | MET.32712601 | 13008286 | 2026-07-26 | Performed
| 92 | 574206-01-1 | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:22 | 1899-12-31 20:41 |  | 0.052778 | Closed | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] |  |  |  |  | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. (32712600) |  | 3 / 3 | [] |  |  | MET.32712600 | 13003390 | 2026-07-26 | Performed
| 93 | 574306-01-1-001 | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 16:05 | 1899-12-31 16:20 |  | 0.10417 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. (28326012) |  | 3 / 3 | [] |  |  | MET.28326012 | 13003390 | 2026-07-26 | Performed
| 94 | 574306-01-1-002 | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 14:12 | 1899-12-31 19:04 |  | 0.048611 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH (28326010) |  | 3 / 3 | [] |  |  | MET.28326010 | 13003390 | 2026-07-26 | Performed
| 95 | 574406-01-1 | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:57 | 1899-12-31 21:02 |  | 0.14931 | Closed | 0 | T: 8; O: 0; C: 8 | 57-46 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. (32712904) |  | 3 / 3 | [] |  |  | MET.32712904 | 13003390 | 2026-07-26 | Performed
| 96 | 574506-01-1-001 | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 16:06 | 1899-12-31 16:18 |  | 0.14583 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. (32712655) |  | 3 / 3 | [] |  |  | MET.32712655 | 13003390 | 2026-07-26 | Performed
| 97 | 574506-01-1-002 | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 24.Jul.2026 14:09 | 1899-12-31 21:07 |  | 0.15972 | Closed | 0 | T: 6; O: 0; C: 6 | 57-46 |  | [] |  |  |  |  | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH (32713057) |  | 3 / 3 | [] |  |  | MET.32713057 | 13003390 | 2026-07-26 | Performed
| 98 | 574606-01-1 | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:44 | 1899-12-31 20:17 |  | 0.024306 | Closed | 0 | T: 4; O: 0; C: 4 | 57-46 |  | [] |  |  |  |  | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. (32712994) |  | 3 / 3 | [] |  |  | MET.32712994 | 13003390 | 2026-07-26 | Performed
| 100 | 575167-01-1-001 | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 | 24.Jul.2026 15:08 | 1900-01-25 04:04 |  | 0.58472 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP (32712654) |  | 5 / 5 | [] |  |  | MET.32712654 | 13008286 | 2026-08-20 | Performed
| 101 | 575167-01-1-002 | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.016667 | 23.Jul.2026 15:41 | 1900-01-26 03:31 |  | 0.55208 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP (32712881) |  | 5 / 5 | [] |  |  | MET.32712881 | 13008286 | 2026-08-20 | Performed
| 102 | 783210-01-1 | 783210-01-1 (0) / THRUST REVERSER STRUCTURE | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:32 | 1899-12-31 16:23 |  | 0.14583 | Closed | 0 | T: 12; O: 0; C: 12 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783210-01-1 (0) / THRUST REVERSER STRUCTURE (32450145) |  | 3 / 3 | [] |  |  | MET.32450145 | 13008286 | 2026-07-26 | Performed
| 103 | ZL-110-01-1 | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 05:57 | 0.040972 |  | 0.040972 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) |  | 1 / 1 | [] |  |  | MET.32712939 | 13003390 | 2026-07-20 | Performed
| 104 | ZL-121-02-1 | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 | 24.Jul.2026 08:23 | 0.041667 |  | 0.083333 | Closed | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP (32712623) |  | 1 / 1 | [] |  |  | MET.32712623 | 13008286 | 2026-07-26 | Performed
| 106 | ZL-127-02-2 | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP (32712599) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070139 | 17.Jul.2026 22:00 | 0.070139 | 25.Jul.2026 13:15 | 1900-01-02 20:47 |  | 0.22917 | Closed | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | INSPECTION |  |  |  | 2 / 3 |  | 1 / 1 | [] |  |  | MET.32712599 | 13003390 | 2026-07-29 | Performed
| 107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION (28325941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:18 | 17.Jul.2026 22:00 | 1899-12-31 14:18 | 21.Jul.2026 08:01 | 0.50694 |  | 0.16667 | Closed | 0 | T: 12; O: 0; C: 12 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.28325941 | 13008286 | 2026-07-22 | Performed
| 109 | ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION (32712626) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.47917 | 17.Jul.2026 22:00 | 0.45833 | 27.Jul.2026 05:02 | 1900-01-20 13:33 |  | 1900-01-15 05:45 | Closed | 0 | T: 16; O: 0; C: 16 | 05-21 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 4 |  | 6 / 6 | [] |  |  | MET.32712626 | 13003390 | 2026-08-17 | Performed
| 110 | ZL-147-03-1 | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP (32712657) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:27 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | INSPECTION |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712657 | 13003390 | 2026-07-20 | Performed
| 113 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.30069 | 17.Jul.2026 22:00 | 0.30069 | 24.Jul.2026 15:32 | 0.16875 |  | 0.084028 | Closed | 0 | T: 10; O: 0; C: 10 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT (28325926) |  | 4 / 4 | [] |  |  | MET.28325926 | 13008286 | 2026-07-26 | Performed
| 115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP (28325987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 05:00 | 17.Jul.2026 22:00 | 1900-01-02 05:00 | 21.Jul.2026 13:54 | 1899-12-31 23:41 |  | 0.10417 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.28325987 | 13003390 | 2026-07-23 | Performed
| 116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 18:22 | 0.077778 |  | 0.10417 | Closed | 0 | T: 23; O: 0; C: 23 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) |  | 1 / 1 | [] |  |  | MET.28325991 | 13008286 | 2026-07-22 | Performed
| 118 | ZL-195-01-1 | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP (32712964) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 07:54 | 0.027778 |  | 0.027778 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 6 / 8 |  | 1 / 1 | [] |  |  | MET.32712964 | 13003390 | 2026-07-20 | Performed
| 119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION (25336636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 21.Jul.2026 08:02 | 0.11736 |  | 0.22917 | Closed | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336636 | 13003390 | 2026-07-21 | Performed
| 120 | ZL-200-02-1 | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI (32712963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.76944 | 17.Jul.2026 22:00 | 0.76944 | 18.Jul.2026 15:30 | 0.10139 |  | 0.097222 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 8 / 9 |  | 1 / 1 | [] |  |  | MET.32712963 | 13008286 | 2026-07-20 | Performed
| 121 | ZL-200-04-1 | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE (32450172) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.525 | 17.Jul.2026 22:00 | 0.525 | 25.Jul.2026 13:10 | 0.27083 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32450172 | 40000930 | 2026-07-28 | Performed
| 122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 05:08 | 1899-12-31 06:23 |  | 0.875 | Closed | 0 | T: 15; O: 0; C: 15 | 05-22 |  | [] | INSPECTION |  |  |  | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) |  | 1 / 1 | [] |  |  | MET.32712928 | 13003390 | 2026-07-23 | Performed
| 123 | ZL-311-01-1 | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP (32712943) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:41 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | PRE INSP |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712943 | 13003390 | 2026-07-20 | Performed
| 124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP (32712980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:43 | 0.37639 |  | 0.625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712980 | 13008286 | 2026-07-21 | Performed
| 125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP (32712954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 12:42 | 0.29375 |  | 0.32639 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712954 | 13008286 | 2026-07-21 | Performed
| 126 | ZL-325-01-1 | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP (32712961) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 16:23 | 1900-01-03 23:20 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 05-23 |  | [] | PRE INSP |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712961 | 13008286 | 2026-07-27 | Performed
| 127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION (32712645) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 18:07 | 0.068056 |  | 0.076389 | Closed | 0 | T: 24; O: 0; C: 24 | 05-23 |  | [] | PRE INSP |  |  |  | 7 / 7 |  | 1 / 1 | [] |  |  | MET.32712645 | 13008286 | 2026-07-21 | Performed
| 128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 15:39 | 0.17153 |  | 0.34722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) |  | 1 / 1 | [] |  |  | MET.28325802 | 13008286 | 2026-07-21 | Performed
| 129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 19:25 | 0.024306 |  | 0.034722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) |  | 1 / 1 | [] |  |  | MET.28325897 | 13008286 | 2026-07-21 | Performed
| 130 | ZL-433-01-1-001 | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP (32712604) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 06:37 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712604 | 13008286 | 2026-07-20 | Performed
| 131 | ZL-433-01-1-002 | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP (32712607) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 09:54 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712607 | 13008286 | 2026-07-20 | Performed
| 132 | ZL-500-03-1-001 | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP (32712936) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 15:50 | 0.095833 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 9 / 12 |  | 1 / 1 | [] |  |  | MET.32712936 | 13008286 | 2026-07-20 | Performed
| 133 | ZL-500-03-1-002 | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 16:10 | 0.082639 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) |  | 1 / 1 | [] |  |  | MET.32712966 | 13008286 | 2026-07-20 | Performed
| 134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 08:06 | 0.035417 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) |  | 1 / 1 | [] |  |  | MET.32712947 | 13003390 | 2026-07-21 | Performed
| 135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP (32712934) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:21 | 1900-01-01 09:48 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712934 | 13008286 | 2026-07-23 | Performed
| 136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP (28325993) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:20 | 1899-12-31 01:32 |  | 0.15625 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 4 |  | 1 / 1 | [] |  |  | MET.28325993 | 13003390 | 2026-07-21 | Performed
| 137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 07:59 | 0.12014 |  | 0.125 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) |  | 1 / 1 | [] |  |  | MET.28325992 | 13003390 | 2026-07-21 | Performed
| 138 | ZL-531-02-1-001 | ZL-531-02-1-001 (02) / L/H FLAP TRACK NO 2 AND FAIRING INSP | ZL-531-02-1-001 (02) / L/H FLAP TRACK NO 2 AND FAIRING INSP (25335895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:28 | 1900-01-01 08:16 |  | 0.083333 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.25335895 | 13008286 | 2026-07-23 | Performed
| 139 | ZL-531-02-1-002 | ZL-531-02-1-002 (02) / R/H FLAP TRACK NO 2 AND FAIRING | ZL-531-02-1-002 (02) / R/H FLAP TRACK NO 2 AND FAIRING (25336980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 2 / 6 |  | 1 / 1 | [] |  |  | MET.25336980 | 13008286 | 2026-07-23 | Performed
| 140 | ZL-532-01-1-001 | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 10:06 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) |  | 1 / 1 | [] |  |  | MET.32712924 | 13003390 | 2026-07-20 | Performed
| 141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP (32712979) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712979 | 13008286 | 2026-07-23 | Performed
| 142 | ZL-532-02-1-001 | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING (25336005) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 10:05 | 0.041667 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336005 | 13003390 | 2026-07-20 | Performed
| 143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 11:29 | 1900-01-01 08:17 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) |  | 1 / 1 | [] |  |  | MET.25336989 | 13008286 | 2026-07-23 | Performed
| 144 | ZL-533-01-1-001 | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP (32712922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 08:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712922 | 13008286 | 2026-07-20 | Performed
| 145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP (32712970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:30 | 1900-01-01 08:15 |  | 0.0625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712970 | 13008286 | 2026-07-23 | Performed
| 146 | ZL-571-02-1-001 | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP (32712933) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:22 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 4 / 5 |  | 1 / 1 | [] |  |  | MET.32712933 | 13008286 | 2026-07-20 | Performed
| 147 | ZL-571-02-1-002 | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP (32712988) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 4 |  | 1 / 1 | [] |  |  | MET.32712988 | 13008286 | 2026-07-20 | Performed
| 148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 22.Jul.2026 08:38 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) |  | 1 / 1 | [] |  |  | MET.32712940 | 13003390 | 2026-07-22 | Performed
| 149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP (32712969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 20.Jul.2026 09:20 | 1900-01-01 10:23 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712969 | 13008286 | 2026-07-23 | Performed
| 150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 15:21 | 0.66806 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) |  | 2 / 2 | [] |  |  | MET.32712956 | 13009981 | 2026-07-23 | Performed
| 151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP (32712918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 14:54 | 0.68611 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | 1 / 1 |  | 2 / 2 | [] |  |  | MET.32712918 | 13009981 | 2026-07-23 | Performed
| 152 | ZL-590-01-1-001 | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:13 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) |  | 1 / 1 | [] |  |  | MET.32712955 | 13008286 | 2026-07-20 | Performed
| 153 | ZL-590-01-1-002 | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) |  | 1 / 1 | [] |  |  | MET.32712923 | 13008286 | 2026-07-20 | Performed
| 154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP (32712974) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:41 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712974 | 13008286 | 2026-07-23 | Performed
| 155 | ZL-812-01-1 | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) |  | 1 / 1 | [] |  |  | MET.32712950 | 13008286 | 2026-07-20 | Performed
| 156 | ZL-824-01-1 | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP (32712976) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712976 | 13008286 | 2026-07-20 | Performed
| 157 | ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP (32712989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.081944 | 21.Jul.2026 08:01 | 1900-01-12 11:21 |  | 0.28472 | Closed | 0 | T: 16; O: 0; C: 16 | 05-28 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32712989 | 13003390 | 2026-08-05 | Performed
| 161 | 21-SVA-01 | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 01:19 | 0.25139 |  | 0.75 | Closed | 0 | T: 2; O: 0; C: 2 | 21-61 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN (32163662) |  | 3 / 3 | [] |  |  | MET.32163662 | 40000930 | 2026-07-28 | Performed
| 162 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 08:56 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-23 |  | [] | TC/P, TC/P |  |  |  | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) |  | 2 / 2 | [] |  |  | MET.32807066 | 13008286 | 2026-07-20 | Performed
| 164 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:33 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-41 |  | [] | OPS/LK |  |  |  | 242000-01-1 (3) / GAPCU OPERATIONAL TEST (32807106) |  | 1 / 1 | [] |  |  | MET.32807106 | 13008286 | 2026-07-26 | Performed
| 166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 06:45 | 0.11597 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-28 |  | [] | OPS/LK |  |  |  | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) |  | 1 / 1 | [] |  |  | MET.32807105 | 13008286 | 2026-07-22 | Performed
| 167 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 26.Jul.2026 05:42 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-38 |  | [] | OPS/LK |  |  |  | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK (32807109) |  | 1 / 1 | [] |  |  | MET.32807109 | 40000929 | 2026-07-26 | Performed
| 179 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:19 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] | PRE INSP |  |  |  | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) |  | 1 / 1 | [] |  |  | MET.29295194 | 13008286 | 2026-07-20 | Performed
| 180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29295141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:26 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.29295141 | 40000929 | 2026-07-21 | Performed
| 181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32807056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 19.Jul.2026 06:36 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  | As per requested by CONF ENGG in T/Q CONF ENGG 805450. | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807056 | 40000929 | 2026-07-21 | Performed
| 182 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 253400-01-1. (03) / GALLEY COOLING CLEANING (32807071) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013889 | 17.Jul.2026 22:00 | 0.013889 | 04.Aug.2026 07:27 | 1900-01-01 13:33 |  | 0.875 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.32807071 | 13008286 | 2026-08-09 | Performed
| 184 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP (32807080) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 01:14 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 6 / 8 |  | 1 / 1 | [] |  |  | MET.32807080 | 13008286 | 2026-07-20 | Performed
| 185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32807093) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32807093 | 13003390 | 2026-07-22 | Performed
| 186 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 05:08 | 0.22222 |  | 0.41667 | Closed | 0 | T: 4; O: 0; C: 4 | 25-62 |  | [] | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK |  |  |  | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN (32807073) |  | 4 / 4 | [] |  |  | MET.32807073 | 13008286 | 2026-07-26 | Performed
| 187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:36 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 26-12 |  | [] | OPS/LK |  |  |  | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) |  | 1 / 1 | [] |  |  | MET.32807063 | 13008286 | 2026-07-23 | Performed
| 188 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 25.Jul.2026 11:20 | 0.041667 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION (32450147) |  | 3 / 3 | [] |  |  | MET.32450147 | 13008286 | 2026-07-26 | Performed
| 189 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 27.Jul.2026 11:03 | 0.043056 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 261700-06-1 (0) / LAVATORY SMOKE DETECTION (32450157) |  | 3 / 3 | [] |  |  | MET.32450157 | 13008286 | 2026-07-28 | Performed
| 191 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 | 14.Aug.2026 09:13 | 0.10694 |  | 0.33681 | Closed | 0 | T: 0; O: 0; C: 0 | 27-44 |  | [] | OPS/LK |  |  |  | 274000-02-1 (4) / THS ACT OPS CHK (CMR) (32807070) |  | 1 / 1 | [] |  |  | MET.32807070 | 13003390 | 2026-08-14 | Performed
| 192 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 02.Aug.2026 16:53 | 0.041667 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 12-22 |  | [] | TC/P |  |  |  | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION (32807100) |  | 1 / 1 | [] |  |  | MET.32807100 | 13008286 | 2026-08-03 | Performed
| 193 | 274451-10-1 | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.44444 | 17.Jul.2026 22:00 | 0.26389 | 10.Aug.2026 08:52 | 0.11389 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD (32807095) |  | 6 / 6 | [] |  |  | MET.32807095 | 13003081 | 2026-08-11 | Performed
| 194 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.58333 | 17.Jul.2026 22:00 | 0.33333 | 10.Aug.2026 06:53 | 0.18333 |  | 0.84722 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP (32807068) |  | 6 / 6 | [] |  |  | MET.32807068 | 13008286 | 2026-08-11 | Performed
| 195 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION (32807110) |  | 2 / 2 | [] |  |  | MET.32807110 | 13008286 | 2026-08-03 | Performed
| 196 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 | 02.Aug.2026 16:58 | 0.041667 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P |  |  |  | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION (32807091) |  | 2 / 2 | [] |  |  | MET.32807091 | 40000930 | 2026-08-03 | Performed
| 197 | 278468-01-1-002 | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 02.Aug.2026 17:01 | 0.041667 |  | 0.083333 | Closed | 0 | T: 12; O: 0; C: 12 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION (32807108) |  | 3 / 3 | [] |  |  | MET.32807108 | 40000930 | 2026-08-03 | Performed
| 198 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 | 27.Jul.2026 04:24 | 0.12569 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 28-11 |  | [] | OPS/LK |  |  |  | 281100-02-1 (3) / TANKS WATER DRAIN (32807069) |  | 1 / 1 | [] |  |  | MET.32807069 | 13003390 | 2026-07-27 | Performed
| 203 | 282800-09-1 | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.014583 | 19.Jul.2026 01:45 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 28-28 |  | [] | PRE INSP |  |  |  | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) |  | 1 / 1 | [] |  |  | MET.29295144 | 13008286 | 2026-07-20 | Performed
| 204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 15:46 | 0.046528 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | TC/P |  |  |  | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) |  | 1 / 1 | [] |  |  | MET.32807081 | 13008286 | 2026-07-23 | Performed
| 205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 15:46 | 0.17639 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 29-27 |  | [] | TC/P |  |  |  | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) |  | 1 / 1 | [] |  |  | MET.32807098 | 13008286 | 2026-07-23 | Performed
| 206 | 292251-02-1 | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 | 15.Aug.2026 14:28 | 1899-12-31 04:14 |  | 1899-12-31 16:30 | Closed | 0 | T: 2; O: 0; C: 2 | 29-22 |  | [] | TC/P |  |  |  | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP (32807096) |  | 1 / 1 | [] |  |  | MET.32807096 | 13008286 | 2026-08-17 | Performed
| 207 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29295088) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 03.Aug.2026 02:32 | 0.25417 |  | 0.875 | Closed | 0 | T: 0; O: 0; C: 0 | 31-63 |  | [] | CLEAN-UP |  |  |  | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. (29295088) |  | 1 / 1 | [] |  |  | MET.29295088 | 40000930 | 2026-08-04 | Performed
| 208 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 08:00 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-30 |  | [] | PRE HGR |  |  |  | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK (32807112) |  | 1 / 1 | [] |  |  | MET.32807112 | 13008286 | 2026-07-26 | Performed
| 209 | 313300-08-1 | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION (32807067) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 05.Aug.2026 06:17 | 0.12569 |  | 0.45833 | Closed | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION (32807067) |  | 3 / 3 | [] |  |  | MET.32807067 | 13003390 | 2026-08-05 | Performed
| 210 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 18.Jul.2026 21:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) |  | 1 / 1 | [] |  |  | MET.32807092 | 13008286 | 2026-07-20 | Performed
| 211 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 01:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807075 | 13008286 | 2026-07-20 | Performed
| 212 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807099) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 00:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32807099 | 13008286 | 2026-07-20 | Performed
| 213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 23.Jul.2026 04:34 | 0.084028 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 32-44 |  | [] | TC/P |  |  |  | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) |  | 1 / 1 | [] |  |  | MET.32807113 | 13009981 | 2026-07-23 | Performed
| 214 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.020833 | 29.Jul.2026 03:26 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-42 |  | [] | CLEAN-UP |  |  |  | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING (32796720) |  | 1 / 1 | [] |  |  | MET.32796720 | 13008286 | 2026-07-29 | Performed
| 215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 05:00 | 0.21528 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) |  | 3 / 3 | [] |  |  | MET.32796726 | 13003390 | 2026-07-21 | Performed
| 216 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 353000-05-1 (5) / CABIN PBE INSP (32796732) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:54 | 0.15764 |  | 0.11458 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 353000-05-1 (5) / CABIN PBE INSP (32796732) |  | 3 / 3 | [] |  |  | MET.32796732 | 13003390 | 2026-07-19 | Performed
| 217 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 | 21.Jul.2026 15:58 | 1900-01-05 00:07 |  | 0.86458 | Closed | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION (29294877) |  | 7 / 7 | [] |  |  | MET.29294877 | 13003390 | 2026-08-20 | Performed
| 218 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29861 | 17.Jul.2026 22:00 | 0.20139 | 21.Jul.2026 14:09 | 1900-01-05 01:56 |  | 0.46181 | Closed | 0 | T: 0; O: 0; C: 0 | 36-11 |  | [] | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP |  |  |  | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION (29295132) |  | 7 / 7 | [] |  |  | MET.29295132 | 13003390 | 2026-08-20 | Performed
| 220 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.076389 | 27.Jul.2026 01:43 | 0.38472 |  | 1899-12-31 03:00 | Closed | 0 | T: 2; O: 0; C: 2 | 20-00 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING (31784910) |  | 3 / 3 | [] |  |  | MET.31784910 | 13003390 | 2026-07-27 | Performed
| 221 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.069444 | 17.Jul.2026 22:00 | 0.069444 | 10.Aug.2026 11:16 | 0.30417 |  | 1899-12-31 11:00 | Closed | 0 | T: 0; O: 0; C: 0 | 52-71-00 |  | [] | JOB-SETUP, --, --, -- |  |  |  | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING (29295087) |  | 4 / 4 | [] |  |  | MET.29295087 | 13008286 | 2026-08-11 | Performed
| 223 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM (32807074) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 | 20.Jul.2026 08:00 | 1899-12-31 03:00 |  | 0.32292 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32807074 | 40000929 | 2026-08-06 | Performed
| 224 | 527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 29.Jul.2026 03:28 | 1900-01-11 11:04 |  | 0.25 | Closed | 0 | T: 5; O: 0; C: 5 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT (32807101) |  | 5 / 5 | [] |  |  | MET.32807101 | 13003081 | 2026-08-11 | Performed
| 227 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION (29295131) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 03:30 | 1900-01-04 14:06 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 9 / 9 |  | 4 / 4 | [] |  |  | MET.29295131 | 40000010 | 2026-07-26 | Performed
| 230 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT (29295107) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 | 18.Aug.2026 04:28 | 0.29167 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 12-13 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  | As per Mail sent by P/P ENGG Mohammed said m Basaif step 3 has been added to T/c as Followng MPD TASK 801110-C3-1 Reference to TASKs 801110-C3-1-001 and 801110-C3-1-002, the Work Template Rev. 4 is not active. However, before activating this revision, amend the following steps: Step 1: No change (keep as is) Step 2: (amend as follow) Take pictures of the drained oil in the measuring glass Carefully examine: The oil removed from the starter for metal particles The magnetic plug for metal particles Take clear pictures of the magnetic plug Record the maximum size of the particles and decide the serviceability of the Starter per AMM 80-11-10-210-001-C Note: Fine metal particles show normal wear. Large pieces of metal show internal damage. Record the drained oil quantity and action as per AMM (if the quantity is less than 0.5 liter, replace the starter). Before replenishment flush the starter with a minimum of 0.5 quart of new oil. Take pictures of the starter when overflow plug is removed during replenishment Record the added oil quantity Issue work order to: Attach the picture of the drained oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of the added oil in a measurable bottle/glass (make sure to show the scale clearly) Attach the picture of overflow Attach the picture of the magnetic plug Indicate the maximum size of the particles if they exist on the magnetic plug Indicate the record of drained and added oil quantity | 1 / 1 |  | 3 / 3 | [] |  |  | MET.29295107 | 13003081 | 2026-08-18 | Performed
| 232 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP (29295096) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.23611 | 17.Jul.2026 22:00 | 0.097222 | 29.Jul.2026 12:57 | 1900-01-10 21:32 |  | 0.94097 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 1 / 1 |  | 2 / 2 | [] |  |  | MET.29295096 | 13008286 | 2026-08-11 | Performed
| 236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32712874) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 17:47 | 0.72222 |  | 0.625 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | INSPECTION |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.32712874 | 13003390 | 2026-07-21 | Performed
| 237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:59 | 0.67431 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28390064 | 13003390 | 2026-07-22 | Performed
| 238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.0375 | 21.Jul.2026 13:41 | 0.21736 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 3 / 3 | [] |  |  | MET.28349854 | 13003390 | 2026-07-21 | Performed
| 239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:57 | 1899-12-31 16:08 |  | 0.125 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) |  | 3 / 3 | [] |  |  | MET.32712959 | 13009981 | 2026-07-23 | Performed
| 240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022222 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 13:45 | 1899-12-31 17:12 |  | 0.14583 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) |  | 3 / 3 | [] |  |  | MET.32712991 | 13009981 | 2026-07-23 | Performed
| 241 | 212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 13:51 | 0.23819 |  | 0.0625 | Closed | 0 | T: 2; O: 0; C: 2 | 21-21 |  | [] | TC/P |  |  |  | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING (32712900) |  | 1 / 1 | [] |  |  | MET.32712900 | 13008286 | 2026-07-26 | Performed
| 242 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 08:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC (32712724) |  | 1 / 1 | [] |  |  | MET.32712724 | 13008286 | 2026-07-26 | Performed
| 243 | 212600-04-1 | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 16:04 | 0.042361 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC (32712870) |  | 3 / 3 | [] |  |  | MET.32712870 | 13008286 | 2026-07-26 | Performed
| 244 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 25.Jul.2026 19:03 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 1; O: 0; C: 1 | 21-26 |  | [] | OPS/LK |  |  |  | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK (32712746) |  | 1 / 1 | [] |  |  | MET.32712746 | 13008286 | 2026-07-26 | Performed
| 245 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 15.Aug.2026 15:15 | 0.090278 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712899) |  | 1 / 1 | [] |  |  | MET.32712899 | 13008286 | 2026-08-16 | Performed
| 247 | 213100-03-1 | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 17:28 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-31 |  | [] | OPS/LK |  |  |  | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC (32712856) |  | 1 / 1 | [] |  |  | MET.32712856 | 13008286 | 2026-07-26 | Performed
| 249 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 20.Jul.2026 02:40 | 0.36736 |  | 1899-12-31 16:00 | Closed | 0 | T: 0; O: 0; C: 0 | 21-61 |  | [] | PRE HGR |  |  |  | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) |  | 1 / 1 | [] |  |  | MET.32712787 | 13003390 | 2026-07-20 | Performed
| 250 | 215000-08-1 | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 31.Jul.2026 12:02 | 1899-12-31 21:03 |  | 0.125 | Closed | 0 | T: 5; O: 0; C: 5 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450151) |  | 3 / 3 | [] |  |  | MET.32450151 | 13003390 | 2026-08-02 | Performed
| 251 | 215000-09-1 | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL (32450144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 23.Jul.2026 13:46 | 0.25069 |  | 0.13542 | Closed | 0 | T: 1; O: 0; C: 1 | 21 |  | [] | --, INSPECTION, -- |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32450144 | 13008286 | 2026-07-26 | Performed
| 252 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP (32712721) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14653 | 17.Jul.2026 22:00 | 0.12222 | 29.Jul.2026 05:20 | 1900-01-15 02:15 |  | 1899-12-31 00:30 | Closed | 0 | T: 2; O: 0; C: 2 | 21-52 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 5 / 5 | [] |  |  | MET.32712721 | 13003390 | 2026-08-14 | Performed
| 253 | 215500-01-1 | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 14.Aug.2026 05:49 | 0.20278 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC (32712847) |  | 3 / 3 | [] |  |  | MET.32712847 | 13003390 | 2026-08-14 | Performed
| 254 | 215500-02-1 | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 14.Aug.2026 05:50 | 0.20278 |  | 0.29167 | Closed | 0 | T: 1; O: 0; C: 1 | 21-55 |  | [] | OPS/LK |  |  |  | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC (32712902) |  | 1 / 1 | [] |  |  | MET.32712902 | 13003390 | 2026-08-14 | Performed
| 255 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 | 31.Jul.2026 17:21 | 1900-01-12 17:19 |  | 0.79167 | Closed | 0 | T: 1; O: 0; C: 1 | 21-63 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK |  |  |  | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP (32712714) |  | 5 / 5 | [] |  |  | MET.32712714 | 13003390 | 2026-08-14 | Performed
| 256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 08:44 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 22-10 |  | [] | OPS/LK |  |  |  | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) |  | 1 / 1 | [] |  |  | MET.32712839 | 40000929 | 2026-07-23 | Performed
| 257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 22:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 23-73 |  | [] | OPS/LK |  |  |  | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) |  | 1 / 1 | [] |  |  | MET.19873618 | 13008286 | 2026-07-22 | Performed
| 258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 22:08 | 0.086111 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 23-33 |  | [] | OPS/LK |  |  |  | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) |  | 1 / 1 | [] |  |  | MET.32712733 | 13008286 | 2026-07-22 | Performed
| 259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:14 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 23-51 |  | [] | OPS/LK, OPS/LK |  |  |  | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) |  | 2 / 2 | [] |  |  | MET.25336141 | 13008286 | 2026-07-23 | Performed
| 260 | 237100-02-1 | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 24.Jul.2026 08:02 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 23-71 |  | [] | OPS/LK |  |  |  | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC (25336248) |  | 1 / 1 | [] |  |  | MET.25336248 | 13008286 | 2026-07-26 | Performed
| 261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.011806 | 23.Jul.2026 13:29 | 0.1 |  | 0.375 | Closed | 0 | T: 1; O: 0; C: 1 | 23-71 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) |  | 3 / 3 | [] |  |  | MET.32712774 | 13003390 | 2026-07-23 | Performed
| 262 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 14:57 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-22 |  | [] | OPS/LK |  |  |  | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC (32712665) |  | 1 / 1 | [] |  |  | MET.32712665 | 13008286 | 2026-07-26 | Performed
| 263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:38 | 0.083333 |  | 0.16667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) |  | 1 / 1 | [] |  |  | MET.32712832 | 13008286 | 2026-07-23 | Performed
| 264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:36 | 0.083333 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 24-25 |  | [] | OPS/LK |  |  |  | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) |  | 1 / 1 | [] |  |  | MET.32712691 | 13008286 | 2026-07-23 | Performed
| 265 | 242600-02-1 | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 08:01 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-26 |  | [] | OPS/LK |  |  |  | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC (32712676) |  | 1 / 1 | [] |  |  | MET.32712676 | 13008286 | 2026-07-26 | Performed
| 266 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 243000-13-1 (01) / DC GENERATION (32712892) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.044444 | 28.Jul.2026 17:20 | 0.043056 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-13-1 (01) / DC GENERATION (32712892) |  | 3 / 3 | [] |  |  | MET.32712892 | 13008286 | 2026-07-29 | Performed
| 267 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 243000-14-1 (01) / DC GENERATION (32712858) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0020833 | 17.Jul.2026 22:00 | 0.043056 | 28.Jul.2026 17:24 | 0.043056 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24-30 |  | [] | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP |  |  |  | 243000-14-1 (01) / DC GENERATION (32712858) |  | 3 / 3 | [] |  |  | MET.32712858 | 13008286 | 2026-07-29 | Performed
| 268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 09:39 | 0.042361 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 24-32 |  | [] | OPS/LK |  |  |  | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) |  | 1 / 1 | [] |  |  | MET.32712840 | 13008286 | 2026-07-23 | Performed
| 269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 24-34 |  | [] | OPS/LK |  |  |  | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) |  | 1 / 1 | [] |  |  | MET.32712850 | 13008286 | 2026-07-23 | Performed
| 270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 08:31 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) |  | 1 / 1 | [] |  |  | MET.32712666 | 13008286 | 2026-07-23 | Performed
| 271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 07:51 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) |  | 1 / 1 | [] |  |  | MET.32712707 | 13008286 | 2026-07-23 | Performed
| 272 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 09.Aug.2026 08:23 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-11 |  | [] |  |  |  |  | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT (28325858) |  | 2 / 2 | [] |  |  | MET.28325858 | 13009981 | 2026-08-12 | Performed
| 277 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 19.Aug.2026 03:00 | 0.27083 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-28 |  | [] | TC/P |  |  |  | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT (28325803) |  | 1 / 1 | [] |  |  | MET.28325803 | 13003390 | 2026-08-20 | Performed
| 293 | 252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00069444 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:56 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | PRE INSP |  |  |  | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) |  | 1 / 1 | [] |  |  | MET.32712731 | 13008286 | 2026-07-20 | Performed
| 294 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 19.Jul.2026 06:58 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | PRE INSP |  |  |  | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) |  | 1 / 1 | [] |  |  | MET.32712700 | 13008286 | 2026-07-20 | Performed
| 295 | 255000-08-1 | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:30 | 17.Jul.2026 22:00 | 0.80208 | 29.Jul.2026 15:35 | 1899-12-31 03:53 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | INSPECTION |  |  |  | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP (25336966) |  | 1 / 1 | [] |  |  | MET.25336966 | 40000010 | 2026-07-30 | Performed
| 297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 07:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | OPS/LK |  |  |  | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) |  | 1 / 1 | [] |  |  | MET.31498183 | 13003390 | 2026-07-22 | Performed
| 298 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.052083 | 17.Jul.2026 22:00 | 0.048611 | 23.Jul.2026 20:53 | 1900-01-15 09:16 |  | 0.64583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION (31498136) |  | 4 / 4 | [] |  |  | MET.31498136 | 13009981 | 2026-08-09 | Performed
| 300 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 29.Jul.2026 03:33 | 1900-01-10 02:36 |  | 0.66667 | Closed | 0 | T: 1; O: 0; C: 1 | 26-15 |  | [] | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP |  |  |  | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES (32712819) |  | 5 / 5 | [] |  |  | MET.32712819 | 13009981 | 2026-08-09 | Performed
| 301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:46 | 0.12222 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) |  | 1 / 1 | [] |  |  | MET.32712831 | 13008286 | 2026-07-23 | Performed
| 302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:48 | 0.12153 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) |  | 1 / 1 | [] |  |  | MET.32712838 | 13008286 | 2026-07-23 | Performed
| 303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:11 | 0.079861 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) |  | 3 / 3 | [] |  |  | MET.32712878 | 13003390 | 2026-07-21 | Performed
| 304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:14 | 0.077083 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) |  | 3 / 3 | [] |  |  | MET.32712803 | 13003390 | 2026-07-21 | Performed
| 306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.020139 | 21.Jul.2026 15:51 | 0.090972 |  | 0.35417 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) |  | 4 / 4 | [] |  |  | MET.32712698 | 13003390 | 2026-07-21 | Performed
| 307 | 262200-04-1 | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:52 | 0.034722 |  | 0.034722 | Closed | 0 | T: 2; O: 0; C: 2 | 26-22 |  | [] | INSPECTION |  |  |  | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) |  | 1 / 1 | [] |  |  | MET.32712842 | 13003390 | 2026-07-20 | Performed
| 308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 13:39 | 0.088889 |  | 0.27083 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) |  | 3 / 3 | [] |  |  | MET.32712744 | 13008286 | 2026-07-23 | Performed
| 309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 19.Jul.2026 04:46 | 0.2 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) |  | 1 / 1 | [] |  |  | MET.32712716 | 13008286 | 2026-07-22 | Performed
| 310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.036806 | 21.Jul.2026 14:33 | 0.14306 |  | 0.45833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) |  | 4 / 4 | [] |  |  | MET.32712799 | 13003390 | 2026-07-21 | Performed
| 311 | 262300-03-1 | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.070833 | 15.Aug.2026 15:06 | 1900-01-02 17:59 |  | 1900-01-02 04:10 | Closed | 0 | T: 3; O: 0; C: 3 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK (32712670) |  | 4 / 4 | [] |  |  | MET.32712670 | 13008286 | 2026-08-19 | Performed
| 312 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 06:59 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) |  | 1 / 1 | [] |  |  | MET.32712705 | 13008286 | 2026-07-20 | Performed
| 313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 16:40 | 0.063194 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 27-14 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) |  | 3 / 3 | [] |  |  | MET.32712730 | 13003390 | 2026-07-23 | Performed
| 314 | 271400-02-2-001 | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 02:46 | 1900-01-04 19:44 |  | 0.54861 | Closed | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK (32712702) |  | 4 / 4 | [] |  |  | MET.32712702 | 13008286 | 2026-07-26 | Performed
| 315 | 271400-02-2-002 | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.14722 | 20.Jul.2026 05:20 | 1900-01-04 17:20 |  | 0.31944 | Closed | 0 | T: 4; O: 0; C: 4 | 27-14 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK (32712756) |  | 4 / 4 | [] |  |  | MET.32712756 | 40000930 | 2026-07-26 | Performed
| 320 | 272100-05-1 | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 18.Jul.2026 12:58 | 1900-01-30 20:13 |  | 1899-12-31 12:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD (31497921) |  | 3 / 3 | [] |  |  | MET.31497921 | 13008286 | 2026-08-19 | Performed
| 321 | 272100-07-1 | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE (31498738) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 13:17 | 1900-01-05 04:25 |  | 1899-12-31 13:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.31498738 | 13008286 | 2026-07-27 | Performed
| 322 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 10.Aug.2026 05:36 | 1900-01-02 04:24 |  | 0.79167 | Closed | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | JOB-SETUP, --, -- |  |  |  | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). (26290694) |  | 3 / 3 | [] |  |  | MET.26290694 | 13003081 | 2026-08-13 | Performed
| 323 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.013889 | 14.Aug.2026 09:11 | 0.11111 |  | 0.21181 | Closed | 0 | T: 6; O: 0; C: 6 | 27-21 |  | [] | TC/P |  |  |  | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK (26224974) |  | 1 / 1 | [] |  |  | MET.26224974 | 13003390 | 2026-08-14 | Performed
| 324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28325998) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.05 | 21.Jul.2026 04:00 | 0.30833 |  | 1899-12-31 16:35 | Closed | 0 | T: 4; O: 0; C: 4 | 27-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 1 / 1 |  | 8 / 8 | [] |  |  | MET.28325998 | 13003390 | 2026-07-21 | Performed
| 325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:10 | 0.38472 |  | 1899-12-31 12:45 | Closed | 0 | T: 9; O: 0; C: 9 | 27-34 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) |  | 4 / 4 | [] |  |  | MET.31481303 | 13003390 | 2026-07-21 | Performed
| 326 | 273400-03-1 | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.043056 | 17.Jul.2026 22:00 | 0.036111 | 16.Aug.2026 05:36 | 0.18542 |  | 0.76042 | Closed | 0 | T: 2; O: 0; C: 2 | 27-34 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE (32712863) |  | 3 / 3 | [] |  |  | MET.32712863 | 13003081 | 2026-08-16 | Performed
| 327 | 274000-04-1 | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 02:44 | 0.36458 |  | 0.875 | Closed | 0 | T: 1; O: 0; C: 1 | 27-96 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) |  | 3 / 3 | [] |  |  | MET.32712668 | 13003390 | 2026-07-20 | Performed
| 328 | 274000-24-1 | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 14.Aug.2026 06:59 | 0.041667 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P |  |  |  | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. (32712885) |  | 1 / 1 | [] |  |  | MET.32712885 | 13003390 | 2026-08-14 | Performed
| 329 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0027778 | 14.Aug.2026 08:16 | 0.14306 |  | 0.50347 | Closed | 0 | T: 6; O: 0; C: 6 | 27-41 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK (32712802) |  | 3 / 3 | [] |  |  | MET.32712802 | 13003390 | 2026-08-14 | Performed
| 331 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.00625 | 10.Aug.2026 09:57 | 0.85625 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | INSPECTION, INSPECTION |  |  |  | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS (32712739) |  | 2 / 2 | [] |  |  | MET.32712739 | 13003081 | 2026-08-11 | Performed
| 332 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 17.Aug.2026 12:23 | 0.2125 |  | 0.20833 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | P/N: Changed from "MIL-PRF-680.TYPEI" TO "PD680" as requestd in T/Q:584726 T/Q: 581544 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP (32712751) |  | 3 / 3 | [] |  |  | MET.32712751 | 13008286 | 2026-08-18 | Performed
| 333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 21.Jul.2026 10:23 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | PRE INSP |  |  |  | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) |  | 1 / 1 | [] |  |  | MET.32712769 | 13003390 | 2026-07-21 | Performed
| 334 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.015278 | 16.Aug.2026 11:09 | 1899-12-31 02:21 |  | 1900-01-01 08:05 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK, OPS/LK |  |  |  | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC (32712759) |  | 2 / 2 | [] |  |  | MET.32712759 | 13003390 | 2026-08-17 | Performed
| 335 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.030556 | 17.Aug.2026 16:38 | 1899-12-31 01:05 |  | 0.35417 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | TC/P, TC/P |  |  |  | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING (32712728) |  | 2 / 2 | [] |  |  | MET.32712728 | 13008286 | 2026-08-19 | Performed
| 336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.014583 | 22.Jul.2026 15:44 | 0.17986 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK |  |  |  | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) |  | 1 / 1 | [] |  |  | MET.32712861 | 13008286 | 2026-07-23 | Performed
| 337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 22.Jul.2026 11:21 | 0.16875 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) |  | 3 / 3 | [] |  |  | MET.32712713 | 13008286 | 2026-07-23 | Performed
| 338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712880) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:04 | 1899-12-31 13:47 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712880 | 13003390 | 2026-07-23 | Performed
| 339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:00 | 1899-12-31 13:50 |  | 0.61458 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) |  | 3 / 3 | [] |  |  | MET.32712843 | 13003390 | 2026-07-23 | Performed
| 340 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 14:33 | 1900-01-01 04:35 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK (32712898) |  | 3 / 3 | [] |  |  | MET.32712898 | 13008286 | 2026-07-27 | Performed
| 341 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.075 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 14:20 | 1899-12-31 18:47 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 27-54 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK (32712723) |  | 3 / 3 | [] |  |  | MET.32712723 | 13003390 | 2026-07-26 | Performed
| 342 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 | 22.Jul.2026 00:06 | 1899-12-31 13:43 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712748) |  | 4 / 4 | [] |  |  | MET.32712748 | 13008286 | 2026-07-26 | Performed
| 343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 | 22.Jul.2026 00:08 | 1899-12-31 13:43 |  | 0.44792 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) |  | 4 / 4 | [] |  |  | MET.32712877 | 13003390 | 2026-07-23 | Performed
| 344 | 275400-01-1-001 | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 | 27.Jul.2026 07:14 | 0.10833 |  | 0.375 | Closed | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP (32712660) |  | 1 / 1 | [] |  |  | MET.32712660 | 13003390 | 2026-07-27 | Performed
| 345 | 275400-01-1-002 | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.10347 | 27.Jul.2026 06:13 | 0.13889 |  | 0.54167 | Closed | 0 | T: 11; O: 0; C: 11 | 27-54 |  | [] | INSPECTION |  |  |  | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP (32712871) |  | 1 / 1 | [] |  |  | MET.32712871 | 13003390 | 2026-07-27 | Performed
| 346 | 275446-02-1-001 | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.048611 | 24.Jul.2026 14:40 | 1900-01-15 05:14 |  | 0.28819 | Closed | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537) dated 20-DEC-2023 as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change the access from 733 and 744 to be 734 and 744. | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP (25337004) |  | 5 / 5 | [] |  |  | MET.25337004 | 13008286 | 2026-08-10 | Performed
| 347 | 275446-02-1-002 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.048611 | 23.Jul.2026 15:39 | 1900-01-16 04:15 |  | 0.46875 | Closed | 0 | T: 1; O: 0; C: 1 | 27-54 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  | Dear Concened, As per Airbus reply (Dossier Reference: 81329537 dated 20-DEC-2023)as following: ("We would like to inform you that your request has been analyzed. To do the AMM-Task 27-54-46-200-001-A (Detailed Inspection of Tracks, Rollers and Spherical Bearings (as far as visible)) it is necessary to open and safety the main landing gear doors LH and RH to have access to the LH and RH flap track 1 (as given in Para. `3.D. Get Access`). To have access to the other flap tracks 2,3 and 4 (on both wings) it is necessary to extend the flaps fully (as given in Para. `3.B. Aircraft Maintenance Configuration`). That is all you need to do this detailed visual inspection. In the related MPD-Task 275446-02-1 you find the access zones 733 and 734. Zone 733 is a typo because this is secondary door which is located at the upper area of the main landing gear (kindly refer to the attached AMM-Figure 06-20-00-13500-00-A). This small door 733 has no relation to the detailed visual inspection of the flap track 1. It is necessary to open the main landing doors which are given in zones 734 and 744 - so it is a clear typo in the MPD-document. This discrepancy was already found in the past and will be corrected by the MPD-department and should be corrected with the next revision of the MPD-document. We will add the (correct) zones 734 and 744 to Para. `2. Job Set-up Information` and they will be shown at `C. Work Zones and Access Panels`. The update will be published with the May`24-Revision. Please note that we will not deliver an advance copy as the update does not affect the feasibility of the task and safety of the aircraft. We trust this answer provides all the information you need. If you require any further information please do not hesitate to get back to us") Therefor, SV-MPDC will take the required action to revise W/T in order to change Panle from 733 and 734 to be 734 and 744 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP (25336868) |  | 5 / 5 | [] |  |  | MET.25336868 | 13008286 | 2026-08-10 | Performed
| 351 | 276400-02-1-001 | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25972 | 17.Jul.2026 22:00 | 0.12986 | 25.Jul.2026 08:25 | 0.57292 |  | 0.44444 | Closed | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION (32712686) |  | 7 / 7 | [] |  |  | MET.32712686 | 13008286 | 2026-07-26 | Performed
| 352 | 276400-02-1-002 | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25972 | 17.Jul.2026 22:00 | 0.14097 | 25.Jul.2026 08:36 | 0.57222 |  | 0.36111 | Closed | 0 | T: 0; O: 0; C: 0 | 27-64 |  | [] | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION (32712857) |  | 7 / 7 | [] |  |  | MET.32712857 | 13008286 | 2026-07-26 | Performed
| 354 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 15:18 | 1899-12-31 17:59 |  | 0.125 | Closed | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION (32712848) |  | 3 / 3 | [] |  |  | MET.32712848 | 13003390 | 2026-07-26 | Performed
| 355 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:00 | 1899-12-31 19:17 |  | 0.076389 | Closed | 0 | T: 17; O: 0; C: 17 | 27-84 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION (32712711) |  | 3 / 3 | [] |  |  | MET.32712711 | 13003390 | 2026-07-26 | Performed
| 359 | 278468-02-1-001 | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION (32712708) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.12431 | 24.Jul.2026 15:06 | 1900-01-15 04:56 |  | 0.125 | Closed | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 5 / 5 | [] |  |  | MET.32712708 | 13008286 | 2026-08-10 | Performed
| 360 | 278468-02-1-002 | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION (32712820) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18681 | 17.Jul.2026 22:00 | 0.12431 | 24.Jul.2026 14:07 | 1900-01-15 05:56 |  | 0.17014 | Closed | 0 | T: 12; O: 0; C: 12 | 27-84 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 5 / 5 | [] |  |  | MET.32712820 | 13008286 | 2026-08-10 | Performed
| 361 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:07 | 0.038194 |  | 0.038194 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) |  | 1 / 1 | [] |  |  | MET.32712890 | 13008286 | 2026-07-20 | Performed
| 362 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:03 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) |  | 1 / 1 | [] |  |  | MET.32712804 | 13008286 | 2026-07-20 | Performed
| 367 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP (32712865) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:15 | 0.16042 |  | 0.25 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712865 | 40000010 | 2026-07-19 | Performed
| 368 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:16 | 0.15972 |  | 0.20833 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) |  | 3 / 3 | [] |  |  | MET.32712800 | 40000010 | 2026-07-19 | Performed
| 369 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 17:07 | 0.125 |  | 0.41667 | Closed | 0 | T: 1; O: 0; C: 1 | 28-23 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) |  | 3 / 3 | [] |  |  | MET.28325816 | 40000010 | 2026-07-19 | Performed
| 370 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP (32712829) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 11:30 | 0.34236 |  | 0.10417 | Closed | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712829 | 13008286 | 2026-07-26 | Performed
| 371 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP (32712767) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 11:30 | 0.33958 |  | 0.17708 | Closed | 0 | T: 1; O: 0; C: 1 | 28-25 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712767 | 13008286 | 2026-07-26 | Performed
| 373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:58 | 0.12569 |  | 0.25 | Closed | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | OPS/LK |  |  |  | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) |  | 1 / 1 | [] |  |  | MET.28325959 | 13003390 | 2026-07-22 | Performed
| 374 | 282800-06-1 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.015278 | 30.Jul.2026 13:35 | 0.2 |  | 0.3125 | Closed | 0 | T: 2; O: 0; C: 2 | 28-28 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  | as req in T/Q: 764919 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT (25336404) |  | 4 / 4 | [] |  |  | MET.25336404 | 40000010 | 2026-07-30 | Performed
| 376 | 291000-04-1 | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 15.Aug.2026 15:18 | 0.088194 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK (32712782) |  | 1 / 1 | [] |  |  | MET.32712782 | 13008286 | 2026-08-16 | Performed
| 377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 14:03 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) |  | 1 / 1 | [] |  |  | MET.32712779 | 13003390 | 2026-07-22 | Performed
| 378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 14:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) |  | 1 / 1 | [] |  |  | MET.32712688 | 13003390 | 2026-07-22 | Performed
| 380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.06875 | 17.Jul.2026 22:00 | 0.034028 | 18.Jul.2026 14:06 | 0.084028 |  | 0.33333 | Closed | 0 | T: 3; O: 0; C: 3 | 29-23 |  | [] | OPS/LK, OPS/LK |  |  |  | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) |  | 2 / 2 | [] |  |  | MET.32712867 | 13003390 | 2026-07-22 | Performed
| 382 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 16.Aug.2026 03:31 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 29 |  | [] | OPS/LK |  |  |  | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER (32712886) |  | 1 / 1 | [] |  |  | MET.32712886 | 13008286 | 2026-08-16 | Performed
| 383 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER (32712891) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 | 10.Aug.2026 04:01 | 0.16667 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 29 |  | [] | JOB-SETUP, --, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712891 | 13008286 | 2026-08-10 | Performed
| 384 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 17.Aug.2026 00:25 | 0.33542 |  | 1899-12-31 16:00 | Closed | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK (32712656) |  | 3 / 3 | [] |  |  | MET.32712656 | 13008286 | 2026-08-17 | Performed
| 385 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 15.Aug.2026 16:26 | 0.041667 |  | 0.041667 | Closed | 0 | T: 6; O: 0; C: 6 | 29-34 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING (32712680) |  | 3 / 3 | [] |  |  | MET.32712680 | 13008286 | 2026-08-16 | Performed
| 386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 14:55 | 0.67778 |  | 0.10417 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) |  | 3 / 3 | [] |  |  | MET.26225037 | 13003390 | 2026-07-22 | Performed
| 387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (26290689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 13:17 | 0.23403 |  | 0.27083 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290689 | 13003390 | 2026-07-21 | Performed
| 388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.01875 | 23.Jul.2026 12:17 | 0.086111 |  | 0.375 | Closed | 0 | T: 2; O: 0; C: 2 | 30-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) |  | 3 / 3 | [] |  |  | MET.32712674 | 13003390 | 2026-07-23 | Performed
| 389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 23.Jul.2026 13:26 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) |  | 1 / 1 | [] |  |  | MET.32712808 | 13003390 | 2026-07-23 | Performed
| 390 | 313300-07-1 | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION (25336435) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.052778 | 17.Jul.2026 22:00 | 0.026389 | 05.Aug.2026 05:24 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION (25336435) |  | 1 / 1 | [] |  |  | MET.25336435 | 13008286 | 2026-08-05 | Performed
| 391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:15 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-50 |  | [] | OPS/LK |  |  |  | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) |  | 1 / 1 | [] |  |  | MET.32712854 | 40000929 | 2026-07-23 | Performed
| 392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 15:09 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) |  | 2 / 2 | [] |  |  | MET.32712781 | 13003390 | 2026-07-22 | Performed
| 393 | 315000-04-1 | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 06:39 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK (32712888) |  | 2 / 2 | [] |  |  | MET.32712888 | 40000929 | 2026-07-26 | Performed
| 394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 22.Jul.2026 18:15 | 0.063194 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) |  | 3 / 3 | [] |  |  | MET.25336785 | 13008286 | 2026-07-23 | Performed
| 395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 19.Jul.2026 19:10 | 1900-01-02 00:43 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) |  | 3 / 3 | [] |  |  | MET.25336733 | 13008286 | 2026-07-23 | Performed
| 396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 12:02 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) |  | 1 / 1 | [] |  |  | MET.32712855 | 13008286 | 2026-07-23 | Performed
| 397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 18:01 | 0.083333 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) |  | 1 / 1 | [] |  |  | MET.32712715 | 13008286 | 2026-07-23 | Performed
| 398 | 321127-01-1-001 | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:41 | 17.Jul.2026 22:00 | 0.74306 | 04.Aug.2026 08:32 | 1900-01-04 01:36 |  | 1900-01-02 12:00 | Closed | 0 | T: 0; O: 0; C: 0 | 32-11 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK (32712696) |  | 7 / 7 | [] |  |  | MET.32712696 | 13008286 | 2026-08-16 | Performed
| 399 | 321127-01-1-002 | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK (32712817) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 14:41 | 17.Jul.2026 22:00 | 0.74306 | 02.Aug.2026 06:30 | 1900-01-01 05:18 |  | 1900-01-03 10:07 | Closed | 0 | T: 0; O: 0; C: 0 | 32-11 |  | [] | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK (32712817) |  | 7 / 7 | [] |  |  | MET.32712817 | 13003390 | 2026-08-04 | Performed
| 400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 18:26 | 0.043056 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 12-12 |  | [] | OPS/LK |  |  |  | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) |  | 1 / 1 | [] |  |  | MET.32712797 | 13008286 | 2026-07-23 | Performed
| 401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.0083333 | 19.Jul.2026 06:43 | 0.11667 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) |  | 1 / 1 | [] |  |  | MET.32712851 | 13008286 | 2026-07-22 | Performed
| 403 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 18.Jul.2026 21:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 32-30 |  | [] | PRE INSP |  |  |  | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) |  | 1 / 1 | [] |  |  | MET.32712809 | 13008286 | 2026-07-20 | Performed
| 404 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 16.Aug.2026 03:31 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 32-61 |  | [] | OPS/LK |  |  |  | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK (32712685) |  | 1 / 1 | [] |  |  | MET.32712685 | 13008286 | 2026-08-16 | Performed
| 405 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 10.Aug.2026 04:46 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION (32712772) |  | 1 / 1 | [] |  |  | MET.32712772 | 13008286 | 2026-08-10 | Performed
| 406 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.022917 | 16.Aug.2026 03:32 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION (32712667) |  | 1 / 1 | [] |  |  | MET.32712667 | 13008286 | 2026-08-16 | Performed
| 407 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.37153 | 17.Jul.2026 22:00 | 0.32292 | 23.Jul.2026 09:59 | 1900-01-18 07:37 |  | 1899-12-31 01:30 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | JOB-SETUP, TC/P, TC/P, CLOSE-UP |  |  |  | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK (28325784) |  | 4 / 4 | [] |  |  | MET.28325784 | 40000010 | 2026-08-11 | Performed
| 408 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.42153 | 17.Jul.2026 22:00 | 0.21042 | 10.Aug.2026 04:47 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | OPS/LK |  |  |  | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK (32712689) |  | 1 / 1 | [] |  |  | MET.32712689 | 13008286 | 2026-08-10 | Performed
| 409 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.090278 | 17.Jul.2026 22:00 | 0.044444 | 13.Aug.2026 07:34 | 0.125 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 32-41 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK (32712726) |  | 3 / 3 | [] |  |  | MET.32712726 | 13003081 | 2026-08-13 | Performed
| 410 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 | 10.Aug.2026 04:53 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-43 |  | [] | OPS/LK |  |  |  | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK (32712788) |  | 1 / 1 | [] |  |  | MET.32712788 | 13008286 | 2026-08-10 | Performed
| 411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 07:49 | 0.125 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) |  | 3 / 3 | [] |  |  | MET.32712725 | 13008286 | 2026-07-22 | Performed
| 412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 23.Jul.2026 03:30 | 0.12569 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-45 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) |  | 2 / 2 | [] |  |  | MET.32712873 | 13009981 | 2026-07-23 | Performed
| 413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 21:07 | 0.12847 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 33-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) |  | 3 / 3 | [] |  |  | MET.32712675 | 13008286 | 2026-07-22 | Performed
| 414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.03125 | 21.Jul.2026 15:25 | 0.10833 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 34-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) |  | 3 / 3 | [] |  |  | MET.32712755 | 13003390 | 2026-07-21 | Performed
| 415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 09:45 | 0.042361 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) |  | 4 / 4 | [] |  |  | MET.32712762 | 40000929 | 2026-07-23 | Performed
| 416 | 341300-02-1 | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 24.Jul.2026 15:59 | 0.043056 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC (32712811) |  | 3 / 3 | [] |  |  | MET.32712811 | 13008286 | 2026-07-26 | Performed
| 417 | 341300-03-1 | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 16:43 | 0.042361 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC (32712846) |  | 4 / 4 | [] |  |  | MET.32712846 | 40000010 | 2026-07-26 | Performed
| 418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) |  | 1 / 1 | [] |  |  | MET.32712719 | 40000929 | 2026-07-23 | Performed
| 419 | 341300-09-1 | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 08:01 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC (32712704) |  | 1 / 1 | [] |  |  | MET.32712704 | 13008286 | 2026-07-26 | Performed
| 420 | 342000-03-1 | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 23.Jul.2026 08:36 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-20 |  | [] | OPS/LK |  |  |  | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK (32712766) |  | 1 / 1 | [] |  |  | MET.32712766 | 13008286 | 2026-07-26 | Performed
| 421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 | 19.Jul.2026 08:08 | 0.056944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) |  | 4 / 4 | [] |  |  | MET.32712695 | 13008286 | 2026-07-22 | Performed
| 422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 | 23.Jul.2026 05:11 | 0.090278 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) |  | 3 / 3 | [] |  |  | MET.32712749 | 13009981 | 2026-07-23 | Performed
| 423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-48 |  | [] | TC/P |  |  |  | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) |  | 1 / 1 | [] |  |  | MET.28325742 | 13008286 | 2026-07-23 | Performed
| 424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.00625 | 21.Jul.2026 09:41 | 0.042361 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) |  | 4 / 4 | [] |  |  | MET.32712786 | 13008286 | 2026-07-23 | Performed
| 425 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 09.Aug.2026 09:11 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | OPS/LK |  |  |  | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC (32712798) |  | 1 / 1 | [] |  |  | MET.32712798 | 13003390 | 2026-08-09 | Performed
| 426 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32712806) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:08 | 0.18194 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712806 | 40000930 | 2026-07-20 | Performed
| 429 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.09375 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:17 | 0.06875 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25-64 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | as per MGR Mial ear @Jinoy Jose, Thanks for the email. As discussed further, the referenced task cards will be revised to change the replacement interval from 6 months to 02 months prior to expiry. Dear @Mohammed A Albukhari, Refer email below. As discussed, please revised the text for following tasks to change the replacement interval from 6 months to 2 month prior to expiry. Remaining instructions (2 & 3 ) will be deleted from the task as well. MP Task Number Title PBE replacement interval 333 353250-01-1-SVA CABIN ATTENDANTS PORTABLE BREATHING EQUIPMENT (PBE) PERIODIC CHECK FOR EXPIRATION 6 Months 773 25-180-00-SVA PROTECTIVE BREATHING EQUIPMENT (PBE) EXPIRATION DATE CHECK 6 Months 787 25-060-00-01-SVA SMOK HOODS PERIODIC CHECK FOR EXPIRATION 6 Months 32S 353000-06-1-SVA PROTECT. BREATHING EQPT (CKPT & CABIN) PERIODIC CHECK FOR EXPIRATION 6 Months Regards, Muhammad Noor Manager, Maintenance Program E-mail: MONOOR@saudia.com Office: +966126867409 Maintenance Program, JED, SA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) |  | 3 / 3 | [] |  |  | MET.28326058 | 13008286 | 2026-07-20 | Performed
| 430 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32712894) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 07:27 | 0.13611 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712894 | 13003390 | 2026-07-19 | Performed
| 431 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 | 31.Jul.2026 06:20 | 0.2 |  | 0.39583 | Closed | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336420) |  | 3 / 3 | [] |  |  | MET.25336420 | 13008286 | 2026-08-02 | Performed
| 432 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0076389 | 31.Jul.2026 06:17 | 0.19861 |  | 0.39583 | Closed | 0 | T: 4; O: 0; C: 4 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST (25336437) |  | 3 / 3 | [] |  |  | MET.25336437 | 13008286 | 2026-08-02 | Performed
| 434 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 | 14.Aug.2026 04:18 | 0.26736 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK (32712764) |  | 3 / 3 | [] |  |  | MET.32712764 | 13003390 | 2026-08-14 | Performed
| 435 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 | 14.Aug.2026 04:19 | 0.26667 |  | 0.5 | Closed | 0 | T: 3; O: 0; C: 3 | 36-11 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK (32712827) |  | 3 / 3 | [] |  |  | MET.32712827 | 13003390 | 2026-08-14 | Performed
| 436 | 361200-02-1 | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED (32712883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.091667 | 18.Jul.2026 13:20 | 0.92778 |  | 1899-12-31 18:40 | Closed | 0 | T: 10; O: 0; C: 10 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712883 | 40000010 | 2026-07-19 | Performed
| 437 | 361200-03-1 | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 | 18.Jul.2026 15:16 | 0.84722 |  | 1899-12-31 17:20 | Closed | 0 | T: 2; O: 0; C: 2 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) |  | 3 / 3 | [] |  |  | MET.32712718 | 40000010 | 2026-07-19 | Performed
| 441 | 384241-01-1 | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 27.Jul.2026 08:27 | 0.12569 |  | 0.625 | Closed | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP (28325945) |  | 3 / 3 | [] |  |  | MET.28325945 | 13003390 | 2026-07-27 | Performed
| 442 | 384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.013194 | 15.Aug.2026 14:32 | 0.16667 |  | 0.1875 | Closed | 0 | T: 2; O: 0; C: 2 | 38-42 |  | [] | TC/P, OPS/LK |  |  |  | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R (25336873) |  | 2 / 2 | [] |  |  | MET.25336873 | 13008286 | 2026-08-16 | Performed
| 443 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. (31498553) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.12986 | 17.Jul.2026 22:00 | 0.12986 | 24.Jul.2026 07:11 | 1899-12-31 12:44 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 49-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.31498553 | 13008286 | 2026-07-26 | Performed
| 444 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.011806 | 17.Jul.2026 22:00 | 0.011806 | 24.Jul.2026 05:55 | 1899-12-31 10:00 |  | 0.25 | Closed | 0 | T: 3; O: 0; C: 3 | 49-16 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL (31498028) |  | 3 / 3 | [] |  |  | MET.31498028 | 13008286 | 2026-07-26 | Performed
| 445 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:51 | 0.020833 |  | 0.020833 | Closed | 0 | T: 3; O: 0; C: 3 | 49-81 |  | [] | INSPECTION |  |  |  | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) |  | 1 / 1 | [] |  |  | MET.32712864 | 13003390 | 2026-07-20 | Performed
| 446 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 | 28.Jul.2026 10:30 | 1900-01-08 04:22 |  | 1900-01-01 06:00 | Closed | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325813) |  | 4 / 4 | [] |  |  | MET.28325813 | 13008286 | 2026-08-11 | Performed
| 448 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 | 28.Jul.2026 10:00 | 1900-01-08 04:51 |  | 1900-01-01 10:30 | Closed | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28326032) |  | 4 / 4 | [] |  |  | MET.28326032 | 13008286 | 2026-08-11 | Performed
| 449 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 | 03.Aug.2026 05:09 | 1900-01-02 15:21 |  | 1900-01-01 20:16 | Closed | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325885) |  | 4 / 4 | [] |  |  | MET.28325885 | 13008286 | 2026-08-11 | Performed
| 453 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.063889 | 17.Jul.2026 22:00 | 0.042361 | 29.Jul.2026 09:30 | 1900-01-21 06:48 |  | 1899-12-31 09:31 | Closed | 0 | T: 7; O: 0; C: 7 | 52-10 |  | [] | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK (32712658) |  | 9 / 9 | [] |  |  | MET.32712658 | 40000010 | 2026-08-20 | Performed
| 454 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.13889 | 03.Aug.2026 04:58 | 1900-01-05 13:43 |  | 0.98958 | Closed | 0 | T: 3; O: 0; C: 3 | 52-10 |  | [] | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP |  |  |  | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT (28325786) |  | 4 / 4 | [] |  |  | MET.28325786 | 13003081 | 2026-08-17 | Performed
| 455 | 521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 | 25.Jul.2026 07:28 | 0.10417 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK (32712813) |  | 4 / 4 | [] |  |  | MET.32712813 | 13008286 | 2026-07-26 | Performed
| 456 | 521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.044444 | 25.Jul.2026 06:37 | 0.14306 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK (32712763) |  | 4 / 4 | [] |  |  | MET.32712763 | 13008286 | 2026-07-26 | Performed
| 458 | 521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.024306 | 26.Jul.2026 08:16 | 1900-01-24 01:03 |  | 0.96528 | Closed | 0 | T: 2; O: 0; C: 2 | 52-10 |  | [] | OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, OPS/LK, OPS/LK |  |  |  | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK (32712735) |  | 6 / 6 | [] |  |  | MET.32712735 | 40000010 | 2026-08-20 | Performed
| 459 | 521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.025 | 25.Jul.2026 06:09 | 0.16111 |  | 0.47917 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC (32712737) |  | 4 / 4 | [] |  |  | MET.32712737 | 13008286 | 2026-07-26 | Performed
| 460 | 521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 24.Jul.2026 06:12 | 0.19097 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK (32712783) |  | 4 / 4 | [] |  |  | MET.32712783 | 13008286 | 2026-07-26 | Performed
| 461 | 521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 24.Jul.2026 05:14 | 0.22361 |  | 0.33333 | Closed | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK (32712823) |  | 4 / 4 | [] |  |  | MET.32712823 | 13008286 | 2026-07-26 | Performed
| 463 | 521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.010417 | 24.Jul.2026 08:05 | 1899-12-31 23:00 |  | 0.66667 | Closed | 0 | T: 4; O: 0; C: 4 | 52-10 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC (32712801) |  | 4 / 4 | [] |  |  | MET.32712801 | 40000929 | 2026-07-26 | Performed
| 464 | 521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.15347 | 17.Jul.2026 22:00 | 0.086806 | 24.Jul.2026 07:40 | 1899-12-31 23:27 |  | 0.52083 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. (32712671) |  | 3 / 3 | [] |  |  | MET.32712671 | 13003390 | 2026-07-26 | Performed
| 465 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 02.Aug.2026 01:34 | 0.16667 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P, TC/P, TC/P, TC/P |  |  |  | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION (32712732) |  | 4 / 4 | [] |  |  | MET.32712732 | 13008286 | 2026-08-02 | Performed
| 469 | 522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.14653 | 17.Jul.2026 22:00 | 0.10486 | 20.Aug.2026 06:32 | 0.13542 |  | 0.30833 | Closed | 0 | T: 6; O: 0; C: 6 | 52-21 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC (25335941) |  | 4 / 4 | [] |  |  | MET.25335941 | 13003390 | 2026-08-20 | Performed
| 472 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 17:04 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION (32712822) |  | 1 / 1 | [] |  |  | MET.32712822 | 40000930 | 2026-08-03 | Performed
| 473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP (32712736) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 04:30 | 0.16111 |  | 0.32292 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712736 | 13003390 | 2026-07-21 | Performed
| 474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.0069444 | 21.Jul.2026 03:47 | 0.125 |  | 0.19792 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) |  | 1 / 1 | [] |  |  | MET.32712895 | 13008286 | 2026-07-22 | Performed
| 475 | 525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 26.Jul.2026 05:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS (32712807) |  | 1 / 1 | [] |  |  | MET.32712807 | 40000929 | 2026-07-26 | Performed
| 476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0027778 | 21.Jul.2026 03:44 | 0.12917 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) |  | 1 / 1 | [] |  |  | MET.32712771 | 13008286 | 2026-07-22 | Performed
| 477 | 525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 25.Jul.2026 10:24 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE (32712727) |  | 1 / 1 | [] |  |  | MET.32712727 | 13008286 | 2026-07-26 | Performed
| 478 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 25.Jul.2026 09:25 | 0.12569 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 52-71 |  | [] | OPS/LK |  |  |  | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST (32712814) |  | 1 / 1 | [] |  |  | MET.32712814 | 13008286 | 2026-07-26 | Performed
| 479 | 527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32712876) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 05.Aug.2026 04:13 | 0.041667 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK, OPS/LK, OPS/LK, OPS/LK |  |  |  | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS (32712876) |  | 4 / 4 | [] |  |  | MET.32712876 | 13008286 | 2026-08-05 | Performed
| 480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 | 23.Jul.2026 03:05 | 0.17639 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK |  |  |  | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) |  | 1 / 1 | [] |  |  | MET.32712706 | 13009981 | 2026-07-23 | Performed
| 481 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 26.Jul.2026 04:30 | 1900-01-02 00:12 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] |  |  |  |  | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. (32712794) |  | 3 / 3 | [] |  |  | MET.32712794 | 40000929 | 2026-07-30 | Performed
| 482 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 | 23.Jul.2026 12:30 | 0.30208 |  | 0.09375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. (32712815) |  | 3 / 3 | [] |  |  | MET.32712815 | 13008286 | 2026-07-26 | Performed
| 483 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 29.Jul.2026 04:07 | 1899-12-31 02:10 |  | 0.50139 | Closed | 0 | T: 2; O: 0; C: 2 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. (32712862) |  | 3 / 3 | [] |  |  | MET.32712862 | 13008286 | 2026-07-30 | Performed
| 484 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.097222 | 17.Jul.2026 22:00 | 0.097222 | 06.Aug.2026 09:38 | 0.083333 |  | 0.125 | Closed | 0 | T: 3; O: 0; C: 3 | 53-11 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH (32712664) |  | 3 / 3 | [] |  |  | MET.32712664 | 13009981 | 2026-08-09 | Performed
| 485 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 13.Aug.2026 07:08 | 0.13125 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 53-19 |  | [] | OPS/LK |  |  |  | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC (32712830) |  | 1 / 1 | [] |  |  | MET.32712830 | 13003081 | 2026-08-13 | Performed
| 486 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 24.Jul.2026 07:37 | 0.10833 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 531900-10-1 (1) / FUSELAGE DRAINAGE (32712789) |  | 3 / 3 | [] |  |  | MET.32712789 | 13008286 | 2026-07-26 | Performed
| 487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.034028 | 21.Jul.2026 14:20 | 0.24514 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP |  |  |  | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) |  | 2 / 2 | [] |  |  | MET.32712835 | 13008286 | 2026-07-22 | Performed
| 488 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16806 | 17.Jul.2026 22:00 | 0.16806 | 24.Jul.2026 05:54 | 1899-12-31 10:00 |  | 0.10486 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 532176-01-1 (0) / FORWARD FUSELAGE (32450143) |  | 3 / 3 | [] |  |  | MET.32450143 | 13008286 | 2026-07-26 | Performed
| 489 | 532181-02-1 | 532181-02-1 (0) / FORWARD FUSELAGE | 532181-02-1 (0) / FORWARD FUSELAGE (32450165) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 05:47 | 1900-01-02 05:04 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 1 / 2 |  | 3 / 3 | [] |  |  | MET.32450165 | 13003390 | 2026-07-27 | Performed
| 490 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 13.Aug.2026 07:08 | 0.13125 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 53-39 |  | [] | OPS/LK |  |  |  | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC (32712818) |  | 1 / 1 | [] |  |  | MET.32712818 | 13003081 | 2026-08-13 | Performed
| 491 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 26.Jul.2026 04:31 | 1900-01-02 00:14 |  | 0.11111 | Closed | 0 | T: 4; O: 0; C: 4 | 53-41 |  | [] |  |  |  |  | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. (32712868) |  | 3 / 3 | [] |  |  | MET.32712868 | 40000929 | 2026-07-30 | Performed
| 492 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.11875 | 17.Jul.2026 22:00 | 0.097917 | 24.Jul.2026 06:52 | 1900-01-22 00:34 |  | 0.52153 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP (32787526) |  | 5 / 5 | [] |  |  | MET.32787526 | 13008286 | 2026-08-16 | Performed
| 493 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 534307-03-1 (0) / REAR FUSELAGE (32450173) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 24.Jul.2026 07:17 | 0.51458 |  | 0.14653 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534307-03-1 (0) / REAR FUSELAGE (32450173) |  | 3 / 3 | [] |  |  | MET.32450173 | 13008286 | 2026-07-26 | Performed
| 494 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 534308-02-1 (0) / REAR FUSELAGE (32450166) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 13:31 | 17.Jul.2026 22:00 | 1899-12-31 13:31 | 24.Jul.2026 06:49 | 0.53194 |  | 0.20903 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 534308-02-1 (0) / REAR FUSELAGE (32450166) |  | 4 / 4 | [] |  |  | MET.32450166 | 13008286 | 2026-07-26 | Performed
| 495 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 13.Aug.2026 07:09 | 0.13056 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-01-1 (3) / FUSELAGE DRAINAGE (32712812) |  | 1 / 1 | [] |  |  | MET.32712812 | 13008286 | 2026-08-19 | Performed
| 496 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 13.Aug.2026 07:07 | 0.13125 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 53-59 |  | [] | OPS/LK |  |  |  | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC (32712669) |  | 1 / 1 | [] |  |  | MET.32712669 | 13003081 | 2026-08-13 | Performed
| 497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 15:11 | 1899-12-31 17:42 |  | 0.17361 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) |  | 3 / 3 | [] |  |  | MET.26224706 | 13009981 | 2026-07-23 | Performed
| 498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (26224854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 14:30 | 1899-12-31 16:39 |  | 0.13542 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26224854 | 13009981 | 2026-07-23 | Performed
| 499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 15:24 | 1899-12-31 15:46 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) |  | 3 / 3 | [] |  |  | MET.26224971 | 13009981 | 2026-07-23 | Performed
| 500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 14:26 | 1899-12-31 16:45 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) |  | 3 / 3 | [] |  |  | MET.26225034 | 13009981 | 2026-07-23 | Performed
| 503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 15:18 | 1899-12-31 15:56 |  | 0.23264 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) |  | 3 / 3 | [] |  |  | MET.19876877 | 13009981 | 2026-07-23 | Performed
| 504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 14:42 | 1899-12-31 16:33 |  | 0.097222 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) |  | 3 / 3 | [] |  |  | MET.19876887 | 13009981 | 2026-07-23 | Performed
| 505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:07 | 1899-12-31 16:09 |  | 0.25 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) |  | 3 / 3 | [] |  |  | MET.25336918 | 13009981 | 2026-07-23 | Performed
| 506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:19 | 1899-12-31 16:59 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) |  | 3 / 3 | [] |  |  | MET.25335813 | 13009981 | 2026-07-23 | Performed
| 507 | 552600-01-1 | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. (32712775) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.12847 | 17.Jul.2026 22:00 | 0.11458 | 26.Jul.2026 02:00 | 1900-01-16 17:30 |  | 1900-01-02 12:30 | Closed | 0 | T: 8; O: 0; C: 8 | 20-00 |  | [] |  |  |  |  | 1 / 1 |  | 6 / 6 | [] |  |  | MET.32712775 | 13008286 | 2026-08-13 | Performed
| 509 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 06.Aug.2026 03:06 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION (32712810) |  | 1 / 1 | [] |  |  | MET.32712810 | 13004037 | 2026-08-06 | Performed
| 514 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:34 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) |  | 1 / 1 | [] |  |  | MET.26290633 | 13008286 | 2026-07-20 | Performed
| 515 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:35 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) |  | 1 / 1 | [] |  |  | MET.19875138 | 13008286 | 2026-07-20 | Performed
| 516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 15:06 | 0.66806 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | OPEN-UP, INSPECTION, CLOSE-UP |  |  |  | 7 / 8 |  | 3 / 3 | [] |  |  | MET.28325730 | 13003390 | 2026-07-22 | Performed
| 517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 14:21 | 0.19167 |  | 0.24306 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 5 / 5 |  | 3 / 3 | [] |  |  | MET.28325833 | 13003390 | 2026-07-21 | Performed
| 518 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 | 26.Jul.2026 14:34 | 0.125 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC (26224780) |  | 3 / 3 | [] |  |  | MET.26224780 | 13008286 | 2026-07-27 | Performed
| 519 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.033333 | 26.Jul.2026 14:35 | 0.125 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 73-13 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC (19875152) |  | 3 / 3 | [] |  |  | MET.19875152 | 13008286 | 2026-07-27 | Performed
| 520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28325843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:50 | 0.67917 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.28325843 | 13003390 | 2026-07-22 | Performed
| 521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28325855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:04 | 0.14653 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.28325855 | 13003390 | 2026-07-21 | Performed
| 522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 15:02 | 0.67153 |  | 0.076389 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) |  | 3 / 3 | [] |  |  | MET.26224711 | 13003390 | 2026-07-22 | Performed
| 523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 14:07 | 0.2 |  | 0.27083 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) |  | 3 / 3 | [] |  |  | MET.26224781 | 13003390 | 2026-07-21 | Performed
| 524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627239) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 11:01 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 2 / 2 |  | 1 / 1 | [] |  |  | MET.23627239 | 40000930 | 2026-07-21 | Performed
| 527 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 | 27.Jul.2026 15:46 | 0.18056 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP (28326014) |  | 3 / 3 | [] |  |  | MET.28326014 | 13008286 | 2026-07-28 | Performed
| 528 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP (28326013) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10625 | 17.Jul.2026 22:00 | 0.052778 | 28.Jul.2026 14:10 | 0.19861 |  | 0.70833 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326013 | 13008286 | 2026-07-29 | Performed
| 529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28326019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:59 | 1899-12-31 17:11 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326019 | 13009981 | 2026-07-23 | Performed
| 530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28326018) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:31 | 1899-12-31 17:32 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326018 | 13009981 | 2026-07-23 | Performed
| 531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) |  | 1 / 1 | [] |  |  | MET.28326017 | 40000930 | 2026-07-21 | Performed
| 532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) |  | 1 / 1 | [] |  |  | MET.28326023 | 40000930 | 2026-07-21 | Performed
| 533 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 | 27.Jul.2026 15:46 | 0.18056 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP (26290668) |  | 3 / 3 | [] |  |  | MET.26290668 | 13008286 | 2026-07-28 | Performed
| 534 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.038889 | 28.Jul.2026 14:10 | 0.19792 |  | 0.875 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP (26290572) |  | 3 / 3 | [] |  |  | MET.26290572 | 13008286 | 2026-07-29 | Performed
| 535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (26290680) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 15:17 | 1899-12-31 16:53 |  | 0.059028 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290680 | 13009981 | 2026-07-23 | Performed
| 536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (26290654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 14:54 | 1899-12-31 17:10 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290654 | 13009981 | 2026-07-23 | Performed
| 539 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:00 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) |  | 1 / 1 | [] |  |  | MET.28326050 | 40000010 | 2026-07-19 | Performed
| 540 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:01 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) |  | 1 / 1 | [] |  |  | MET.28325746 | 40000010 | 2026-07-19 | Performed
| 543 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.040972 | 17.Jul.2026 22:00 | 0.034028 | 26.Jul.2026 16:00 | 1900-01-12 17:49 |  | 0.34028 | Closed | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP (19873954) |  | 3 / 3 | [] |  |  | MET.19873954 | 13009981 | 2026-08-09 | Performed
| 544 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.040972 | 17.Jul.2026 22:00 | 0.034028 | 26.Jul.2026 13:39 | 1900-01-12 20:08 |  | 0.59028 | Closed | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP (19875040) |  | 3 / 3 | [] |  |  | MET.19875040 | 13009981 | 2026-08-09 | Performed
| 545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:04 | 0.66667 |  | 0.16667 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) |  | 3 / 3 | [] |  |  | MET.26224712 | 13003390 | 2026-07-22 | Performed
| 546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:35 | 0.18264 |  | 0.43056 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) |  | 3 / 3 | [] |  |  | MET.26224783 | 13003390 | 2026-07-21 | Performed
| 547 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 26.Jul.2026 14:18 | 0.24861 |  | 0.60417 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP (26290667) |  | 3 / 3 | [] |  |  | MET.26290667 | 13008286 | 2026-07-27 | Performed
| 548 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 26.Jul.2026 14:18 | 0.24861 |  | 0.60417 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP (19875078) |  | 3 / 3 | [] |  |  | MET.19875078 | 13008286 | 2026-07-27 | Performed
| 549 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 17.Jul.2026 22:00 | 0.059028 | 26.Jul.2026 16:02 | 1900-01-12 17:45 |  | 0.34028 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP (28325884) |  | 3 / 3 | [] |  |  | MET.28325884 | 13009981 | 2026-08-09 | Performed
| 550 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.059028 | 17.Jul.2026 22:00 | 0.059028 | 26.Jul.2026 16:03 | 1900-01-12 17:45 |  | 0.63194 | Closed | 0 | T: 2; O: 0; C: 2 | 78-31 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP (28326044) |  | 3 / 3 | [] |  |  | MET.28326044 | 13009981 | 2026-08-09 | Performed
| 552 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.05 | 25.Jul.2026 14:54 | 1900-01-17 21:40 |  | 0.57292 | Closed | 0 | T: 2; O: 0; C: 2 | 78-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP (32712897) |  | 5 / 5 | [] |  |  | MET.32712897 | 13008286 | 2026-08-19 | Performed
| 554 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP (32712743) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.51944 | 17.Jul.2026 22:00 | 0.51944 | 18.Jul.2026 13:45 | 0.041667 |  | 0.055556 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712743 | 13008286 | 2026-07-20 | Performed
| 555 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP (32712816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 21:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 6 / 6 |  | 1 / 1 | [] |  |  | MET.32712816 | 13008286 | 2026-07-20 | Performed
| 556 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 01:26 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) |  | 1 / 1 | [] |  |  | MET.32712791 | 13008286 | 2026-07-20 | Performed
| 557 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP (32712684) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.32712684 | 13008286 | 2026-07-20 | Performed
| 558 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:11 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) |  | 1 / 1 | [] |  |  | MET.32712661 | 13008286 | 2026-07-20 | Performed
| 559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 03:43 | 17.Jul.2026 22:00 | 1900-01-02 03:43 | 23.Jul.2026 13:06 | 0.020833 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) |  | 1 / 1 | [] |  |  | MET.31498481 | 13003390 | 2026-07-23 | Performed
| 560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP (28326031) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 08:02 | 0.71389 |  | 0.34722 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.28326031 | 13008286 | 2026-07-22 | Performed
| 561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 05:47 | 1900-01-01 01:43 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) |  | 1 / 1 | [] |  |  | MET.32712776 | 40000930 | 2026-07-21 | Performed
| 562 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) (32712792) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 10:05 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | INSPECTION |  |  |  | 5 / 5 |  | 1 / 1 | [] |  |  | MET.32712792 | 13003390 | 2026-07-20 | Performed
| 563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 14:55 | 0.21667 |  | 1899-12-31 22:50 | Closed | 0 | T: 8; O: 0; C: 8 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) |  | 1 / 1 | [] |  |  | MET.32712826 | 13008286 | 2026-07-21 | Performed
| 564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32712836) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.042361 |  | 0.076389 | Closed | 0 | T: 9; O: 0; C: 9 | 05-24 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712836 | 13008286 | 2026-07-21 | Performed
| 565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32712703) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.044444 |  | 0.083333 | Closed | 0 | T: 16; O: 0; C: 16 | 05-24 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712703 | 13008286 | 2026-07-21 | Performed
| 566 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:10 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) |  | 1 / 1 | [] |  |  | MET.32712987 | 13008286 | 2026-07-20 | Performed
| 567 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE (32712965) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:11 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712965 | 13008286 | 2026-07-20 | Performed
| 568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28325878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:20 | 1900-01-01 14:44 |  | 0.3125 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 4 |  | 3 / 3 | [] |  |  | MET.28325878 | 40000929 | 2026-07-23 | Performed
| 569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28325791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.030556 | 19.Jul.2026 16:20 | 1900-01-01 02:35 |  | 0.5 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 4 / 7 |  | 3 / 3 | [] |  |  | MET.28325791 | 13003390 | 2026-07-21 | Performed
| 570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32712853) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:09 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | 3 / 4 |  | 1 / 1 | [] |  |  | MET.32712853 | 40000930 | 2026-07-21 | Performed
| 571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) |  | 1 / 1 | [] |  |  | MET.32712760 | 40000930 | 2026-07-21 | Performed
| 572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:24 | 0.025 |  | 0.034722 | Closed | 0 | T: 12; O: 0; C: 12 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) |  | 1 / 1 | [] |  |  | MET.32712742 | 13008286 | 2026-07-21 | Performed
| 573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:00 | 0.040972 |  | 0.048611 | Closed | 0 | T: 10; O: 0; C: 10 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) |  | 1 / 1 | [] |  |  | MET.32712778 | 13008286 | 2026-07-21 | Performed
| 574 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP (32712761) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:22 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 5 / 10 |  | 1 / 1 | [] |  |  | MET.32712761 | 13008286 | 2026-07-20 | Performed
| 575 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP (32712690) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:20 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 3 / 7 |  | 1 / 1 | [] |  |  | MET.32712690 | 13008286 | 2026-07-20 | Performed
| 576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32712777) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 20.Jul.2026 07:31 | 1900-01-01 01:55 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 5 / 5 |  | 1 / 1 | [] |  |  | MET.32712777 | 13003390 | 2026-07-22 | Performed
| 577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32712872) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 22.Jul.2026 17:23 | 0.097917 |  | 0.0625 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 5 / 5 |  | 1 / 1 | [] |  |  | MET.32712872 | 13008286 | 2026-07-23 | Performed
| 578 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION (32712687) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 22:32 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP, PRE INSP |  |  |  | 2 / 2 |  | 2 / 2 | [] |  |  | MET.32712687 | 13008286 | 2026-07-20 | Performed
| 579 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP (32712925) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 01:46 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 6 / 8 |  | 1 / 1 | [] |  |  | MET.32712925 | 13008286 | 2026-07-20 | Performed
| 580 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP (32712945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 02:21 | 0.027083 |  | 0.027083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 3 / 3 |  | 1 / 1 | [] |  |  | MET.32712945 | 13008286 | 2026-07-20 | Performed
| 581 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP (32712796) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:15 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712796 | 13008286 | 2026-07-20 | Performed
| 582 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 09.Aug.2026 14:19 | 0.125 |  | 0.20833 | Closed | 0 | T: 1; O: 0; C: 1 | 27-21 |  | [] | TC/P |  |  |  | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION (28375011) |  | 1 / 1 | [] |  |  | MET.28375011 | 13008286 | 2026-08-10 | Performed
| 583 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 | 10.Aug.2026 10:16 | 0.041667 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 12-22 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION (32712914) |  | 3 / 3 | [] |  |  | MET.32712914 | 13003081 | 2026-08-11 | Performed
| 589 | 344200-02-2 | 344200-02-2 (01) / RADIO ALTIMETER | 344200-02-2 (01) / RADIO ALTIMETER (32712908) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.30069 | 17.Jul.2026 22:00 | 0.30069 | 29.Jul.2026 17:19 | 1900-01-17 15:22 |  | 0.58333 | Closed | 0 | T: 2; O: 0; C: 2 | 34-42 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32712908 | 13008286 | 2026-08-19 | Performed
| 593 | 494000-B2-1 | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 24.Jul.2026 07:06 | 1899-12-31 08:46 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 49-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG (32712910) |  | 3 / 3 | [] |  |  | MET.32712910 | 13008286 | 2026-07-26 | Performed
| 594 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 03:22 | 0.084028 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB (32807087) |  | 1 / 1 | [] |  |  | MET.32807087 | 13008286 | 2026-08-02 | Performed
| 595 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 02.Aug.2026 03:25 | 0.083333 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB (32807086) |  | 1 / 1 | [] |  |  | MET.32807086 | 13008286 | 2026-08-02 | Performed
| 596 | 532178-01-1 | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00625 | 17.Jul.2026 22:00 | 0.00625 | 29.Jul.2026 01:08 | 0.30764 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA (32450175) |  | 3 / 3 | [] |  |  | MET.32450175 | 13008286 | 2026-07-29 | Performed
| 597 | 533130-01-1 | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP (32450197) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.031944 | 17.Jul.2026 22:00 | 0.028472 | 27.Jul.2026 04:01 | 1900-01-07 10:54 |  | 0.72917 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP (32450197) |  | 5 / 5 | [] |  |  | MET.32450197 | 13003390 | 2026-08-04 | Performed
| 598 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.15 | 17.Jul.2026 22:00 | 0.14306 | 27.Jul.2026 02:07 | 1900-01-13 08:16 |  | 1899-12-31 02:30 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP (32712911) |  | 7 / 7 | [] |  |  | MET.32712911 | 13008286 | 2026-08-11 | Performed
| 599 | 534112-01-1 | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION (32450199) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.025 | 27.Jul.2026 04:04 | 1900-01-07 10:52 |  | 0.86458 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION (32450199) |  | 5 / 5 | [] |  |  | MET.32450199 | 40000929 | 2026-08-06 | Performed
| 600 | 572610-02-2 | 572610-02-2 (0) / OUTER WING | 572610-02-2 (0) / OUTER WING (32450162) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 24.Jul.2026 14:05 | 1900-01-01 05:18 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-2 (0) / OUTER WING (32450162) |  | 4 / 4 | [] |  |  | MET.32450162 | 13008286 | 2026-07-27 | Performed
| 601 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP (32807084) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:02 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32807084 | 13003390 | 2026-07-20 | Performed
| 602 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR (32807085) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 11:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP, PRE INSP |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.32807085 | 13008286 | 2026-07-20 | Performed
| 605 | 12-21-11-03-0-SVA | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) | On Demand Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 04:30 | 17.Jul.2026 22:00 | 0.32292 | 17.Jul.2026 17:00 | 1900-01-12 02:36 |  | 1900-01-04 17:30 | Closed | 0 | T: 0; O: 0; C: 0 | 12-21 |  | [] | WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH |  |  |  | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH (23560156) |  | 25 / 25 | [] |  |  | MET.23560156 | 13003390 | 2026-08-03 | Performed
| 606 | 32-10-00-01-0-SVA | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (30931752) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.0625 | 29.Jul.2026 04:05 | 1900-01-11 04:40 |  | 0.60417 | Closed | 0 | T: 0; O: 0; C: 0 | 32-12 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB (30931752) |  | 3 / 3 | [] |  |  | MET.30931752 | 13008286 | 2026-08-11 | Performed
| 607 | 321000-01-1 | 321000-01-1 (5) / MLG AND DOORS LUBRICATION | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 321000-01-1 (5) / MLG AND DOORS LUBRICATION (32807082) |  | 3 / 3 | [] |  |  | MET.32807082 | 40000930 | 2026-08-03 | Performed
| 608 | 322100-07-1 | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP (32713055) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:38 | 17.Jul.2026 22:00 | 0.48194 | 26.Jul.2026 02:10 | 1900-01-16 09:48 |  | 1900-01-05 00:36 | Closed | 0 | T: 2; O: 0; C: 2 | 32-21 |  | [] | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  | OK TO INSTALL NLG LEG ASSY IPC 32-21-01-10 | 2 / 3 |  | 10 / 10 | [] |  |  | MET.32713055 | 13008286 | 2026-08-13 | Performed
| 609 | 521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 27.Jul.2026 04:20 | 0.021528 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. (32713053) |  | 1 / 1 | [] |  |  | MET.32713053 | 13008286 | 2026-07-27 | Performed
| 611 | 521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP (32713003) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14653 | 17.Jul.2026 22:00 | 0.11319 | 27.Jul.2026 08:33 | 1900-01-22 00:22 |  | 0.9375 | Closed | 0 | T: 10; O: 0; C: 10 | 52-13 |  | [] | TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION |  |  |  | 0 / 2 |  | 10 / 10 | [] |  |  | MET.32713003 | 40000010 | 2026-08-20 | Performed
| 616 | 523119-01-2 | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.023611 | 24.Jul.2026 08:22 | 1900-01-21 22:59 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 52-32 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP (32713047) |  | 4 / 4 | [] |  |  | MET.32713047 | 13008286 | 2026-08-16 | Performed
| 618 | 531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.2625 | 17.Jul.2026 22:00 | 0.22083 | 27.Jul.2026 14:35 | 1900-01-01 20:53 |  | 0.60417 | Closed | 0 | T: 1; O: 0; C: 1 | 53-11 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP |  |  |  | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP (32712875) |  | 6 / 6 | [] |  |  | MET.32712875 | 13008286 | 2026-08-02 | Performed
| 622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.023611 | 21.Jul.2026 13:16 | 0.11458 |  | 0.5625 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) |  | 3 / 3 | [] |  |  | MET.32712995 | 13003390 | 2026-07-21 | Performed
| 624 | 532180-04-2 | 532180-04-2 (0) / FORWARD FUSELAGE | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 06:21 | 1899-12-31 09:32 |  | 0.12639 | Closed | 0 | T: 1; O: 0; C: 1 | 53 |  | [] |  |  |  |  | 532180-04-2 (0) / FORWARD FUSELAGE (32450146) |  | 3 / 3 | [] |  |  | MET.32450146 | 13008286 | 2026-07-26 | Performed
| 625 | 533111-01-1 | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 29.Jul.2026 08:16 | 0.14514 |  | 0.042361 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | CLEAN-UP, INSPECTION |  |  |  | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP (25336513) |  | 2 / 2 | [] |  |  | MET.25336513 | 13003390 | 2026-07-29 | Performed
| 626 | 533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0875 | 17.Jul.2026 22:00 | 0.0875 | 29.Jul.2026 08:17 | 0.86319 |  | 0.25694 | Closed | 0 | T: 4; O: 0; C: 4 | 53 |  | [] |  |  |  |  | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS (32450148) |  | 3 / 3 | [] |  |  | MET.32450148 | 40000930 | 2026-07-30 | Performed
| 627 | 533139-02-1 | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 29.Jul.2026 11:46 | 0.71667 |  | 0.12639 | Closed | 0 | T: 0; O: 0; C: 0 | 53-31 |  | [] | JOB-SETUP, INSPECTION, -- |  |  |  | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE (25336237) |  | 3 / 3 | [] |  |  | MET.25336237 | 13008286 | 2026-07-30 | Performed
| 628 | 533152-01-7 | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.1875 | 25.Jul.2026 14:36 | 1900-01-21 21:28 |  | 1899-12-31 | Closed | 0 | T: 1; O: 0; C: 1 | 53-31 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP (32713023) |  | 9 / 9 | [] |  |  | MET.32713023 | 13003081 | 2026-08-17 | Performed
| 629 | 534107-03-1 | 534107-03-1 (0) / REAR FUSELAGE | 534107-03-1 (0) / REAR FUSELAGE (32450155) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.025 | 17.Jul.2026 22:00 | 0.025 | 27.Jul.2026 14:31 | 0.76319 |  | 0.11458 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534107-03-1 (0) / REAR FUSELAGE (32450155) |  | 3 / 3 | [] |  |  | MET.32450155 | 13003390 | 2026-07-28 | Performed
| 631 | 534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 534135-02-1 (0) / REAR FUSELAGE (32450158) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027778 | 17.Jul.2026 22:00 | 0.027778 | 03.Aug.2026 05:40 | 0.56458 |  | 0.35417 | Closed | 0 | T: 2; O: 0; C: 2 | 57-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 534135-02-1 (0) / REAR FUSELAGE (32450158) |  | 3 / 3 | [] |  |  | MET.32450158 | 13003390 | 2026-08-04 | Performed
| 637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.050694 | 17.Jul.2026 22:00 | 0.047917 | 21.Jul.2026 15:00 | 1899-12-31 16:19 |  | 0.29167 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) |  | 4 / 4 | [] |  |  | MET.32713050 | 13008286 | 2026-07-23 | Performed
| 638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038889 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 14:53 | 0.98194 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) |  | 4 / 4 | [] |  |  | MET.32713048 | 13008286 | 2026-07-23 | Performed
| 651 | 572044-01-2-001 | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 14:47 | 1899-12-31 05:06 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP (26209161) |  | 4 / 4 | [] |  |  | MET.26209161 | 13008286 | 2026-07-26 | Performed
| 652 | 572044-01-2-002 | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 23.Jul.2026 15:43 | 0.17639 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-SETUP |  |  |  | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP (26290432) |  | 4 / 4 | [] |  |  | MET.26290432 | 13008286 | 2026-07-26 | Performed
| 653 | 572062-01-1-001 | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 24.Jul.2026 15:19 | 1900-01-01 04:52 |  | 0.11458 | Closed | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP (32713037) |  | 4 / 4 | [] |  |  | MET.32713037 | 13008286 | 2026-07-27 | Performed
| 654 | 572062-01-1-002 | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 23.Jul.2026 18:53 | 0.038194 |  | 0.052083 | Closed | 0 | T: 2; O: 0; C: 2 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP (32713013) |  | 4 / 4 | [] |  |  | MET.32713013 | 13008286 | 2026-07-26 | Performed
| 655 | 572063-01-1-001 | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.12986 | 17.Jul.2026 22:00 | 0.077778 | 24.Jul.2026 17:22 | 1900-01-25 17:31 |  | 0.27917 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP |  |  |  | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP (32713040) |  | 6 / 6 | [] |  |  | MET.32713040 | 13003390 | 2026-08-20 | Performed
| 659 | 572111-01-1-001 | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 24.Jul.2026 15:09 | 1900-01-01 05:03 |  | 0.0625 | Closed | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP (28325749) |  | 4 / 4 | [] |  |  | MET.28325749 | 13008286 | 2026-07-27 | Performed
| 660 | 572111-01-1-002 | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 23.Jul.2026 18:50 | 0.041667 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP (28325815) |  | 4 / 4 | [] |  |  | MET.28325815 | 13008286 | 2026-07-26 | Performed
| 661 | 572111-02-1 | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.017361 | 17.Jul.2026 22:00 | 0.017361 | 24.Jul.2026 13:29 | 1900-01-01 05:52 |  | 0.036806 | Closed | 0 | T: 8; O: 0; C: 8 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- (32450174) |  | 3 / 3 | [] |  |  | MET.32450174 | 13008286 | 2026-07-27 | Performed
| 662 | 572112-01-1-001 | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP (25336200) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 15:11 | 1900-01-01 05:00 |  | 0.090278 | Closed | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 4 / 4 |  | 4 / 4 | [] |  |  | MET.25336200 | 13008286 | 2026-07-27 | Performed
| 663 | 572112-01-1-002 | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.075 | 24.Jul.2026 13:56 | 1899-12-31 19:08 |  | 0.052083 | Closed | 0 | T: 9; O: 0; C: 9 | 57-21 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP (25336328) |  | 4 / 4 | [] |  |  | MET.25336328 | 13003390 | 2026-07-26 | Performed
| 668 | 572607-01-1-001 | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31498801) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 | 24.Jul.2026 15:21 | 1900-01-01 04:46 |  | 0.16111 | Closed | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 2 / 2 |  | 4 / 4 | [] |  |  | MET.31498801 | 13008286 | 2026-07-27 | Performed
| 669 | 572607-01-1-002 | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.031944 | 23.Jul.2026 15:36 | 0.17778 |  | 0.30208 | Closed | 0 | T: 6; O: 0; C: 6 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH (31497936) |  | 4 / 4 | [] |  |  | MET.31497936 | 13008286 | 2026-07-26 | Performed
| 670 | 572610-02-1-001 | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:27 | 1900-01-05 09:40 |  | 0.29167 | Closed | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP (32712825) |  | 4 / 4 | [] |  |  | MET.32712825 | 13008286 | 2026-07-27 | Performed
| 671 | 572610-02-1-002 | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.032639 | 20.Jul.2026 10:28 | 1900-01-02 09:28 |  | 0.53125 | Closed | 0 | T: 3; O: 0; C: 3 | 57-26 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP (32712722) |  | 4 / 4 | [] |  |  | MET.32712722 | 13008286 | 2026-07-26 | Performed
| 672 | 574101-01-3-001 | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 | 24.Jul.2026 15:28 | 1899-12-31 17:36 |  | 0.083333 | Closed | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP (32713045) |  | 4 / 4 | [] |  |  | MET.32713045 | 13003390 | 2026-07-26 | Performed
| 673 | 574101-01-3-002 | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP (32713035) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.26736 | 17.Jul.2026 22:00 | 0.26736 | 23.Jul.2026 15:17 | 1900-01-01 19:47 |  | 0.36458 | Closed | 0 | T: 12; O: 0; C: 12 | 57-41 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32713035 | 13003390 | 2026-07-26 | Performed
| 674 | 574202-01-2-001 | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 28.Jul.2026 18:30 | 0.54514 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713043) |  | 4 / 4 | [] |  |  | MET.32713043 | 13003390 | 2026-07-29 | Performed
| 675 | 574202-01-2-002 | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP (32713031) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 24.Jul.2026 14:23 | 1900-01-04 19:14 |  | 0.89583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 4 / 4 | [] |  |  | MET.32713031 | 40000010 | 2026-07-30 | Performed
| 676 | 574205-01-1-001 | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP (32713033) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:45 | 1899-12-31 17:00 |  | 0.022917 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713033 | 13003390 | 2026-07-26 | Performed
| 677 | 574205-01-1-002 | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP (32713018) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:31 | 1899-12-31 18:39 |  | 0.055556 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 2 |  | 4 / 4 | [] |  |  | MET.32713018 | 13003390 | 2026-07-26 | Performed
| 678 | 574302-01-2-001 | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:35 | 0.08125 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32712905) |  | 4 / 4 | [] |  |  | MET.32712905 | 13003390 | 2026-07-27 | Performed
| 679 | 574302-01-2-002 | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:24 | 1900-01-02 05:26 |  | 0.18056 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP (32713020) |  | 4 / 4 | [] |  |  | MET.32713020 | 13008286 | 2026-07-28 | Performed
| 680 | 574305-01-1-001 | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP (32713038) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:42 | 1899-12-31 18:10 |  | 0.10486 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, --, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713038 | 13003390 | 2026-07-26 | Performed
| 681 | 574305-01-1-002 | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:13 | 1899-12-31 18:56 |  | 0.045139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-43 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP (32713029) |  | 4 / 4 | [] |  |  | MET.32713029 | 13003390 | 2026-07-26 | Performed
| 682 | 574402-01-2-001 | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:29 | 0.086111 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713028) |  | 4 / 4 | [] |  |  | MET.32713028 | 13003390 | 2026-07-27 | Performed
| 683 | 574402-01-2-002 | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:08 | 1899-12-31 19:03 |  | 0.22222 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP (32713010) |  | 4 / 4 | [] |  |  | MET.32713010 | 13003390 | 2026-07-26 | Performed
| 684 | 574405-01-1-001 | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION (32713012) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:26 | 1899-12-31 18:24 |  | 0.14653 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713012 | 13003390 | 2026-07-26 | Performed
| 685 | 574405-01-1-002 | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:11 | 1899-12-31 18:57 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-44 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION (32713030) |  | 4 / 4 | [] |  |  | MET.32713030 | 13003390 | 2026-07-26 | Performed
| 686 | 574502-01-2-001 | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 12:16 | 0.13819 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713015) |  | 4 / 4 | [] |  |  | MET.32713015 | 13003390 | 2026-07-27 | Performed
| 687 | 574502-01-2-002 | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP (32713034) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 14:38 | 1899-12-31 18:35 |  | 0.21181 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 4 / 4 | [] |  |  | MET.32713034 | 13003390 | 2026-07-26 | Performed
| 688 | 574505-01-1-001 | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION (32713024) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 15:16 | 1899-12-31 18:02 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713024 | 13003390 | 2026-07-26 | Performed
| 689 | 574505-01-1-002 | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 13:36 | 1899-12-31 19:32 |  | 0.045139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-45 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION (32713011) |  | 4 / 4 | [] |  |  | MET.32713011 | 13003390 | 2026-07-26 | Performed
| 690 | 574602-01-2-001 | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 27.Jul.2026 13:33 | 0.13819 |  | 0.09375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713025) |  | 4 / 4 | [] |  |  | MET.32713025 | 13003390 | 2026-07-27 | Performed
| 691 | 574602-01-2-002 | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 24.Jul.2026 13:27 | 1899-12-31 20:41 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP (32713005) |  | 4 / 4 | [] |  |  | MET.32713005 | 13003390 | 2026-07-26 | Performed
| 692 | 574605-01-1-001 | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION (32713014) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 15:11 | 1899-12-31 18:09 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 4 / 4 | [] |  |  | MET.32713014 | 13003390 | 2026-07-26 | Performed
| 693 | 574605-01-1-002 | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION (32713009) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029167 | 17.Jul.2026 22:00 | 0.029167 | 24.Jul.2026 13:46 | 1899-12-31 21:22 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32713009 | 13003390 | 2026-07-26 | Performed
| 694 | 575107-01-1-001 | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 | 26.Jul.2026 06:24 | 1899-12-31 02:28 |  | 1899-12-31 01:00 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713004) |  | 4 / 4 | [] |  |  | MET.32713004 | 40000930 | 2026-07-27 | Performed
| 695 | 575107-01-1-002 | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22361 | 17.Jul.2026 22:00 | 0.22361 | 24.Jul.2026 14:28 | 1899-12-31 18:27 |  | 0.024306 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP (32713022) |  | 4 / 4 | [] |  |  | MET.32713022 | 13003390 | 2026-07-26 | Performed
| 696 | 575120-03-1-001 | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 | 29.Jul.2026 08:16 | 1899-12-31 01:24 |  | 0.0625 | Closed | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712998) |  | 4 / 4 | [] |  |  | MET.32712998 | 40000010 | 2026-07-30 | Performed
| 697 | 575120-03-1-002 | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.10972 | 24.Jul.2026 13:36 | 1899-12-31 06:14 |  | 0.065972 | Closed | 0 | T: 5; O: 0; C: 5 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP (32712999) |  | 4 / 4 | [] |  |  | MET.32712999 | 13008286 | 2026-07-26 | Performed
| 698 | 575150-01-2-001 | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 19.Jul.2026 16:36 | 1900-01-05 22:36 |  | 0.61111 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP (32713008) |  | 4 / 4 | [] |  |  | MET.32713008 | 40000010 | 2026-07-26 | Performed
| 699 | 575150-01-2-002 | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP (32713016) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 29.Jul.2026 06:14 | 1899-12-31 00:02 |  | 0.34722 | Closed | 0 | T: 2; O: 0; C: 2 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.32713016 | 13008286 | 2026-07-30 | Performed
| 700 | 575158-01-5-001 | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 24.Jul.2026 15:48 | 1899-12-31 04:04 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP (25336910) |  | 4 / 4 | [] |  |  | MET.25336910 | 13008286 | 2026-07-26 | Performed
| 701 | 575158-01-5-002 | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP (25336066) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 29.Jul.2026 07:15 | 0.95903 |  | 0.25139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 4 / 4 | [] |  |  | MET.25336066 | 13008286 | 2026-07-30 | Performed
| 702 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.19444 | 17.Jul.2026 22:00 | 0.19444 | 31.Jul.2026 10:56 | 1899-12-31 06:42 |  | 1899-12-31 18:10 | Closed | 0 | T: 0; O: 0; C: 0 | 78-30 |  | [] |  |  |  |  | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. (26290436) |  | 3 / 3 | [] |  |  | MET.26290436 | 13008286 | 2026-08-02 | Performed
| 703 | 22586962 | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION | 22586962 / 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 10:20 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 22586962 / 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION (22586962) |  | 0 / 1 | [] |  |  | MET.22586962 | 40000929 | 2026-07-29 | Performed
| 704 | 23464908 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 | 23464908 / 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 10:30 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 23464908 / 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 (23464908) |  | 0 / 1 | [] |  |  | MET.23464908 | 40000929 | 2026-07-29 | Performed
| 705 | 31905379 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) | Single Running Taskcard | RI | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 17:31 | 1900-01-02 00:35 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) |  | 0 / 2 | [] |  |  | MET.31905379 | 13008286 | 2026-08-10 | Performed
| 706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 29294847 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29294847) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 | 22.Jul.2026 04:55 | 0.14931 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 1 / 5 |  | 0 / 1 | [] |  |  | ME.29294847 | 13003390 | 2026-08-10 | Performed
| 708 | 29749798 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 27.Jul.2026 16:26 | 1900-01-03 18:23 |  | 0.91667 | Closed | 0 | T: 0; O: 0; C: 0 | 23 |  | [] |  |  |  |  | 29749798 / EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI (29749798) |  | 0 / 4 | [] |  |  | ME.29749798 | 40000930 | 2026-08-02 | Performed
| 711 | 30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) | Document | AD | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 09.Aug.2026 06:49 | 0.12639 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 30970374 / EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT (30970374) |  | 0 / 4 | [] |  | 000 | ME.30970374 | 13003390 | 2026-08-10 | Performed
| 714 | 31889267 | EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66111 | 17.Jul.2026 22:00 | 0.6875 | 17.Aug.2026 13:04 | 1899-12-31 06:28 |  | 1900-01-02 22:10 | Closed | 0 | T: 0; O: 0; C: 0 | 27 |  | [] |  |  |  |  | 31889267 / EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. (31889267) |  | 0 / 12 | [] |  | 000 | ME.31889267 | 13008286 | 2026-08-19 | Performed
| 717 | 30482091 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 02:16 | 1899-12-31 05:19 |  | 0.875 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30482091 / EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 (30482091) |  | 0 / 6 | [] |  |  | ME.30482091 | 13003390 | 2026-08-10 | Performed
| 718 | 30481965 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20486 | 17.Jul.2026 22:00 | 0.20486 | 30.Jul.2026 10:20 | 1900-01-01 19:15 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 30481965 / EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 (30481965) |  | 0 / 6 | [] |  |  | ME.30481965 | 40000930 | 2026-08-02 | Performed
| 719 | 29155526 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 27.Jul.2026 09:51 | 0.12639 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155526 / EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE (29155526) |  | 0 / 6 | [] |  |  | ME.29155526 | 40000930 | 2026-08-02 | Performed
| 721 | 29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.10417 | 06.Aug.2026 07:05 | 1900-01-01 22:17 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 29155749 / EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX (29155749) |  | 0 / 6 | [] |  |  | ME.29155749 | 13009981 | 2026-08-09 | Performed
| 724 | 23745496 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.53125 | 17.Jul.2026 22:00 | 0.51042 | 03.Aug.2026 15:00 | 1900-01-14 19:25 |  | 0.95139 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  | In case of finding. Bring aircraft to the hangar to correct the finding. | 23745496 / EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C (23745496) |  | 0 / 3 | [] |  | S32SRT731LH | ME.23745496 | 13003390 | 2026-08-19 | Performed
| 730 | 29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.4375 | 26.Jul.2026 11:00 | 1900-01-13 00:16 |  | 1900-01-03 02:10 | Closed | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156039 / EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX (29156039) |  | 0 / 8 | [] |  |  | ME.29156039 | 13003390 | 2026-08-09 | Performed
| 731 | 29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.77083 | 17.Jul.2026 22:00 | 0.60417 | 27.Jul.2026 07:30 | 1900-01-13 23:46 |  | 1900-01-01 17:00 | Closed | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156133 / EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX (29156133) |  | 0 / 9 | [] |  |  | ME.29156133 | 13003081 | 2026-08-11 | Performed
| 732 | 29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) | Document | C | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 06.Aug.2026 17:21 | 1900-01-05 13:43 |  | 1899-12-31 01:00 | Closed | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156195 / EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU (29156195) |  | 0 / 5 | [] |  |  | ME.29156195 | 13009981 | 2026-08-13 | Performed
| 733 | 29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | 29157165 / EOD-320-46-00008-R00/FOMAX 4 ACTIVATION (29157165) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.14583 | 05.Aug.2026 05:53 | 0.23681 |  | 1899-12-31 01:15 | Closed | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29157165 / EOD-320-46-00008-R00/FOMAX 4 ACTIVATION (29157165) |  | 0 / 8 | [] |  |  | ME.29157165 | 40000929 | 2026-08-06 | Performed
| 734 | 29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.083333 | 04.Aug.2026 17:40 | 0.74583 |  | 0.71875 | Closed | 0 | T: 0; O: 0; C: 0 | 46 |  | [] |  |  |  |  | 29156249 / EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 (29156249) |  | 0 / 5 | [] |  |  | ME.29156249 | 13008286 | 2026-08-09 | Performed
| 749 | 32362499 | S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) | Document | ACHK | <html><span style="font-weight: normal;">No part requests</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 25.Jul.2026 23:42 | 0.44514 |  | 0.10833 | Closed | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] | --, --, --, CLOSE-UP |  |  |  | 32362499 / S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION (32362499) |  | 0 / 4 | [] |  |  | ME.32362499 | 13003390 | 2026-07-26 | Performed
| 752 | 30358131 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 11:53 | 0.21528 |  | 0.875 | Closed | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 30358131 / S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS (30358131) |  | 0 / 3 | [] |  |  | ME.30358131 | 13008286 | 2026-08-03 | Performed
| 763 | 31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) | Replacement Event | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:28 | 0.24931 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 31197928 / REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) (31197928) |  | 0 / 1 | [] |  | 100 | ME.31197928 | 13008286 | 2026-08-10 | Performed
| 764 | 26290429 | 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:43 | 1900-01-21 17:15 |  | 1900-01-01 01:35 | Closed | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 26290429 / 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK (26290429) |  | 0 / 3 | [] |  | 201 | ME.26290429 | 13003390 | 2026-08-19 | Performed
| 765 | 28781470 | 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:38 | 1900-01-19 22:21 |  | 1900-01-01 23:35 | Closed | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781470 / 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781470) |  | 0 / 3 | [] |  | 101 | ME.28781470 | 13008286 | 2026-08-20 | Performed
| 766 | 28781472 | 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 30.Jul.2026 08:34 | 1900-01-17 08:27 |  | 1900-01-01 21:30 | Closed | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 28781472 / 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK (28781472) |  | 0 / 3 | [] |  | 102 | ME.28781472 | 13008286 | 2026-08-20 | Performed
| 767 | 22574878 | 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.052083 | 27.Jul.2026 18:44 | 1900-01-19 22:23 |  | 1900-01-01 08:50 | Closed | 0 | T: 0; O: 0; C: 0 | 26-23 |  | [] |  |  |  |  | 22574878 / 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK (22574878) |  | 0 / 3 | [] |  | 000 | ME.22574878 | 13003390 | 2026-08-19 | Performed
| 768 | 23772081 | 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772081 / 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772081) | Part Requirement | CCHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 | 12.Aug.2026 17:21 | 0.047917 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 0 / 3 | [] |  | 002 | ME.23772081 | 13008286 | 2026-08-20 | Performed
| 769 | 23772080 | 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) | Part Requirement | CCHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.086806 | 17.Jul.2026 22:00 | 0.065972 | 12.Aug.2026 16:10 | 0.1375 |  | 0.16528 | Closed | 0 | T: 1; O: 0; C: 1 | 21-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 23772080 / 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK (23772080) |  | 0 / 3 | [] |  | 001 | ME.23772080 | 13008286 | 2026-08-20 | Performed
| 771 | 30304386 | CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.56667 | 17.Jul.2026 22:00 | 0.33403 | 27.Jul.2026 15:50 | 1899-12-31 17:12 |  | 1900-01-04 05:31 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP |  |  |  | 30304386 / CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB (30304386) |  | 0 / 7 | [] |  | ENG200 | ME.30304386 | 40000929 | 2026-08-10 | Performed
| 780 | 94740818 | BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 27.Apr.2026 10:57 | 1900-04-12 18:23 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 94740818 / BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN (94740818) |  | 0 / 1 | [] |  |  | WO.94740818 | 13009981 | 2026-08-09 | Performed
| 782 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.375 | 18.Jul.2026 13:46 | 0.51806 |  | 0.071528 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) |  | 9 / 9 | [] |  |  | JCA.32924592 | 13008286 | 2026-07-20 | Performed
| 786 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) | Jobcard | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.37847 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | STJC-20-00-00-06-A32S-SV / HEAVEY CHECK PRE-HANGAR PREPARATION (32924606) |  | 20 / 20 | [] |  |  | JCA.32924606 | 13003081 | 2026-08-03 | Performed
| 788 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 10:13 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | TC/P |  |  |  | STJC-20-00-00-08-A32S-SV / CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL (32924631) |  | 1 / 1 | [] |  |  | JCA.32924631 | 13008286 | 2026-08-18 | Performed
| 802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0013889 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:36 | 0.11944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) |  | 1 / 1 | [] |  |  | MET.32608234 | 13008286 | 2026-07-22 | Performed
| 813 | 32977683 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL | 32977683 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL (32977683) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 25.Jul.2026 06:28 | 1900-01-11 05:55 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977683 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL (32977683) |  | 0 / 1 | [] |  |  | WO.32977683 | 40000010 | 2026-08-06 | Performed
| 814 | 32977684 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 27.Jul.2026 15:39 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977684 / LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE (32977684) |  | 0 / 1 | [] |  |  | WO.32977684 | 40000010 | 2026-07-27 | Performed
| 815 | 32977685 | LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 08:32 | 0.083333 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977685 / LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA (32977685) |  | 0 / 1 | [] |  |  | WO.32977685 | 13003390 | 2026-08-10 | Performed
| 817 | 32977871 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 08:32 | 0.083333 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977871 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. (32977871) |  | 0 / 1 | [] |  |  | WO.32977871 | 13003390 | 2026-08-10 | Performed
| 818 | 32977873 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 09.Aug.2026 14:59 | 0.084028 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977873 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. (32977873) |  | 0 / 1 | [] |  |  | WO.32977873 | 13008286 | 2026-08-10 | Performed
| 819 | 32977874 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 03.Aug.2026 02:00 | 0.12569 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977874 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. (32977874) |  | 0 / 1 | [] |  |  | WO.32977874 | 40000929 | 2026-08-03 | Performed
| 820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 15:58 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) |  | 0 / 1 | [] |  |  | WO.32977881 | 13003390 | 2026-07-23 | Performed
| 821 | 32977882 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.16667 | 07.Aug.2026 09:13 | 1900-01-01 23:23 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977882 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. (32977882) |  | 0 / 1 | [] |  |  | WO.32977882 | 13003081 | 2026-08-18 | Performed
| 822 | 32977883 | PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:40 | 1900-01-21 06:50 |  | 1900-01-04 17:40 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977883 / PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH (32977883) |  | 0 / 1 | [] |  |  | WO.32977883 | 40000010 | 2026-08-10 | Performed
| 823 | 32977884 | PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 03:50 | 1900-01-24 10:30 |  | 1900-01-02 05:40 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977884 / PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH (32977884) |  | 0 / 1 | [] |  |  | WO.32977884 | 13003081 | 2026-08-13 | Performed
| 824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 12:12 | 0.16667 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) |  | 0 / 1 | [] |  |  | WO.32977904 | 13003390 | 2026-07-21 | Performed
| 825 | 32977905 | PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 05:46 | 0.27083 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977905 / PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. (32977905) |  | 0 / 1 | [] |  |  | WO.32977905 | 13003390 | 2026-08-03 | Performed
| 827 | 32977907 | PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 04:01 | 1900-01-19 05:03 |  | 1900-01-01 16:02 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977907 / PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. (32977907) |  | 0 / 2 | [] |  |  | WO.32977907 | 13008286 | 2026-08-20 | Performed
| 828 | 32977908 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. | 32977908 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. (32977908) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 28.Jul.2026 11:11 | 1900-01-06 03:49 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977908 / PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. (32977908) |  | 0 / 1 | [] |  |  | WO.32977908 | 13003390 | 2026-08-12 | Performed
| 829 | 32977909 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 11:19 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977909 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. (32977909) |  | 0 / 1 | [] |  |  | WO.32977909 | 40000930 | 2026-07-28 | Performed
| 830 | 32977910 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 24.Jul.2026 13:34 | 1900-01-14 15:50 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977910 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977910) |  | 0 / 1 | [] |  |  | WO.32977910 | 13009981 | 2026-08-09 | Performed
| 831 | 32977911 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 24.Jul.2026 04:24 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977911 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. (32977911) |  | 0 / 1 | [] |  |  | WO.32977911 | 13009981 | 2026-08-12 | Performed
| 832 | 32978070 | FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 09:05 | 1900-01-06 00:11 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 28-21 |  | [] |  |  |  |  | 32978070 / FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN (32978070) |  | 0 / 1 | [] |  | 01 | WO.32978070 | 13003081 | 2026-08-13 | Performed
| 833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 04:38 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) |  | 0 / 1 | [] |  |  | WO.32978236 | 13003390 | 2026-07-22 | Performed
| 834 | 32978238 | NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. | 32978238 / NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 06:55 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978238 / NLG DOOR---AP--NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. (32978238) |  | 0 / 1 | [] |  |  | WO.32978238 | 13008286 | 2026-08-17 | Performed
| 835 | 32978240 | NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 02.Aug.2026 06:15 | 1900-01-08 04:07 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978240 / NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. (32978240) |  | 0 / 1 | [] |  |  | WO.32978240 | 13003390 | 2026-08-11 | Performed
| 836 | 32978243 | NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 13:43 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978243 / NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN (32978243) |  | 0 / 1 | [] |  |  | WO.32978243 | 13008286 | 2026-07-26 | Performed
| 837 | 32978247 | NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 11:34 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978247 / NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. (32978247) |  | 0 / 1 | [] |  |  | WO.32978247 | 13003390 | 2026-08-02 | Performed
| 838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 05:29 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) |  | 0 / 1 | [] |  |  | WO.32978249 | 13003390 | 2026-07-22 | Performed
| 839 | 32978253 | LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:24 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978253 / LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. (32978253) |  | 0 / 1 | [] |  |  | WO.32978253 | 13008286 | 2026-07-26 | Performed
| 841 | 32978259 | LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. | 32978259 / LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 06:49 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978259 / LH MLG---AP NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. (32978259) |  | 0 / 1 | [] |  |  | WO.32978259 | 13008286 | 2026-08-17 | Performed
| 842 | 32978265 | LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. | 32978265 / LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. (32978265) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 18:04 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978265 / LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. (32978265) |  | 0 / 1 | [] |  |  | WO.32978265 | 13008286 | 2026-08-05 | Performed
| 843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 17:15 | 0.20903 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) |  | 0 / 1 | [] |  |  | WO.32978273 | 13008286 | 2026-07-22 | Performed
| 844 | 32978279 | RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:19 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978279 / RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. (32978279) |  | 0 / 1 | [] |  |  | WO.32978279 | 13008286 | 2026-07-26 | Performed
| 845 | 32978280 | MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 09:54 | 0.064583 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978280 / MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. (32978280) |  | 0 / 1 | [] |  |  | WO.32978280 | 13003390 | 2026-08-02 | Performed
| 846 | 32978281 | RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. | 32978281 / RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. (32978281) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 18:09 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978281 / RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. (32978281) |  | 0 / 1 | [] |  |  | WO.32978281 | 13008286 | 2026-08-05 | Performed
| 848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:59 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) |  | 0 / 1 | [] |  |  | WO.32978291 | 13008286 | 2026-07-21 | Performed
| 849 | 32978481 | RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 28.Jul.2026 04:30 | 0.28264 |  | 0.39583 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] |  |  |  |  | 32978481 / RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. (32978481) |  | 0 / 1 | [] |  |  | WO.32978481 | 13003390 | 2026-07-28 | Performed
| 853 | 32978510 | FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 11:00 | 1900-01-27 05:32 |  | 1900-01-02 02:49 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978510 / FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. (32978510) |  | 0 / 2 | [] |  |  | WO.32978510 | 13003081 | 2026-08-18 | Performed
| 854 | 32978546 | FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 03:20 | 1900-01-18 05:56 |  | 1900-01-01 14:59 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978546 / FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. (32978546) |  | 0 / 2 | [] |  |  | WO.32978546 | 13008286 | 2026-08-20 | Performed
| 855 | 32978563 | FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 27.Jul.2026 02:00 | 1900-01-06 10:00 |  | 1900-01-01 05:40 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978563 / FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. (32978563) |  | 0 / 1 | [] |  |  | WO.32978563 | 13003081 | 2026-08-11 | Performed
| 856 | 32978565 | FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED | 32978565 / FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED (32978565) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 03:00 | 1900-01-12 06:00 |  | 1899-12-31 03:39 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978565 / FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED (32978565) |  | 0 / 1 | [] |  |  | WO.32978565 | 13003390 | 2026-08-04 | Performed
| 857 | 32978566 | FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. | 32978566 / FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. (32978566) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 20:40 | 1900-01-07 12:05 |  | 1899-12-31 05:40 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978566 / FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. (32978566) |  | 0 / 1 | [] |  |  | WO.32978566 | 13003390 | 2026-08-04 | Performed
| 858 | 32978568 | FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:33 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] |  |  |  |  | 32978568 / FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. (32978568) |  | 0 / 1 | [] |  |  | WO.32978568 | 40000010 | 2026-07-30 | Performed
| 859 | 32978570 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 28.Jul.2026 07:03 | 0.17708 |  | 0.67708 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978570 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY (32978570) |  | 0 / 1 | [] |  |  | WO.32978570 | 13003390 | 2026-07-28 | Performed
| 860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 21:01 | 0.14653 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) |  | 0 / 1 | [] |  |  | WO.32978583 | 13008286 | 2026-07-22 | Performed
| 861 | 32978585 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 11.Aug.2026 05:57 | 0.25833 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978585 / FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. (32978585) |  | 0 / 1 | [] |  |  | WO.32978585 | 13009981 | 2026-08-12 | Performed
| 862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 20:28 | 0.084722 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) |  | 0 / 1 | [] |  |  | WO.32978590 | 13008286 | 2026-07-22 | Performed
| 865 | 32978600 | FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. | 32978600 / FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. (32978600) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 04:00 | 1900-01-05 08:30 |  | 1899-12-31 09:30 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978600 / FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. (32978600) |  | 0 / 1 | [] |  |  | WO.32978600 | 40000930 | 2026-08-04 | Performed
| 866 | 32978626 | FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 05:37 | 1900-01-07 23:59 |  | 0.39583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978626 / FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. (32978626) |  | 0 / 1 | [] |  |  | WO.32978626 | 13008286 | 2026-08-11 | Performed
| 870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 16:18 | 0.25 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) |  | 0 / 1 | [] |  |  | WO.32978648 | 13008286 | 2026-07-22 | Performed
| 871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 21.Jul.2026 15:51 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) |  | 0 / 1 | [] |  |  | WO.32978649 | 13008286 | 2026-07-22 | Performed
| 872 | 32978650 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 25.Jul.2026 01:18 | 0.25 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978650 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY (32978650) |  | 0 / 1 | [] |  |  | WO.32978650 | 40000930 | 2026-07-26 | Performed
| 873 | 32978651 | AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. | 32978651 / AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Aug.2026 10:03 | 0.29028 |  | 0.39583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978651 / AFT CARGO DOOR---AP---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. (32978651) |  | 0 / 1 | [] |  |  | WO.32978651 | 40000010 | 2026-08-19 | Performed
| 874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 10:40 | 0.25 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) |  | 0 / 1 | [] |  |  | WO.32978848 | 40000010 | 2026-07-21 | Performed
| 875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-04 | 17.Jul.2026 22:00 | 0.27778 | 19.Jul.2026 03:10 | 1900-01-01 05:17 |  | 1900-01-04 00:30 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) |  | 0 / 1 | [] |  |  | WO.32978869 | 40000010 | 2026-07-21 | Performed
| 877 | 32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.91667 | 17.Jul.2026 22:00 | 0.22917 | 21.Jul.2026 01:47 | 1900-01-03 10:04 |  | 0.91667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978900 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED (32978900) |  | 0 / 1 | [] |  |  | WO.32978900 | 40000010 | 2026-07-26 | Performed
| 878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:00 | 1900-01-29 08:42 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) |  | 0 / 1 | [] |  |  | WO.32978919 | 40000010 | 2026-08-20 | Performed
| 879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 15:11 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) |  | 0 / 1 | [] |  |  | WO.32978925 | 40000010 | 2026-07-21 | Performed
| 880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:38 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) |  | 0 / 1 | [] |  |  | WO.32978965 | 40000930 | 2026-07-21 | Performed
| 881 | 32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 02:18 | 1900-01-03 09:41 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979121 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING (32979121) |  | 0 / 1 | [] |  |  | WO.32979121 | 40000010 | 2026-07-26 | Performed
| 882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 22.Jul.2026 14:02 | 0.12639 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) |  | 0 / 1 | [] |  |  | WO.32979157 | 13003390 | 2026-07-22 | Performed
| 883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:23 | 0.17083 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) |  | 0 / 1 | [] |  |  | WO.32979156 | 13008286 | 2026-07-21 | Performed
| 884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 06:43 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) |  | 0 / 1 | [] |  |  | WO.32979222 | 13008286 | 2026-07-21 | Performed
| 885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 04:06 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) |  | 0 / 1 | [] |  |  | WO.32979231 | 40000930 | 2026-07-21 | Performed
| 889 | 32979322 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN (32979322) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 17:00 | 1900-01-16 14:05 |  | 0.15278 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979322 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN (32979322) |  | 0 / 1 | [] |  |  | WO.32979322 | 13009981 | 2026-08-09 | Performed
| 890 | 32979401 | FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.20833 | 20.Jul.2026 19:00 | 1900-01-15 23:30 |  | 1900-01-02 06:30 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979401 / FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979401) |  | 0 / 3 | [] |  |  | WO.32979401 | 13003081 | 2026-08-11 | Performed
| 891 | 32979406 | FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 20.Jul.2026 19:00 | 1900-01-15 15:45 |  | 1899-12-31 16:40 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32979406 / FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. (32979406) |  | 0 / 3 | [] |  |  | WO.32979406 | 13003081 | 2026-08-11 | Performed
| 894 | 32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 03:52 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] |  |  |  |  | 32979661 / FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 (32979661) |  | 0 / 1 | [] |  |  | WO.32979661 | 13009981 | 2026-08-09 | Performed
| 895 | 32979731 | FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. | 32979731 / FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 05:27 | 0.11875 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32979731 / FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. (32979731) |  | 0 / 1 | [] |  |  | WO.32979731 | 13008286 | 2026-07-26 | Performed
| 896 | 32979723 | APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 03:35 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 36-12 |  | [] |  |  |  |  | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) |  | 0 / 1 | [] |  |  | WO.32979723 | 40000010 | 2026-07-19 | Performed
| 897 | 32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:25 | 1900-01-04 08:36 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979981 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE (32979981) |  | 0 / 1 | [] |  |  | WO.32979981 | 40000010 | 2026-07-26 | Performed
| 898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:26 | 0.33333 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) |  | 0 / 1 | [] |  |  | WO.32980018 | 40000010 | 2026-07-21 | Performed
| 899 | 32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 23:00 | 17.Jul.2026 22:00 | 0.29167 | 21.Jul.2026 01:48 | 1900-01-01 08:05 |  | 1899-12-31 23:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980020 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE (32980020) |  | 0 / 1 | [] |  |  | WO.32980020 | 40000010 | 2026-07-26 | Performed
| 900 | 32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-01 04:00 | 17.Jul.2026 22:00 | 1899-12-31 21:30 | 23.Jul.2026 04:16 | 1900-01-25 03:23 |  | 1900-01-01 04:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980022 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32980022) |  | 0 / 1 | [] |  |  | WO.32980022 | 40000010 | 2026-08-19 | Performed
| 901 | 32391506 | 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 | 02.Aug.2026 16:47 | 1900-01-12 17:45 |  | 0.11111 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32391506 / 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS (32391506) |  | 0 / 3 | [] |  | 002 | ME.32391506 | 13003081 | 2026-08-16 | Performed
| 902 | 32439904 | 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) | Part Requirement | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.048611 | 02.Aug.2026 15:23 | 1900-01-12 19:10 |  | 0.59722 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | JOB-SETUP, TC/P, TC/P |  |  |  | 32439904 / 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS (32439904) |  | 0 / 3 | [] |  | 2522GM | ME.32439904 | 13003081 | 2026-08-16 | Performed
| 911 | 94844836 | RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.14583 | 12.Jul.2026 07:49 | 1900-02-05 23:01 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 94844836 / RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED (94844836) |  | 0 / 1 | [] |  |  | WO.94844836 | 13008286 | 2026-08-20 | Performed
| 913 | 32345876 | EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 | 32345876 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345876) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.10417 | 17.Jul.2026 22:00 | 0.22222 | 05.Aug.2026 15:05 | 1899-12-31 01:45 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 11 |  | [] |  |  |  |  | 32345876 / EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 (32345876) |  | 0 / 5 | [] |  |  | ME.32345876 | 40000010 | 2026-08-06 | Performed
| 914 | 32850432 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) | Document | RON | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 09.Aug.2026 08:31 | 0.85694 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 21 |  | [] |  |  |  |  | 32850432 / EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA (32850432) |  | 0 / 6 | [] |  |  | ME.32850432 | 13003390 | 2026-08-10 | Performed
| 920 | 32822529 | S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 06.Aug.2026 03:27 | 0.085417 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 32822529 / S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. (32822529) |  | 0 / 2 | [] |  |  | ME.32822529 | 13008286 | 2026-08-09 | Performed
| 921 | 30205720 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) | Document | ACHK | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 | 29.Jul.2026 10:42 | 1900-01-10 21:45 |  | 0.11111 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] | INSPECTION |  |  |  | 30205720 / S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION (30205720) |  | 0 / 1 | [] |  |  | ME.30205720 | 13003390 | 2026-08-10 | Performed
| 924 | 32872501 | S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) | Document | LINE | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 15.Aug.2026 10:59 | 0.013194 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 36 |  | [] |  |  |  |  | 32872501 / S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS (32872501) |  | 0 / 3 | [] |  |  | ME.32872501 | 13003390 | 2026-08-15 | Performed
| 925 | 32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.0625 | 19.Jul.2026 12:05 | 0.18403 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 38 |  | [] |  |  |  |  | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) |  | 0 / 1 | [] |  |  | ME.32930830 | 13003390 | 2026-07-19 | Performed
| 927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 05:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) |  | 0 / 1 | [] |  |  | WO.32980031 | 40000930 | 2026-07-21 | Performed
| 931 | 32980071 | LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 11.Aug.2026 08:05 | 0.10417 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980071 / LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) (32980071) |  | 0 / 1 | [] |  |  | WO.32980071 | 13003390 | 2026-08-11 | Performed
| 932 | 32980080 | LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 11.Aug.2026 09:11 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980080 / LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) (32980080) |  | 0 / 1 | [] |  |  | WO.32980080 | 13003390 | 2026-08-11 | Performed
| 933 | 32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 04:16 | 1900-01-01 11:17 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980070 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY (32980070) |  | 0 / 1 | [] |  |  | WO.32980070 | 40000010 | 2026-07-26 | Performed
| 934 | 32980077 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. | 32980077 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. (32980077) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 11:09 | 1900-01-09 03:49 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980077 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. (32980077) |  | 0 / 1 | [] |  |  | WO.32980077 | 13003081 | 2026-08-04 | Performed
| 935 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 02.Aug.2026 17:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 12-22 |  | [] | TC/P |  |  |  | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB (32807083) |  | 1 / 1 | [] |  |  | MET.32807083 | 13008286 | 2026-08-03 | Performed
| 936 | 32980091 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 07:55 | 0.05625 |  | 0.12847 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980091 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. (32980091) |  | 0 / 1 | [] |  |  | WO.32980091 | 13003390 | 2026-08-02 | Performed
| 938 | 32980083 | LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 06:47 | 1900-01-08 00:04 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32980083 / LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 (32980083) |  | 0 / 1 | [] |  |  | WO.32980083 | 13008286 | 2026-08-19 | Performed
| 940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14583 | 21.Jul.2026 15:12 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) |  | 0 / 1 | [] |  |  | WO.32980087 | 40000010 | 2026-07-21 | Performed
| 942 | 32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 05:00 | 17.Jul.2026 22:00 | 0.27083 | 20.Jul.2026 03:27 | 1900-01-04 08:38 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980133 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE (32980133) |  | 0 / 1 | [] |  |  | WO.32980133 | 40000010 | 2026-07-26 | Performed
| 946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:11 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) |  | 0 / 1 | [] |  |  | WO.32980135 | 13003390 | 2026-07-22 | Performed
| 949 | 32980140 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 19.Aug.2026 17:16 | 0.11458 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980140 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. (32980140) |  | 0 / 1 | [] |  |  | WO.32980140 | 13008286 | 2026-08-20 | Performed
| 950 | 32980164 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 19.Aug.2026 15:02 | 0.20972 |  | 0.9375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980164 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. (32980164) |  | 0 / 1 | [] |  |  | WO.32980164 | 13008286 | 2026-08-20 | Performed
| 952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:37 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) |  | 0 / 1 | [] |  |  | WO.32980177 | 13008286 | 2026-07-21 | Performed
| 954 | 32980176 | REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 11.Aug.2026 07:08 | 0.020833 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32980176 / REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) (32980176) |  | 0 / 1 | [] |  |  | WO.32980176 | 13008286 | 2026-08-12 | Performed
| 955 | 32980920 | FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 04:40 | 1900-01-13 06:15 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 32980920 / FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. (32980920) |  | 0 / 1 | [] |  |  | WO.32980920 | 13008286 | 2026-08-10 | Performed
| 958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:14 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) |  | 0 / 1 | [] |  |  | WO.32981716 | 13003390 | 2026-07-22 | Performed
| 959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 11:18 | 0.25069 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) |  | 0 / 1 | [] |  |  | WO.32981721 | 13003390 | 2026-07-22 | Performed
| 960 | 32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 19.Aug.2026 04:58 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981726 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING (32981726) |  | 0 / 1 | [] |  |  | WO.32981726 | 40000010 | 2026-08-19 | Performed
| 961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:25 | 0.125 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) |  | 0 / 1 | [] |  |  | WO.32981754 | 40000930 | 2026-07-21 | Performed
| 962 | 32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 15:52 | 1899-12-31 20:17 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981772 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. (32981772) |  | 0 / 1 | [] |  |  | WO.32981772 | 40000010 | 2026-07-26 | Performed
| 963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:28 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) |  | 0 / 1 | [] |  |  | WO.32981774 | 13003390 | 2026-07-22 | Performed
| 964 | 32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 08:30 | 17.Jul.2026 22:00 | 0.72917 | 03.Aug.2026 11:56 | 1899-12-31 03:48 |  | 1899-12-31 08:30 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981816 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. (32981816) |  | 0 / 1 | [] |  |  | WO.32981816 | 40000010 | 2026-08-19 | Performed
| 967 | 32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 12:20 | 0.090278 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) |  | 0 / 1 | [] |  |  | WO.32982191 | 13003390 | 2026-07-20 | Performed
| 975 | 32982253 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:34 | 0.78889 |  | 1900-01-01 18:30 | Closed | 0 | T: 6; O: 0; C: 6 | 27-84 |  | [] |  |  |  |  | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) |  | 0 / 1 | [] |  |  | WO.32982253 | 13003390 | 2026-07-20 | Performed
| 976 | 32982260 | R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:40 | 0.8125 |  | 1900-01-01 20:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-84 |  | [] |  |  |  |  | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) |  | 0 / 1 | [] |  |  | WO.32982260 | 13003390 | 2026-07-20 | Performed
| 977 | 32982263 | BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 03:00 | 0.38889 |  | 0.66319 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] |  |  |  |  | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) |  | 0 / 1 | [] |  |  | WO.32982263 | 13003390 | 2026-07-20 | Performed
| 978 | 32983857 | PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 12:00 | 1900-01-22 20:34 |  | 1899-12-31 07:10 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32983857 / PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. (32983857) |  | 0 / 2 | [] |  |  | WO.32983857 | 13008286 | 2026-08-17 | Performed
| 979 | 32983861 | PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 14.Aug.2026 09:39 | 1899-12-31 00:34 |  | 0.41736 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983861 / PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. (32983861) |  | 0 / 1 | [] |  |  | WO.32983861 | 13003390 | 2026-08-15 | Performed
| 980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 18:11 | 0.16736 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) |  | 0 / 1 | [] |  |  | WO.32983866 | 13008286 | 2026-07-22 | Performed
| 981 | 32983876 | PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. | 32983876 / PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. (32983876) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 04.Aug.2026 18:12 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983876 / PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. (32983876) |  | 0 / 1 | [] |  |  | WO.32983876 | 13008286 | 2026-08-05 | Performed
| 982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:11 | 0.10417 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) |  | 0 / 1 | [] |  |  | WO.32983882 | 13003390 | 2026-07-23 | Performed
| 983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 23.Jul.2026 13:45 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) |  | 0 / 1 | [] |  |  | WO.32983893 | 13003390 | 2026-07-23 | Performed
| 985 | 32983897 | PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. | 32983897 / PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. (32983897) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 13:47 | 0.25 |  | 0.75 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983897 / PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. (32983897) |  | 0 / 1 | [] |  |  | WO.32983897 | 13008286 | 2026-08-05 | Performed
| 986 | 32983910 | PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 24.Jul.2026 23:49 | 1900-01-04 05:33 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983910 / PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. (32983910) |  | 0 / 1 | [] |  |  | WO.32983910 | 13008286 | 2026-07-30 | Performed
| 987 | 32983929 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 19.Aug.2026 14:44 | 0.21875 |  | 0.6875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983929 / PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. (32983929) |  | 0 / 1 | [] |  |  | WO.32983929 | 13008286 | 2026-08-20 | Performed
| 990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) |  | 0 / 1 | [] |  |  | WO.32983950 | 13003390 | 2026-07-23 | Performed
| 991 | 32983948 | OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 05:25 | 1900-01-16 00:51 |  | 1899-12-31 08:30 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32983948 / OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS (32983948) |  | 0 / 1 | [] |  |  | WO.32983948 | 13009981 | 2026-08-09 | Performed
| 993 | 32984016 | OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) | 32984016 / OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) (32984016) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 08:01 | 1900-01-05 22:34 |  | 0.38889 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984016 / OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) (32984016) |  | 0 / 1 | [] |  |  | WO.32984016 | 40000930 | 2026-08-04 | Performed
| 994 | 32984140 | AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 07:37 | 1900-01-09 03:02 |  | 0.43056 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984140 / AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED (32984140) |  | 0 / 1 | [] |  |  | WO.32984140 | 13008286 | 2026-08-20 | Performed
| 995 | 32984158 | PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 14:50 | 1900-01-04 14:40 |  | 0.1875 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 32984158 / PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED (32984158) |  | 0 / 1 | [] |  |  | WO.32984158 | 13003390 | 2026-07-27 | Performed
| 996 | 32984174 | PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 08:08 | 0.050694 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32984174 / PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. (32984174) |  | 0 / 1 | [] |  |  | WO.32984174 | 13003390 | 2026-08-10 | Performed
| 997 | 32984360 | FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 09:34 | 1900-01-18 04:31 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984360 / FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 (32984360) |  | 0 / 1 | [] |  |  | WO.32984360 | 13008286 | 2026-08-19 | Performed
| 998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) |  | 0 / 1 | [] |  |  | WO.32984375 | 13008286 | 2026-07-21 | Performed
| 1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:46 | 0.60208 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) |  | 0 / 1 | [] |  |  | WO.32984479 | 13009981 | 2026-07-23 | Performed
| 1001 | 32984513 | R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 29.Jul.2026 11:01 | 0.96111 |  | 0.76042 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984513 / R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION (32984513) |  | 0 / 1 | [] |  |  | WO.32984513 | 40000010 | 2026-07-30 | Performed
| 1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:43 | 0.60347 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) |  | 0 / 1 | [] |  |  | WO.32984550 | 13009981 | 2026-07-23 | Performed
| 1007 | 32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 05:25 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984781 / CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984781) |  | 0 / 1 | [] |  |  | WO.32984781 | 13003390 | 2026-08-10 | Performed
| 1008 | 32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Aug.2026 04:44 | 0.096528 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984766 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L (32984766) |  | 0 / 1 | [] |  |  | WO.32984766 | 13008286 | 2026-08-18 | Performed
| 1010 | 32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Aug.2026 07:44 | 0.098611 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984820 / CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K (32984820) |  | 0 / 1 | [] |  |  | WO.32984820 | 13008286 | 2026-08-19 | Performed
| 1011 | 32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 05:20 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32984829 / CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. (32984829) |  | 0 / 1 | [] |  |  | WO.32984829 | 13003390 | 2026-08-10 | Performed
| 1012 | 32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 26.Jul.2026 20:20 | 1900-01-22 14:10 |  | 0.90972 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984848 / SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. (32984848) |  | 0 / 1 | [] |  |  | WO.32984848 | 13008286 | 2026-08-20 | Performed
| 1013 | 32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 08:36 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984883 / PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. (32984883) |  | 0 / 1 | [] |  |  | WO.32984883 | 13008286 | 2026-07-26 | Performed
| 1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 15:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) |  | 0 / 1 | [] |  |  | WO.32984905 | 13003390 | 2026-07-21 | Performed
| 1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 18:00 | 0.27847 |  | 0.44444 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) |  | 0 / 1 | [] |  |  | WO.32984942 | 13008286 | 2026-07-23 | Performed
| 1017 | 32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 25.Jul.2026 01:00 | 0.16736 |  | 0.16736 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984945 / PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. (32984945) |  | 0 / 1 | [] |  |  | WO.32984945 | 40000930 | 2026-07-28 | Performed
| 1018 | 32984975 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 26.Jul.2026 07:59 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32984975 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. (32984975) |  | 0 / 1 | [] |  |  | WO.32984975 | 13003390 | 2026-07-26 | Performed
| 1019 | 32984986 | AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 15.Aug.2026 09:21 | 1899-12-31 23:17 |  | 0.89583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32984986 / AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK (32984986) |  | 0 / 1 | [] |  |  | WO.32984986 | 13008286 | 2026-08-19 | Performed
| 1020 | 32984983 | PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. | 32984983 / PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. (32984983) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 08:01 | 1900-01-02 02:16 |  | 0.64583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32984983 / PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. (32984983) |  | 0 / 1 | [] |  |  | WO.32984983 | 13003390 | 2026-08-05 | Performed
| 1022 | 32985009 | PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 25.Jul.2026 00:48 | 1900-01-04 04:27 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985009 / PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. (32985009) |  | 0 / 1 | [] |  |  | WO.32985009 | 13008286 | 2026-07-30 | Performed
| 1023 | 32984981 | DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... | 32984981 / DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... (32984981) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 04:28 | 1900-01-10 05:29 |  | 0.22014 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32984981 / DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... (32984981) |  | 0 / 1 | [] |  |  | WO.32984981 | 13003390 | 2026-08-04 | Performed
| 1024 | 32985016 | PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 07:33 | 0.17361 |  | 0.12153 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985016 / PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. (32985016) |  | 0 / 1 | [] |  |  | WO.32985016 | 13003390 | 2026-07-26 | Performed
| 1025 | 32985033 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. | 32985033 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. (32985033) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 05.Aug.2026 01:10 | 0.35694 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985033 / PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. (32985033) |  | 0 / 1 | [] |  |  | WO.32985033 | 13003390 | 2026-08-11 | Performed
| 1026 | 32985022 | --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 20.Jul.2026 11:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 53-79 |  | [] |  |  |  |  | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) |  | 0 / 1 | [] |  |  | WO.32985022 | 13003390 | 2026-07-20 | Performed
| 1027 | 32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 08:11 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985067 / CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. (32985067) |  | 0 / 1 | [] |  |  | WO.32985067 | 13008286 | 2026-08-11 | Performed
| 1028 | 32985066 | PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 22:24 | 1900-01-05 08:43 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985066 / PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. (32985066) |  | 0 / 1 | [] |  |  | WO.32985066 | 13008286 | 2026-07-30 | Performed
| 1029 | 32985072 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:00 | 1900-01-13 23:45 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985072 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. (32985072) |  | 0 / 1 | [] |  |  | WO.32985072 | 13009981 | 2026-08-09 | Performed
| 1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 06:58 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) |  | 0 / 1 | [] |  |  | WO.32985081 | 13008286 | 2026-07-21 | Performed
| 1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 15:15 | 0.076389 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) |  | 0 / 1 | [] |  |  | WO.32985124 | 13003390 | 2026-07-23 | Performed
| 1034 | 32985127 | CAB - RII - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 32985127 / CAB - RII - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 03.Aug.2026 02:36 | 1899-12-31 06:58 |  | 0.10764 | Closed | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] |  |  |  |  | 32985127 / CAB - RII - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. (32985127) |  | 0 / 1 | [] |  |  | WO.32985127 | 13003390 | 2026-08-04 | Performed
| 1035 | 32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 32985290 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT (32985290) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985290 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT (32985290) |  | 0 / 1 | [] |  |  | WO.32985290 | 40000929 | 2026-08-06 | Performed
| 1037 | 32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 32985321 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985321) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985321 / CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985321) |  | 0 / 1 | [] |  |  | WO.32985321 | 40000929 | 2026-08-06 | Performed
| 1039 | 32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:43 | 0.088194 |  | 0.24306 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985334 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985334) |  | 0 / 1 | [] |  |  | WO.32985334 | 13008286 | 2026-07-26 | Performed
| 1040 | 32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:22 | 0.10625 |  | 0.25694 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985336 / PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED (32985336) |  | 0 / 1 | [] |  |  | WO.32985336 | 13008286 | 2026-07-26 | Performed
| 1041 | 32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 14:41 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985337 / CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT (32985337) |  | 0 / 1 | [] |  |  | WO.32985337 | 13003390 | 2026-08-02 | Performed
| 1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:56 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) |  | 0 / 1 | [] |  |  | WO.32985338 | 13003390 | 2026-07-22 | Performed
| 1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:05 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) |  | 0 / 1 | [] |  |  | WO.32985341 | 13003390 | 2026-07-22 | Performed
| 1044 | 32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985342 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED (32985342) |  | 0 / 1 | [] |  |  | WO.32985342 | 13008286 | 2026-07-26 | Performed
| 1046 | 32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 32985344 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED (32985344) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985344 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED (32985344) |  | 0 / 1 | [] |  |  | WO.32985344 | 40000929 | 2026-08-06 | Performed
| 1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:04 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) |  | 0 / 1 | [] |  |  | WO.32985347 | 13003390 | 2026-07-22 | Performed
| 1048 | 32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 32985349 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985349) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985349 / CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT (32985349) |  | 0 / 1 | [] |  |  | WO.32985349 | 40000929 | 2026-08-06 | Performed
| 1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:47 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) |  | 0 / 1 | [] |  |  | WO.32985351 | 13003390 | 2026-07-22 | Performed
| 1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:40 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) |  | 0 / 1 | [] |  |  | WO.32985352 | 13003390 | 2026-07-22 | Performed
| 1052 | 32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 15:43 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985353 / CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985353) |  | 0 / 1 | [] |  |  | WO.32985353 | 13003390 | 2026-08-02 | Performed
| 1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:21 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) |  | 0 / 1 | [] |  |  | WO.32985355 | 13003390 | 2026-07-22 | Performed
| 1055 | 32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 14:57 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985357 / CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT (32985357) |  | 0 / 1 | [] |  |  | WO.32985357 | 13003390 | 2026-08-02 | Performed
| 1056 | 32985503 | VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 24.Jul.2026 16:25 | 1900-01-01 00:42 |  | 0.52083 | Closed | 0 | T: 0; O: 0; C: 0 | 27-21 |  | [] |  |  |  |  | 32985503 / VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP (32985503) |  | 0 / 1 | [] |  |  | WO.32985503 | 13008286 | 2026-07-27 | Performed
| 1057 | 32985575 | RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 11:00 | 0.3125 |  | 0.79514 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] |  |  |  |  | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) |  | 0 / 1 | [] |  |  | WO.32985575 | 13003390 | 2026-07-20 | Performed
| 1058 | 32985619 | ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 15:20 | 0.055556 |  | 0.10764 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPEN-UP |  |  |  | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) |  | 0 / 1 | [] |  |  | WO.32985619 | 13003390 | 2026-07-20 | Performed
| 1059 | 32985582 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 14:20 | 0.090278 |  | 0.16667 | Closed | 0 | T: 3; O: 0; C: 3 | 57-41 |  | [] | OPEN-UP |  |  |  | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) |  | 0 / 1 | [] |  |  | WO.32985582 | 13003390 | 2026-07-20 | Performed
| 1060 | 32985655 | BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 16:35 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] |  |  |  |  | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) |  | 0 / 1 | [] |  |  | WO.32985655 | 13003390 | 2026-07-20 | Performed
| 1063 | 32985836 | RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 27.Jul.2026 10:12 | 1900-01-23 04:20 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985836 / RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED (32985836) |  | 0 / 1 | [] |  |  | WO.32985836 | 40000010 | 2026-08-20 | Performed
| 1064 | 32985860 | L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 27.Jul.2026 10:13 | 1900-01-21 08:24 |  | 0.85417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985860 / L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED (32985860) |  | 0 / 1 | [] |  |  | WO.32985860 | 13008286 | 2026-08-19 | Performed
| 1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 22.Jul.2026 03:13 | 1899-12-31 06:00 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) |  | 0 / 1 | [] |  |  | WO.32985861 | 13009981 | 2026-07-23 | Performed
| 1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 20:37 | 0.52431 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) |  | 0 / 1 | [] |  |  | WO.32985871 | 13009981 | 2026-07-23 | Performed
| 1067 | 32985872 | THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 05:22 | 0.20903 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985872 / THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY (32985872) |  | 0 / 1 | [] |  |  | WO.32985872 | 40000930 | 2026-07-26 | Performed
| 1068 | 32985870 | L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH | 32985870 / L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH (32985870) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 11:00 | 1900-01-04 19:50 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985870 / L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH (32985870) |  | 0 / 1 | [] |  |  | WO.32985870 | 13003390 | 2026-08-04 | Performed
| 1069 | 32985875 | ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 07:52 | 0.16042 |  | 0.66875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985875 / ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985875) |  | 0 / 1 | [] |  |  | WO.32985875 | 13003390 | 2026-07-28 | Performed
| 1070 | 32985877 | ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 07:08 | 0.19028 |  | 0.20972 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985877 / ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. (32985877) |  | 0 / 1 | [] |  |  | WO.32985877 | 13003390 | 2026-07-28 | Performed
| 1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 19:30 | 0.68056 |  | 1899-12-31 04:50 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | OPEN-UP |  |  |  | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) |  | 0 / 1 | [] |  |  | WO.32985880 | 40000930 | 2026-07-22 | Performed
| 1072 | 32986985 | PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. | 32986985 / PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. (32986985) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 16:40 | 1900-01-16 01:15 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32986985 / PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. (32986985) |  | 0 / 1 | [] |  |  | WO.32986985 | 13003081 | 2026-08-18 | Performed
| 1073 | 32987001 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO#26`191`406 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE AT FLAP RIB STATION 4 WITH MULTIPL... | 32987001 / DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO#26`191`406 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE AT FLAP RIB STATION 4 WITH MULTIPL... (32987001) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 04:48 | 1900-01-06 01:12 |  | 0.45139 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987001 / DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO#26`191`406 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE AT FLAP RIB STATION 4 WITH MULTIPL... (32987001) |  | 0 / 1 | [] |  |  | WO.32987001 | 13003390 | 2026-08-04 | Performed
| 1074 | 32987040 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO# 26191411 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS UPPER SKIN SURFACE 9 INCHES FROM THE TRAILING EDGE OF THE INBOARD FLAP AT... | 32987040 / DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO# 26191411 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS UPPER SKIN SURFACE 9 INCHES FROM THE TRAILING EDGE OF THE INBOARD FLAP AT... (32987040) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 05:08 | 1900-01-06 01:02 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987040 / DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO# 26191411 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS UPPER SKIN SURFACE 9 INCHES FROM THE TRAILING EDGE OF THE INBOARD FLAP AT... (32987040) |  | 0 / 1 | [] |  |  | WO.32987040 | 13003390 | 2026-08-04 | Performed
| 1076 | 32987146 | AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS | 32987146 / AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS (32987146) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 28.Jul.2026 02:00 | 0.33542 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 32987146 / AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS (32987146) |  | 0 / 1 | [] |  |  | WO.32987146 | 13003390 | 2026-07-28 | Performed
| 1078 | 32987238 | LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. | 32987238 / LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. (32987238) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 16:54 | 1900-01-18 15:41 |  | 0.9375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32987238 / LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. (32987238) |  | 0 / 1 | [] |  |  | WO.32987238 | 13003081 | 2026-08-12 | Performed
| 1079 | 32987295 | PRE---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW WEATHER SEAL UPPER AREA FOUND WITH MISSING MATERIAL/WORNOUT AND AFT LOWER AREA FOUND WITH OLD IMPROPER REPAIR. | 32987295 / PRE---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW WEATHER SEAL UPPER AREA FOUND WITH MISSING MATERIAL/WORNOUT AND AFT LOWER AREA FOUND WITH OLD IMPROPER REPAIR. (32987295) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 08:20 | 1900-01-11 10:16 |  | 0.23333 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987295 / PRE---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW WEATHER SEAL UPPER AREA FOUND WITH MISSING MATERIAL/WORNOUT AND AFT LOWER AREA FOUND WITH OLD IMPROPER REPAIR. (32987295) |  | 0 / 1 | [] |  |  | WO.32987295 | 13008286 | 2026-08-05 | Performed
| 1080 | 32987301 | DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 07:06 | 1900-01-17 00:34 |  | 0.23611 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) |  | 0 / 1 | [] |  |  | WO.32987301 | 13003390 | 2026-08-10 | Performed
| 1081 | 32987455 | PRE---F/O SLIDING WINDOW---RII---AP R/H SIDE F/O SLIDING WINDOW OUTER SURFACE AFT UPPER AND LOWER WEATHER SEAL FOUND DAMAGE. | 32987455 / PRE---F/O SLIDING WINDOW---RII---AP R/H SIDE F/O SLIDING WINDOW OUTER SURFACE AFT UPPER AND LOWER WEATHER SEAL FOUND DAMAGE. (32987455) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 17:31 | 1899-12-31 00:59 |  | 0.21458 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987455 / PRE---F/O SLIDING WINDOW---RII---AP R/H SIDE F/O SLIDING WINDOW OUTER SURFACE AFT UPPER AND LOWER WEATHER SEAL FOUND DAMAGE. (32987455) |  | 0 / 1 | [] |  |  | WO.32987455 | 13008286 | 2026-08-05 | Performed
| 1082 | 94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | 94844868 / L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. (94844868) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 15.Jul.2026 17:19 | 1900-01-30 19:04 |  | 1899-12-31 12:35 | Closed | 0 | T: 0; O: 0; C: 0 | 52 | WO transferred DD NOT STR Damage | [] |  |  |  |  | 94844868 / L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. (94844868) |  | 0 / 5 | [] |  |  | WO.94844868 | 13008286 | 2026-08-17 | Performed
| 1083 | 32968390 | S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) | 32968390 / S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) (32968390) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.024306 | 17.Jul.2026 22:00 | 0.017361 | 13.Aug.2026 05:48 | 0.17569 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] |  |  |  |  | 32968390 / S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) (32968390) |  | 0 / 3 | [] |  |  | ME.32968390 | 13003390 | 2026-08-14 | Performed
| 1088 | 32987715 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD OUTER SURFACE UPPER SURFACE WEATHER SEAL FOUND WITH IMPROPER REPAIR APPLICATION AND R/H SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR. | 32987715 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD OUTER SURFACE UPPER SURFACE WEATHER SEAL FOUND WITH IMPROPER REPAIR APPLICATION AND R/H SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR. (32987715) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 15:20 | 0.13333 |  | 0.18958 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987715 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD OUTER SURFACE UPPER SURFACE WEATHER SEAL FOUND WITH IMPROPER REPAIR APPLICATION AND R/H SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR. (32987715) |  | 0 / 1 | [] |  |  | WO.32987715 | 13008286 | 2026-08-05 | Performed
| 1089 | 32987725 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 06:51 | 1900-01-04 21:49 |  | 0.034722 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) |  | 0 / 1 | [] |  |  | WO.32987725 | 13003390 | 2026-07-29 | Performed
| 1090 | 32987776 | --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 21.Jul.2026 03:00 | 0.97917 |  | 1899-12-31 05:00 | Closed | 0 | T: 1; O: 0; C: 1 | 11-21 |  | [] |  |  |  |  | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) |  | 0 / 1 | [] |  |  | WO.32987776 | 40000930 | 2026-07-22 | Performed
| 1091 | 32987890 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`424 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 32987890 / DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`424 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... (32987890) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 05:28 | 1900-01-12 01:02 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987890 / DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`424 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... (32987890) |  | 0 / 1 | [] |  |  | WO.32987890 | 13003390 | 2026-08-04 | Performed
| 1092 | 32987935 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`432 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 32987935 / DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`432 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... (32987935) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:30 | 1900-01-11 02:30 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987935 / DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`432 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... (32987935) |  | 0 / 1 | [] |  |  | WO.32987935 | 13003390 | 2026-08-04 | Performed
| 1093 | 32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:56 | 0.23333 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) |  | 0 / 1 | [] |  |  | WO.32987952 | 13008286 | 2026-07-23 | Performed
| 1094 | 32987951 | PRE---CPT SLIDING WINDOW---RII---AP L/H SIDE CPT SLIDING WINDOW OUTER SURFACE AFT AND LOWER SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR APPLICATION. | 32987951 / PRE---CPT SLIDING WINDOW---RII---AP L/H SIDE CPT SLIDING WINDOW OUTER SURFACE AFT AND LOWER SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR APPLICATION. (32987951) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 15:24 | 0.13125 |  | 0.16875 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987951 / PRE---CPT SLIDING WINDOW---RII---AP L/H SIDE CPT SLIDING WINDOW OUTER SURFACE AFT AND LOWER SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR APPLICATION. (32987951) |  | 0 / 1 | [] |  |  | WO.32987951 | 13008286 | 2026-08-05 | Performed
| 1095 | 32987959 | PRE---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW WEATHER SEAL AFT LOWER CORNER AREA FOUND DAMAGE. | 32987959 / PRE---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW WEATHER SEAL AFT LOWER CORNER AREA FOUND DAMAGE. (32987959) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 15:26 | 0.13056 |  | 0.21458 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987959 / PRE---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW WEATHER SEAL AFT LOWER CORNER AREA FOUND DAMAGE. (32987959) |  | 0 / 1 | [] |  |  | WO.32987959 | 13008286 | 2026-08-05 | Performed
| 1096 | 32987947 | DBC/DOCUMENT S51-R10008- LH WING--RII--SM REF TO WO#26191340 DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE BETWEEN FLAP RIB STATION 6 TO 7 WITH MULTIPLE SMALL DENTS LARGEST DIMENSIO... | 32987947 / DBC/DOCUMENT S51-R10008- LH WING--RII--SM REF TO WO#26191340 DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE BETWEEN FLAP RIB STATION 6 TO 7 WITH MULTIPLE SMALL DENTS LARGEST DIMENSIO... (32987947) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:20 | 1900-01-11 01:40 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987947 / DBC/DOCUMENT S51-R10008- LH WING--RII--SM REF TO WO#26191340 DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE BETWEEN FLAP RIB STATION 6 TO 7 WITH MULTIPLE SMALL DENTS LARGEST DIMENSIO... (32987947) |  | 0 / 1 | [] |  |  | WO.32987947 | 13003390 | 2026-08-04 | Performed
| 1097 | 32987964 | DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 08:32 | 1900-01-03 00:57 |  | 0.13194 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) |  | 0 / 1 | [] |  |  | WO.32987964 | 13008286 | 2026-07-27 | Performed
| 1098 | 32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:29 | 0.25 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) |  | 0 / 1 | [] |  |  | WO.32987966 | 13008286 | 2026-07-23 | Performed
| 1099 | 32987973 | DBC/DOCUMENT S51-R10008- RH WING--RII--SM REF TO WO#26`191`414 DURING COMPLIANCE OF RH WING DBC SCANNING FOUND RH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE SECTION BETWEEN FLAP RIB STATION 4 TO 5 WITH MULTIPLE SMALL DENTS LARGES... | 32987973 / DBC/DOCUMENT S51-R10008- RH WING--RII--SM REF TO WO#26`191`414 DURING COMPLIANCE OF RH WING DBC SCANNING FOUND RH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE SECTION BETWEEN FLAP RIB STATION 4 TO 5 WITH MULTIPLE SMALL DENTS LARGES... (32987973) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:10 | 1900-01-09 05:41 |  | 0.25694 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987973 / DBC/DOCUMENT S51-R10008- RH WING--RII--SM REF TO WO#26`191`414 DURING COMPLIANCE OF RH WING DBC SCANNING FOUND RH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE SECTION BETWEEN FLAP RIB STATION 4 TO 5 WITH MULTIPLE SMALL DENTS LARGES... (32987973) |  | 0 / 1 | [] |  |  | WO.32987973 | 13003390 | 2026-08-04 | Performed
| 1102 | 32987979 | DBC/DOCUMENT S51-R10008-RH HORIZONTAL STABILIZER LE- RII--SM REF TO WO#26`191`479 DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND RH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN THS RIB STATION 9 WITH MULTIPLE SMALL DEN... | 32987979 / DBC/DOCUMENT S51-R10008-RH HORIZONTAL STABILIZER LE- RII--SM REF TO WO#26`191`479 DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND RH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN THS RIB STATION 9 WITH MULTIPLE SMALL DEN... (32987979) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 04:00 | 1900-01-11 01:30 |  | 0.034722 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 32987979 / DBC/DOCUMENT S51-R10008-RH HORIZONTAL STABILIZER LE- RII--SM REF TO WO#26`191`479 DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND RH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN THS RIB STATION 9 WITH MULTIPLE SMALL DEN... (32987979) |  | 0 / 1 | [] |  |  | WO.32987979 | 13003390 | 2026-08-04 | Performed
| 1103 | 32988009 | PRE---L/H WING FIXED L/E---NOCALLBACK---AP L/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 32988009 / PRE---L/H WING FIXED L/E---NOCALLBACK---AP L/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. (32988009) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 04.Aug.2026 16:51 | 0.042361 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32988009 / PRE---L/H WING FIXED L/E---NOCALLBACK---AP L/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. (32988009) |  | 0 / 1 | [] |  |  | WO.32988009 | 13008286 | 2026-08-05 | Performed
| 1104 | 32988013 | PRE---R/H WING FIXED L/E---NOCALLBACK---AP R/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 32988013 / PRE---R/H WING FIXED L/E---NOCALLBACK---AP R/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. (32988013) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 03.Aug.2026 05:29 | 0.29514 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32988013 / PRE---R/H WING FIXED L/E---NOCALLBACK---AP R/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. (32988013) |  | 0 / 1 | [] |  |  | WO.32988013 | 13003390 | 2026-08-04 | Performed
| 1105 | 32988015 | PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED | 32988015 / PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED (32988015) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 29.Jul.2026 05:59 | 0.31944 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32988015 / PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED (32988015) |  | 0 / 1 | [] |  |  | WO.32988015 | 40000010 | 2026-07-29 | Performed
| 1106 | 32988202 | RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS | 32988202 / RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS (32988202) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 13.Aug.2026 12:28 | 1900-01-04 21:42 |  | 1899-12-31 12:40 | Closed | 0 | T: 0; O: 0; C: 0 | 27-24 |  | [] |  |  |  |  | 32988202 / RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS (32988202) |  | 0 / 1 | [] |  | E27ACT325RH | WO.32988202 | 13008286 | 2026-08-20 | Performed
| 1109 | 32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 32988470 / CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. (32988470) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 29.Jul.2026 11:22 | 0.125 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988470 / CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. (32988470) |  | 0 / 1 | [] |  |  | WO.32988470 | 13003390 | 2026-07-29 | Performed
| 1110 | 32988479 | CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ | 32988479 / CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ (32988479) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 05.Aug.2026 07:00 | 0.10417 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988479 / CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ (32988479) |  | 0 / 1 | [] |  |  | WO.32988479 | 40000929 | 2026-08-06 | Performed
| 1111 | 32988506 | CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED | 32988506 / CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED (32988506) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988506 / CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED (32988506) |  | 0 / 1 | [] |  |  | WO.32988506 | 40000929 | 2026-08-06 | Performed
| 1117 | 32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 32988794 / PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA (32988794) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 24.Jul.2026 06:28 | 1900-01-16 08:01 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32988794 / PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA (32988794) |  | 0 / 1 | [] |  |  | WO.32988794 | 13003390 | 2026-08-10 | Performed
| 1118 | 32988998 | PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. | 32988998 / PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. (32988998) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 11.Aug.2026 06:23 | 0.063889 |  | 0.35417 | Closed | 0 | T: 0; O: 0; C: 0 | 28-18 |  | [] |  |  |  |  | 32988998 / PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. (32988998) |  | 0 / 1 | [] |  |  | WO.32988998 | 13003390 | 2026-08-20 | Performed
| 1119 | 32989018 | PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:24 | 0.27153 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) |  | 0 / 1 | [] |  |  | WO.32989018 | 13008286 | 2026-07-23 | Performed
| 1120 | 32989039 | PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. | 32989039 / PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. (32989039) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 24.Jul.2026 19:10 | 1900-01-04 09:13 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989039 / PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. (32989039) |  | 0 / 1 | [] |  |  | WO.32989039 | 13008286 | 2026-07-30 | Performed
| 1122 | 32989105 | PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. | 32989105 / PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. (32989105) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 10:16 | 1900-01-18 08:47 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989105 / PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. (32989105) |  | 0 / 1 | [] |  |  | WO.32989105 | 13008286 | 2026-08-19 | Performed
| 1123 | 32989125 | PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. | 32989125 / PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. (32989125) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 10:06 | 1900-01-18 03:55 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32989125 / PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. (32989125) |  | 0 / 1 | [] |  |  | WO.32989125 | 13008286 | 2026-08-19 | Performed
| 1125 | 32989174 | BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:16 | 0.27083 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-56 |  | [] |  |  |  |  | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) |  | 0 / 1 | [] |  |  | WO.32989174 | 13008286 | 2026-07-23 | Performed
| 1130 | 32989476 | CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE | 32989476 / CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE (32989476) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 03:00 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 32989476 / CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE (32989476) |  | 0 / 1 | [] |  |  | WO.32989476 | 40000929 | 2026-08-06 | Performed
| 1134 | 32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 32989497 / CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED (32989497) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 06:23 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989497 / CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED (32989497) |  | 0 / 1 | [] |  |  | WO.32989497 | 13003390 | 2026-08-10 | Performed
| 1136 | 32989545 | L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. | 32989545 / L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. (32989545) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.27083 | 24.Jul.2026 11:03 | 1900-01-04 02:30 |  | 0.56597 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32989545 / L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. (32989545) |  | 0 / 1 | [] |  |  | WO.32989545 | 13008286 | 2026-07-30 | Performed
| 1137 | 32989556 | R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... | 32989556 / R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... (32989556) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 11:02 | 1900-01-27 04:50 |  | 1899-12-31 09:00 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32989556 / R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... (32989556) |  | 0 / 1 | [] |  |  | WO.32989556 | 13003390 | 2026-08-20 | Performed
| 1138 | 32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 32989575 / PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989575) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 15:40 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989575 / PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989575) |  | 0 / 1 | [] |  |  | WO.32989575 | 40000010 | 2026-07-28 | Performed
| 1139 | 32989577 | BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION | 32989577 / BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION (32989577) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.83333 | 17.Jul.2026 22:00 | 0.20833 | 23.Jul.2026 00:00 | 1900-01-02 09:45 |  | 0.93125 | Closed | 0 | T: 0; O: 0; C: 0 | 50-11-33 |  | [] |  |  |  |  | 32989577 / BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION (32989577) |  | 0 / 1 | [] |  | BULK CARGO COM | WO.32989577 | 13008286 | 2026-07-27 | Performed
| 1140 | 32989579 | AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. | 32989579 / AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. (32989579) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.625 | 17.Jul.2026 22:00 | 0.20833 | 30.Jul.2026 04:28 | 1900-01-03 03:05 |  | 0.50347 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989579 / AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. (32989579) |  | 0 / 1 | [] |  |  | WO.32989579 | 40000929 | 2026-08-03 | Performed
| 1142 | 32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 32989743 / CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING (32989743) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:20 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989743 / CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING (32989743) |  | 0 / 1 | [] |  |  | WO.32989743 | 13003390 | 2026-08-20 | Performed
| 1143 | 32989796 | CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY | 32989796 / CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY (32989796) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 05:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989796 / CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY (32989796) |  | 0 / 1 | [] |  |  | WO.32989796 | 40000929 | 2026-08-06 | Performed
| 1145 | 32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 32989800 / CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING (32989800) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:22 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989800 / CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING (32989800) |  | 0 / 1 | [] |  |  | WO.32989800 | 13003390 | 2026-08-20 | Performed
| 1148 | 32989854 | CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE | 32989854 / CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE (32989854) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 02:00 | 0.27083 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989854 / CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE (32989854) |  | 0 / 1 | [] |  |  | WO.32989854 | 13003081 | 2026-08-04 | Performed
| 1150 | 32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 32989874 / CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING (32989874) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:45 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989874 / CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING (32989874) |  | 0 / 1 | [] |  |  | WO.32989874 | 13003390 | 2026-08-20 | Performed
| 1151 | 32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 32989888 / PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989888) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 28.Jul.2026 15:42 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32989888 / PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT (32989888) |  | 0 / 1 | [] |  |  | WO.32989888 | 40000010 | 2026-07-28 | Performed
| 1152 | 32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:41 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) |  | 0 / 1 | [] |  |  | WO.32989938 | 13003390 | 2026-07-23 | Performed
| 1153 | 32989942 | #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 32989942 / #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32989942) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 17:23 | 1899-12-31 02:23 |  | 0.73264 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989942 / #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32989942) |  | 0 / 1 | [] |  | #2 ENG | WO.32989942 | 40000010 | 2026-07-28 | Performed
| 1155 | 32989944 | #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... | 32989944 / #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... (32989944) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 01.Aug.2026 06:14 | 0.084028 |  | 0.45833 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989944 / #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... (32989944) |  | 0 / 1 | [] |  | #2 ENG | WO.32989944 | 13008286 | 2026-08-20 | Performed
| 1157 | 32989954 | #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 32989954 / #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32989954) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:53 | 0.083333 |  | 0.083333 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989954 / #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32989954) |  | 0 / 1 | [] |  | #2 ENG | WO.32989954 | 40000010 | 2026-07-30 | Performed
| 1158 | 32989962 | #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 32989962 / #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32989962) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 11:00 | 1900-01-21 07:30 |  | 1899-12-31 16:30 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32989962 / #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32989962) |  | 0 / 1 | [] |  | #2 ENG | WO.32989962 | 13003390 | 2026-08-14 | Performed
| 1159 | 32989953 | FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 02:56 | 0.27222 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 11-35 |  | [] |  |  |  |  | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) |  | 0 / 1 | [] |  | UNDER FLOOR | WO.32989953 | 13003390 | 2026-07-22 | Performed
| 1160 | 32989963 | #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. | 32989963 / #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. (32989963) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 13:30 | 1900-01-16 00:22 |  | 0.32292 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989963 / #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. (32989963) |  | 0 / 1 | [] |  | #2 ENG | WO.32989963 | 13003390 | 2026-08-10 | Performed
| 1161 | 32989964 | #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . | 32989964 / #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . (32989964) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 28.Jul.2026 06:19 | 0.10417 |  | 0.27083 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32989964 / #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . (32989964) |  | 0 / 1 | [] |  | #2 ENG | WO.32989964 | 40000930 | 2026-07-28 | Performed
| 1162 | 32989965 | #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). | 32989965 / #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). (32989965) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 11:27 | 1900-01-08 18:51 |  | 0.10417 | Closed | 0 | T: 1; O: 0; C: 1 | 30-21 |  | [] |  |  |  |  | 32989965 / #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). (32989965) |  | 0 / 1 | [] |  | #2 ENG | WO.32989965 | 13008286 | 2026-08-20 | Performed
| 1164 | 32989967 | #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. | 32989967 / #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. (32989967) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 10.Aug.2026 07:28 | 1900-01-07 23:22 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 24-92 |  | [] |  |  |  |  | 32989967 / #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. (32989967) |  | 0 / 1 | [] |  | #2 ENG | WO.32989967 | 13008286 | 2026-08-19 | Performed
| 1167 | 32989975 | #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 32989975 / #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32989975) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 09:33 | 0.024306 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32989975 / #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32989975) |  | 0 / 1 | [] |  | #2 ENG | WO.32989975 | 13008286 | 2026-08-02 | Performed
| 1168 | 32989976 | #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . | 32989976 / #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . (32989976) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 10:17 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989976 / #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . (32989976) |  | 0 / 1 | [] |  | #2 ENG | WO.32989976 | 13003390 | 2026-08-11 | Performed
| 1169 | 32989982 | #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... | 32989982 / #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... (32989982) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 17:00 | 1900-01-15 18:30 |  | 0.38542 | Closed | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989982 / #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... (32989982) |  | 0 / 1 | [] |  | #2 ENG | WO.32989982 | 13008286 | 2026-08-20 | Performed
| 1172 | 32989994 | #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... | 32989994 / #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... (32989994) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 11:00 | 1900-01-16 00:20 |  | 0.26736 | Closed | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32989994 / #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... (32989994) |  | 0 / 1 | [] |  | #2 ENG | WO.32989994 | 13008286 | 2026-08-20 | Performed
| 1173 | 32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 22.Jul.2026 16:10 | 0.070139 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) |  | 0 / 1 | [] |  |  | WO.32990006 | 13003390 | 2026-07-22 | Performed
| 1175 | 32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL | 32990007 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL (32990007) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 17.Aug.2026 08:12 | 0.086111 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990007 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO:33L,34JL,35K,37JL (32990007) |  | 0 / 1 | [] |  |  | WO.32990007 | 13008286 | 2026-08-18 | Performed
| 1176 | 32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 32990011 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L (32990011) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 17.Aug.2026 08:13 | 0.086806 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990011 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L (32990011) |  | 0 / 1 | [] |  |  | WO.32990011 | 13008286 | 2026-08-18 | Performed
| 1177 | 32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 32990012 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C (32990012) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 18.Aug.2026 07:13 | 0.084722 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990012 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C (32990012) |  | 0 / 1 | [] |  |  | WO.32990012 | 13008286 | 2026-08-18 | Performed
| 1178 | 32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 32990013 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C (32990013) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 18.Aug.2026 07:21 | 0.12917 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990013 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C (32990013) |  | 0 / 1 | [] |  |  | WO.32990013 | 13008286 | 2026-08-18 | Performed
| 1179 | 32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B | 32990020 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B (32990020) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 18.Aug.2026 07:31 | 0.085417 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990020 / PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD NOT SECURED SEAT NO: 33B,C 32A,B,C AND 31A,B (32990020) |  | 0 / 1 | [] |  |  | WO.32990020 | 13008286 | 2026-08-18 | Performed
| 1180 | 32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 16:10 | 0.072917 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) |  | 0 / 1 | [] |  |  | WO.32990021 | 13003390 | 2026-07-22 | Performed
| 1181 | 32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:53 | 1899-12-31 06:50 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) |  | 0 / 1 | [] |  |  | WO.32990026 | 13003390 | 2026-07-23 | Performed
| 1182 | 32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 08:00 | 1899-12-31 05:44 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) |  | 0 / 1 | [] |  |  | WO.32990029 | 13003390 | 2026-07-23 | Performed
| 1183 | 32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:00 | 1899-12-31 06:42 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) |  | 0 / 1 | [] |  |  | WO.32990034 | 13003390 | 2026-07-23 | Performed
| 1184 | 32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:03 | 1899-12-31 06:41 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) |  | 0 / 1 | [] |  |  | WO.32990037 | 13003390 | 2026-07-23 | Performed
| 1185 | 32990036 | #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 32990036 / #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32990036) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 16:43 | 1900-01-03 03:02 |  | 1899-12-31 00:05 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] |  |  |  |  | 32990036 / #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . (32990036) |  | 0 / 1 | [] |  | #1 ENG | WO.32990036 | 40000010 | 2026-07-28 | Performed
| 1186 | 32990048 | #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... | 32990048 / #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... (32990048) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 05:00 | 1900-01-21 13:30 |  | 1900-01-03 20:35 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990048 / #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... (32990048) |  | 0 / 2 | [] |  | #1 ENG | WO.32990048 | 13008286 | 2026-08-20 | Performed
| 1187 | 32990053 | #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... | 32990053 / #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... (32990053) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 27.Jul.2026 08:00 | 1900-01-22 05:00 |  | 1899-12-31 05:44 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990053 / #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... (32990053) |  | 0 / 2 | [] |  | #1 ENG | WO.32990053 | 13008286 | 2026-08-20 | Performed
| 1188 | 32990054 | #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... | 32990054 / #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... (32990054) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 22.Jul.2026 11:00 | 1900-01-19 06:23 |  | 1899-12-31 03:10 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990054 / #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... (32990054) |  | 0 / 2 | [] |  | #1 ENG | WO.32990054 | 13008286 | 2026-08-20 | Performed
| 1189 | 32990067 | #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 32990067 / #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32990067) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 22.Jul.2026 15:00 | 1900-01-19 02:26 |  | 1899-12-31 11:30 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990067 / #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... (32990067) |  | 0 / 2 | [] |  | #1 ENG | WO.32990067 | 13008286 | 2026-08-20 | Performed
| 1190 | 32990167 | #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 32990167 / #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32990167) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:41 | 0.083333 |  | 0.083333 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990167 / #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . (32990167) |  | 0 / 1 | [] |  | #1 ENG | WO.32990167 | 40000010 | 2026-07-30 | Performed
| 1191 | 32990169 | #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. | 32990169 / #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. (32990169) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 04:22 | 1900-01-09 09:28 |  | 0.17708 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990169 / #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. (32990169) |  | 0 / 1 | [] |  | #1 ENG | WO.32990169 | 13003390 | 2026-08-10 | Performed
| 1193 | 32990171 | #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... | 32990171 / #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... (32990171) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 09:31 | 1900-01-20 09:58 |  | 1900-01-03 13:45 | Closed | 0 | T: 1; O: 0; C: 1 | 71-13 |  | [] |  |  |  |  | 32990171 / #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... (32990171) |  | 0 / 2 | [] |  | #1 ENG | WO.32990171 | 13008286 | 2026-08-20 | Performed
| 1194 | 32990173 | #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. | 32990173 / #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. (32990173) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 30.Jul.2026 13:57 | 1900-01-15 01:47 |  | 0.42708 | Closed | 0 | T: 1; O: 0; C: 1 | 24-92 |  | [] |  |  |  |  | 32990173 / #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. (32990173) |  | 0 / 1 | [] |  | #1 ENG | WO.32990173 | 13008286 | 2026-08-16 | Performed
| 1197 | 32990203 | #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 32990203 / #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32990203) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 09:05 | 0.025694 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] |  |  |  |  | 32990203 / #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . (32990203) |  | 0 / 1 | [] |  | #1 ENG | WO.32990203 | 13008286 | 2026-08-02 | Performed
| 1198 | 32990219 | #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... | 32990219 / #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... (32990219) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 27.Jul.2026 15:00 | 1900-01-15 20:10 |  | 0.42361 | Closed | 0 | T: 1; O: 0; C: 1 | 05-24 |  | [] |  |  |  |  | 32990219 / #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... (32990219) |  | 0 / 1 | [] |  | #1 ENG | WO.32990219 | 13008286 | 2026-08-20 | Performed
| 1203 | 32991517 | PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 32991517 / PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. (32991517) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 23.Jul.2026 14:37 | 1900-01-02 14:08 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32991517 / PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. (32991517) |  | 0 / 1 | [] |  |  | WO.32991517 | 40000930 | 2026-07-28 | Performed
| 1208 | 32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:33 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) |  | 0 / 1 | [] |  |  | WO.32991585 | 13003390 | 2026-07-22 | Performed
| 1211 | 32991646 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. | 32991646 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. (32991646) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:45 | 1900-01-28 01:34 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32991646 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. (32991646) |  | 0 / 1 | [] |  |  | WO.32991646 | 13008286 | 2026-08-20 | Performed
| 1212 | 32991651 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. | 32991651 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. (32991651) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:48 | 1900-01-28 01:26 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 32991651 / AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. (32991651) |  | 0 / 1 | [] |  |  | WO.32991651 | 13008286 | 2026-08-20 | Performed
| 1218 | 32992461 | MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. | 32992461 / MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. (32992461) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 03:30 | 0.44444 |  | 0.27778 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32992461 / MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. (32992461) |  | 0 / 1 | [] |  |  | WO.32992461 | 40000010 | 2026-08-19 | Performed
| 1226 | 32992522 | RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT | 32992522 / RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT (32992522) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 03:00 | 1900-01-03 00:10 |  | 1900-01-01 14:50 | Closed | 0 | T: 0; O: 0; C: 0 | 55-10-00 |  | [] |  |  |  |  | 32992522 / RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT (32992522) |  | 0 / 1 | [] |  |  | WO.32992522 | 40000929 | 2026-07-26 | Performed
| 1227 | 32992699 | CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING | 32992699 / CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING (32992699) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:30 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992699 / CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING (32992699) |  | 0 / 1 | [] |  |  | WO.32992699 | 13003390 | 2026-08-20 | Performed
| 1228 | 32992702 | CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING | 32992702 / CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING (32992702) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992702 / CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING (32992702) |  | 0 / 1 | [] |  |  | WO.32992702 | 13003390 | 2026-08-20 | Performed
| 1229 | 32992708 | CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING | 32992708 / CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING (32992708) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 08:39 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32992708 / CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING (32992708) |  | 0 / 1 | [] |  |  | WO.32992708 | 13003390 | 2026-08-20 | Performed
| 1236 | 32993162 | UPPER AFT FUSELAGE SKIN=====SM====RII ACCESS THRU VERTICAL STABILIZER LEADING EDGE PNL 321AL FUSELAGE SKIN AREA AROUND 02EA HARNESS CONNECTION (4202VB, 4204VB) FOUND WITH PITTING CORROSION AROUND THE WHOLE CIRCUMFERENCE MAXIMUM LENGTH = 0.9" | 32993162 / UPPER AFT FUSELAGE SKIN=====SM====RII ACCESS THRU VERTICAL STABILIZER LEADING EDGE PNL 321AL FUSELAGE SKIN AREA AROUND 02EA HARNESS CONNECTION (4202VB, 4204VB) FOUND WITH PITTING CORROSION AROUND THE WHOLE CIRCUMFERENCE MAXIMUM LENGTH = 0.9" (32993162) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 16:30 | 1900-01-22 12:37 |  | 1900-01-01 07:45 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 32993162 / UPPER AFT FUSELAGE SKIN=====SM====RII ACCESS THRU VERTICAL STABILIZER LEADING EDGE PNL 321AL FUSELAGE SKIN AREA AROUND 02EA HARNESS CONNECTION (4202VB, 4204VB) FOUND WITH PITTING CORROSION AROUND THE WHOLE CIRCUMFERENCE MAXIMUM LENGTH = 0.9" (32993162) |  | 0 / 3 | [] |  |  | WO.32993162 | 13008286 | 2026-08-17 | Performed
| 1237 | 32993180 | FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. | 32993180 / FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. (32993180) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:10 | 1900-01-01 13:20 |  | 0.28472 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 32993180 / FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. (32993180) |  | 0 / 1 | [] |  |  | WO.32993180 | 40000929 | 2026-07-26 | Performed
| 1238 | 32993201 | L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION | 32993201 / L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION (32993201) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.79167 | 17.Jul.2026 22:00 | 0.20833 | 25.Jul.2026 00:39 | 0.27153 |  | 0.54167 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] |  |  |  |  | 32993201 / L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION (32993201) |  | 0 / 1 | [] |  |  | WO.32993201 | 40000930 | 2026-07-26 | Performed
| 1239 | 32993252 | ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT | 32993252 / ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT (32993252) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 31.Jul.2026 18:14 | 0.083333 |  | 0.17708 | Closed | 0 | T: 0; O: 0; C: 0 | 54-50 |  | [] |  |  |  |  | 32993252 / ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT (32993252) |  | 0 / 1 | [] |  |  | WO.32993252 | 40000010 | 2026-08-02 | Performed
| 1240 | 32993255 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #5 OUT BOARD HINGE BONDING JUMPER BROKEN. | 32993255 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #5 OUT BOARD HINGE BONDING JUMPER BROKEN. (32993255) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 07:19 | 1900-01-05 22:58 |  | 0.51389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993255 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #5 OUT BOARD HINGE BONDING JUMPER BROKEN. (32993255) |  | 0 / 1 | [] |  |  | WO.32993255 | 40000010 | 2026-08-11 | Performed
| 1241 | 32993268 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #4 IN BOARD HINGE BONDING JUMPER BROKEN. | 32993268 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #4 IN BOARD HINGE BONDING JUMPER BROKEN. (32993268) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 28.Jul.2026 08:57 | 1900-01-05 21:25 |  | 0.34722 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993268 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #4 IN BOARD HINGE BONDING JUMPER BROKEN. (32993268) |  | 0 / 1 | [] |  |  | WO.32993268 | 40000010 | 2026-08-11 | Performed
| 1242 | 32993275 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. | 32993275 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. (32993275) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-17 19:00 |  | 1899-12-31 14:50 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993275 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. (32993275) |  | 0 / 1 | [] |  |  | WO.32993275 | 13003081 | 2026-08-11 | Performed
| 1243 | 32993277 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. | 32993277 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. (32993277) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-17 22:00 |  | 0.97222 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993277 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. (32993277) |  | 0 / 1 | [] |  |  | WO.32993277 | 13003081 | 2026-08-11 | Performed
| 1244 | 32993284 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. | 32993284 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. (32993284) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 11:00 | 1900-01-17 23:30 |  | 0.80556 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993284 / R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. (32993284) |  | 0 / 1 | [] |  |  | WO.32993284 | 13003081 | 2026-08-11 | Performed
| 1245 | 32993287 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN | 32993287 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN (32993287) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 17:47 | 1899-12-31 14:58 |  | 0.8875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993287 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN (32993287) |  | 0 / 1 | [] |  |  | WO.32993287 | 13003390 | 2026-08-11 | Performed
| 1246 | 32993288 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. | 32993288 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. (32993288) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 19:05 | 1900-01-09 12:42 |  | 0.69375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32993288 / R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. (32993288) |  | 0 / 1 | [] |  |  | WO.32993288 | 13003390 | 2026-08-11 | Performed
| 1247 | 32994020 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS | 32994020 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS (32994020) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 01:49 | 0.33403 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994020 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS (32994020) |  | 0 / 1 | [] |  |  | WO.32994020 | 40000010 | 2026-07-26 | Performed
| 1248 | 32994039 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS | 32994039 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS (32994039) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 23.Jul.2026 05:20 | 1900-01-01 13:24 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994039 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS (32994039) |  | 0 / 1 | [] |  |  | WO.32994039 | 40000010 | 2026-07-26 | Performed
| 1249 | 32994166 | FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:32 | 0.12153 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) |  | 0 / 1 | [] |  |  | WO.32994166 | 13003390 | 2026-07-23 | Performed
| 1251 | 32994173 | FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 02:00 | 0.35139 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) |  | 0 / 1 | [] |  |  | WO.32994173 | 13003390 | 2026-07-23 | Performed
| 1252 | 32994187 | FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:42 | 1900-01-18 02:38 |  | 0.19097 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) |  | 0 / 1 | [] |  |  | WO.32994187 | 13003390 | 2026-08-19 | Performed
| 1253 | 32994193 | FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:58 | 0.10139 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) |  | 0 / 1 | [] |  |  | WO.32994193 | 13003390 | 2026-07-23 | Performed
| 1254 | 32994746 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 32994746 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32994746) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 26.Jul.2026 14:32 | 1900-01-06 16:57 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32994746 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS (32994746) |  | 0 / 1 | [] |  |  | WO.32994746 | 40000010 | 2026-08-19 | Performed
| 1255 | 32994800 | AFT OF BLK CGO-----F/S---------NO CALL BACK BLK CGO AFT OF AFT PARTTION AREA DIRTY | 32994800 / AFT OF BLK CGO-----F/S---------NO CALL BACK BLK CGO AFT OF AFT PARTTION AREA DIRTY (32994800) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.60417 | 17.Jul.2026 22:00 | 0.12083 | 29.Jul.2026 10:34 | 1900-01-13 01:58 |  | 0.6875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32994800 / AFT OF BLK CGO-----F/S---------NO CALL BACK BLK CGO AFT OF AFT PARTTION AREA DIRTY (32994800) |  | 0 / 1 | [] |  |  | WO.32994800 | 13003081 | 2026-08-12 | Performed
| 1256 | 32995398 | NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING | 32995398 / NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING (32995398) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.125 | 24.Jul.2026 03:48 | 0.12569 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32995398 / NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING (32995398) |  | 0 / 1 | [] |  |  | WO.32995398 | 40000930 | 2026-07-26 | Performed
| 1257 | 32995496 | L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS | 32995496 / L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS (32995496) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:00 | 1900-01-01 21:50 |  | 0.51389 | Closed | 0 | T: 0; O: 0; C: 0 | 55-33 |  | [] |  |  |  |  | 32995496 / L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS (32995496) |  | 0 / 1 | [] |  |  | WO.32995496 | 40000929 | 2026-07-26 | Performed
| 1259 | 32995625 | RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE | 32995625 / RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE (32995625) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:20 | 1900-01-01 15:00 |  | 0.29861 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 32995625 / RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE (32995625) |  | 0 / 1 | [] |  |  | WO.32995625 | 40000929 | 2026-07-26 | Performed
| 1260 | 32995946 | FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. | 32995946 / FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. (32995946) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 13:22 | 0.097222 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-25 |  | [] |  |  |  |  | 32995946 / FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. (32995946) |  | 0 / 1 | [] |  |  | WO.32995946 | 40000010 | 2026-07-26 | Performed
| 1263 | 32996598 | FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) | 32996598 / FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) (32996598) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 26.Jul.2026 04:10 | 1900-01-14 06:40 |  | 1900-01-01 11:53 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32996598 / FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) (32996598) |  | 0 / 4 | [] |  |  | WO.32996598 | 13009981 | 2026-08-12 | Performed
| 1264 | 32996610 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. | 32996610 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. (32996610) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.16667 | 25.Jul.2026 08:53 | 0.28056 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32996610 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. (32996610) |  | 0 / 1 | [] |  |  | WO.32996610 | 40000010 | 2026-07-26 | Performed
| 1265 | 32996715 | FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. | 32996715 / FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. (32996715) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 01.Aug.2026 17:57 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] |  |  |  |  | 32996715 / FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. (32996715) |  | 0 / 1 | [] |  |  | WO.32996715 | 40000010 | 2026-08-02 | Performed
| 1268 | 32996857 | CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" | 32996857 / CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" (32996857) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 26.Jul.2026 08:53 | 1900-01-14 23:11 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32996857 / CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" (32996857) |  | 0 / 1 | [] |  |  | WO.32996857 | 13003081 | 2026-08-11 | Performed
| 1270 | 32998086 | RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. | 32998086 / RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. (32998086) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 08:50 | 1900-01-18 07:55 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 55-40 |  | [] |  |  |  |  | 32998086 / RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. (32998086) |  | 0 / 1 | [] |  |  | WO.32998086 | 13008286 | 2026-08-19 | Performed
| 1271 | 32998113 | GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . | 32998113 / GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . (32998113) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.27083 | 24.Jul.2026 01:57 | 1900-01-16 11:29 |  | 0.60417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 32998113 / GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . (32998113) |  | 0 / 1 | [] |  |  | WO.32998113 | 13003390 | 2026-08-10 | Performed
| 1272 | 32998140 | ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. | 32998140 / ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. (32998140) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 24.Jul.2026 02:01 | 1900-01-15 03:53 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 32998140 / ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. (32998140) |  | 0 / 1 | [] |  |  | WO.32998140 | 13009981 | 2026-08-09 | Performed
| 1275 | 32998246 | FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 32998246 / FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998246) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 | 24.Jul.2026 07:26 | 0.042361 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 52-30-00 |  | [] |  |  |  |  | 32998246 / FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998246) |  | 0 / 1 | [] |  |  | WO.32998246 | 40000930 | 2026-07-26 | Performed
| 1276 | 32998252 | AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 32998252 / AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998252) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.041667 | 24.Jul.2026 07:30 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 52-30-00 |  | [] |  |  |  |  | 32998252 / AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY (32998252) |  | 0 / 1 | [] |  |  | WO.32998252 | 40000930 | 2026-07-26 | Performed
| 1277 | 32998934 | FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... | 32998934 / FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... (32998934) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-03 04:00 | 17.Jul.2026 22:00 | 1900-01-01 02:00 | 29.Jul.2026 07:01 | 1900-01-15 08:42 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32998934 / FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... (32998934) |  | 0 / 1 | [] |  |  | WO.32998934 | 13008286 | 2026-08-16 | Performed
| 1278 | 33000741 | FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . | 33000741 / FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . (33000741) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 25.Jul.2026 06:14 | 1900-01-13 23:57 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 11-00 |  | [] |  |  |  |  | 33000741 / FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . (33000741) |  | 0 / 1 | [] |  |  | WO.33000741 | 13009981 | 2026-08-09 | Performed
| 1279 | 33000793 | AP---RII---APU DOOR APU RIGHT ACCESS DOOR FWD AND MID WALL FIRE SEAL DETACHED | 33000793 / AP---RII---APU DOOR APU RIGHT ACCESS DOOR FWD AND MID WALL FIRE SEAL DETACHED (33000793) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 05.Aug.2026 05:13 | 0.18403 |  | 0.3125 | Closed | 0 | T: 2; O: 0; C: 2 | 49-13 |  | [] |  |  |  |  | 33000793 / AP---RII---APU DOOR APU RIGHT ACCESS DOOR FWD AND MID WALL FIRE SEAL DETACHED (33000793) |  | 0 / 1 | [] |  |  | WO.33000793 | 13003390 | 2026-08-05 | Performed
| 1281 | 33001011 | L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF | 33001011 / L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF (33001011) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.1875 | 25.Jul.2026 08:26 | 1900-01-13 21:13 |  | 0.39583 | Closed | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33001011 / L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF (33001011) |  | 0 / 1 | [] |  |  | WO.33001011 | 13009981 | 2026-08-09 | Performed
| 1282 | 33001198 | AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT | 33001198 / AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT (33001198) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 30.Jul.2026 08:37 | 1900-01-18 09:06 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 33001198 / AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT (33001198) |  | 0 / 1 | [] |  |  | WO.33001198 | 13008286 | 2026-08-19 | Performed
| 1283 | 33001199 | AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN | 33001199 / AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN (33001199) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 31.Jul.2026 15:59 | 0.16736 |  | 0.34583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 33001199 / AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN (33001199) |  | 0 / 1 | [] |  |  | WO.33001199 | 40000010 | 2026-08-02 | Performed
| 1284 | 33001270 | FS---CALLBACK---AVN COMP AVIONICS COMP. STRUCTURE AFTER INSULATION BLANKET REMOVAL NEED DEEP CLEANING | 33001270 / FS---CALLBACK---AVN COMP AVIONICS COMP. STRUCTURE AFTER INSULATION BLANKET REMOVAL NEED DEEP CLEANING (33001270) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 07:05 | 1899-12-31 01:31 |  | 0.11806 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33001270 / FS---CALLBACK---AVN COMP AVIONICS COMP. STRUCTURE AFTER INSULATION BLANKET REMOVAL NEED DEEP CLEANING (33001270) |  | 0 / 1 | [] |  |  | WO.33001270 | 40000929 | 2026-08-06 | Performed
| 1285 | 33001460 | LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS | 33001460 / LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS (33001460) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 25.Jul.2026 17:30 | 0.50694 |  | 0.74306 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] |  |  |  |  | 33001460 / LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS (33001460) |  | 0 / 1 | [] |  |  | WO.33001460 | 40000929 | 2026-07-26 | Performed
| 1288 | 33002750 | PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF | 33002750 / PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF (33002750) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.66667 | 28.Jul.2026 02:18 | 0.27639 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33002750 / PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF (33002750) |  | 0 / 1 | [] |  |  | WO.33002750 | 40000930 | 2026-07-28 | Performed
| 1290 | 33002861 | AP---CALLBACK---RH WING SLAT 5 RH WING SLAT 5 OUTBOARD EDGE SEAL CUT OFF | 33002861 / AP---CALLBACK---RH WING SLAT 5 RH WING SLAT 5 OUTBOARD EDGE SEAL CUT OFF (33002861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 04.Aug.2026 08:42 | 0.14583 |  | 0.73264 | Closed | 0 | T: 0; O: 0; C: 0 | 57-46 |  | [] |  |  |  |  | 33002861 / AP---CALLBACK---RH WING SLAT 5 RH WING SLAT 5 OUTBOARD EDGE SEAL CUT OFF (33002861) |  | 0 / 1 | [] |  |  | WO.33002861 | 13003081 | 2026-08-16 | Performed
| 1300 | 33007172 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 33007172 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (33007172) | Document | PJED | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 07:10 | 0.91319 |  | 0.95833 | Closed | 0 | T: 0; O: 0; C: 0 | 31 |  | [] |  |  |  |  | 33007172 / EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX (33007172) |  | 0 / 6 | [] |  |  | ME.33007172 | 13003390 | 2026-08-03 | Performed
| 1302 | 33011258 | PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) | 33011258 / PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) (33011258) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 30.Jul.2026 13:31 | 0.1875 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33011258 / PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) (33011258) |  | 0 / 1 | [] |  |  | WO.33011258 | 40000010 | 2026-07-30 | Performed
| 1303 | 33011331 | FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF | 33011331 / FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF (33011331) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.66667 | 28.Jul.2026 02:15 | 0.27153 |  | 0.70833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33011331 / FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF (33011331) |  | 0 / 1 | [] |  |  | WO.33011331 | 40000930 | 2026-07-28 | Performed
| 1304 | 33012238 | UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... | 33012238 / UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... (33012238) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 28.Jul.2026 03:00 | 1900-01-07 06:51 |  | 1900-01-01 20:05 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33012238 / UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... (33012238) |  | 0 / 2 | [] |  |  | WO.33012238 | 13008286 | 2026-08-20 | Performed
| 1305 | 33012374 | L/H WING --- A/P ---CALL BACK L/H WING T/EDGE BETWEEN RIB 5 TO RIB 8 WITH TPS MISSING | 33012374 / L/H WING --- A/P ---CALL BACK L/H WING T/EDGE BETWEEN RIB 5 TO RIB 8 WITH TPS MISSING (33012374) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 04.Aug.2026 15:37 | 1900-01-05 20:02 |  | 0.73958 | Closed | 0 | T: 10; O: 0; C: 10 | 57-51 |  | [] |  |  |  |  | 33012374 / L/H WING --- A/P ---CALL BACK L/H WING T/EDGE BETWEEN RIB 5 TO RIB 8 WITH TPS MISSING (33012374) |  | 0 / 1 | [] |  |  | WO.33012374 | 13003081 | 2026-08-13 | Performed
| 1306 | 33012961 | L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY | 33012961 / L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY (33012961) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 02.Aug.2026 08:56 | 1900-01-08 01:25 |  | 0.19097 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33012961 / L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY (33012961) |  | 0 / 1 | [] |  |  | WO.33012961 | 13003081 | 2026-08-18 | Performed
| 1307 | 33013426 | L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY | 33013426 / L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY (33013426) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 19:56 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33013426 / L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY (33013426) |  | 0 / 1 | [] |  |  | WO.33013426 | 13003081 | 2026-08-11 | Performed
| 1308 | 33013430 | L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN | 33013430 / L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN (33013430) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 10:11 | 1900-01-12 22:42 |  | 1899-12-31 12:47 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33013430 / L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN (33013430) |  | 0 / 2 | [] |  |  | WO.33013430 | 13008286 | 2026-08-11 | Performed
| 1309 | 33013444 | L/H WING--- AP-- NO CALL BACK L/H WING TRAILING EDGE SPOILER NO.4 I/B HINGE BONDING WIRE WITH BROKEN. | 33013444 / L/H WING--- AP-- NO CALL BACK L/H WING TRAILING EDGE SPOILER NO.4 I/B HINGE BONDING WIRE WITH BROKEN. (33013444) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 18:45 | 1900-01-04 11:33 |  | 0.3875 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33013444 / L/H WING--- AP-- NO CALL BACK L/H WING TRAILING EDGE SPOILER NO.4 I/B HINGE BONDING WIRE WITH BROKEN. (33013444) |  | 0 / 1 | [] |  |  | WO.33013444 | 40000010 | 2026-08-11 | Performed
| 1310 | 33013470 | L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. | 33013470 / L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. (33013470) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 29.Jul.2026 18:39 | 1900-01-19 00:57 |  | 1899-12-31 07:30 | Closed | 0 | T: 0; O: 0; C: 0 | 57-26 |  | [] |  |  |  |  | 33013470 / L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. (33013470) |  | 0 / 1 | [] |  |  | WO.33013470 | 13003390 | 2026-08-19 | Performed
| 1311 | 33013486 | L/H WING--- S/M ---- RII L/H WING O/B ACCESS THROUGHT PANEL # 575LB STRIP METAL DETACHED | 33013486 / L/H WING--- S/M ---- RII L/H WING O/B ACCESS THROUGHT PANEL # 575LB STRIP METAL DETACHED (33013486) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 04:20 | 1900-01-04 01:30 |  | 0.048611 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33013486 / L/H WING--- S/M ---- RII L/H WING O/B ACCESS THROUGHT PANEL # 575LB STRIP METAL DETACHED (33013486) |  | 0 / 1 | [] |  |  | WO.33013486 | 40000929 | 2026-08-04 | Performed
| 1312 | 33013510 | AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST | 33013510 / AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST (33013510) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.083333 | 02.Aug.2026 06:58 | 0.16667 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 33013510 / AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST (33013510) |  | 0 / 1 | [] |  |  | WO.33013510 | 13003390 | 2026-08-12 | Performed
| 1313 | 33013536 | VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION | 33013536 / VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION (33013536) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.125 | 01.Aug.2026 17:59 | 1899-12-31 13:33 |  | 0.50347 | Closed | 0 | T: 0; O: 0; C: 0 | 55-36 |  | [] |  |  |  |  | 33013536 / VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION (33013536) |  | 0 / 1 | [] |  |  | WO.33013536 | 40000929 | 2026-08-03 | Performed
| 1315 | 33014957 | RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES | 33014957 / RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES (33014957) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 04:36 | 1900-01-03 04:02 |  | 0.70139 | Closed | 0 | T: 2; O: 0; C: 2 | 34-42 |  | [] |  |  |  |  | 33014957 / RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES (33014957) |  | 0 / 1 | [] |  |  | WO.33014957 | 13008286 | 2026-08-20 | Performed
| 1318 | 33017645 | CAB - NO CALL BACK - GALLEY G2 GALLEY COMP. 204 2EA TURN CATCH FADED | 33017645 / CAB - NO CALL BACK - GALLEY G2 GALLEY COMP. 204 2EA TURN CATCH FADED (33017645) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 07:00 | 0.10417 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33017645 / CAB - NO CALL BACK - GALLEY G2 GALLEY COMP. 204 2EA TURN CATCH FADED (33017645) |  | 0 / 1 | [] |  |  | WO.33017645 | 40000929 | 2026-08-06 | Performed
| 1319 | 33017650 | FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED | 33017650 / FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED (33017650) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:30 | 1900-01-18 05:10 |  | 1900-01-01 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 33017650 / FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED (33017650) |  | 0 / 1 | [] |  |  | WO.33017650 | 13003081 | 2026-08-18 | Performed
| 1320 | 33018932 | CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) | 33018932 / CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) (33018932) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 18.Aug.2026 05:23 | 0.16736 |  | 0.73958 | Closed | 0 | T: 0; O: 0; C: 0 | 57-10 |  | [] |  |  |  |  | 33018932 / CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) (33018932) |  | 0 / 1 | [] |  |  | WO.33018932 | 13008286 | 2026-08-18 | Performed
| 1326 | 33019665 | FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION | 33019665 / FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION (33019665) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.83333 | 17.Jul.2026 22:00 | 0.27778 | 29.Jul.2026 00:38 | 1899-12-31 09:26 |  | 0.84375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33019665 / FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION (33019665) |  | 0 / 1 | [] |  |  | WO.33019665 | 40000010 | 2026-07-30 | Performed
| 1328 | 33014940 | S71-R10397/HZ-ASD ENG.2 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 33014940 / S71-R10397/HZ-ASD ENG.2 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33014940) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.14583 | 02.Aug.2026 03:00 | 1900-01-08 14:25 |  | 1900-01-02 01:30 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 4 | [] |  | 000 | ME.33014940 | 13008286 | 2026-08-19 | Performed
| 1329 | 33014947 | S71-R10398/HZ-ASD ENG.1 REPLACEMENT OF LH FAN COWL AFT EDGE PROTECTORS | 33014947 / S71-R10398/HZ-ASD ENG.1 REPLACEMENT OF LH FAN COWL AFT EDGE PROTECTORS (33014947) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.22917 | 05.Aug.2026 03:00 | 1900-01-05 14:24 |  | 1900-01-02 14:05 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 0 / 1 |  | 0 / 4 | [] |  | 000 | ME.33014947 | 13008286 | 2026-08-19 | Performed
| 1330 | 33019887 | AFT CARGO - UNDERFLOOR - FS -CALLBACK AFT CARGO UNDERFLOOR REQ ZONAL CLEANING FROM FRAME 46 TO 51 | 33019887 / AFT CARGO - UNDERFLOOR - FS -CALLBACK AFT CARGO UNDERFLOOR REQ ZONAL CLEANING FROM FRAME 46 TO 51 (33019887) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 27.Jul.2026 11:14 | 1900-01-01 22:54 |  | 1899-12-31 17:00 | Closed | 0 | T: 0; O: 0; C: 0 | 53 |  | [] |  |  |  |  | 33019887 / AFT CARGO - UNDERFLOOR - FS -CALLBACK AFT CARGO UNDERFLOOR REQ ZONAL CLEANING FROM FRAME 46 TO 51 (33019887) |  | 0 / 1 | [] |  |  | WO.33019887 | 40000929 | 2026-08-06 | Performed
| 1331 | 95001843 | ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 | 95001843 / ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 (95001843) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 27.Jul.2026 14:02 | 1900-01-12 16:00 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 21-00 |  | [] |  |  |  |  | 95001843 / ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 (95001843) |  | 0 / 1 | [] |  |  | WO.95001843 | 13008286 | 2026-08-10 | Performed
| 1332 | 33020601 | FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . | 33020601 / FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . (33020601) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 28.Jul.2026 16:47 | 1899-12-31 23:25 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 33020601 / FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . (33020601) |  | 0 / 1 | [] |  |  | WO.33020601 | 40000010 | 2026-07-30 | Performed
| 1333 | 33020680 | AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. | 33020680 / AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. (33020680) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 28.Jul.2026 14:49 | 1900-01-01 01:08 |  | 0.6875 | Closed | 0 | T: 0; O: 0; C: 0 | 52-10 |  | [] |  |  |  |  | 33020680 / AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. (33020680) |  | 0 / 1 | [] |  |  | WO.33020680 | 40000010 | 2026-07-30 | Performed
| 1334 | 33020727 | CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . | 33020727 / CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . (33020727) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:40 | 1900-01-17 05:42 |  | 0.11111 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020727 / CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . (33020727) |  | 0 / 1 | [] |  |  | WO.33020727 | 13003953 | 2026-08-17 | Performed
| 1336 | 33020729 | CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... | 33020729 / CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... (33020729) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 11:35 | 1900-01-12 21:26 |  | 0.51389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 33020729 / CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... (33020729) |  | 0 / 2 | [] |  |  | WO.33020729 | 13003390 | 2026-08-12 | Performed
| 1340 | 33021799 | EMERGENCY EXIT HATCH - CABIN - CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL | 33021799 / EMERGENCY EXIT HATCH - CABIN - CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL (33021799) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 13:58 | 1900-01-21 21:03 |  | 1899-12-31 23:30 | Closed | 0 | T: 0; O: 0; C: 0 | 53-00-00 |  | [] |  |  |  |  | 33021799 / EMERGENCY EXIT HATCH - CABIN - CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL (33021799) |  | 0 / 1 | [] |  |  | WO.33021799 | 40000010 | 2026-08-20 | Performed
| 1341 | 33021843 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP 207. LATCH INOP | 33021843 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP 207. LATCH INOP (33021843) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 05.Aug.2026 05:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33021843 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP 207. LATCH INOP (33021843) |  | 0 / 1 | [] |  |  | WO.33021843 | 40000929 | 2026-08-06 | Performed
| 1344 | 33022853 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP | 33022853 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP (33022853) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 05:48 | 0.10417 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022853 / CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP (33022853) |  | 0 / 1 | [] |  |  | WO.33022853 | 13003390 | 2026-08-10 | Performed
| 1345 | 33022868 | CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. | 33022868 / CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. (33022868) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 09.Aug.2026 06:14 | 0.10417 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33022868 / CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. (33022868) |  | 0 / 1 | [] |  |  | WO.33022868 | 13009981 | 2026-08-09 | Performed
| 1346 | 33022924 | RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW | 33022924 / RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW (33022924) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 11:00 | 0.083333 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33022924 / RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW (33022924) |  | 0 / 1 | [] |  |  | WO.33022924 | 40000010 | 2026-07-28 | Performed
| 1347 | 33022953 | CAB - NO CALLBACK - COCKPIT CAPTAIN FOOTREST RUBBER MAT WORN-OUT. | 33022953 / CAB - NO CALLBACK - COCKPIT CAPTAIN FOOTREST RUBBER MAT WORN-OUT. (33022953) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 04:39 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022953 / CAB - NO CALLBACK - COCKPIT CAPTAIN FOOTREST RUBBER MAT WORN-OUT. (33022953) |  | 0 / 1 | [] |  |  | WO.33022953 | 13003390 | 2026-08-04 | Performed
| 1348 | 33022966 | CAB - NO CALLBACK - COCKPIT FLIGHT DECK CAPTAIN AND FIRST OFFICER PEDAL RUBBER MAT DIRTY. | 33022966 / CAB - NO CALLBACK - COCKPIT FLIGHT DECK CAPTAIN AND FIRST OFFICER PEDAL RUBBER MAT DIRTY. (33022966) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 10:34 | 1900-01-06 05:22 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33022966 / CAB - NO CALLBACK - COCKPIT FLIGHT DECK CAPTAIN AND FIRST OFFICER PEDAL RUBBER MAT DIRTY. (33022966) |  | 0 / 1 | [] |  |  | WO.33022966 | 13003390 | 2026-08-12 | Performed
| 1349 | 33022983 | CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. | 33022983 / CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. (33022983) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 16.Aug.2026 06:31 | 0.10417 |  | 0.10417 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33022983 / CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. (33022983) |  | 0 / 1 | [] |  |  | WO.33022983 | 13008286 | 2026-08-16 | Performed
| 1350 | 33023367 | AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB | 33023367 / AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB (33023367) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.125 | 29.Jul.2026 13:49 | 1900-01-11 16:49 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33023367 / AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB (33023367) |  | 0 / 1 | [] |  |  | WO.33023367 | 13003390 | 2026-08-19 | Performed
| 1351 | 33023576 | AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED | 33023576 / AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED (33023576) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.083333 | 29.Jul.2026 14:01 | 0.068056 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33023576 / AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED (33023576) |  | 0 / 1 | [] |  |  | WO.33023576 | 40000010 | 2026-07-29 | Performed
| 1352 | 33023575 | FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 33023575 / FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023575) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.375 | 29.Jul.2026 04:22 | 0.21458 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33023575 / FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023575) |  | 0 / 1 | [] |  |  | WO.33023575 | 13003390 | 2026-07-29 | Performed
| 1354 | 33023735 | FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 33023735 / FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023735) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 29.Jul.2026 04:24 | 0.21181 |  | 0.33333 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] |  |  |  |  | 33023735 / FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING (33023735) |  | 0 / 1 | [] |  |  | WO.33023735 | 13003390 | 2026-07-29 | Performed
| 1355 | 33023745 | CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. | 33023745 / CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. (33023745) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 03.Aug.2026 03:17 | 0.24722 |  | 0.31597 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023745 / CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. (33023745) |  | 0 / 1 | [] |  |  | WO.33023745 | 13003390 | 2026-08-03 | Performed
| 1356 | 33023803 | CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. | 33023803 / CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. (33023803) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 04:02 | 1900-01-08 08:42 |  | 0.60417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023803 / CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. (33023803) |  | 0 / 1 | [] |  |  | WO.33023803 | 13003390 | 2026-08-12 | Performed
| 1357 | 33023820 | CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED | 33023820 / CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED (33023820) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 17.Aug.2026 07:24 | 0.0625 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33023820 / CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED (33023820) |  | 0 / 1 | [] |  |  | WO.33023820 | 13008286 | 2026-08-17 | Performed
| 1359 | 33024557 | VERTICAL STABLIZER HINGE FITTING (EOD-320-55-00001-R00) AS PER (EOD-320-55-00001-R00) ALL HINGE FITTINGS REQUIRE NDT AFTER REMOVAL . | 33024557 / VERTICAL STABLIZER HINGE FITTING (EOD-320-55-00001-R00) AS PER (EOD-320-55-00001-R00) ALL HINGE FITTINGS REQUIRE NDT AFTER REMOVAL . (33024557) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 28.Jul.2026 05:39 | 1900-01-05 05:15 |  | 0.70833 | Closed | 0 | T: 0; O: 0; C: 0 | 55 |  | [] |  |  |  |  | 33024557 / VERTICAL STABLIZER HINGE FITTING (EOD-320-55-00001-R00) AS PER (EOD-320-55-00001-R00) ALL HINGE FITTINGS REQUIRE NDT AFTER REMOVAL . (33024557) |  | 0 / 7 | [] |  |  | WO.33024557 | 40000930 | 2026-08-04 | Performed
| 1361 | 33025672 | ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 | 33025672 / ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 (33025672) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 08.Aug.2026 22:51 | 0.33819 |  | 0.9375 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 33025672 / ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 (33025672) |  | 0 / 1 | [] |  |  | WO.33025672 | 13009981 | 2026-08-09 | Performed
| 1362 | 33025883 | RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) | 33025883 / RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) (33025883) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 08:42 | 1899-12-31 00:38 |  | 0.40625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025883 / RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) (33025883) |  | 0 / 1 | [] |  |  | WO.33025883 | 40000930 | 2026-07-30 | Performed
| 1363 | 33025887 | RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) | 33025887 / RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) (33025887) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 29.Jul.2026 06:28 | 0.35972 |  | 0.34375 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025887 / RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) (33025887) |  | 0 / 1 | [] |  |  | WO.33025887 | 40000930 | 2026-07-30 | Performed
| 1364 | 33025881 | ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... | 33025881 / ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... (33025881) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 12:02 | 0.31944 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 33025881 / ENG #2 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #2 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... (33025881) |  | 0 / 1 | [] |  |  | WO.33025881 | 13003390 | 2026-08-03 | Performed
| 1365 | 33025894 | LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN | 33025894 / LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN (33025894) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 04:21 | 1900-01-02 03:58 |  | 0.70139 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025894 / LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN (33025894) |  | 0 / 1 | [] |  |  | WO.33025894 | 13003390 | 2026-08-09 | Performed
| 1366 | 33025896 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF | 33025896 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF (33025896) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.40625 | 17.Jul.2026 22:00 | 0.28125 | 29.Jul.2026 08:03 | 1899-12-31 00:40 |  | 0.44792 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025896 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF (33025896) |  | 0 / 1 | [] |  |  | WO.33025896 | 13007897 | 2026-07-30 | Performed
| 1367 | 33025897 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF | 33025897 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF (33025897) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 29.Jul.2026 06:53 | 0.34097 |  | 0.38542 | Closed | 0 | T: 0; O: 0; C: 0 | 57-21 |  | [] |  |  |  |  | 33025897 / LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF (33025897) |  | 0 / 1 | [] |  |  | WO.33025897 | 40000930 | 2026-07-30 | Performed
| 1368 | 33027334 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT | 33027334 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT (33027334) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 11:02 | 1899-12-31 21:19 |  | 1899-12-31 02:30 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027334 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT (33027334) |  | 0 / 1 | [] |  |  | WO.33027334 | 13003390 | 2026-08-09 | Performed
| 1369 | 33027336 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 | 33027336 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 (33027336) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 06:50 | 1900-01-01 01:30 |  | 0.61806 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027336 / FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 (33027336) |  | 0 / 1 | [] |  |  | WO.33027336 | 13003390 | 2026-08-09 | Performed
| 1370 | 33027335 | OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. | 33027335 / OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. (33027335) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 30.Jul.2026 11:22 | 1900-01-19 05:20 |  | 1899-12-31 04:00 | Closed | 0 | T: 0; O: 0; C: 0 | 56-21 |  | [] |  |  |  |  | 33027335 / OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. (33027335) |  | 0 / 1 | [] |  |  | WO.33027335 | 13003081 | 2026-08-20 | Performed
| 1371 | 33027363 | FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF | 33027363 / FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF (33027363) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 08:15 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33027363 / FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF (33027363) |  | 0 / 1 | [] |  |  | WO.33027363 | 13003390 | 2026-07-29 | Performed
| 1374 | 33028214 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT RH DOOR CUTOUT AT FR 68 AREA CORRODED AROUND GIRT BAR FITTING AND AT THE DRAIN HOLE | 33028214 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT RH DOOR CUTOUT AT FR 68 AREA CORRODED AROUND GIRT BAR FITTING AND AT THE DRAIN HOLE (33028214) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 03:40 | 1900-01-03 23:57 |  | 1899-12-31 04:05 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33028214 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT RH DOOR CUTOUT AT FR 68 AREA CORRODED AROUND GIRT BAR FITTING AND AT THE DRAIN HOLE (33028214) |  | 0 / 4 | [] |  |  | WO.33028214 | 40000930 | 2026-08-04 | Performed
| 1375 | 33028291 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT LH DOOR CUTOUT AT FR 68 AND FR 66 AREA CORRODED AT GIRT BAR FITTINGS RIVETS 2EA | 33028291 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT LH DOOR CUTOUT AT FR 68 AND FR 66 AREA CORRODED AT GIRT BAR FITTINGS RIVETS 2EA (33028291) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 29.Jul.2026 03:00 | 1900-01-04 07:30 |  | 0.71875 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33028291 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT LH DOOR CUTOUT AT FR 68 AND FR 66 AREA CORRODED AT GIRT BAR FITTINGS RIVETS 2EA (33028291) |  | 0 / 4 | [] |  |  | WO.33028291 | 40000930 | 2026-08-04 | Performed
| 1381 | 33028590 | FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF | 33028590 / FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF (33028590) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.41667 | 31.Jul.2026 02:20 | 1900-01-08 03:41 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] |  |  |  |  | 33028590 / FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF (33028590) |  | 0 / 1 | [] |  |  | WO.33028590 | 13009981 | 2026-08-09 | Performed
| 1382 | 33028952 | NO.1 ENGINE ACOUSTICAL PANEL MISSING SCREW--CALL BACK--AP NO.1 ENGINE ACOUSTICAL PANEL FOUND WITH MISSING SCREW MARKED WITH GREEN TAPE | 33028952 / NO.1 ENGINE ACOUSTICAL PANEL MISSING SCREW--CALL BACK--AP NO.1 ENGINE ACOUSTICAL PANEL FOUND WITH MISSING SCREW MARKED WITH GREEN TAPE (33028952) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.083333 | 04.Aug.2026 06:06 | 0.14583 |  | 0.62847 | Closed | 0 | T: 0; O: 0; C: 0 | 20-00 |  | [] |  |  |  |  | 33028952 / NO.1 ENGINE ACOUSTICAL PANEL MISSING SCREW--CALL BACK--AP NO.1 ENGINE ACOUSTICAL PANEL FOUND WITH MISSING SCREW MARKED WITH GREEN TAPE (33028952) |  | 0 / 1 | [] |  |  | WO.33028952 | 13003390 | 2026-08-04 | Performed
| 1383 | 33029195 | ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP | 33029195 / ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029195) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 30.Jul.2026 11:04 | 1900-01-03 00:47 |  | 0.62847 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 33029195 / ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029195) |  | 0 / 1 | [] |  |  | WO.33029195 | 13003390 | 2026-08-03 | Performed
| 1384 | 33029199 | ENG NO#02======AP=====CALL BACK REFER TO TASK CARD 712213-01-1-002 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP | 33029199 / ENG NO#02======AP=====CALL BACK REFER TO TASK CARD 712213-01-1-002 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029199) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 29.Jul.2026 20:12 | 1900-01-04 11:07 |  | 0.47917 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 33029199 / ENG NO#02======AP=====CALL BACK REFER TO TASK CARD 712213-01-1-002 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP (33029199) |  | 0 / 1 | [] |  |  | WO.33029199 | 13003390 | 2026-08-04 | Performed
| 1385 | 33029239 | FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... | 33029239 / FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... (33029239) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 30.Jul.2026 05:50 | 1900-01-11 00:14 |  | 1900-01-01 06:10 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33029239 / FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... (33029239) |  | 0 / 2 | [] |  |  | WO.33029239 | 13003081 | 2026-08-11 | Performed
| 1386 | 33029270 | RH WING MLG SUPPORT RIBS=====AP==== CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC | 33029270 / RH WING MLG SUPPORT RIBS=====AP==== CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC (33029270) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 02.Aug.2026 13:43 | 1900-01-16 21:31 |  | 0.19583 | Closed | 0 | T: 0; O: 0; C: 0 | 57-51 |  | [] |  |  |  |  | 33029270 / RH WING MLG SUPPORT RIBS=====AP==== CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC (33029270) |  | 0 / 1 | [] |  |  | WO.33029270 | 13003390 | 2026-08-20 | Performed
| 1387 | 33030770 | SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE | 33030770 / SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE (33030770) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 03.Aug.2026 04:30 | 1900-01-02 14:00 |  | 1900-01-01 00:47 | Closed | 0 | T: 0; O: 0; C: 0 | 57-42 |  | [] |  |  |  |  | 33030770 / SM---RII---RH WING SLAT 1 RH WING SLAT 1 TRACK NO.3 SLAT FITTING WITH CHAFING MARK L= 2 IN, W= 1 IN & DEPTH= 0.15 MM FITTING CHAFED WITH WING LE FITTING GROOVE (33030770) |  | 0 / 3 | [] |  |  | WO.33030770 | 13008286 | 2026-08-10 | Performed
| 1391 | 33032681 | FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM | 33032681 / FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM (33032681) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 02.Aug.2026 06:44 | 1900-01-01 11:51 |  | 1899-12-31 04:55 | Closed | 0 | T: 0; O: 0; C: 0 | 51 |  | [] |  |  |  |  | 33032681 / FINDING (NRC) DOCUMENT S51-R10008 SM--RII LH WING SLAT # 3 WITH DENT AT LE EDGE TOP SKIN BETWEEN TRACK RIB #7 AND TRACK RIB #8 WITH THE FOLLOWING DIMENSION L=55 MM W= 20 MM D= 0.2 MM DISTANCE TO NEAREST FASTENER = 65 MM (33032681) |  | 0 / 2 | [] |  |  | WO.33032681 | 40000929 | 2026-08-10 | Performed
| 1392 | 33033307 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED | 33033307 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED (33033307) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 08:00 | 17.Jul.2026 22:00 | 1899-12-31 08:00 | 30.Jul.2026 10:22 | 0.31181 |  | 1899-12-31 07:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33033307 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDEWALL AT SEAT 3JL, 4JL, 11JL AND 5AC TEDLAR DAMAGED (33033307) |  | 0 / 1 | [] |  |  | WO.33033307 | 40000010 | 2026-07-30 | Performed
| 1396 | 33037808 | LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK | 33037808 / LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK (33037808) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 01.Aug.2026 09:07 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33037808 / LH WING FLAP UPEER MID NO CALL BACK PNT LH WING FLAP UPEER MID WITH BLACK MARK (33037808) |  | 0 / 1 | [] |  |  | WO.33037808 | 13003081 | 2026-08-09 | Performed
| 1397 | 33037811 | RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK | 33037811 / RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK (33037811) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 01.Aug.2026 09:04 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 51-75 |  | [] |  |  |  |  | 33037811 / RH WING FLAP UPEER MID NO CALL BACK PNT RH WING FLAP UPEER MID WITH BLACK MARK (33037811) |  | 0 / 1 | [] |  |  | WO.33037811 | 13003081 | 2026-08-09 | Performed
| 1401 | 33040155 | S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 33040155 / S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33040155) | Document | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.14583 | 05.Aug.2026 03:00 | 1900-01-05 14:28 |  | 1899-12-31 23:01 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33040155 / S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS (33040155) |  | 0 / 4 | [] |  | 000 | ME.33040155 | 13003390 | 2026-08-12 | Performed
| 1402 | 33040973 | FINDING (NRC) TASKCARD 534150-01-1 (02) / AFT CARGO --- NO CALLBACK - AFT CARGO COMPARTMENT 152EF LOOSE BRACKET ON THE AFT END, BETWEEN FR52 AND FR53. | 33040973 / FINDING (NRC) TASKCARD 534150-01-1 (02) / AFT CARGO --- NO CALLBACK - AFT CARGO COMPARTMENT 152EF LOOSE BRACKET ON THE AFT END, BETWEEN FR52 AND FR53. (33040973) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 03:00 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 53-41 |  | [] |  |  |  |  | 33040973 / FINDING (NRC) TASKCARD 534150-01-1 (02) / AFT CARGO --- NO CALLBACK - AFT CARGO COMPARTMENT 152EF LOOSE BRACKET ON THE AFT END, BETWEEN FR52 AND FR53. (33040973) |  | 0 / 1 | [] |  |  | WO.33040973 | 13003081 | 2026-08-11 | Performed
| 1403 | 33041186 | CAB- SIEDWALL-NO CALLBACK SIDEWALL BETWEEN 3 LJ / 4LJ TEDLAR DAMAGE | 33041186 / CAB- SIEDWALL-NO CALLBACK SIDEWALL BETWEEN 3 LJ / 4LJ TEDLAR DAMAGE (33041186) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 1899-12-31 | 04.Aug.2026 02:00 | 0.61111 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33041186 / CAB- SIEDWALL-NO CALLBACK SIDEWALL BETWEEN 3 LJ / 4LJ TEDLAR DAMAGE (33041186) |  | 0 / 1 | [] |  |  | WO.33041186 | 13003081 | 2026-08-04 | Performed
| 1404 | 33041202 | CAB-SIDEWALL-NO CALL BACK SIDEWALL 1LJ TEDLAR DAMAGE | 33041202 / CAB-SIDEWALL-NO CALL BACK SIDEWALL 1LJ TEDLAR DAMAGE (33041202) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 04.Aug.2026 02:00 | 0.61111 |  | 0.66667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33041202 / CAB-SIDEWALL-NO CALL BACK SIDEWALL 1LJ TEDLAR DAMAGE (33041202) |  | 0 / 1 | [] |  |  | WO.33041202 | 13003081 | 2026-08-04 | Performed
| 1406 | 571192-09-1 | 571192-09-1 (0) / CENTER WING BOX | 571192-09-1 (0) / CENTER WING BOX (33044425) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 | 30.Jul.2026 06:51 | 1900-01-11 23:43 |  | 0.27778 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | As per response in T/Q:843420 and airbus response in Dosseeier #81845619. to add Advance AMM. | 571192-09-1 (0) / CENTER WING BOX (33044425) |  | 3 / 3 | [] |  |  | MET.33044425 | 13008286 | 2026-08-12 | Performed
| 1407 | 571192-19-1 | 571192-19-1 (0) / CENTER WING BOX | 571192-19-1 (0) / CENTER WING BOX (33044444) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.070833 | 17.Jul.2026 22:00 | 0.070833 | 30.Jul.2026 06:53 | 1900-01-11 23:44 |  | 0.28125 | Closed | 0 | T: 2; O: 0; C: 2 | 57 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | As per T/Q: 843444 and airbus response Dossier TA# 81845708. | 571192-19-1 (0) / CENTER WING BOX (33044444) |  | 3 / 3 | [] |  |  | MET.33044444 | 13008286 | 2026-08-12 | Performed
| 1411 | 33047936 | NO CALL BACK LH WING UPPER PANEL 575 AT PAINT PEELED OFF | 33047936 / NO CALL BACK LH WING UPPER PANEL 575 AT PAINT PEELED OFF (33047936) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 07:40 | 0.084028 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 33047936 / NO CALL BACK LH WING UPPER PANEL 575 AT PAINT PEELED OFF (33047936) |  | 0 / 1 | [] |  |  | WO.33047936 | 13003390 | 2026-08-04 | Performed
| 1412 | 33047948 | NO CALL BACK LH WING LOWER PANEL 575 MB PAINT PEELED OFF | 33047948 / NO CALL BACK LH WING LOWER PANEL 575 MB PAINT PEELED OFF (33047948) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 04.Aug.2026 07:02 | 0.11111 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 33047948 / NO CALL BACK LH WING LOWER PANEL 575 MB PAINT PEELED OFF (33047948) |  | 0 / 1 | [] |  |  | WO.33047948 | 13003390 | 2026-08-04 | Performed
| 1413 | 33049397 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY 2 DOOR 206 TEDLAR DAMAGED | 33049397 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY 2 DOOR 206 TEDLAR DAMAGED (33049397) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 04.Aug.2026 10:17 | 0.27083 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33049397 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY 2 DOOR 206 TEDLAR DAMAGED (33049397) |  | 0 / 1 | [] |  |  | WO.33049397 | 13003081 | 2026-08-04 | Performed
| 1414 | 33049403 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND ICE BUCKET BOX 208 TEDLAR DAMAGED | 33049403 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND ICE BUCKET BOX 208 TEDLAR DAMAGED (33049403) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 04.Aug.2026 10:18 | 0.27083 |  | 0.3125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33049403 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND ICE BUCKET BOX 208 TEDLAR DAMAGED (33049403) |  | 0 / 1 | [] |  |  | WO.33049403 | 13003081 | 2026-08-04 | Performed
| 1415 | 33049404 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY DOOR 515 TEDLAR DAMAGED | 33049404 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY DOOR 515 TEDLAR DAMAGED (33049404) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 04.Aug.2026 10:19 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33049404 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND GALLEY DOOR 515 TEDLAR DAMAGED (33049404) |  | 0 / 1 | [] |  |  | WO.33049404 | 13003081 | 2026-08-04 | Performed
| 1418 | 33058303 | FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED | 33058303 / FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED (33058303) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 05.Aug.2026 02:00 | 1900-01-07 15:07 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33058303 / FINDING (NRC) TASKCARD CCC-32S (05) / ITEM ONE LAV D INNER WALL TEDLAR DAMMAGED (33058303) |  | 0 / 1 | [] |  |  | WO.33058303 | 13003390 | 2026-08-14 | Performed
| 1420 | 33060679 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND UPPER WALL OF COCKPIT DOOR TEDLAR DAMAGED | 33060679 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND UPPER WALL OF COCKPIT DOOR TEDLAR DAMAGED (33060679) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 05.Aug.2026 14:11 | 1899-12-31 03:38 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33060679 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND UPPER WALL OF COCKPIT DOOR TEDLAR DAMAGED (33060679) |  | 0 / 1 | [] |  |  | WO.33060679 | 40000010 | 2026-08-06 | Performed
| 1421 | 33060680 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED | 33060680 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED (33060680) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 10.Aug.2026 11:08 | 0.27083 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33060680 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND L1 DOOR LOWER OF F/A SEAT UNDER LIFE VEST TEDLAR DAMAGED (33060680) |  | 0 / 1 | [] |  |  | WO.33060680 | 40000010 | 2026-08-10 | Performed
| 1422 | 33060681 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL BESIDE L1 DOOR LOWER AREA TEDLAR DAMAGED | 33060681 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL BESIDE L1 DOOR LOWER AREA TEDLAR DAMAGED (33060681) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 05.Aug.2026 14:08 | 0.88819 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33060681 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL BESIDE L1 DOOR LOWER AREA TEDLAR DAMAGED (33060681) |  | 0 / 1 | [] |  |  | WO.33060681 | 40000010 | 2026-08-06 | Performed
| 1424 | 33062121 | PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED | 33062121 / PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED (33062121) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:00 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062121 / PNT - NO CALLBACK - COCKPIT COCKPIT SEVERAL CEILING PANELS PAINT CHIPPED (33062121) |  | 0 / 1 | [] |  |  | WO.33062121 | 13003081 | 2026-08-09 | Performed
| 1425 | 33062156 | PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED | 33062156 / PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED (33062156) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:00 | 0.125 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062156 / PNT - NO CALLBACK - WINDOW FRAMES BOTH CAPTAIN AND F/O WINDOW FRAMES PAINT REQUIRED (33062156) |  | 0 / 1 | [] |  |  | WO.33062156 | 13003081 | 2026-08-09 | Performed
| 1426 | 33062169 | PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED | 33062169 / PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED (33062169) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 07.Aug.2026 06:35 | 0.10417 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33062169 / PNT - NO CALLBACK - SLIDING TABLES SLIDING TABLES PAINT REQUIRED (33062169) |  | 0 / 1 | [] |  |  | WO.33062169 | 13003081 | 2026-08-09 | Performed
| 1428 | 33067651 | LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. | 33067651 / LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. (33067651) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 09.Aug.2026 03:06 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 53-00 |  | [] |  |  |  |  | 33067651 / LOWER FUSELAGE ----- SM ----- NO CALL BACK LOWER FUSELAGE ACCESS PANELS NO. 191LB, 191EB. WITH ANCHOR NUTS BROKEN. (33067651) |  | 0 / 1 | [] |  |  | WO.33067651 | 13009981 | 2026-08-09 | Performed
| 1429 | 95001847 | ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 | 95001847 / ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 (95001847) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 13:00 | 1900-01-09 22:23 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 95001847 / ROB REF TO TQ #: 846595 ENGINE FAN COWL ROD PN: A3410-2 S/N:18806 ROB TO SVC AS75 (95001847) |  | 0 / 1 | [] |  |  | WO.95001847 | 13009981 | 2026-08-20 | Performed
| 1430 | 33069516 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED | 33069516 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED (33069516) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 06.Aug.2026 11:20 | 1900-01-03 06:24 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33069516 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND SIDE WALL AT SEAT 41JKL TEDLAR DAMAGED (33069516) |  | 0 / 1 | [] |  |  | WO.33069516 | 40000010 | 2026-08-10 | Performed
| 1433 | 33073939 | FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-765 WITH SURFACE CORROSION | 33073939 / FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-765 WITH SURFACE CORROSION (33073939) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 09.Aug.2026 03:00 | 0.48056 |  | 0.86458 | Closed | 0 | T: 0; O: 0; C: 0 | 53-11 |  | [] |  |  |  |  | 33073939 / FINDING (NRC) TASKCARD 531194-01-2 (2) / ITEM-1 SM--RII FLOOR ATTACHMENT STRUCTURE AT FR 20 AND Y-765 WITH SURFACE CORROSION (33073939) |  | 0 / 2 | [] |  |  | WO.33073939 | 40000010 | 2026-08-10 | Performed
| 1434 | 33074086 | SM-----CALLBACK NOSE LANDING GEAR LEG LOCK STAY ASSY LOWER ATTACHMENT FOUND WITH CHAFFING MARKS | 33074086 / SM-----CALLBACK NOSE LANDING GEAR LEG LOCK STAY ASSY LOWER ATTACHMENT FOUND WITH CHAFFING MARKS (33074086) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 09.Aug.2026 04:00 | 0.43819 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | 33074086 / SM-----CALLBACK NOSE LANDING GEAR LEG LOCK STAY ASSY LOWER ATTACHMENT FOUND WITH CHAFFING MARKS (33074086) |  | 0 / 2 | [] |  |  | WO.33074086 | 40000010 | 2026-08-10 | Performed
| 1435 | 33075708 | MAIN BATT REQUIRED R/R BOTH MAIN BATT #1 AND #2 DUE TO BATTERY VOLTAGE FOUND LOW | 33075708 / MAIN BATT REQUIRED R/R BOTH MAIN BATT #1 AND #2 DUE TO BATTERY VOLTAGE FOUND LOW (33075708) | Workorder | N | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 07:25 | 0.084028 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-00 |  | [] |  |  |  |  | 33075708 / MAIN BATT REQUIRED R/R BOTH MAIN BATT #1 AND #2 DUE TO BATTERY VOLTAGE FOUND LOW (33075708) |  | 0 / 1 | [] |  |  | WO.33075708 | 13003390 | 2026-08-10 | Performed
| 1440 | 33079373 | CAB - CALL BACK - AFT GALLEY AFT GALLEY 2 EACH BUSHING MISSING | 33079373 / CAB - CALL BACK - AFT GALLEY AFT GALLEY 2 EACH BUSHING MISSING (33079373) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 14:08 | 0.19653 |  | 0.23611 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33079373 / CAB - CALL BACK - AFT GALLEY AFT GALLEY 2 EACH BUSHING MISSING (33079373) |  | 0 / 1 | [] |  |  | WO.33079373 | 13003390 | 2026-08-10 | Performed
| 1441 | 33080727 | HORIZ - PNT - NO CALL BACK LH AND RH HORIZONTAL UPPER SURFACE CAUTION DECAL PEELED OFF | 33080727 / HORIZ - PNT - NO CALL BACK LH AND RH HORIZONTAL UPPER SURFACE CAUTION DECAL PEELED OFF (33080727) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 08:41 | 0.36597 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 51-21 |  | [] |  |  |  |  | 33080727 / HORIZ - PNT - NO CALL BACK LH AND RH HORIZONTAL UPPER SURFACE CAUTION DECAL PEELED OFF (33080727) |  | 0 / 1 | [] |  |  | WO.33080727 | 40000010 | 2026-08-10 | Performed
| 1443 | 33081333 | HYDRAULIC FLUID ANALYSIS ---- NO CALL BACK REF TO TASK CARD NO.291000-26-1 ANALYZE HYDRAULIC FLUID FOR CHLORINE, DENSITY, VISCOSITY AND CONDUCTIVITY CONTAMINATION. | 33081333 / HYDRAULIC FLUID ANALYSIS ---- NO CALL BACK REF TO TASK CARD NO.291000-26-1 ANALYZE HYDRAULIC FLUID FOR CHLORINE, DENSITY, VISCOSITY AND CONDUCTIVITY CONTAMINATION. (33081333) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 17.Aug.2026 09:16 | 0.083333 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 29-00 |  | [] |  |  |  |  | 33081333 / HYDRAULIC FLUID ANALYSIS ---- NO CALL BACK REF TO TASK CARD NO.291000-26-1 ANALYZE HYDRAULIC FLUID FOR CHLORINE, DENSITY, VISCOSITY AND CONDUCTIVITY CONTAMINATION. (33081333) |  | 0 / 1 | [] |  |  | WO.33081333 | 13008286 | 2026-08-20 | Performed
| 1444 | 33081618 | FWD AND AFT CBN COMP - PNT - NO CALL BACK FWD COMPARTMENT C101 AND AFT C201 COMPARTMENT INNER SIDE PAINT PEELED OFF | 33081618 / FWD AND AFT CBN COMP - PNT - NO CALL BACK FWD COMPARTMENT C101 AND AFT C201 COMPARTMENT INNER SIDE PAINT PEELED OFF (33081618) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 10.Aug.2026 07:16 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33081618 / FWD AND AFT CBN COMP - PNT - NO CALL BACK FWD COMPARTMENT C101 AND AFT C201 COMPARTMENT INNER SIDE PAINT PEELED OFF (33081618) |  | 0 / 1 | [] |  |  | WO.33081618 | 13008286 | 2026-08-11 | Performed
| 1445 | 33084011 | CAB - NO CALL BACK - LOWER SHROUD CAP SEAT AFT LOWER SHROUD CRACKED | 33084011 / CAB - NO CALL BACK - LOWER SHROUD CAP SEAT AFT LOWER SHROUD CRACKED (33084011) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 17.Aug.2026 02:47 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084011 / CAB - NO CALL BACK - LOWER SHROUD CAP SEAT AFT LOWER SHROUD CRACKED (33084011) |  | 0 / 1 | [] |  |  | WO.33084011 | 13008286 | 2026-08-17 | Performed
| 1446 | 33084029 | CAB - NO CALLBACK - UPPER SHROUD CAPTAIN UPPER SHROUD LOWER CORNER CUT | 33084029 / CAB - NO CALLBACK - UPPER SHROUD CAPTAIN UPPER SHROUD LOWER CORNER CUT (33084029) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 04:54 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084029 / CAB - NO CALLBACK - UPPER SHROUD CAPTAIN UPPER SHROUD LOWER CORNER CUT (33084029) |  | 0 / 1 | [] |  |  | WO.33084029 | 13003390 | 2026-08-20 | Performed
| 1447 | 33084129 | PNT - NO CALL BACK - CAP SEAT BOTTOM R/H BLACK METAL OF CAP. SEAT PAINT REQUIRED | 33084129 / PNT - NO CALL BACK - CAP SEAT BOTTOM R/H BLACK METAL OF CAP. SEAT PAINT REQUIRED (33084129) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 16.Aug.2026 07:07 | 0.16667 |  | 0.20139 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084129 / PNT - NO CALL BACK - CAP SEAT BOTTOM R/H BLACK METAL OF CAP. SEAT PAINT REQUIRED (33084129) |  | 0 / 1 | [] |  |  | WO.33084129 | 13008286 | 2026-08-18 | Performed
| 1448 | 33084211 | CAB - NO CALLLBACK - ARM CAP CAPTAIN SEAT R/H ARM CAP DISCOLORATION | 33084211 / CAB - NO CALLLBACK - ARM CAP CAPTAIN SEAT R/H ARM CAP DISCOLORATION (33084211) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 04:42 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084211 / CAB - NO CALLLBACK - ARM CAP CAPTAIN SEAT R/H ARM CAP DISCOLORATION (33084211) |  | 0 / 1 | [] |  |  | WO.33084211 | 13003390 | 2026-08-20 | Performed
| 1449 | 33084235 | CAB - NO CALLBACK- ARM CAP CAPTAIN SEAT L/H ARM CAP AND PLASTIC CASE DISCOLORATION | 33084235 / CAB - NO CALLBACK- ARM CAP CAPTAIN SEAT L/H ARM CAP AND PLASTIC CASE DISCOLORATION (33084235) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 03:32 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084235 / CAB - NO CALLBACK- ARM CAP CAPTAIN SEAT L/H ARM CAP AND PLASTIC CASE DISCOLORATION (33084235) |  | 0 / 1 | [] |  |  | WO.33084235 | 13003390 | 2026-08-20 | Performed
| 1450 | 33084561 | CAB - NO CALLBACK - WASTE COVER WASTE COVER SPRING STUCK IN THE OPEN POSITION | 33084561 / CAB - NO CALLBACK - WASTE COVER WASTE COVER SPRING STUCK IN THE OPEN POSITION (33084561) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 04:04 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33084561 / CAB - NO CALLBACK - WASTE COVER WASTE COVER SPRING STUCK IN THE OPEN POSITION (33084561) |  | 0 / 1 | [] |  |  | WO.33084561 | 40000010 | 2026-08-20 | Performed
| 1452 | 33088307 | CAB - NO CALLBACK - FLIGHT DECK DISK-LOCATING MISSING INSIDE CAP. SLIDING TABLE | 33088307 / CAB - NO CALLBACK - FLIGHT DECK DISK-LOCATING MISSING INSIDE CAP. SLIDING TABLE (33088307) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 04:37 | 0.0625 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33088307 / CAB - NO CALLBACK - FLIGHT DECK DISK-LOCATING MISSING INSIDE CAP. SLIDING TABLE (33088307) |  | 0 / 1 | [] |  |  | WO.33088307 | 13003390 | 2026-08-20 | Performed
| 1453 | 33088441 | FINDING (NRC) TASKCARD 25-20-00-00-SVA (01) / ITEM ONE ALL FLT ATT SEAT PAINT FADDED . | 33088441 / FINDING (NRC) TASKCARD 25-20-00-00-SVA (01) / ITEM ONE ALL FLT ATT SEAT PAINT FADDED . (33088441) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 11.Aug.2026 03:33 | 1900-01-05 07:27 |  | 1900-01-01 02:50 | Closed | 0 | T: 0; O: 0; C: 0 | 25-00 |  | [] |  |  |  |  | 33088441 / FINDING (NRC) TASKCARD 25-20-00-00-SVA (01) / ITEM ONE ALL FLT ATT SEAT PAINT FADDED . (33088441) |  | 0 / 1 | [] |  |  | WO.33088441 | 13008286 | 2026-08-17 | Performed
| 1454 | 33110305 | NLG DECAL -NO CALL BACK - NLG R/H TYRE PRESSURE AND INFLATE TYRES DECAL MISSING | 33110305 / NLG DECAL -NO CALL BACK - NLG R/H TYRE PRESSURE AND INFLATE TYRES DECAL MISSING (33110305) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 12.Aug.2026 06:53 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 11-00 |  | [] |  |  |  |  | 33110305 / NLG DECAL -NO CALL BACK - NLG R/H TYRE PRESSURE AND INFLATE TYRES DECAL MISSING (33110305) |  | 0 / 1 | [] |  |  | WO.33110305 | 13008286 | 2026-08-18 | Performed
| 1456 | 33110972 | NLG-CALL-BACK. NLG ACTUATOR CYLINDER REQUIRE SEALANT. | 33110972 / NLG-CALL-BACK. NLG ACTUATOR CYLINDER REQUIRE SEALANT. (33110972) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 09:56 | 0.052778 |  | 0.048611 | Closed | 0 | T: 0; O: 0; C: 0 | 32-21 |  | [] |  |  |  |  | 33110972 / NLG-CALL-BACK. NLG ACTUATOR CYLINDER REQUIRE SEALANT. (33110972) |  | 0 / 1 | [] |  |  | WO.33110972 | 13003081 | 2026-08-17 | Performed
| 1457 | 33111013 | NLG--CALL-BACK. NLG REQUIRE SEALANT. | 33111013 / NLG--CALL-BACK. NLG REQUIRE SEALANT. (33111013) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 16.Aug.2026 09:36 | 0.068056 |  | 0.069444 | Closed | 0 | T: 0; O: 0; C: 0 | 32-21 |  | [] |  |  |  |  | 33111013 / NLG--CALL-BACK. NLG REQUIRE SEALANT. (33111013) |  | 0 / 1 | [] |  |  | WO.33111013 | 13003081 | 2026-08-17 | Performed
| 1459 | 33112008 | LH WING MOVABLE FAIRING NO.3 --AV---NO CALLBACK LH WING MOVABLE FAIRING #3 (532CB) FOUND WITH DAMAGED STATIC DISCHARGE. | 33112008 / LH WING MOVABLE FAIRING NO.3 --AV---NO CALLBACK LH WING MOVABLE FAIRING #3 (532CB) FOUND WITH DAMAGED STATIC DISCHARGE. (33112008) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 14.Aug.2026 10:20 | 0.092361 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 33112008 / LH WING MOVABLE FAIRING NO.3 --AV---NO CALLBACK LH WING MOVABLE FAIRING #3 (532CB) FOUND WITH DAMAGED STATIC DISCHARGE. (33112008) |  | 0 / 1 | [] |  |  | WO.33112008 | 13003390 | 2026-08-14 | Performed
| 1460 | 33112583 | CAB - NO CALLBACK - COCKPIT L/H WINDOW LINING BOTTOM CORNER DAMAGED | 33112583 / CAB - NO CALLBACK - COCKPIT L/H WINDOW LINING BOTTOM CORNER DAMAGED (33112583) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 07:19 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33112583 / CAB - NO CALLBACK - COCKPIT L/H WINDOW LINING BOTTOM CORNER DAMAGED (33112583) |  | 0 / 1 | [] |  |  | WO.33112583 | 13003390 | 2026-08-20 | Performed
| 1467 | 33114000 | CAB - NO CALLBACK - COCKPIT PROTECTIVE CB PANEL FOUND BROKEN | 33114000 / CAB - NO CALLBACK - COCKPIT PROTECTIVE CB PANEL FOUND BROKEN (33114000) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Aug.2026 06:31 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33114000 / CAB - NO CALLBACK - COCKPIT PROTECTIVE CB PANEL FOUND BROKEN (33114000) |  | 0 / 1 | [] |  |  | WO.33114000 | 13003390 | 2026-08-20 | Performed
| 1469 | 33114126 | PNT - NO CALLBACK - COCKPIT FLIGHT OFFICER ALL AROUND WINDOW FRAME REQUIRED PAINT | 33114126 / PNT - NO CALLBACK - COCKPIT FLIGHT OFFICER ALL AROUND WINDOW FRAME REQUIRED PAINT (33114126) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 14.Aug.2026 09:38 | 1900-01-02 19:10 |  | 0.45833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33114126 / PNT - NO CALLBACK - COCKPIT FLIGHT OFFICER ALL AROUND WINDOW FRAME REQUIRED PAINT (33114126) |  | 0 / 1 | [] |  |  | WO.33114126 | 13008286 | 2026-08-18 | Performed
| 1471 | 33115217 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 AFT & FWD PAX DOOR GIRT-BAR FITTING BALNKING -PLATES REQ PNT | 33115217 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 AFT & FWD PAX DOOR GIRT-BAR FITTING BALNKING -PLATES REQ PNT (33115217) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 13.Aug.2026 10:27 | 0.34653 |  | 0.77083 | Closed | 0 | T: 0; O: 0; C: 0 | 52-13-15 |  | [] |  |  |  |  | 33115217 / FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 AFT & FWD PAX DOOR GIRT-BAR FITTING BALNKING -PLATES REQ PNT (33115217) |  | 0 / 1 | [] |  |  | WO.33115217 | 13003390 | 2026-08-14 | Performed
| 1472 | 33118102 | ENG NO.1 RH FAN COWL. PNT NO CALL BACK ENG NO.1 RH FAN COWL INBD SIDE REQUIRE PRIMER. | 33118102 / ENG NO.1 RH FAN COWL. PNT NO CALL BACK ENG NO.1 RH FAN COWL INBD SIDE REQUIRE PRIMER. (33118102) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 15.Aug.2026 02:54 | 1900-01-02 01:53 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 71 |  | [] |  |  |  |  | 33118102 / ENG NO.1 RH FAN COWL. PNT NO CALL BACK ENG NO.1 RH FAN COWL INBD SIDE REQUIRE PRIMER. (33118102) |  | 0 / 1 | [] |  |  | WO.33118102 | 13008286 | 2026-08-18 | Performed
| 1473 | 33118115 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV D BEHIND CLOSET S302 TEDLAR DAMAGED | 33118115 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV D BEHIND CLOSET S302 TEDLAR DAMAGED (33118115) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Aug.2026 10:24 | 1900-01-01 02:21 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33118115 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV D BEHIND CLOSET S302 TEDLAR DAMAGED (33118115) |  | 0 / 1 | [] |  |  | WO.33118115 | 13003390 | 2026-08-14 | Performed
| 1474 | 33118117 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV E BEHIND CLOSET S201 TEDLAR DAMAGED | 33118117 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV E BEHIND CLOSET S201 TEDLAR DAMAGED (33118117) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 13.Aug.2026 10:31 | 1900-01-01 02:11 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33118117 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND FWD WALL OF LAV E BEHIND CLOSET S201 TEDLAR DAMAGED (33118117) |  | 0 / 1 | [] |  |  | WO.33118117 | 13003390 | 2026-08-14 | Performed
| 1475 | 33119289 | FINDING (NRC) TASKCARD 215222-01-1 (3) / ITEM-1 AP--NOCALLBACK LEFT HAND PACK CONNECTION BETWEEN AIR CYCLE MACHINE AND PRIMARY HEAT EXCHANGER AND ACM TURBINE LINE WITH LEAK | 33119289 / FINDING (NRC) TASKCARD 215222-01-1 (3) / ITEM-1 AP--NOCALLBACK LEFT HAND PACK CONNECTION BETWEEN AIR CYCLE MACHINE AND PRIMARY HEAT EXCHANGER AND ACM TURBINE LINE WITH LEAK (33119289) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 14.Aug.2026 09:38 | 1899-12-31 00:09 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 21-52 |  | [] |  |  |  |  | 33119289 / FINDING (NRC) TASKCARD 215222-01-1 (3) / ITEM-1 AP--NOCALLBACK LEFT HAND PACK CONNECTION BETWEEN AIR CYCLE MACHINE AND PRIMARY HEAT EXCHANGER AND ACM TURBINE LINE WITH LEAK (33119289) |  | 0 / 1 | [] |  |  | WO.33119289 | 13003390 | 2026-08-15 | Performed
| 1476 | 33119810 | 191BT PEELED OFF PAINT - PNT - NO CALLBACK WING TO FUSELAGE PANEL # 191BT FOUND WITH PEELED OFF PAINT, REQUIRE PAINT. | 33119810 / 191BT PEELED OFF PAINT - PNT - NO CALLBACK WING TO FUSELAGE PANEL # 191BT FOUND WITH PEELED OFF PAINT, REQUIRE PAINT. (33119810) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.41667 | 15.Aug.2026 10:55 | 0.25 |  | 0.4375 | Closed | 0 | T: 0; O: 0; C: 0 | 53-09 |  | [] |  |  |  |  | 33119810 / 191BT PEELED OFF PAINT - PNT - NO CALLBACK WING TO FUSELAGE PANEL # 191BT FOUND WITH PEELED OFF PAINT, REQUIRE PAINT. (33119810) |  | 0 / 1 | [] |  |  | WO.33119810 | 13003081 | 2026-08-16 | Performed
| 1477 | 33122442 | FADED IDENTIFICATION DECAL - PNT - NO CALL BACK FADED IDENTIFICATION DECAL ON LH/RH WING L/E PNL 522NB AND 621AB | 33122442 / FADED IDENTIFICATION DECAL - PNT - NO CALL BACK FADED IDENTIFICATION DECAL ON LH/RH WING L/E PNL 522NB AND 621AB (33122442) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 20.Aug.2026 13:26 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33122442 / FADED IDENTIFICATION DECAL - PNT - NO CALL BACK FADED IDENTIFICATION DECAL ON LH/RH WING L/E PNL 522NB AND 621AB (33122442) |  | 0 / 1 | [] |  |  | WO.33122442 | 13003081 | 2026-08-20 | Performed
| 1478 | 33122455 | CHIPPED OFF PAINT ON WING L/E PNLS - PNT- NO CALL BACK CHIPPED OFF PAINT ON WING L/E PNLS 522AB, 522UB, AND 622LB | 33122455 / CHIPPED OFF PAINT ON WING L/E PNLS - PNT- NO CALL BACK CHIPPED OFF PAINT ON WING L/E PNLS 522AB, 522UB, AND 622LB (33122455) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 16.Aug.2026 05:31 | 1899-12-31 23:16 |  | 0.26389 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] |  |  |  |  | 33122455 / CHIPPED OFF PAINT ON WING L/E PNLS - PNT- NO CALL BACK CHIPPED OFF PAINT ON WING L/E PNLS 522AB, 522UB, AND 622LB (33122455) |  | 0 / 1 | [] |  |  | WO.33122455 | 13008286 | 2026-08-18 | Performed
| 1479 | 33126431 | MAIN BATT# 2 REQUIRED R/R MAIN BATT #2 DUE TO BATTERY VOLTAGE FOUND LOW | 33126431 / MAIN BATT# 2 REQUIRED R/R MAIN BATT #2 DUE TO BATTERY VOLTAGE FOUND LOW (33126431) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 17.Aug.2026 06:35 | 0.084028 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 24 |  | [] |  |  |  |  | 33126431 / MAIN BATT# 2 REQUIRED R/R MAIN BATT #2 DUE TO BATTERY VOLTAGE FOUND LOW (33126431) |  | 0 / 1 | [] |  |  | WO.33126431 | 13008286 | 2026-08-17 | Performed
| 1480 | 33126961 | PNT - NO CALLBACK - LAV A LAV A UPPER SERVICE CABINET DOOR PAINT FADED | 33126961 / PNT - NO CALLBACK - LAV A LAV A UPPER SERVICE CABINET DOOR PAINT FADED (33126961) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 20.Aug.2026 12:36 | 0.16667 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 33126961 / PNT - NO CALLBACK - LAV A LAV A UPPER SERVICE CABINET DOOR PAINT FADED (33126961) |  | 0 / 1 | [] |  |  | WO.33126961 | 13003081 | 2026-08-20 | Performed
| 1481 | 33126962 | LH WING TRAILING EDGE PANELS PAINT CHIPPED -- PNT -- NO CALL BACK LH WING TRAILING EDGE PANELS # 573BB AND 573AB FOUND WITH CHIPPED PAINT. | 33126962 / LH WING TRAILING EDGE PANELS PAINT CHIPPED -- PNT -- NO CALL BACK LH WING TRAILING EDGE PANELS # 573BB AND 573AB FOUND WITH CHIPPED PAINT. (33126962) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 16.Aug.2026 13:15 | 0.10486 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 57-32 |  | [] |  |  |  |  | 33126962 / LH WING TRAILING EDGE PANELS PAINT CHIPPED -- PNT -- NO CALL BACK LH WING TRAILING EDGE PANELS # 573BB AND 573AB FOUND WITH CHIPPED PAINT. (33126962) |  | 0 / 1 | [] |  |  | WO.33126962 | 40000010 | 2026-08-16 | Performed
| 1483 | 33127887 | S29-R10066/HYDRAULIC SYS FLUID SAMPLE ANALYSIS. | 33127887 / S29-R10066/HYDRAULIC SYS FLUID SAMPLE ANALYSIS. (33127887) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1875 | 17.Jul.2026 22:00 | 0.1875 | 19.Aug.2026 08:38 | 0.91736 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 29 |  | [] |  |  |  |  | 33127887 / S29-R10066/HYDRAULIC SYS FLUID SAMPLE ANALYSIS. (33127887) |  | 0 / 2 | [] |  |  | ME.33127887 | 13008286 | 2026-08-20 | Performed
| 1484 | 33129454 | PANEL 344AT DETERIORATED DECAL---PNT---NO CALLBACK---- ELEVATOR PANEL NO (344AT) UPPER SURFACE HAS DETERIORATED DECAL REQ PNT ACTION | 33129454 / PANEL 344AT DETERIORATED DECAL---PNT---NO CALLBACK---- ELEVATOR PANEL NO (344AT) UPPER SURFACE HAS DETERIORATED DECAL REQ PNT ACTION (33129454) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 17.Aug.2026 05:08 | 0.18194 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] |  |  |  |  | 33129454 / PANEL 344AT DETERIORATED DECAL---PNT---NO CALLBACK---- ELEVATOR PANEL NO (344AT) UPPER SURFACE HAS DETERIORATED DECAL REQ PNT ACTION (33129454) |  | 0 / 1 | [] |  |  | WO.33129454 | 13008286 | 2026-08-17 | Performed
| 1485 | 33129954 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D INNER WALL TEDLAR DAMAGED | 33129954 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D INNER WALL TEDLAR DAMAGED (33129954) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.5 | 16.Aug.2026 12:56 | 1899-12-31 03:54 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33129954 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D INNER WALL TEDLAR DAMAGED (33129954) |  | 0 / 1 | [] |  |  | WO.33129954 | 13003953 | 2026-08-17 | Performed
| 1486 | 33129955 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C101 TEDLAR DAMAGED | 33129955 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C101 TEDLAR DAMAGED (33129955) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 17.Aug.2026 02:00 | 0.61736 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33129955 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C101 TEDLAR DAMAGED (33129955) |  | 0 / 1 | [] |  |  | WO.33129955 | 13003953 | 2026-08-17 | Performed
| 1487 | 33129977 | ELEVATOR PANELS UPPER SIDE WITH BROKEN SCREWS -SM--NO CALLBACK-- ELEVATOR UPPER/AFT SIDE PANELS R/H SIDE ( 344AT, 344CT) L/H SIDE ( 334AT, 334BT, 334CT, 334DT) SCREWS HEAD BEEN CUT OFF , REMAINING SCREW SHANKS WITHIN CLIP NUTS. REQ S/M ACTI... | 33129977 / ELEVATOR PANELS UPPER SIDE WITH BROKEN SCREWS -SM--NO CALLBACK-- ELEVATOR UPPER/AFT SIDE PANELS R/H SIDE ( 344AT, 344CT) L/H SIDE ( 334AT, 334BT, 334CT, 334DT) SCREWS HEAD BEEN CUT OFF , REMAINING SCREW SHANKS WITHIN CLIP NUTS. REQ S/M ACTI... (33129977) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 17.Aug.2026 04:15 | 1899-12-31 06:15 |  | 1899-12-31 18:45 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 33129977 / ELEVATOR PANELS UPPER SIDE WITH BROKEN SCREWS -SM--NO CALLBACK-- ELEVATOR UPPER/AFT SIDE PANELS R/H SIDE ( 344AT, 344CT) L/H SIDE ( 334AT, 334BT, 334CT, 334DT) SCREWS HEAD BEEN CUT OFF , REMAINING SCREW SHANKS WITHIN CLIP NUTS. REQ S/M ACTI... (33129977) |  | 0 / 1 | [] |  |  | WO.33129977 | 13003081 | 2026-08-18 | Performed
| 1488 | 33141095 | PNT - NO CALL BACK - COCKPIT CAPTAIN SLIDING FOLDABLE TABLE AROUND DISK-LOCATING BLACK RUBBER AND MIDDLE LATCH REQ PAINT | 33141095 / PNT - NO CALL BACK - COCKPIT CAPTAIN SLIDING FOLDABLE TABLE AROUND DISK-LOCATING BLACK RUBBER AND MIDDLE LATCH REQ PAINT (33141095) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 17.Aug.2026 17:16 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 33141095 / PNT - NO CALL BACK - COCKPIT CAPTAIN SLIDING FOLDABLE TABLE AROUND DISK-LOCATING BLACK RUBBER AND MIDDLE LATCH REQ PAINT (33141095) |  | 0 / 1 | [] |  |  | WO.33141095 | 13003081 | 2026-08-17 | Performed
| 1491 | 33143477 | CAB - NO CALL BACK CLOSET DOOR C101 UPPER SIDE TEDLAR DAMMAGE | 33143477 / CAB - NO CALL BACK CLOSET DOOR C101 UPPER SIDE TEDLAR DAMMAGE (33143477) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 17.Aug.2026 02:00 | 0.61597 |  | 0.625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33143477 / CAB - NO CALL BACK CLOSET DOOR C101 UPPER SIDE TEDLAR DAMMAGE (33143477) |  | 0 / 1 | [] |  |  | WO.33143477 | 13003953 | 2026-08-17 | Performed
| 1493 | 33147441 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 35J, 36C AND 39C BUMPER – ENDBAY LOOSE. | 33147441 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 35J, 36C AND 39C BUMPER – ENDBAY LOOSE. (33147441) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Aug.2026 13:20 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 33147441 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 35J, 36C AND 39C BUMPER – ENDBAY LOOSE. (33147441) |  | 0 / 1 | [] |  |  | WO.33147441 | 40000010 | 2026-08-19 | Performed
| 1497 | 33151610 | ENGINE 1 STARTER SERVICING -- AP REFER TO TASKCARD: 801110-C3-1-001 STEP 1(7) | 33151610 / ENGINE 1 STARTER SERVICING -- AP REFER TO TASKCARD: 801110-C3-1-001 STEP 1(7) (33151610) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 18.Aug.2026 10:14 | 1899-12-31 00:09 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 12-13 |  | [] |  |  |  |  | 33151610 / ENGINE 1 STARTER SERVICING -- AP REFER TO TASKCARD: 801110-C3-1-001 STEP 1(7) (33151610) |  | 0 / 1 | [] |  |  | WO.33151610 | 13003390 | 2026-08-19 | Performed
| 1499 | 33152581 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND AFT WALL OF SEAT 44 ABC TEDLAR DAMAGED | 33152581 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND AFT WALL OF SEAT 44 ABC TEDLAR DAMAGED (33152581) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.54167 | 18.Aug.2026 10:43 | 0.27083 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33152581 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND AFT WALL OF SEAT 44 ABC TEDLAR DAMAGED (33152581) |  | 0 / 1 | [] |  |  | WO.33152581 | 13008286 | 2026-08-19 | Performed
| 1500 | 33152650 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D OUTER WALL TEDLAR DAMAGED | 33152650 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D OUTER WALL TEDLAR DAMAGED (33152650) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.54167 | 18.Aug.2026 10:52 | 0.27292 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33152650 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D OUTER WALL TEDLAR DAMAGED (33152650) |  | 0 / 1 | [] |  |  | WO.33152650 | 13008286 | 2026-08-19 | Performed
| 1501 | 33152727 | WING ROOT PANEL 192DT HAS BROKEN ANCHOR NUTS--SM--NO CALLBACK-- R/H WING ROOT PANEL 192DT HAS 2 BROKEN ANCHOR NUTS, REQ S/M ACTION. | 33152727 / WING ROOT PANEL 192DT HAS BROKEN ANCHOR NUTS--SM--NO CALLBACK-- R/H WING ROOT PANEL 192DT HAS 2 BROKEN ANCHOR NUTS, REQ S/M ACTION. (33152727) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Aug.2026 03:00 | 0.35417 |  | 1899-12-31 04:20 | Closed | 0 | T: 1; O: 0; C: 1 | 28-11 |  | [] |  |  |  |  | 33152727 / WING ROOT PANEL 192DT HAS BROKEN ANCHOR NUTS--SM--NO CALLBACK-- R/H WING ROOT PANEL 192DT HAS 2 BROKEN ANCHOR NUTS, REQ S/M ACTION. (33152727) |  | 0 / 1 | [] |  |  | WO.33152727 | 13008286 | 2026-08-20 | Performed
| 1503 | 33157310 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D DOOR BOTH SIDE TEDLAR DAMAGED | 33157310 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D DOOR BOTH SIDE TEDLAR DAMAGED (33157310) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.54167 | 17.Jul.2026 22:00 | 0.54167 | 19.Aug.2026 09:37 | 0.27222 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33157310 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND LAV D DOOR BOTH SIDE TEDLAR DAMAGED (33157310) |  | 0 / 1 | [] |  |  | WO.33157310 | 40000010 | 2026-08-19 | Performed
| 1504 | 33157316 | FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C201, C202, C203 TEDLAR DAMAGED | 33157316 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C201, C202, C203 TEDLAR DAMAGED (33157316) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.29167 | 17.Jul.2026 22:00 | 0.29167 | 19.Aug.2026 09:19 | 0.29167 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 25-20 |  | [] |  |  |  |  | 33157316 / FINDING (NRC) TASKCARD DCC-32S (13) / ITEM ONE DURING DCC FOUND CLOSET C201, C202, C203 TEDLAR DAMAGED (33157316) |  | 0 / 1 | [] |  |  | WO.33157316 | 40000010 | 2026-08-19 | Performed
| 1505 | 33157427 | PNT - RH WING - 631AB - NO CALLBACK RH WING 631AB ACCESS PANEL FWD EDGE REQUIRES PAINT TOUCH UP AS PER INSP FINDING. | 33157427 / PNT - RH WING - 631AB - NO CALLBACK RH WING 631AB ACCESS PANEL FWD EDGE REQUIRES PAINT TOUCH UP AS PER INSP FINDING. (33157427) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 20.Aug.2026 11:59 | 0.19653 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 33157427 / PNT - RH WING - 631AB - NO CALLBACK RH WING 631AB ACCESS PANEL FWD EDGE REQUIRES PAINT TOUCH UP AS PER INSP FINDING. (33157427) |  | 0 / 1 | [] |  |  | WO.33157427 | 13003081 | 2026-08-20 | Performed