## HZ-ASD Tracker
POOL CABIN ✈ HZ-ASD ✈ C2+6Y CHECK WORK PACKAGE TRACKER |  |  |  | DAY 6/38 |  |  | ✅ 36 / 349 Closed (10%)
LAST UPDATE: 22-Jul · 36 row(s) updated — filter column L for details | [6 empty] | AOG/Critical: 5
WO / Event Number | Task Description | Seq. No. | Category | Status | Priority | Specialty | PARTS REQ. | Remarks | Time EVAL? | AREA | Updated | Closed Date | Est MH | ATA | Booked MH | Actual Dur (h)
32797253 | 6Y_N/6Y_N YEARS STRUCTURE | 1 | ACFT GENERAL T/C | Open | Normal | AP |  |  | N/A | JOINT |  |  | 0 | 05
200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 24 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 5.2 | 24-92 | 8.5 | 18.6
200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 25 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A |  |  |  | 3 | 24-92 | 11 | 19.1
200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 26 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | AFT |  |  | 2.1 | 24-92 | 9.5 | 18.5
25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 32 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509031 | N/A | FWD | 2026-07-19 |  | 2 | 25-11
25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 33 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509039 | N/A | FWD | 2026-07-19 |  | 2 | 25-11
25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 34 | F/A SEAT | Open | AOG | CAB | Requested | P/S 4509037 (SOME PARTS S/D) | N/A | JOINT | 2026-07-19 |  | 4 | 25-22
253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 35 | GALLEY | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 0.5 | 25-30 | 44 | 74.8
254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 36 | LAVATORY | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 0.2 | 25-40 | 15 | 62.2
256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 37 | FLIGHT DECK | Closed | Normal | JOINT |  | C/W | N/A | FWD | 2026-07-22 | 2026-07-20 | 0.4 | 25-61 | 12 | 2.8
262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 38 | LAVATORY | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-20 | 0.2 | 26-25 | 0.8 | 0.8
323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 44 | ACFT GENERAL T/C | Open | Normal |  |  | CABIN + COCKPIT ACCESS | N/A |  |  |  | 2.2 | 32-33
323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 45 | ACFT GENERAL T/C | Open | Normal |  |  | CABIN + COCKPIT ACCESS | N/A |  |  |  | 0.6 | 32-33
531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 51 | PAX DOORS | Open | Normal |  |  | EXTERNAL | N/A | FWD |  |  | 0.7 | 53-11
531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 52 | ACFT GENERAL T/C | Open | Normal |  |  | A&P | N/A | FWD |  |  | 2.9 | 53-11
531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 53 | ACFT GENERAL T/C | Open | Normal |  |  | FWD DOORS GIRT FITTINGS | N/A | FWD |  |  | 3.5 | 53-11
531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 55 | ACFT GENERAL T/C | Open | Normal | INSP |  | FWD GALLEY + LAV A + SOME B/C SEATS + COCKPIT DOOR + FLOOR PANELS REMOVAL | N/A | FWD | 2026-07-19 |  | 4.9 | 53-11
531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 56 | ACFT GENERAL T/C | Open | Normal | INSP |  | FWD GALLEY + LAV A + SOME B/C SEATS + COCKPIT DOOR + FLOOR PANELS REMOVAL | N/A | FWD | 2026-07-19 |  | 21.9 | 53-11
531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 57 | ACFT GENERAL T/C | Open | Normal | INSP |  | G2 GALLEY + SOME B/C SEATS REMOVAL | N/A | FWD | 2026-07-19 |  | 39.8 | 53-11
534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 60 | ACFT GENERAL T/C | Open | Normal | JOINT |  | CAB + INSP | N/A | AFT |  |  | 0.8 | 53-41
534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 61 | ACFT GENERAL T/C | Open | Normal | JOINT |  | CAB + INSP | N/A | AFT |  |  | 5.7 | 53-41
534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 62 | ACFT GENERAL T/C | Open | Normal |  |  | REMOVE ALL GALLEYS AND LAVS + SOME ROWS OF G/C SEATS | N/A | JOINT |  |  | 89 | 53-41
534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 66 | ACFT GENERAL T/C | Open | Normal |  |  | AFT AREA / OPEN UP | N/A | AFT |  |  | 8 | 53-41
562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 79 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 13.2 | 56-21
ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | 109 | ACFT GENERAL T/C | Open | Normal |  |  | CAB + INSP / FR 36 TO FR 46 | N/A | JOINT |  |  | 11.5 | 05-21
ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | 115 | ACFT GENERAL T/C | Open | Normal | INSP |  | ISNP | N/A | AFT |  |  | 77 | 05-21 | 2 | 17.4
ZL-193-01-1 | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA | 117 | ACFT GENERAL T/C | Open | Normal | AP |  | OFFWING SLIDE (AP) | N/A |  |  |  | 1.8 | 05-21
ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | 122 | FLIGHT DECK | Open | Normal | INSP |  | INSP | N/A | FWD |  |  | 0.4 | 05-22
ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | 157 | PAX DOORS | Open | Normal | AP |  | AP | N/A | JOINT |  |  | 2 | 05-28 | 2 | 23.2
31871161 | A_N (A_N09)/A_N-CHECK | 158 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 0 | 20-00
05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 159 | GENERAL CABIN | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 2.2 | 05 | 8 | 42.3
11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 160 | GENERAL CABIN | Open | Normal | PAINT |  | PAINT | N/A | JOINT |  |  | 1 | 11-11
212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 162 | LAVATORY | Closed | Normal | CAB | Requested | P/S 4509043 | N/A | JOINT | 2026-07-22 | 2026-07-20 | 0.4 | 21-23 | 2 | 1
25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 168 | FLIGHT DECK | Open | Normal | CAB |  | CAB ONLY | N/A | FWD |  |  | 5.8 | 25-10 | 25.5 | 27.3
25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 169 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 5.8 | 25-10 | 26.5 | 46.5
25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 170 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 2.3 | 25-10 | 7.5 | 23.4
25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 171 | PAX SEAT | Open | Normal | SEAT |  | STEP 8 (CAB POOL SPLTY) | N/A | JOINT |  |  | 1.5 | 25-10 | 6 | 23.6
25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 172 | F/A SEAT | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 2.75 | 25-10 | 18 | 39.4
25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 173 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509045 | N/A | JOINT | 2026-07-19 |  | 4 | 25-26
25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 174 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509318 | N/A | JOINT | 2026-07-19 |  | 4 | 25-28
25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 175 | GALLEY | Open | Normal | AV |  | AV | N/A | JOINT |  |  | 2 | 25-30
25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 176 | GALLEY | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 0.5 | 25-30
25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 177 | GALLEY | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 6.9 | 25-10 | 28.5 | 75.3
25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 178 | LAVATORY | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 7.4 | 25-10 | 3.5 | 16.1
25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 179 | F/A SEAT | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-20 | 2 | 25-60 | 1 | 1
25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 180 | GENERAL CABIN | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-21 | 2 | 25-65 | 1 | 1
25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 181 | GENERAL CABIN | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-21 | 1 | 25-65 | 1 | 1
253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 182 | GALLEY | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.3 | 20-00
253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 183 | GALLEY | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.4 | 25-34
256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 186 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.9 | 25-62
261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 189 | LAVATORY | Open | Normal | AV |  | AV | N/A | JOINT |  |  | 0.5 | 24
31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 207 | FLIGHT DECK | Open | Normal | AV |  | AV | N/A | FWD |  |  | 2 | 31-63
353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 215 | GENERAL CABIN | Closed | Normal | JOINT |  | CAB + INSP | N/A | JOINT | 2026-07-22 | 2026-07-21 | 0.4 | 35-32 | 6.5 | 5.2
353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 216 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-19 | 0.4 | 35-30 | 2.8 | 3.8
383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 219 | LAVATORY | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.2 | 38-32
525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 223 | FLIGHT DECK | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 0.9 | 52-51 | 7.8 | 47.3
527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 224 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A |  |  |  | 0.4 | 12-22
561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 227 | FLIGHT DECK | Open | Normal | AP |  | AP + INSP (ACCESS) | N/A | FWD |  |  | 2 | 56-10 | 10 | 27.8
31574335 | C_N (C_N02)/C-CHECK | 233 | ACFT GENERAL T/C | Open | Normal | AP |  |  | N/A | JOINT |  |  | 0 | 20-00
05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 234 | ACFT GENERAL T/C | Open | Normal | INSP |  | SVTI | N/A | JOINT |  |  | 1 | 05-00
08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 235 | ACFT GENERAL T/C | Open | Normal | AP |  |  | N/A | JOINT |  |  | 65 | 08-10
212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 241 | FLIGHT DECK | Open | Normal | AP |  | AP | N/A | FWD |  |  | 0.4 | 21-21
23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 257 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 8 | 23-73 | 4 | 2
233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 258 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 0.9 | 23-33 | 6 | 2.1
235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 259 | FLIGHT DECK | Open | Normal | AV |  | AV | N/A | FWD |  |  | 0.22 | 23-51 | 4 | 45
25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 272 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509325 | N/A | FWD | 2026-07-19 |  | 0.5 | 25-11
25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 273 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509326 | N/A | FWD | 2026-07-19 |  | 1 | 25-11
25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 274 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509328 | N/A | FWD | 2026-07-19 |  | 4 | 25-11
25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 275 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509333 | N/A | FWD | 2026-07-19 |  | 0.5 | 25-11
25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 276 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509334 | N/A | JOINT | 2026-07-19 |  | 48 | 25-28
25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 277 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509336 | N/A | FWD | 2026-07-19 |  | 6 | 25-28
25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 278 | FLIGHT DECK | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 3.3 | 25 | 2 | 46.5
25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 279 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 11.7 | 25 | 3 | 46.9
25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 280 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 5.2 | 25 | 7 | 16
25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 281 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 19 | 25
25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 282 | PAX SEAT | Open | Normal | SEAT |  | STEP 6 (CAB POOL SPLTY) | N/A | JOINT |  |  | 1.8 | 25 | 14.5 | 30
25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 283 | GALLEY | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 2 | 25 | 8 | 18.9
25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 284 | LAVATORY | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 2 | 25 | 4.5 | 16
25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 285 | F/A SEAT | Open | Normal | CAB |  | CAB ONLY | N/A | JOINT |  |  | 3 | 25
25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 286 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 0.5 | 25
25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 287 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 0.5 | 25
252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 288 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 38 | 25-21 | 28.5 | 51.3
252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 289 | PAX SEAT | Open | Normal | CAB |  | CAB + INSP (AND SHOP) | N/A | JOINT |  |  | 2.7 | 25-21 | 17.5 | 19.6
2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 290 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 3 | 25-21 | 2 | 25.1
2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 291 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 7 | 25-21 | 6 | 26.1
252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 292 | F/A SEAT | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 0.7 | 25-22
252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 293 | F/A SEAT | Closed | Normal | INSP |  | INSP | N/A | JOINT | 2026-07-22 | 2026-07-20 | 0 | 25-22 | 0.8 | 0.8
254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 294 | LAVATORY | Closed | Normal | INSP |  | INSP | N/A | JOINT | 2026-07-22 | 2026-07-20 | 3.3 | 25-40 | 0.8 | 0.8
256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 297 | GENERAL CABIN | Open | Normal | AV |  | AV | N/A | JOINT |  |  | 0.22 | 25-65 | 2 | 71.5
256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 299 | GENERAL CABIN | Open | Normal | JOINT |  | MAPPING COMPLETED, CONTINUE DAY SHIFT | N/A | JOINT | 2026-07-19 |  | 0.5 | 25-11 | 46.5 | 74.8
262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 312 | LAVATORY | Closed | Normal | INSP |  | INSP | N/A | JOINT | 2026-07-22 | 2026-07-20 | 0.2 | 26-25 | 0.8 | 0.8
335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 413 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 0.2 | 33-51 | 9 | 3.1
351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 425 | FLIGHT DECK | Open | Normal | CAB |  | CAB | N/A | FWD |  |  | 0.2 | 35-12
351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 426 | FLIGHT DECK | Closed | Normal | JOINT |  | TO DO | N/A | FWD | 2026-07-22 | 2026-07-20 | 0.6 | 35-12 | 10 | 4.4
352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 427 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 2 | 35-23 | 45 | 47.9
352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 428 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 2.4 | 35-21 | 48.5 | 51.3
353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 429 | FLIGHT DECK | Closed | Normal | JOINT |  | C/W | N/A | FWD | 2026-07-22 | 2026-07-20 | 2.2 | 25-64 | 3.5 | 1.6
353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 430 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-19 | 0.4 | 35-30 | 3.5 | 3.3
383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 439 | LAVATORY | Open | Normal | AP |  | OPEN UP | N/A | JOINT |  |  | 10 | 38-31
384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 442 | ACFT GENERAL T/C | Open | Normal | AP |  | AP | N/A | JOINT |  |  | 0.7 | 38-42
521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 446 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 5 | 52-10
521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 447 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.7 | 52-10
521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 448 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 5 | 52-10
521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 449 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 5 | 52-10
521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 450 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 1.5 | 52-10
521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 451 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 1.5 | 52-10
521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 452 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 1.5 | 52-10
521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 453 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 1.5 | 52-10
521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 454 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 5 | 52-10
521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 455 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.9 | 52-10
521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 456 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 1.8 | 52-10
521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 457 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 0.9 | 52-10
521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 458 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 0.9 | 52-10
521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 459 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.9 | 52-10
521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 460 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.9 | 52-10
521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 461 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.4 | 52-10
521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 462 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 1.5 | 52-10
521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 463 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.4 | 52-10
521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 464 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 3.7 | 52-10
521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 465 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.9 | 12-22
522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 466 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 467 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 468 | PAX DOORS | Open | Normal | AP |  | AP + INSP | N/A |  |  |  | 3.5 | 52-21
522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 469 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 473 | FLIGHT DECK | Closed | Normal | JOINT |  | CAB + INSP | N/A | FWD | 2026-07-22 | 2026-07-21 | 0.6 | 52-51 | 7.8 | 3.9
525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 474 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-22 | 2026-07-22 | 0.3 | 52-51 | 4.8 | 3
525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 475 | FLIGHT DECK | Open | Normal | AV |  | AV + INSP | N/A | FWD |  |  | 0.4 | 52-51
525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 476 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-22 | 2026-07-22 | 0.1 | 52-51 | 4.5 | 3.1
525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 477 | FLIGHT DECK | Open | Normal | AV |  | AV + INSP | N/A | FWD |  |  | 0.1 | 52-51
527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 478 | PAX DOORS | Open | Normal | AV |  | AV | N/A | JOINT |  |  | 0.1 | 52-71
527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 479 | PAX DOORS | Open | Normal | AV |  | AV + INSP | N/A | JOINT |  |  | 0.2 | 52-73
527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 480 | PAX DOORS | Open | Normal | AV |  | AV + INSP | N/A | JOINT |  |  | 0.2 | 52-73
531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 481 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 0.9 | 53-11
531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 482 | FLIGHT DECK | Open | Normal | AP |  | AP + INSP | N/A | FWD |  |  | 0.4 | 53-11
531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 483 | FLIGHT DECK | Open | Normal | AP |  | AP + INSP | N/A | FWD |  |  | 2.3 | 53-11
531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 484 | FLIGHT DECK | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 2.3 | 53-11
561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 509 | FLIGHT DECK | Open | Normal | CAB |  | P/S 4509339 | N/A | FWD |  |  | 0.4 | 12-22
38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 591 | ACFT GENERAL T/C | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 10 | 38-10
521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 594 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.9 | 12-22
521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 595 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 0.9 | 12-22
ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | 602 | PAX DOORS | Closed | Normal | CAB |  | INSP | N/A | AFT | 2026-07-22 | 2026-07-20 | 0.2 | 05-28 | 1 | 1
05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 603 | ACFT GENERAL T/C | Open | Normal | PLNG |  | PLNG | N/A | JOINT |  |  | 1 | 05-11
521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 609 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 2.5 | 52-10
521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 610 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 3.5 | 25-62
521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 611 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | AFT |  |  | 3.5 | 52-13
522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 612 | PAX DOORS | Open | Normal | AP |  | AP + INSP | N/A | JOINT |  |  | 10.1 | 52-21
531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 618 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 6.3 | 53-11
533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 626 | ACFT GENERAL T/C | Open | Normal | AP |  | AP + INSP | N/A |  |  |  | 2.1 | 53
534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 630 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (AFT GALLEY/LAVS - AFT DOOR LININGS - BLANKETS) | N/A | AFT |  |  | 16.4 | 53-41
534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 631 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (AFT GALLEY/LAVS - AFT DOOR LININGS - BLANKETS) | N/A | AFT |  |  | 0.7 | 57-21
534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 632 | ACFT GENERAL T/C | Open | Normal | JOINT |  | CAB + INSP | N/A | AFT |  |  | 2.2 | 53-41
534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 635 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (AFT AREA) | N/A | AFT |  |  | 6.2 | 53-41
534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 636 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (AFT AREA - GALLEY/LAVS) | N/A | AFT |  |  | 3.5 | 53-51
29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 706 | LAVATORY | Open | Normal | INSP |  | INSP | N/A | JOINT |  |  | 1.5 | 25 | 2 | 2.4
30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 711 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509340 | N/A | FWD | 2026-07-19 |  | 0.5 | 25
29155624 | EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX | 720 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2.5 | 31
29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 721 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2.5 | 31
29155864 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 722 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2 | 31
30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 727 | ACFT GENERAL T/C | Open | Normal | AV |  | REVIEW FOR ACCESS | N/A | JOINT |  |  | 471 | 44
31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | 728 | ACFT GENERAL T/C | Open | Normal | AV |  | REVIEW FOR ACCESS | N/A | JOINT |  |  | 170 | 44
29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | 729 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX (ACCESS COCKPIT) | N/A | JOINT |  |  | 23.2 | 46
29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 730 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX (B/C BLANKETS REMOVAL) | N/A | JOINT |  |  | 18 | 46
29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 731 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | FWD |  |  | 18.5 | 46
29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 732 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2.5 | 46
29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | 733 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 4 | 46
29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | 734 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2.5 | 46
15777417 | EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 735 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A | FWD |  |  | 1.5 | 53
15777631 | EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | 736 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A | FWD |  |  | 3 | 53
16152729 | EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS | 737 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A | FWD |  |  | 8.3 | 53
16152761 | EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS | 738 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A | FWD |  |  | 8.3 | 53
17837147 | EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- | 739 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A |  |  |  | 25 | 53
18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 740 | ACFT GENERAL T/C | Open | Normal |  |  | CABIN ACCESS | N/A |  |  |  | 62 | 53
29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 741 | ACFT GENERAL T/C | Open | Normal |  |  | AFT AREA / OPEN UP | N/A | AFT |  |  | 33.8 | 53
28479751 | EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 | 742 | ACFT GENERAL T/C | Open | Normal |  |  | REVIEW FOR ACCESS | N/A |  |  |  | 19.8 | 53
31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | 743 | ACFT GENERAL T/C | Open | Normal |  |  | SEATS REMOVAL | N/A | AFT |  |  | 42.2 | 53
31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 745 | PAX SEAT | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 1.7 | 25
31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 746 | PAX SEAT | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 1.7 | 25
30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | 751 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (FLOOR PANLES/SEATS) | N/A |  |  |  | 22.5 | 32-33
31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | 763 | FLIGHT DECK | Open | Normal | CAB |  | CAB | N/A | FWD |  |  | 0 | 20-00
80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | 772 | TEDLAR/SIDEWALL | Open | Normal | CAB |  | LOGBOOK CABIN | N/A |  |  |  | 0 | 25 | 16.2 | 6553.2
81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | 773 | GALLEY | Open | Normal | CAB |  | LOGBOOK CABIN | N/A | AFT |  |  | 0 | 25 | 15 | 2045.8
STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | 782 | ACFT GENERAL T/C | Closed | Normal |  |  |  | N/A | JOINT | 2026-07-22 | 2026-07-20 | 9 | 20 | 1.7 | 12.4
STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | 786 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 13 | 20
STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | 787 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 22 | 20
STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | 788 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 2 | 20
STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | 789 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 3 | 05-00
STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | 790 | ACFT GENERAL T/C | Open | Normal | CAB |  | CAB | N/A | FWD |  |  | 2 | 05-00
STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | 798 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 0.5 | 05-11
STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | 799 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 7 | 05-00
381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 803 | ACFT GENERAL T/C | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 16 | 38-10
32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 804 | GENERAL CABIN | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 10 | 25-00
CCC-32S | CCC-32S (05) / A32S CABIN CRITICAL CHECK | 810 | GENERAL CABIN | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 3.2 | 25-00
32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 874 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 12 |  | 12 | 6
32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 875 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 120 |  | 120.5 | 53.3
32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 876 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 2
32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 877 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 22 |  | 17.5 | 29.5
32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 878 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 5 |  | 5 | 5
32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 879 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 3 |  | 3 | 1.5
32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 880 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 3 |  | 3 | 3
32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 881 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 12 |  | 6.5 | 29
32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 882 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 3
32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 885 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 2 |  | 2 | 2
32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 892 | GENERAL CABIN | Open | Normal | AV |  |  |  | AFT
32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 893 | GENERAL CABIN | Open | Normal | CAB |  |  |  | AFT |  |  | 1
32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 894 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD
32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 897 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 24 |  | 22 | 51.9
32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 898 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-21 | 24 |  | 24 | 8
32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 899 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 12 |  | 7 | 29.5
32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 900 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 6
81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | 905 | GENERAL CABIN | Open | Normal | AV |  |  |  | N/A |  |  |  |  | 3.5 | 454.9
28611923 | S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION | 918 | GALLEY | Open | Normal | CAB | [6 empty] | 1.5
32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | 925 | GENERAL CABIN | Closed | Normal | CAB |  |  |  |  | 2026-07-22 | 2026-07-19 | 2 |  | 4 | 4.4
32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 926 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 24
32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 927 | PAX SEAT | Closed | Normal | SEAT |  |  |  |  | 2026-07-22 | 2026-07-21 | 1 |  | 1 | 1
32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 933 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 6
32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 940 | PAX SEAT | Closed | Normal | SEAT |  |  |  |  | 2026-07-22 | 2026-07-21 | 3.5 |  | 3 | 1.5
32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 942 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 16 |  | 16 | 51.8
44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 943 | GENERAL CABIN | Open | Normal | AV | [6 empty] | 1.5
32917899 | ISC/IN SERVCE CHECK_N | 944 | ACFT GENERAL T/C | Open | Normal | AP
32420054 | W_N/WEEKLY CHECK | 945 | ACFT GENERAL T/C | Open | Normal | AP
32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 946 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 2
ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | 947 | ACFT GENERAL T/C | Open | Normal | AP | [6 empty] | 2.8
WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | 948 | ACFT GENERAL T/C | Open | Normal | AP | [6 empty] | 5.9
32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 956 | GENERAL CABIN | Open | Normal | CAB
32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 957 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 3
32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 958 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 2
32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 959 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 6
32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 960 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 6
32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 961 | PAX SEAT | Closed | Normal | SEAT |  |  |  |  | 2026-07-22 | 2026-07-21 | 5 |  | 5 | 3
32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 962 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 2
32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 963 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 2
32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 964 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 15 |  | 7 | 29.5
32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 965 | FLIGHT DECK | Closed | Normal | CAB |  |  |  |  | 2026-07-22 | 2026-07-20 |  |  | 4.5 | 2.4
32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 966 | GALLEY | Open | Normal | S/M | [6 empty] | 8
32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 967 | GENERAL CABIN | Closed | Normal | S/M |  |  |  |  | 2026-07-22 | 2026-07-20 |  |  | 6 | 2.2
32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 968 | GENERAL CABIN | Open | Normal | CAB | [8 empty] | 7.5 | 39.2
32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 969 | GENERAL CABIN | Open | Normal | CAB
32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 970 | GENERAL CABIN | Open | Normal | CAB | [8 empty] | 9.5 | 64.4
32982199 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 971 | F/A SEAT | Open | Normal | CAB | [8 empty] | 1.5 | 62.1
32982200 | SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 972 | F/A SEAT | Open | Normal | CAB | [8 empty] | 2 | 62.3
32982202 | R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 973 | F/A SEAT | Open | Normal | CAB
32982203 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 974 | F/A SEAT | Open | Normal | CAB | [8 empty] | 4 | 62.6
32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 992 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 8.5
32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 999 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 6
32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 1003 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 12 |  | 7 | 29.6
32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 1004 | GALLEY | Open | Normal | CAB | [6 empty] | 3
32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 1005 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 1006 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1007 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 1008 | GENERAL CABIN | Open | Normal | AV
32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 1009 | LAVATORY | Open | Normal | PAINT | [6 empty] | 4
32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 1010 | GENERAL CABIN | Open | Normal | AV
32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1011 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 1012 | GALLEY | Open | Normal | S/M
32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 1013 | LAVATORY | Open | Normal | PAINT | [6 empty] | 4
32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 1014 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 6 |  | 6.5 | 27.3
32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 1015 | LAVATORY | Closed | Normal | PAINT |  |  |  |  | 2026-07-22 | 2026-07-21 | 2 |  | 2 | 1
32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 1017 | GALLEY | Open | Normal | PAINT | [6 empty] | 3
32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 1027 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1030 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1031 | GALLEY | Open | Normal | CAB | [6 empty] | 2
32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 1034 | FLIGHT DECK | Open | Normal | CAB | [6 empty] | 2
32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 1035 | F/A SEAT | Open | Normal | CAB
32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT | 1036 | F/A SEAT | Open | Normal | CAB
32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1037 | F/A SEAT | Open | Normal | CAB
32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 1038 | F/A SEAT | Open | AOG | CAB
32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1039 | F/A SEAT | Open | Normal | PAINT
32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 1040 | F/A SEAT | Open | Normal | PAINT
32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 1041 | F/A SEAT | Open | Normal | CAB
32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 1042 | F/A SEAT | Open | Normal | PAINT
32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 1043 | F/A SEAT | Open | Normal | PAINT
32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 1044 | F/A SEAT | Open | Normal | PAINT
32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 1045 | F/A SEAT | Open | AOG | CAB
32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 1046 | F/A SEAT | Open | Normal | CAB
32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1047 | F/A SEAT | Open | Normal | PAINT
32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1048 | F/A SEAT | Open | Normal | CAB
32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 1049 | F/A SEAT | Open | Normal | CAB
32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 1050 | F/A SEAT | Open | Normal | PAINT
32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1051 | F/A SEAT | Open | Normal | PAINT
32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1052 | F/A SEAT | Open | Normal | CAB
32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 1053 | F/A SEAT | Open | Normal | CAB
32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1054 | F/A SEAT | Open | Normal | PAINT
32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1055 | F/A SEAT | Open | Normal | CAB
32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 1061 | GENERAL CABIN | Open | AOG | CAB |  |  |  |  | 2026-07-21
32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 1062 | GENERAL CABIN | Open | AOG | CAB |  |  |  |  | 2026-07-21
32987066 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 1075 | PAX SEAT | Open | Normal | SEAT | [6 empty] | 6
32987097 | CABIN FLOOR PANELS - CAB -CALLBACK CABIN FLOOR PANEL NO: 241EF, 241KF, 241LF, 241MF, 242FF, 242KF, 242LF AND 242MF REQUIRES REMOVAL FOR ACCESS. | 1077 | ACCESS | Open | Normal | CAB
94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | 1082 | PAX DOORS | Open | Normal | CAB | [8 empty] | 35 | 157.9
32974165 | S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1086 | PAX DOORS | Open | Normal | CAB | [6 empty] | 0.2
32974180 | S52-R10176/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1087 | PAX DOORS | Open | Normal | CAB | [6 empty] | 0.5
32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 1093 | FLIGHT DECK | Open | Normal | CAB
32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 1098 | FLIGHT DECK | Open | Normal | CAB
32988329 | PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ | 1107 | GENERAL CABIN | Open | Normal | PAINT | [6 empty] | 2
32988444 | PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA | 1108 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 4
32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 1109 | PAX DOORS | Open | Normal | CAB | [6 empty] | 1.5
32988479 | CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ | 1110 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 1.5
32988506 | CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED | 1111 | GALLEY | Open | Normal | CAB
32988660 | PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS | 1112 | GENERAL CABIN | Open | Normal | PAINT |  | REQ REMOVAL |  |  |  |  | 4
32988687 | CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ | 1113 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 2
32988706 | CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED | 1114 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 1
32988779 | CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA | 1115 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 1.5
32988786 | PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA | 1116 | GENERAL CABIN | Open | Normal | PAINT |  | REQ REMOVAL |  |  |  |  | 1
32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 1117 | GENERAL CABIN | Open | Normal | CAB | [6 empty] | 2
32988850 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY SEVERAL AIR FLAP SEAL DETORIATED | 1121 | GALLEY | Open | Normal | CAB
32989457 | CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. | 1126 | ACCESS | Open | Normal | CAB
32989455 | CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP | 1127 | GALLEY | Open | Normal | CAB
32989472 | CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING | 1128 | GENERAL CABIN | Open | Normal | CAB
32989475 | AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. | 1129 | ACCESS | Open | Normal | CAB
32989476 | CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE | 1130 | GENERAL CABIN | Open | Normal | CAB
32989482 | CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT | 1131 | GALLEY | Open | Normal | CAB
32989491 | CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. | 1132 | GALLEY | Open | Normal | CAB
32989492 | CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT | 1133 | GALLEY | Open | Normal | CAB
32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 1134 | GALLEY | Open | Normal | CAB
32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1138 | PAX DOORS | Open | Normal | PAINT | [6 empty] | 4
32989728 | CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING | 1141 | LAVATORY | Open | Normal | CAB
32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 1142 | LAVATORY | Open | Normal | CAB
32989796 | CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY | 1143 | LAVATORY | Open | Normal | CAB
32989797 | S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE | 1144 | GENERAL CABIN | Open | Normal | S/M
32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 1145 | LAVATORY | Open | Normal | CAB
32989825 | CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING | 1146 | GENERAL CABIN | Open | Normal | CAB
32989853 | CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER | 1147 | GALLEY | Open | Normal | CAB
32989854 | CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE | 1148 | GALLEY | Open | Normal | CAB
32989860 | CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING | 1149 | LAVATORY | Open | Normal | CAB
32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 1150 | LAVATORY | Open | Normal | CAB
32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1151 | PAX DOORS | Open | Normal | PAINT | [6 empty] | 4
32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 1152 | LAVATORY | Open | Normal | PAINT
32989943 | CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. | 1154 | LAVATORY | Open | Normal | CAB
32989952 | CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. | 1156 | LAVATORY | Open | Normal | CAB
32989995 | RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. | 1171 | ACCESS | Open | Normal | CAB
32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 1173 | PAX SEAT | Open | Normal | SEAT
32990008 | CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS | 1174 | ACCESS | Open | Normal | CAB
32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO:33L,34JL,35K,37JL | 1175 | PAX SEAT | Open | Normal | AV
32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 1176 | PAX SEAT | Open | Normal | AV
32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 1177 | PAX SEAT | Open | Normal | AV
32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 1178 | PAX SEAT | Open | Normal | AV
32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 33B,C 32A,B,C AND 31A,B | 1179 | PAX SEAT | Open | Normal | AV
32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 1180 | PAX SEAT | Open | Normal | SEAT
32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 1181 | PAX SEAT | Open | Normal | SEAT
32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 1182 | PAX SEAT | Open | Normal | SEAT
32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 1183 | PAX SEAT | Open | Normal | SEAT
32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 1184 | PAX SEAT | Open | Normal | SEAT
32991206 | CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA | 1199 | GENERAL CABIN | Open | Normal | CAB
32991276 | AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. | 1200 | ACCESS | Open | Normal | AV
32991499 | CAB - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. | 1201 | LAVATORY | Open | Normal | CAB
32991511 | CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | 1202 | LAVATORY | Open | Normal | CAB
32991517 | PNT - RII - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 1203 | LAVATORY | Open | Normal | PAINT
32991527 | CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP | 1205 | LAVATORY | Open | Normal | CAB
32991534 | PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. | 1206 | LAVATORY | Open | Normal | PAINT
32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 1208 | GENERAL CABIN | Open | Normal | SEAT | [6 empty] | 2
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal

## DASHBOARD
📊 HZ-ASD C2+6Y — WORK PACKAGE DASHBOARD |  |  |  |  | DAY 6/38 |  | START → | 2026-07-18
✅ ON TRACK — Completed 10% vs Time 14% · Days Left: 32 · Pace needed: 9.8/day vs avg 7.2/day | [6 empty] | END → | 2026-08-24
TOTAL WOs | CLOSED | OPEN | HPC ⏳ | 🚨 AOG/CRIT | MH DONE ⏱ | DONE
349 | 36 | 313 | 0 | 5 | 9.524% | 10.32%
TIMELINE — linked to LAYOVER sheet
🛬 O.O.S 17-Jul 🛫 B.I.S 24-Aug GROUND TIME 38 days · DAY 6/38
📍 Now: PHASE 3 — Mod & Rectification
⏳ Findings window closes in: 9 day(s)
📅 no upcoming milestone set
🔒 Close-up in 27 day(s) · 2 still open
BY SOURCE
| Closed | Total | % | Window ⏱ | Left
ROUTINE TASKS (WP) | 22 | 167 | 13.17% | 13.51% | 145 | 0.13174
ENG ORDERS (EOD/AD/EO) | 0 | 29 | 0% | 0% | 29
FINDINGS (AMOS) | 14 | 153 | 9.15% | 18.18% | 139 | 0.091503
BY CATEGORY
| Closed | Total | % | Share | Left
GENERAL CABIN | 10 | 57 | 17.54% | 16.33% | 47 | 0.17544
GALLEY | 0 | 29 | 0% | 8.309% | 29
LAVATORY | 5 | 28 | 17.86% | 8.023% | 23 | 0.17857
PAX DOORS | 1 | 47 | 2.128% | 13.47% | 46 | 0.021277
F/A SEAT | 2 | 31 | 6.452% | 8.883% | 29 | 0.064516
PAX SEAT | 10 | 55 | 18.18% | 15.76% | 45 | 0.18182
FLIGHT DECK | 7 | 34 | 20.59% | 9.742% | 27 | 0.20588
TEDLAR/SIDEWALL | 0 | 1 | 0% | 0.2865% | 1
ACCESS | 0 | 6 | 0% | 1.719% | 6
ACFT GENERAL T/C | 1 | 61 | 1.639% | 17.48% | 60 | 0.016393
SPECIALTY
| Closed | Total | % | Share | Left
CAB | 4 | 145 | 2.759% | 41.55% | 141 | 0.027586
SEAT | 10 | 48 | 20.83% | 13.75% | 38 | 0.20833
AV | 5 | 37 | 13.51% | 10.6% | 32 | 0.13514
WALL | 0 | 0 | 0% | 0% | 0
S/M | 1 | 4 | 25% | 1.146% | 3 | 0.25
PAINT | 1 | 22 | 4.545% | 6.304% | 21 | 0.045455
JOINT | 7 | 31 | 22.58% | 8.883% | 24 | 0.22581
INSP | 7 | 14 | 50% | 4.011% | 7 | 0.5
AP | 0 | 18 | 0% | 5.158% | 18
DAILY CLOSURES — last 10 days |  | Σ Closed | Left | Cum %
2026-07-14 | 0 | 0 | 349 | 0%
2026-07-15 | 0 | 0 | 349 | 0%
2026-07-16 | 0 | 0 | 349 | 0%
2026-07-17 | 0 | 0 | 349 | 0%
2026-07-18 | 0 | 0 | 349 | 0%
2026-07-19 | 3 | 3 | 346 | 0.8596% | 0.008596 | 3
2026-07-20 | 13 | 16 | 333 | 4.585% | 0.045845 | 13
2026-07-21 | 15 | 31 | 318 | 8.883% | 0.088825 | 15
2026-07-22 | 5 | 36 | 313 | 10.32% | 0.10315 | 5
2026-07-23 | 0 | 36 | 313 | 10.32% | 0.10315
OPEN UP / ACCESS — removed items status |  |  |  | close-up in 27 d
| Closed | Total | %
🔴 Still Open | 2 | 2 | 100% |  |  | 1
🟡 Partially | 0 | 2 | 0%
🟢 Re-Installed | 0 | 2 | 0%
🔧 PARTS — Requested: 13 · Pending EVAL: 0
⚙️ Deferred: 0 · On Hold: 0 · N/A: 0 🚨 AOG open: 5 · Critical open: 0 · 🔁 Reopened: 0
🕐 WORKLOAD — Est 2,261 MH · Booked 938 · Closed 215 · MH 10% vs cards 10% · cabin 41% of acft pkg
WORKLOAD BY SPECIALTY (Est MH) |  | MH | Done | Share
CAB |  | 264.05 | 0.9847% | 11.68% |  | 0.11681
SEAT |  | 448.3 | 39.82% | 19.83% |  | 0.19831
AV |  | 733.64 | 1.295% | 32.45% |  | 0.32453
WALL |  | 0 | 0% | 0%
S/M |  | 8 | 0% | 0.3539% |  | 0.0035389
PAINT |  | 29 | 6.897% | 1.283% |  | 0.012829
JOINT |  | 86.3 | 5.794% | 3.818% |  | 0.038176
INSP |  | 155.2 | 5.606% | 6.865% |  | 0.068655
AP |  | 109 | 0% | 4.822% |  | 0.048218
👥 CREW (MH · done%) — FWD 186 (2%) · AFT 217 (0%) · JOINT 1,248 (2%) · unassig. 610
✈️ AIRCRAFT PACKAGE — ALL TRADES (whole-aircraft AMOS data · separate from cabin stats above)
TOTAL | CLOSED | OPEN | DONE | TIME | EST MH | BOOKED
1204 | 166 | 1038 | 13.79% | 15.79% | 5526.8 | 2416.6
⚖️ CARDS — Cabin: 10% · Non-cabin: 15% · Whole pkg: 14% · cabin share of pkg closures: 22%
⏱ MAN-HOURS — Cabin: 10% · Non-cabin: 8% · Whole pkg: 8% · cabin weight in pkg: 41%

## LAYOVER
|  |  | HZ-ASD C2+6Y-CHK + WIFI — LAYOVER SCHEDULE | [38 empty] | O.O.S 17-Jul B.I.S 24-Aug GROUND TIME 38 DAYS
TASK | Start | Finish | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Day 11 |  |  | Day 12 |  |  | Day 13 |  |  | Day 14 |  |  | Day 15 |  |  | Day 16 |  |  | Day 17 |  |  | Day 18 |  |  | Day 19 |  |  | Day 20 |  |  | Day 21 |  |  | Day 22 |  |  | Day 23 |  |  | Day 24 |  |  | Day 25 |  |  | Day 26 |  |  | Day 27 |  |  | Day 28 |  |  | Day 29 |  |  | Day 30 |  |  | Day 31 |  |  | Day 32 |  |  | Day 33 |  |  | Day 34 |  |  | Day 35 |  |  | Day 36 |  |  | Day 37 |  |  | Day 38
|  |  | 2026-07-18 |  |  | 2026-07-19 |  |  | 2026-07-20 |  |  | 2026-07-21 |  |  | 2026-07-22 |  |  | 2026-07-23 |  |  | 2026-07-24 |  |  | 2026-07-25 |  |  | 2026-07-26 |  |  | 2026-07-27 |  |  | 2026-07-28 |  |  | 2026-07-29 |  |  | 2026-07-30 |  |  | 2026-07-31 |  |  | 2026-08-01 |  |  | 2026-08-02 |  |  | 2026-08-03 |  |  | 2026-08-04 |  |  | 2026-08-05 |  |  | 2026-08-06 |  |  | 2026-08-07 |  |  | 2026-08-08 |  |  | 2026-08-09 |  |  | 2026-08-10 |  |  | 2026-08-11 |  |  | 2026-08-12 |  |  | 2026-08-13 |  |  | 2026-08-14 |  |  | 2026-08-15 |  |  | 2026-08-16 |  |  | 2026-08-17 |  |  | 2026-08-18 |  |  | 2026-08-19 |  |  | 2026-08-20 |  |  | 2026-08-21 |  |  | 2026-08-22 |  |  | 2026-08-23 |  |  | 2026-08-24
|  |  | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G
PHASE 1 (Pre Hangar)
Aircraft Arrival | 2026-07-18 |  | 18-Jul
Heavy Wash | 2026-07-19 |  |  |  |  | 19-Jul
Both ENG Preservation | 2026-07-18 14:00
Pre HGR | 2026-07-19 | 2026-07-21 | [9 empty] | 21-Jul
Pre Insp | 2026-07-19 | 2026-07-21 | [9 empty] | 21-Jul
Defuel | 2026-07-22 | [13 empty] | 22-Jul
PHASE 2 (Inspection)
Nose Jacking – Prox Sensor Check | 2026-07-23 | [16 empty] | 23-Jul
Open-Up | 2026-07-21 | 2026-07-26 | [24 empty] | 26-Jul
Cabin Structure
Joint Cards Insp | 2026-07-21 | 2026-08-03 | [48 empty] | 3-Aug
Power Off | 2026-07-26 | 2026-08-02 | [45 empty] | 2-Aug
FINDING CUT-OFF | 2026-08-01 | [29 empty] | ◆ 1 Aug | [13 empty] | ◆
PHASE 3 (Modification & Rectification)
Findings & Rectification | 2026-07-17 | 2026-08-19 | [96 empty] | 19-Aug
Engineering Orders Doc (EOD's / ER's) | 2026-07-25 | 2026-08-08 | [63 empty] | 8-Aug
FOMAX & Eclipse Connectivity Mods | 2026-07-26 | 2026-08-05 | [54 empty] | 5-Aug
Jacking – Free Fall Func Chk & NLG | 2026-07-23 | 2026-07-23 | [15 empty] | 23-Jul
MATERIALS ARRIVAL CUT-OFF | 2026-08-10 | [47 empty] | ◆ 10 Aug | [22 empty] | ◆
PHASE 4 (Close Up & Final Inspection)
Cabin Restoration
Areas Close Up | 2026-08-14 | 2026-08-19 | [96 empty] | 19-Aug
Cabin, Cargos & Cockpit
Fuselage, Empennage & Wings
Engines
OPS & Func Check (Power On) | 2026-08-17 | 2026-08-19 | [96 empty] | 19-Aug
W&B | 2026-08-20 | [100 empty] | 20-Aug
Refuel & Leak Checks | 2026-08-21 | [103 empty] | 21-Aug
Engine Run | 2026-08-22 | [106 empty] | 22-Aug
PHASE 5 (Release)
Final Product Quality Inspection (FPQI) | 2026-08-23 | 2026-08-24 | [111 empty] | 24-Aug
Aircraft Release | 2026-08-24 | [112 empty] | 24-Aug
MILESTONES — auto from the schedule above
FINDINGS CUTOFF | 2026-08-01
FOMAX START | 2026-07-26
FOMAX END | 2026-08-05
POWER OFF | 2026-07-26
POWER ON | 2026-08-17
CABIN CLOSE-UP | 2026-08-19
FINAL INSPECTION | 2026-08-23
DE-HANGAR | 2026-08-24

## OPEN UP-ACCESS
OPEN UP / ACCESS LOG ✈ HZ-ASD ✈ C2+6Y CHECK |  |  |  |  | 🔧 0 / 2 Re-Installed (0%)
Open by area: F/DECK 0 · FWD 1 · MID 0 · AFT 1 · JOINT 0 |  |  |  |  | ⚠️ Still Open: 2
Seq. No. | Item Removed (panel / seat / component) | AREA | Relevant WO No. | Removed By | Status | Date Removed | Re-Installed By | Date Re-Installed | Remarks
1 | FWD GALLEY FITTINGS COVERS | FWD |  | 40000706 | Open | 2026-07-19 |  |  | FOR INSP ACCESS
2 | AFT GALLEY FITTINGS COVERS | AFT |  | 13009042 | Open | 2026-07-19 |  |  | FOR INSP ACCESS

## Findings Draft
📋 FINDINGS DRAFT — Pre-AMOS
Findings sourced from ACFT Finding Report App · Review & assign P/N before raising on AMOS
# | By | Category | Sub-Category | Finding Description | Remarks | Photo URL | AMOS Status | WO No. | P/N Required | Qty
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised

## DASHBOARD OLD (hidden)
📊 ASD C2+6Y-CHECK — WORK PACKAGE DASHBOARD | [6 empty] | DAY 6/38 | CHECK START → | 2026-07-18
✅ ON TRACK — Completed 10% vs Time 14% · Days Left: 32 · Pace needed: 9.8/day vs avg 7.2/day | [7 empty] | CHECK END → | 2026-08-24
STATUS OVERVIEW | [5 empty] | ⏳ Findings window closes in: 9 day(s)
| Total Items/WOs | 349 | Closed | 36 |  | Completion | 10%
| Open | 313 | In Work (I/W) | 0 |  | Deferred / Hold | 0
PRIORITY ALERTS | [5 empty] | 📅 no upcoming milestone set
| AOG | 5 | Critical | 0 |  | 🚨 AOG/CRIT — STILL OPEN | 5
BY SOURCE — ROUTINE · ENG ORDERS · FINDINGS |  |  |  |  | 📍 Now: PHASE 3 — Mod & Rectification
| ROUTINE TASKS (WP) | 22 / 167 | ENG ORDERS (EOD/AD/EO) | 0 / 29 |  | FINDINGS (AMOS WOs) | 14 / 153
| Completion: 13% |  | Completion: 0% · Window: 0% elapsed |  |  | Completion: 9% · Share: 44% · Window: 18% elapsed
OPEN UP / ACCESS — removed items |  |  |  |  | 🔒 Close-up in 27 day(s) · 2 still open
| ⚠️ STILL OPEN | 2 | PARTIALLY | 0 |  | RE-INSTALLED | 0
| of 2 recorded items |  | need completion before closing |  |  | Restoration: 0%
BY CATEGORY
| ACFT GENERAL T/C | 1 / 61 | LAVATORY | 5 / 28 |  | GALLEY | 0 / 29
| Completion: 2% |  | Completion: 18% |  |  | Completion: 0%
| GENERAL CABIN | 10 / 57 | TEDLAR/SIDEWALL | 0 / 1 |  | PAX SEAT | 10 / 55
| Completion: 18% |  | Completion: 0% |  |  | Completion: 18%
| PAX DOORS | 1 / 47 | F/A SEAT | 2 / 31 |  | — | -6 / 0 | 0 | 0
| Completion: 2% |  | Completion: 6% |  |  | —
| FLIGHT DECK | 7 / 34 | ACCESS | 0 / 6
| Completion: 21% |  | Completion: 0%
SPECIALTY
| CABIN | 4 / 145 | SEAT SHOP | 10 / 48 |  | AV/FOMAX | 5 / 37
| Completion: 3% |  | Completion: 21% |  |  | Completion: 14%
| SIDEWALL | 0 / 0 | S/M | 1 / 4 |  | PAINT | 1 / 22
| - |  | Completion: 25% |  |  | Completion: 5%
| JOINT | 7 / 31 | INSP | 7 / 14 |  | A/P | 0 / 18
| Completion: 23% |  | Completion: 50% |  |  | Completion: 0%
PARTS REQUIREMENTS (count of WOs with each status)
| Requested | 13 | Requested – CR | 0 |  | Requested – R | 0
| Pending - Require Evaluation | 0 | N/R (not required) | 0 |  | N/A (Not available) | 0

## FULL PKG (hidden)
Seq | WO / Task | Title | Priority | Est MH | Booked MH | Dur (h) | Progress | ATA | Phase
1 | 32797253 | 6Y_N/6Y_N YEARS STRUCTURE | N |  |  |  | Not Started | 05
2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 1 | 4.4 |  |  | Not Started | 24-92 | OPS/LK, OPS/LK
3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 1 | 0.3 |  |  | Not Started | 24-92 | INSPECTION
4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 1 | 0.3 |  |  | Not Started | 24-92 | INSPECTION
6 | 200121-01-1 | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING | 1 | 1.3 |  |  | Not Started | 24-92 | TC/P, TC/P
7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 1 | 2.2 |  |  | Not Started | 24-92 | INSPECTION
8 | 200121-04-1 | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP | 1 | 1.3 |  |  | Not Started | 24-92 | INSPECTION
9 | 200125-01-1 | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING | 1 | 1.4 |  |  | Not Started | 24-92 | CLEAN-UP
11 | 200125-06-1 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP | 1 | 10.2 |  |  | Not Started | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
12 | 200127-02-1 | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING | 1 | 1.3 |  |  | Not Started | 24-92 | CLEAN-UP
13 | 200127-05-1 | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION | 1 | 3.3 |  |  | Not Started | 24-92 | TC/P
14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 1 | 8.3 |  |  | Not Started | 24-92 | INSPECTION
15 | 200131-01-1 | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING | 1 | 6.3 | 8 | 16.8 | Idle | 24-92 | JOB-SETUP, CLEAN-UP, CLOSE-UP, CLOSE-UP
16 | 200133-01-1 | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN | 1 | 10.3 | 4 | 14.7 | Idle | 24-92 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
17 | 200137-01-1 | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING | 1 | 38.1 |  |  | Not Started | 24-92 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
18 | 200145-01-1 | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING | 1 | 9.9 |  |  | Not Started | 24-92 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
19 | 200151-01-1 | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING | 1 | 78.5 |  |  | Not Started | 24-92 | INSPECTION, INSPECTION, CLEAN-UP, JOB-SETUP, JOB-CLOSEUP, INSPECTION
20 | 200151-03-1 | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP | 1 | 13.8 |  |  | Not Started | 24-92 | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
21 | 200161-01-1 | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING | 1 | 81.4 |  |  | Not Started | 24-92 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
22 | 200191-01-1 | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING | 1 | 0.7 |  |  | Not Started | 24-92 | PWR-OFF
23 | 200211-02-1 | 200211-02-1 (01) / COCKPIT WIRING CLEANING | 1 | 5.7 |  |  | Not Started | 24-92 | PWR-OFF
24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 1 | 5.2 | 8.5 | 18.6 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
25 | 200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 1 | 3 | 11 | 19.1 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
26 | 200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 1 | 2.1 | 9.5 | 18.5 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 1 | 0.8 | 3.8 | 15.8 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 1 | 0.8 | 0.3 | 16.4 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
30 | 212100-03-1 | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION | 1 | 1 |  |  | Not Started | 21 | --, INSPECTION, --
31 | 212600-09-1 | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING | 1 | 0.7 |  |  | Not Started | 21-26 | CLEAN-UP
32 | 25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 1 | 2 |  |  | Not Started | 25-11 | TC/P
33 | 25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 1 | 2 |  |  | Not Started | 25-11 | TC/P
34 | 25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 1 | 4 |  |  | Not Started | 25-22 | TC/P
35 | 253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 1 | 0.5 | 44 | 74.8 | Idle | 25-30 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
36 | 254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 1 | 0.2 | 15 | 62.2 | Idle | 25-40 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
39 | 272100-13-1 | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL | 1 |  |  |  | Not Started | 27
42 | 282800-08-1 | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC | 1 | 1.1 |  |  | Not Started | 28-28 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
43 | 282800-18-1 | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC | 1 | 1.5 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
44 | 323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 1 | 2.2 |  |  | Not Started | 32-33 | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
45 | 323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 1 | 0.6 |  |  | Not Started | 32-33 | JOB-SETUP, JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
46 | 341300-13-1 | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST | 1 | 0.8 |  |  | Not Started | 34-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 1 | 0.2 |  |  | Not Started | 35-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 1 | 0.2 |  |  | Not Started | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 1 | 0.4 |  |  | Not Started | 52-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
50 | 530000-01-1 | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP | 1 | 0.9 |  |  | Not Started | 53-00 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
51 | 531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 1 | 0.7 |  |  | Not Started | 53-11 | CLEAN-UP, INSPECTION, INSPECTION
52 | 531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 1 | 2.9 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
53 | 531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 1 | 3.5 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
54 | 531171-01-1 | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS | 1 | 0.9 |  |  | Not Started | 53-11 | INSPECTION, INSPECTION
55 | 531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 1 | 4.9 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
56 | 531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 1 | 21.9 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
57 | 531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 1 | 39.8 |  |  | Not Started | 53-11 | JOB-SETUP, JOB-SETUP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
58 | 532137-03-1 | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION | 1 | 1.6 |  |  | Not Started | 53-21 | JOB-SETUP, INSPECTION, CLOSE-UP
59 | 533136-01-1 | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP | 1 | 0.4 | 12 | 62.6 | Idle | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
60 | 534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 1 | 0.8 |  |  | Not Started | 53-41
61 | 534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 1 | 5.7 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
62 | 534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 1 | 89 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
63 | 534148-01-1 | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP | 1 | 13.5 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
64 | 534159-02-1 | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. | 1 | 2.3 | 5 | 36.4 | Idle | 53-41
65 | 534171-02-1 | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | 1 | 0.5 |  |  | Not Started | 53-41
66 | 534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 1 | 8 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
67 | 534301-01-1 | 534301-01-1 (0) / REAR FUSELAGE | 1 | 2 |  |  | Not Started | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
68 | 535101-01-1 | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP | 1 | 5.5 |  |  | Not Started | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
69 | 551020-01-1 | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP | 1 | 3.3 |  |  | Not Started | 55-16 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
70 | 552002-01-1 | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP | 1 | 3.3 |  |  | Not Started | 55-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
71 | 553004-01-1 | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP | 1 | 0.7 |  |  | Not Started | 55-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
72 | 553005-01-1 | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP | 1 | 0.4 |  |  | Not Started | 55-30 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
73 | 553006-01-2 | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION | 1 | 0.3 |  |  | Not Started | 55-30 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
74 | 554003-01-1 | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION | 1 | 1.3 | 0.5 | 443.9 | Idle | 55-40 | JOB-SETUP, CLEAN-UP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
75 | 554005-01-1 | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP | 1 | 0.4 |  |  | Not Started | 55-40 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
76 | 554006-01-1 | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP | 1 | 0.3 |  |  | Not Started | 55-40 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
77 | 554008-01-1 | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP | 1 | 3 | 0.5 | 11.9 | Idle | 55-40 | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
78 | 554009-01-1 | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP | 1 | 6 | 0.5 | 11.9 | Idle | 55-40 | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
79 | 562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 1 | 13.2 |  |  | Not Started | 56-21 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
80 | 571122-01-1 | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION | 1 | 3.3 |  |  | Not Started | 57-10 | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
81 | 571157-01-1 | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP | 1 | 7.7 |  |  | Not Started | 57-10 | JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-SETUP
82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 1 | 0.3 | 1 | 13.8 | Idle | 57-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 1 | 0.3 | 1 | 13.8 | Idle | 57-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
84 | 572065-01-1-001 | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 2.3 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
85 | 572065-01-1-002 | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 2.3 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 1 | 0.3 | 1 | 13.8 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 1 | 0.3 | 1 | 13.8 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
88 | 572161-01-11-001 | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP | 1 | 1.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
89 | 572161-01-11-002 | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP | 1 | 1.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
90 | 572651-01-2-001 | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP | 1 | 0.4 |  |  | Not Started | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
91 | 572651-01-2-002 | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING | 1 | 0.4 |  |  | Not Started | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
92 | 574206-01-1 | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. | 1 | 2 |  |  | Not Started | 57-46
93 | 574306-01-1-001 | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. | 1 | 2.3 |  |  | Not Started | 57-46
94 | 574306-01-1-002 | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH | 1 | 2.3 |  |  | Not Started | 57-46
95 | 574406-01-1 | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. | 1 | 2.5 |  |  | Not Started | 57-46 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
96 | 574506-01-1-001 | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. | 1 | 2.3 |  |  | Not Started | 57-46
97 | 574506-01-1-002 | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH | 1 | 2.3 |  |  | Not Started | 57-46
98 | 574606-01-1 | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. | 1 | 2 |  |  | Not Started | 57-46
99 | 575151-03-1 | 575151-03-1 (0) / TRAILING EDGE | 1 | 2 |  |  | Not Started | 57-51 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
100 | 575167-01-1-001 | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP | 1 | 0.4 |  |  | Not Started | 57-51 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
101 | 575167-01-1-002 | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP | 1 | 0.4 |  |  | Not Started | 57-51 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
102 | 783210-01-1 | 783210-01-1 (0) / THRUST REVERSER STRUCTURE | 1 | 0.8 | 1 | 16.7 | Idle | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
104 | ZL-121-02-1 | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP | 1 | 1.7 |  |  | Not Started | 05-21 | INSPECTION
105 | ZL-125-02-1 | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP | 1 | 1.3 |  |  | Not Started | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
106 | ZL-127-02-2 | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP | 1 | 1.7 |  |  | Not Started | 05-21 | INSPECTION
108 | ZL-133-01-1 | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP | 1 | 10.3 |  |  | Not Started | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
109 | ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | 1 | 11.5 |  |  | Not Started | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
111 | ZL-151-02-3 | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP | 1 | 37 |  |  | Not Started | 28-11 | JOB-SETUP, INSPECTION, INSPECTION, CLOSE-UP, CLOSE-UP
112 | ZL-153-01-1 | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY | 1 | 10.2 | 8 | 37.4 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
113 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | 1 | 7.2 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
114 | ZL-163-01-1 | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP | 1 | 9.9 |  |  | Not Started | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | 1 | 77 | 2 | 17.4 | Idle | 05-21 | INSPECTION
117 | ZL-193-01-1 | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA | 1 | 1.8 |  |  | Not Started | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
121 | ZL-200-04-1 | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE | 1 | 12.6 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | 1 | 0.4 |  |  | Not Started | 05-22 | INSPECTION
126 | ZL-325-01-1 | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP | 1 | 0.4 | 6.5 | 38.9 | Idle | 05-23 | PRE INSP
135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | 1 | 0.9 | 0.2 | 45.9 | Idle | 05-25 | INSPECTION
138 | ZL-531-02-1-001 | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP | 1 | 1.4 | 0.8 | 43.8 | Idle | 05-25 | INSPECTION
139 | ZL-531-02-1-002 | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING | 1 | 1.4 | 0.2 | 43.8 | Idle | 05-25 | INSPECTION
141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | 1 | 0.5 | 0.2 | 43.8 | Idle | 05-25 | INSPECTION
143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | 1 | 1.4 | 0.2 | 43.8 | Idle | 05-25 | INSPECTION
145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | 1 | 0.5 | 0.2 | 43.8 | Idle | 05-25 | INSPECTION
148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | 1 | 0.5 |  |  | Not Started | 05-25 | PRE INSP
149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | 1 | 0.5 | 0.2 | 45.9 | Idle | 05-25 | PRE INSP
150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | 1 | 3.1 |  |  | Not Started | 05-25 | --, PRE INSP
151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | 1 | 3.1 |  |  | Not Started | 05-25 | --, PRE INSP
154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | 1 | 0.2 |  |  | Not Started | 05-28 | PRE INSP
157 | ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | 1 | 2 | 2 | 23.2 | Idle | 05-28 | PRE INSP, PRE INSP, PRE INSP, PRE INSP
158 | 31871161 | A_N (A_N09)/A_N-CHECK | N |  |  |  | Not Started | 20-00
159 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 1 | 2.2 | 8 | 42.3 | Idle | 05
160 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 1 | 1 |  |  | Not Started | 11-11 | PRE INSP
161 | 21-SVA-01 | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN | 1 | 3 |  |  | Not Started | 21-61 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
163 | 212600-11-1 | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R | 1 | 0.2 |  |  | Not Started | 21-26 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
164 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 1 | 0.2 |  |  | Not Started | 24-41 | OPS/LK
165 | 242000-25-1 | 242000-25-1 (02) / AC GENERATION | 1 | 1 |  |  | Not Started | 53-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
167 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 1 | 0.2 |  |  | Not Started | 24-38 | OPS/LK
168 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 1 | 5.8 | 25.5 | 27.3 | Idle | 25-10
169 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 1 | 5.8 | 26.5 | 46.5 | Idle | 25-10
170 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 1 | 2.3 | 7.5 | 23.4 | Idle | 25-10
171 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 1 | 1.5 | 6 | 23.6 | Idle | 25-10
172 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 1 |  | 18 | 39.4 | Idle | 25-10
173 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 1 | 4 |  |  | Not Started | 25-26 | TC/P
174 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 1 | 4 |  |  | Not Started | 25-28 | PRE INSP
175 | 25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 1 | 2 |  |  | Not Started | 25-30 | PRE HGR
176 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 1 | 0.5 |  |  | Not Started | 25-30 | PRE INSP
177 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 1 | 6.9 | 28.5 | 75.3 | Idle | 25-10
178 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 1 | 7.4 | 3.5 | 16.1 | Idle | 25-10
182 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 1 | 0.3 |  |  | Not Started | 20-00
183 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 1 | 0.4 |  |  | Not Started | 25-34 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 1 |  |  |  | Idle | 25-50 | PRE INSP
186 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 1 | 0.9 |  |  | Not Started | 25-62 | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK
187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 1 |  | 4 | 70.7 | Idle | 26-12 | OPS/LK
188 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 1 | 0.5 |  |  | Not Started | 24
189 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 1 | 0.5 |  |  | Not Started | 24
190 | 262200-02-1 | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS | 1 | 0.2 |  |  | Not Started | 26-22 | OPS/LK
191 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 1 | 0.2 |  |  | Not Started | 27-44 | OPS/LK
192 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 1 | 0.2 |  |  | Not Started | 12-22 | TC/P
193 | 274451-10-1 | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD | 1 | 10.7 |  |  | Not Started | 27-44 | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
194 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 1 | 14 |  |  | Not Started | 27-44 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
195 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 1 | 1.8 |  |  | Not Started | 12-22 | TC/P, TC/P
196 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 1 | 1.8 |  |  | Not Started | 12-22 | TC/P, TC/P
197 | 278468-01-1-002 | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION | 1 | 2.2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, JOB-CLOSEUP
198 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 1 | 0.1 |  |  | Not Started | 28-11 | OPS/LK
199 | 281100-05-1 | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | 1 | 0.7 |  |  | Not Started | 28-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
200 | 281100-06-1 | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES | 1 | 0.7 |  |  | Not Started | 53-11 | JOB-SETUP, OPS/LK
201 | 282800-01-1 | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK | 1 | 1.1 |  |  | Not Started | 28-28 | OPS/LK, OPS/LK
202 | 282800-03-1 | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK | 1 | 0.4 |  |  | Not Started | 12-32 | TC/P, TC/P
204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 1 | 0.2 |  |  | Not Started | 29-10 | TC/P
205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 1 | 0.7 |  |  | Not Started | 29-27 | TC/P
206 | 292251-02-1 | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP | 1 | 0.7 |  |  | Not Started | 29-22 | TC/P
207 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 1 | 2 |  |  | Not Started | 31-63 | CLEAN-UP
208 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 1 | 0.2 |  |  | Not Started | 31-30 | PRE HGR
209 | 313300-08-1 | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION | 1 | 2.5 |  |  | Not Started | 31-33 | JOB-SETUP, TC/P, JOB-CLOSEUP
213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 1 | 0.1 |  |  | Not Started | 32-44 | TC/P
214 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 1 | 1 |  |  | Not Started | 34-42 | CLEAN-UP
217 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 1 | 6.2 | 4 | 15.3 | Idle | 36-11 | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP
218 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 1 | 6.2 | 0.3 | 17.1 | Idle | 36-11 | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP
219 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 1 | 0.2 |  |  | Not Started | 38-32 | CLEAN-UP, CLEAN-UP, CLEAN-UP
220 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 1 | 1.8 |  |  | Not Started | 20-00 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
221 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 1 | 1.7 |  |  | Not Started | 52-71-00 | JOB-SETUP, --, --, --
222 | 52-32-00-01-0-SVA | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | 1 | 1.3 |  |  | Not Started | 52-71-00 | CLEAN-UP, TC/P, TC/P, --, JOB-CLOSEUP
223 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 1 |  | 7.8 | 47.3 | Idle | 52-51 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
224 | 527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 1 | 0.4 |  |  | Not Started | 12-22 | TC/P, TC/P, TC/P, TC/P, TC/P
225 | 533154-06-1-A | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP | 1 | 17.5 | 4 | 60.6 | Idle | 53-31 | JOB-SETUP, JOB-SETUP, --, --, --, --, INSPECTION, --, INSPECTION, --, --, --
226 | 31675402 | EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE | 1 | 30.3 |  |  | Not Started | 53
227 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 1 | 2 | 10 | 27.8 | Idle | 56-10 | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP
228 | 72-00-00-01-0-SVA-001 | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH | 1 | 13 |  |  | Not Started | 72-00 | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
229 | 72-00-00-01-0-SVA-002 | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH | 1 | 13 |  |  | Not Started | 72-00 | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
230 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 1 | 0.7 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, JOB-CLOSEUP
231 | 801110-C3-1-002 | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT | 1 | 0.7 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, JOB-CLOSEUP
232 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | 1 | 5.7 |  |  | Not Started | 20-00
233 | 31574335 | C_N (C_N02)/C-CHECK | N |  |  |  | Not Started | 20-00
234 | 05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 1 | 1 |  |  | Not Started | 05-00 | ACFT RELEASE, ACFT RELEASE
235 | 08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 1 | 65 |  |  | Not Started | 08-10 | WT&BAL
237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 1 |  | 2.5 | 16.3 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 1 | 0.8 | 1 | 16.3 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 1 | 0.3 | 1.5 | 17.5 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
241 | 212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 1 | 0.4 |  |  | Not Started | 21-21 | TC/P
242 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 1 | 0.2 |  |  | Not Started | 21-26 | OPS/LK
243 | 212600-04-1 | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC | 1 | 0.2 |  |  | Not Started | 21-26 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
244 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 1 | 0.2 |  |  | Not Started | 21-26 | OPS/LK
245 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.2 |  |  | Not Started | 21-31 | OPS/LK
246 | 213100-02-1 | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC | 1 | 0.2 |  |  | Not Started | 21-31 | OPS/LK
247 | 213100-03-1 | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.2 |  |  | Not Started | 21-31 | OPS/LK
248 | 213100-04-1 | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
250 | 215000-08-1 | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 1 | 0.5 |  |  | Not Started | 21 | --, INSPECTION, --
251 | 215000-09-1 | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 1 | 0.5 |  |  | Not Started | 21 | --, INSPECTION, --
252 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 1 | 3.5 |  |  | Not Started | 21-52 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
253 | 215500-01-1 | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC | 1 | 0.2 |  |  | Not Started | 21-55 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
254 | 215500-02-1 | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC | 1 | 0.2 |  |  | Not Started | 21-55 | OPS/LK
255 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 1 | 2.6 |  |  | Not Started | 21-63 | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK
256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 1 |  | 4 | 22.5 | Idle | 22-10 | OPS/LK
259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 1 |  | 4 | 45 | Idle | 23-51 | OPS/LK, OPS/LK
260 | 237100-02-1 | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC | 1 | 1.1 |  |  | Not Started | 23-71 | OPS/LK
261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 1 | 0.3 |  |  | Not Started | 23-71 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
262 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 1 | 0.2 |  |  | Not Started | 24-22 | OPS/LK
263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 1 | 0.2 |  |  | Not Started | 24-24 | OPS/LK
264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 1 | 0.2 |  |  | Not Started | 24-25 | OPS/LK
265 | 242600-02-1 | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC | 1 | 0.2 |  |  | Not Started | 24-26 | OPS/LK
266 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 1 | 0.1 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
267 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 1 | 0.1 |  |  | Not Started | 24-30 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 1 | 0.3 |  |  | Not Started | 24-32 | OPS/LK
269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 1 | 0.3 |  |  | Not Started | 24-34 | OPS/LK
270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 1 | 0.7 |  |  | Not Started | 24-51 | OPS/LK
271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 1 |  | 4 | 47.4 | Idle | 24-51 | OPS/LK
272 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 1 | 0.5 |  |  | Not Started | 25-11
273 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 1 | 1 |  |  | Not Started | 25-11 | INSPECTION, --
274 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 1 | 4 |  |  | Not Started | 25-11 | TC/P, TC/P
275 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 1 | 0.5 |  |  | Not Started | 25-11 | PRE INSP, --
276 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 1 | 48 |  |  | Not Started | 25-28 | TC/P, TC/P, TC/P, TC/P
277 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 1 | 6 |  |  | Not Started | 25-28 | TC/P
278 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 1 | 3.3 | 2 | 46.5 | Idle | 25
279 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 1 | 11.7 | 3 | 46.9 | Idle | 25
280 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 1 | 5.2 | 7 | 16 | Idle | 25
281 | 25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 1 | 19 |  |  | Not Started | 25
282 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 1 | 1.8 | 14.5 | 30 | Idle | 25
283 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 1 | 2 | 8 | 18.9 | Idle | 25
284 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 1 | 2 | 4.5 | 16 | Idle | 25
285 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 1 | 3 |  |  | Not Started | 25
286 | 25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 1 | 0.5 |  |  | Not Started | 25
287 | 25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 1 | 0.5 |  |  | Not Started | 25
288 | 252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 1 | 38 | 28.5 | 51.3 | Idle | 25-21 | TC/P, TC/P
289 | 252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 1 | 2.7 | 17.5 | 19.6 | Idle | 25-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
290 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 1 | 3 | 2 | 25.1 | Idle | 25-21 | TC/P, TC/P
291 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 1 | 7 | 6 | 26.1 | Idle | 25-21 | TC/P, TC/P, TC/P, TC/P
292 | 252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 1 | 0.7 |  |  | Not Started | 25-22 | --, PRE INSP, --
295 | 255000-08-1 | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP | 1 | 38.5 |  |  | Not Started | 25-50 | INSPECTION
296 | 255000-10-1 | 255000-10-1 (3) / LOWER DECK CARGO LOADING | 1 | 5.5 |  |  | Not Started | 25-50 | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P
297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 1 |  | 2 | 71.5 | Idle | 25-65 | OPS/LK
298 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 1 | 1.2 |  |  | Not Started | 25 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
299 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 1 | 0.5 | 46.5 | 74.8 | Idle | 25-11 | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP
300 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 1 | 0.2 |  |  | Not Started | 26-15 | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP
301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 1 | 0.4 |  |  | Not Started | 26-21 | OPS/LK
302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 1 | 0.4 |  |  | Not Started | 26-21 | OPS/LK
305 | 262100-05-1 | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC | 1 | 1.1 |  |  | Not Started | 26-21 | OPS/LK
308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 1 | 0.4 |  |  | Not Started | 26-22 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
311 | 262300-03-1 | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK | 1 | 4.4 |  |  | Not Started | 26-23 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 1 | 0.2 |  |  | Not Started | 27-14 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
314 | 271400-02-2-001 | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK | 1 | 3.5 | 6 | 52.5 | Idle | 27-14 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
315 | 271400-02-2-002 | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK | 1 | 3.5 | 2 | 49.9 | Idle | 27-14 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
316 | 271400-03-1-001 | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK | 1 | 0.9 |  |  | Not Started | 27-14 | PRE HGR, PRE HGR, PRE HGR
317 | 271400-03-1-002 | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK | 1 | 0.9 |  |  | Not Started | 27-14 | PRE HGR, PRE HGR, PRE HGR
318 | 272100-02-1 | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP | 1 | 75.5 |  |  | Not Started | 27-21 | TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION
319 | 272100-04-1 | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK | 1 | 0.4 |  |  | Not Started | 27-26 | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP
320 | 272100-05-1 | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD | 1 |  | 10 | 90.3 | Idle | 27-21 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
321 | 272100-07-1 | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE | 1 | 0.2 | 36 | 42 | Idle | 27-21 | INSPECTION
322 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 1 | 1.3 |  |  | Not Started | 27-21 | JOB-SETUP, --, --
323 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 1 | 0.7 |  |  | Not Started | 27-21 | TC/P
326 | 273400-03-1 | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE | 1 | 1 |  |  | Not Started | 27-34 | JOB-SETUP, TC/P, JOB-CLOSEUP
328 | 274000-24-1 | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. | 1 | 0.5 |  |  | Not Started | 27-44 | TC/P
329 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 1 | 0.1 |  |  | Not Started | 27-41 | JOB-SETUP, TC/P, JOB-CLOSEUP
330 | 274400-03-1 | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC | 1 | 0.7 |  |  | Not Started | 27-44 | OPS/LK, OPS/LK
331 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 1 | 0.3 |  |  | Not Started | 27-44 | INSPECTION, INSPECTION
332 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 1 | 0.3 |  |  | Not Started | 27-44 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
334 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 1 | 0.9 |  |  | Not Started | 27-44 | OPS/LK, OPS/LK
335 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 1 | 1.1 |  |  | Not Started | 27-44 | TC/P, TC/P
336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 1 | 0.7 |  |  | Not Started | 27-44 | OPS/LK
337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 1 | 0.7 |  |  | Not Started | 27-51 | PRE HGR, PRE HGR, PRE HGR
338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 1 | 0.2 |  |  | Not Started | 27-51 | PRE HGR, PRE HGR, PRE HGR
339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 1 | 0.2 |  |  | Not Started | 27-51 | PRE HGR, PRE HGR, PRE HGR
340 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 1 | 1.8 |  |  | Not Started | 27-54 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
341 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 1 | 1.8 |  |  | Not Started | 27-54 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
342 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 1 | 1.4 |  |  | Not Started | 27-51 | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP
343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 1 | 1.4 |  |  | Not Started | 27-51 | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP
344 | 275400-01-1-001 | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP | 1 | 4.5 |  |  | Not Started | 27-54 | INSPECTION
345 | 275400-01-1-002 | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP | 1 | 4.5 |  |  | Not Started | 27-54 | INSPECTION
346 | 275446-02-1-001 | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP | 1 | 1.4 |  |  | Not Started | 27-54 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
347 | 275446-02-1-002 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP | 1 | 1.4 |  |  | Not Started | 27-54 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
348 | 275449-06-1-001 | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS | 1 | 17.6 |  |  | Not Started | 12-13 | TC/P
349 | 275449-06-1-002 | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES | 1 | 17.6 |  |  | Not Started | 12-13 | TC/P
350 | 275451-01-1 | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT | 1 | 0.2 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
351 | 276400-02-1-001 | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION | 1 | 6.2 |  |  | Not Started | 27-64 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
352 | 276400-02-1-002 | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION | 1 | 6.2 |  |  | Not Started | 27-64 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
353 | 278100-03-1 | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC | 1 | 0.4 |  |  | Not Started | 27-81 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
354 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 1 | 0.4 |  |  | Not Started | 27-84 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
355 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 1 | 0.4 |  |  | Not Started | 27-84 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
356 | 278400-01-1-001 | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION | 1 | 4.4 |  |  | Not Started | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
357 | 278400-01-1-002 | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION | 1 | 4.4 |  |  | Not Started | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
358 | 278451-01-1 | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT | 1 | 0.2 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
359 | 278468-02-1-001 | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION | 1 | 4.5 |  |  | Not Started | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
360 | 278468-02-1-002 | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION | 1 | 4.5 |  |  | Not Started | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
363 | 281600-01-1-001 | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK | 1 | 0.2 | 16 | 87.4 | Idle | 28-16 | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP
364 | 281600-01-1-002 | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK | 1 | 0.2 | 16 | 87.4 | Idle | 28-16 | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP
365 | 281800-01-1 | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK | 1 | 4.4 |  |  | Not Started | 28-18 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
366 | 282100-02-1 | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC | 1 | 0.2 |  |  | Not Started | 28-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
370 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 1 | 0.4 |  |  | Not Started | 28-25 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
371 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 1 | 0.4 |  |  | Not Started | 28-25 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
372 | 282800-04-1 | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC | 1 | 1.3 |  |  | Not Started | 28-28 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 1 |  | 6 | 72.3 | Idle | 28-28 | OPS/LK
374 | 282800-06-1 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT | 1 | 0.6 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
375 | 282800-07-1 | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC | 1 | 0.5 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
376 | 291000-04-1 | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK | 1 | 0.2 |  |  | Not Started | 29-23 | OPS/LK
377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 1 |  | 4 | 89.2 | Idle | 29-23 | OPS/LK
378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 1 |  | 4 | 89.1 | Idle | 29-10 | OPS/LK
379 | 291000-10-1 | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK | 1 | 0.5 |  |  | Not Started | 29-10 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 1 |  | 8 | 89.2 | Idle | 29-23 | OPS/LK, OPS/LK
381 | 291000-20-1 | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS | 1 | 0.6 |  |  | Not Started | 29-10 | OPS/LK
382 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 1 | 0.6 |  |  | Not Started | 29 | OPS/LK
383 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 1 | 0.6 |  |  | Not Started | 29 | JOB-SETUP, --, JOB-CLOSEUP
384 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 1 | 0.7 |  |  | Not Started | 29-10 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
385 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 1 | 0.2 |  |  | Not Started | 29-34 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 1 |  | 2.5 | 16.4 | Idle | 30-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 1 | 0.6 |  |  | Not Started | 30-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 1 | 0.3 |  |  | Not Started | 31-33 | OPS/LK
390 | 313300-07-1 | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION | 1 | 1.3 |  |  | Not Started | 31-33 | OPS/LK
391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 1 |  | 4 | 71 | Idle | 31-50 | OPS/LK
392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 1 |  | 4 | 88.1 | Idle | 31-60 | JOB-SETUP, OPS/LK
393 | 315000-04-1 | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK | 1 | 0.4 |  |  | Not Started | 31-60 | JOB-SETUP, OPS/LK
394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 1 | 13.6 |  |  | Not Started | 12-12 | JOB-SETUP, TC/P, JOB-CLOSEUP
395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 1 | 13.6 | 2 | 60.1 | Idle | 12-12 | JOB-SETUP, TC/P, JOB-CLOSEUP
396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 1 | 1.8 |  |  | Not Started | 12-14 | OPS/LK
397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 1 | 1.8 |  |  | Not Started | 12-14 | OPS/LK
398 | 321127-01-1-001 | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK | 1 | 38.7 |  |  | Not Started | 32-11 | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
399 | 321127-01-1-002 | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK | 1 | 38.7 |  |  | Not Started | 32-11 | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 1 | 0.9 |  |  | Not Started | 12-12 | OPS/LK
402 | 323100-04-1 | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK | 1 | 0.9 |  |  | Not Started | 32-31 | OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-SETUP, TC/P
404 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 1 | 0.2 |  |  | Not Started | 32-61 | OPS/LK
405 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 1 | 2.2 |  |  | Not Started | 32-31 | OPS/LK
406 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 1 | 1.1 |  |  | Not Started | 32-31 | OPS/LK
407 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 1 | 8.9 |  |  | Not Started | 32-31 | JOB-SETUP, TC/P, TC/P, CLOSE-UP
408 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 1 | 10.1 |  |  | Not Started | 32-42 | OPS/LK
409 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 1 | 2.2 |  |  | Not Started | 32-41 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
410 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 1 | 1.3 |  |  | Not Started | 32-43 | OPS/LK
412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 1 | 1.8 |  |  | Not Started | 32-45 | JOB-SETUP, OPS/LK
415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 1 |  | 8 | 21.5 | Idle | 34-13 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
416 | 341300-02-1 | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC | 1 | 0.2 |  |  | Not Started | 34-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
417 | 341300-03-1 | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC | 1 | 0.4 |  |  | Not Started | 34-13 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 1 |  | 4 | 70.7 | Idle | 34-13 | OPS/LK
419 | 341300-09-1 | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC | 1 | 0.4 |  |  | Not Started | 34-13 | OPS/LK
420 | 342000-03-1 | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK | 1 | 0.7 |  |  | Not Started | 34-20 | OPS/LK
422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 1 | 0.9 |  |  | Not Started | 34-22 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 1 |  | 4 | 70.7 | Idle | 34-48 | TC/P
424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 1 |  | 8 | 21.6 | Idle | 34-52 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
425 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 1 | 0.2 |  |  | Not Started | 35-12 | OPS/LK
427 | 352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 1 | 2 | 45 | 47.9 | Idle | 35-23 | JOB-SETUP, TC/P, TC/P, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
428 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 1 | 2.4 | 48.5 | 51.3 | Idle | 35-21 | JOB-SETUP, --, --, JOB-CLOSEUP, --
431 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 1 | 0.4 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
432 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 1 | 0.4 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
433 | 361100-SVA-01 | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | 1 | 14.2 |  |  | Not Started | 36 | JOB-SETUP, OPS/LK, OPS/LK, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
434 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
435 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
438 | 361251-01-3 | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP | 1 | 1.1 |  |  | Not Started | 36-12 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, OPS/LK, JOB-CLOSEUP
439 | 383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 1 | 10 |  |  | Not Started | 38-31 | CLEAN-UP
440 | 384142-01-1 | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT | 1 | 0.4 |  |  | Not Started | 38-41 | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, OPS/LK, JOB-CLOSEUP
441 | 384241-01-1 | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP | 1 | 0.2 |  |  | Not Started | 38-42 | JOB-SETUP, TC/P, JOB-CLOSEUP
442 | 384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 1 | 0.7 |  |  | Not Started | 38-42 | TC/P, OPS/LK
443 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 1 | 3.1 |  |  | Not Started | 49-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
444 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 1 | 0.3 |  |  | Not Started | 49-16 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
446 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
447 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 1 | 0.7 |  |  | Not Started | 52-10 | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
448 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
449 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
450 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 1 | 1.5 |  |  | Not Started | 52-10 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
451 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 1 | 1.5 |  |  | Not Started | 52-10 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
452 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 1 | 1.5 |  |  | Not Started | 52-10 | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
453 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 1 | 1.5 |  |  | Not Started | 52-10 | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
454 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
455 | 521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 1 | 0.9 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
456 | 521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 1 | 1.8 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
457 | 521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 1 | 0.9 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
458 | 521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 1 | 0.9 |  |  | Not Started | 52-10 | OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, OPS/LK, OPS/LK
459 | 521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 1 | 0.9 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
460 | 521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 1 | 0.9 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
461 | 521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 1 | 0.4 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
462 | 521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 1 | 1.5 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK
463 | 521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 1 | 0.4 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
464 | 521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 1 | 3.7 |  |  | Not Started | 52-10 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
465 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P, TC/P, TC/P, TC/P
466 | 522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
467 | 522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
468 | 522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
469 | 522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
470 | 523100-01-1 | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC | 1 | 0.4 |  |  | Not Started | 52-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
471 | 523200-01-1 | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC | 1 | 0.4 |  |  | Not Started | 52-32 | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
472 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | TC/P
475 | 525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 1 | 0.4 |  |  | Not Started | 52-51 | OPS/LK
477 | 525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 1 | 0.1 |  |  | Not Started | 52-51 | OPS/LK
478 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 1 | 0.1 |  |  | Not Started | 52-71 | OPS/LK
479 | 527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 1 | 0.2 |  |  | Not Started | 52-73 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 1 | 0.2 |  |  | Not Started | 52-73 | OPS/LK
481 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 1 | 0.9 |  |  | Not Started | 53-11
482 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 1 | 0.4 |  |  | Not Started | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
483 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 1 | 2.3 |  |  | Not Started | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
484 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 1 | 2.3 |  |  | Not Started | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
485 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 1 | 1.3 |  |  | Not Started | 53-19 | OPS/LK
486 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 1 | 1.5 |  |  | Not Started | 53 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
488 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 1 | 4 |  |  | Not Started | 53 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
489 | 532181-02-1 | 532181-02-1 (0) / FORWARD FUSELAGE | 1 | 3 |  |  | Not Started | 53
490 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 1 | 0.2 |  |  | Not Started | 53-39 | OPS/LK
491 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 1 | 0.9 |  |  | Not Started | 53-41
492 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 1 | 2.9 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
493 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 1 | 1.5 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
494 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 1 | 37.5 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
495 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 1 | 0.1 |  |  | Not Started | 53-59 | OPS/LK
496 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 1 | 0.2 |  |  | Not Started | 53-59 | OPS/LK
497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 1 | 0.3 | 1 | 16.1 | Idle | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 1 | 0.3 | 1 | 16.8 | Idle | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 1 | 2.4 | 0.5 | 15.9 | Idle | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 1 | 2.4 | 1.5 | 16.8 | Idle | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
501 | 545000-05-1-001 | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP | 1 | 11.6 | 3.5 | 15.9 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
502 | 545000-05-1-002 | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP | 1 | 11.6 | 4.3 | 16.5 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 1 | 0.9 | 3.3 | 16 | Idle | 05-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 1 | 0.9 | 0.3 | 16.6 | Idle | 05-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 1 | 0.7 | 4 | 16.1 | Idle | 54-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 1 | 0.7 | 1 | 16.9 | Idle | 54-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
507 | 552600-01-1 | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. | 1 | 3.1 |  |  | Not Started | 20-00
508 | 553600-01-1 | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION | 1 | 5.8 |  |  | Not Started | 55-47 | TC/P
509 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | TC/P
510 | 572178-01-1-001 | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP | 1 | 2.3 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
511 | 572178-01-1-002 | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP | 1 | 2.3 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
512 | 572179-01-1-001 | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 1 | 2.3 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
513 | 572179-01-1-002 | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 1 | 2.3 |  |  | Not Started | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 1 |  | 2 | 16.2 | Idle | 71-13 | OPEN-UP, INSPECTION, CLOSE-UP
518 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 1 | 1.1 |  |  | Not Started | 73-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
519 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 1 | 1.1 |  |  | Not Started | 73-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 1 |  | 3 | 16.4 | Idle | 71-13 | INSPECTION
522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 1 |  | 1.8 | 16.2 | Idle | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
525 | 711300-C1-1-001 | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION | 1 | 1.2 |  |  | Not Started | 71-13 | OPS/LK, OPS/LK
526 | 711300-C1-1-002 | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION | 1 | 1.2 |  |  | Not Started | 71-13 | OPS/LK, OPS/LK
527 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 1 | 2.5 |  |  | Not Started | 71-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
528 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 1 | 2.5 |  |  | Not Started | 71-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 1 | 2.2 | 0.3 | 16.3 | Idle | 71-21 | PRE INSP, PRE INSP, PRE INSP
530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 1 | 2.2 | 0.3 | 16.8 | Idle | 71-21 | PRE INSP, PRE INSP, PRE INSP
533 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 1 | 2.2 |  |  | Not Started | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
534 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 1 | 2.2 |  |  | Not Started | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 1 | 2.5 | 0.5 | 16 | Idle | 71-22 | PRE INSP, PRE INSP, PRE INSP
536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 1 | 2.5 | 0.3 | 16.4 | Idle | 71-22 | PRE INSP, PRE INSP, PRE INSP
537 | 712213-01-1-001 | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP | 1 | 3.5 |  |  | Not Started | 71-22 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
538 | 712213-01-1-002 | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP | 1 | 3.5 |  |  | Not Started | 71-22 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
541 | 72-00-00-27-0-SVA-001 | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK | 1 | 2 |  |  | Not Started | 72 | OPS/LK
542 | 72-00-00-27-0-SVA-002 | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK | 1 | 2 |  |  | Not Started | 72 | OPS/LK
543 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 1 | 1 |  |  | Not Started | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
544 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 1 | 1 |  |  | Not Started | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 1 |  | 4 | 16.2 | Idle | 78-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
547 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 1 | 0.9 |  |  | Not Started | 78-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
548 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 1 | 0.9 |  |  | Not Started | 78-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
549 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 1 | 1.4 |  |  | Not Started | 78-31 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
550 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 1 | 1.4 |  |  | Not Started | 78-31 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
551 | 783200-01-1-001 | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | 1 | 1.3 |  |  | Not Started | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
552 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 1 | 1.3 |  |  | Not Started | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
553 | 783209-01-1 | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | 1 | 3 | 1 | 16.8 | Idle | 78-32
559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | 1 | 75.7 |  |  | Not Started | 05-21 | INSPECTION
568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | 1 | 0.2 | 7.5 | 62.9 | Idle | 05-24 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | 1 | 1.4 | 0.2 | 47.8 | Idle | 05-25 | INSPECTION
577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | 1 | 1.4 |  |  | Not Started | 05-25 | INSPECTION
582 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 1 | 0.2 |  |  | Not Started | 27-21 | TC/P
583 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, JOB-CLOSEUP
584 | 282200-04-1 | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE | 1 | 2.5 |  |  | Not Started | 28-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
585 | 282400-01-1-001 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC | 1 | 0.5 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP
586 | 282400-01-1-002 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP
587 | 282400-02-1-001 | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, JOB-CLOSEUP
588 | 282400-02-1-002 | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, JOB-CLOSEUP
589 | 344200-02-2 | 344200-02-2 (01) / RADIO ALTIMETER | 1 | 7.2 |  |  | Not Started | 34-42 | JOB-SETUP, TC/P, JOB-CLOSEUP, JOB-CLOSEUP
590 | 344200-04-1 | 344200-04-1 (01) / RADIO ALTIMETER | 1 | 10.2 |  |  | Not Started | 34-42 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
591 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 1 | 10 |  |  | Not Started | 38-10 | JOB-SETUP, --, JOB-CLOSEUP
592 | 383100-02-1 | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY | 1 | 3.1 |  |  | Not Started | 38-31 | JOB-SETUP, TC/P, CLOSE-UP
593 | 494000-B2-1 | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG | 1 | 0.5 |  |  | Not Started | 49-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
594 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P
595 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P
596 | 532178-01-1 | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA | 1 | 0.1 |  |  | Not Started | 53
597 | 533130-01-1 | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP | 1 | 0.8 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
598 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 1 | 3.6 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
599 | 534112-01-1 | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION | 1 | 0.7 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
600 | 572610-02-2 | 572610-02-2 (0) / OUTER WING | 1 | 2.5 |  |  | Not Started | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
603 | 05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 1 | 1 |  |  | Not Started | 05-11 | TC/P
604 | 12-21-11-01-0-SVA | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH | 1 | 9.8 | 12 | 108.3 | Idle | 12-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
605 | 12-21-11-03-0-SVA | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH | 1 | 15 | 135 | 110.3 | Idle | 12-21 | WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH
606 | 32-10-00-01-0-SVA | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB | 1 | 2.5 |  |  | Not Started | 32-12 | JOB-SETUP, TC/P, TC/P
607 | 321000-01-1 | 321000-01-1 (5) / MLG AND DOORS LUBRICATION | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
608 | 322100-07-1 | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP | 1 | 30.6 |  |  | Not Started | 32-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
609 | 521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 1 | 2.5 |  |  | Not Started | 52-10
610 | 521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 1 | 3.5 |  |  | Not Started | 25-62 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
611 | 521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 1 | 3.5 |  |  | Not Started | 52-13 | TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION
612 | 522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 1 | 10.1 |  |  | Not Started | 52-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
613 | 523103-01-1 | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP | 1 | 4.6 |  |  | Not Started | 52-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
614 | 523109-01-1 | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP | 1 | 1.1 |  |  | Not Started | 52-31 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
615 | 523113-01-1 | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP | 1 | 4.6 |  |  | Not Started | 52-32 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
616 | 523119-01-2 | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP | 1 | 1.1 |  |  | Not Started | 52-32 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
617 | 523303-01-1 | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP | 1 | 1.8 |  |  | Not Started | 52-33 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
618 | 531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 1 | 6.3 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
619 | 532130-09-1 | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION | 1 | 2.8 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
620 | 532130-29-1 | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION | 1 | 4.4 |  |  | Not Started | 53-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
621 | 532132-01-1 | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP | 1 | 2 |  |  | Not Started | 53-21 | CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
623 | 532175-01-1 | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR | 1 | 7.5 |  |  | Not Started | 53-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
624 | 532180-04-2 | 532180-04-2 (0) / FORWARD FUSELAGE | 1 | 3 |  |  | Not Started | 53
625 | 533111-01-1 | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP | 1 | 3.3 |  |  | Not Started | 53-31 | CLEAN-UP, INSPECTION
626 | 533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 1 | 2.1 |  |  | Not Started | 53
627 | 533139-02-1 | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE | 1 | 1.5 |  |  | Not Started | 53-31 | JOB-SETUP, INSPECTION, --
628 | 533152-01-7 | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP | 1 | 5.5 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
629 | 534107-03-1 | 534107-03-1 (0) / REAR FUSELAGE | 1 | 0.6 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
630 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 1 | 16.4 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, --
631 | 534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 1 | 0.7 |  |  | Not Started | 57-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
632 | 534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 1 | 2.2 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
633 | 534150-01-1 | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION | 1 | 3.7 |  |  | Not Started | 53-41 | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
634 | 534164-01-1 | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC | 1 | 1.8 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
635 | 534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 1 | 6.2 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
636 | 534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 1 | 3.5 |  |  | Not Started | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 1 | 0.6 | 4 | 16.3 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 1 | 0.3 | 3.3 | 16.4 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
639 | 545134-09-6-001 | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP | 1 | 1.3 | 12.9 | 16.8 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
640 | 545134-09-6-002 | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP | 1 | 1.3 | 0.8 | 16.4 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
641 | 571192-09-1 | 571192-09-1 (0) / CENTER WING BOX | 1 | 1.7 |  |  | Not Started | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
642 | 571192-19-1 | 571192-19-1 (0) / CENTER WING BOX | 1 | 1.7 |  |  | Not Started | 57 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
643 | 572001-01-1-001 | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP | 1 | 2.2 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
644 | 572001-01-1-002 | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP | 1 | 2.2 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
645 | 572007-01-2-001 | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP | 1 | 2.2 |  |  | Not Started | 57-20 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
646 | 572007-01-2-002 | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP | 1 | 2.2 |  |  | Not Started | 57-20 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
647 | 572020-01-1-001 | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP | 1 | 13.2 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
648 | 572020-01-1-002 | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP | 1 | 13.2 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
649 | 572040-01-2-001 | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP | 1 | 0.4 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
650 | 572040-01-2-002 | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP | 1 | 0.4 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
651 | 572044-01-2-001 | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
652 | 572044-01-2-002 | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-SETUP
653 | 572062-01-1-001 | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP | 1 | 0.9 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
654 | 572062-01-1-002 | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP | 1 | 0.9 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
655 | 572063-01-1-001 | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP | 1 | 3.1 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
656 | 572063-01-1-002 | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP | 1 | 3.1 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
657 | 572066-01-1-001 | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 2.3 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
658 | 572066-01-1-002 | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 2.3 |  |  | Not Started | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
659 | 572111-01-1-001 | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP | 1 | 0.9 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
660 | 572111-01-1-002 | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP | 1 | 0.9 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
661 | 572111-02-1 | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- | 1 | 0.4 |  |  | Not Started | 57 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
662 | 572112-01-1-001 | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP | 1 | 3.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
663 | 572112-01-1-002 | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP | 1 | 3.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
664 | 572139-01-2-001 | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 1 | 1.1 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
665 | 572139-01-2-002 | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 1 | 1.1 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
666 | 32712996 | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP | 1 | 1.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
667 | 572140-01-2-002 | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP | 1 | 1.3 |  |  | Not Started | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
668 | 572607-01-1-001 | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 1 | 1.3 |  |  | Not Started | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
669 | 572607-01-1-002 | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 1 | 1.3 |  |  | Not Started | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
670 | 572610-02-1-001 | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP | 1 | 1.4 | 5 | 44.8 | Idle | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
671 | 572610-02-1-002 | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP | 1 | 1.4 | 5 | 44.8 | Idle | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
672 | 574101-01-3-001 | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP | 1 | 6.4 |  |  | Not Started | 57-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
673 | 574101-01-3-002 | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP | 1 | 6.4 |  |  | Not Started | 57-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
674 | 574202-01-2-001 | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 1 | 0.9 |  |  | Not Started | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
675 | 574202-01-2-002 | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 1 | 0.9 |  |  | Not Started | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
676 | 574205-01-1-001 | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP | 1 | 0.5 |  |  | Not Started | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
677 | 574205-01-1-002 | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP | 1 | 0.5 |  |  | Not Started | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
678 | 574302-01-2-001 | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 1 | 0.5 |  |  | Not Started | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
679 | 574302-01-2-002 | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 1 | 0.5 |  |  | Not Started | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
680 | 574305-01-1-001 | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP | 1 | 0.5 |  |  | Not Started | 57-43 | JOB-SETUP, --, INSPECTION, JOB-CLOSEUP
681 | 574305-01-1-002 | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP | 1 | 0.5 |  |  | Not Started | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
682 | 574402-01-2-001 | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
683 | 574402-01-2-002 | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
684 | 574405-01-1-001 | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION | 1 | 0.5 |  |  | Not Started | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
685 | 574405-01-1-002 | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION | 1 | 0.5 |  |  | Not Started | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
686 | 574502-01-2-001 | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
687 | 574502-01-2-002 | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
688 | 574505-01-1-001 | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION | 1 | 0.5 |  |  | Not Started | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
689 | 574505-01-1-002 | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION | 1 | 0.5 |  |  | Not Started | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
690 | 574602-01-2-001 | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
691 | 574602-01-2-002 | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 1 | 0.5 |  |  | Not Started | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
692 | 574605-01-1-001 | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION | 1 | 0.7 |  |  | Not Started | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
693 | 574605-01-1-002 | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION | 1 | 0.7 |  |  | Not Started | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
694 | 575107-01-1-001 | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 1 | 5.4 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
695 | 575107-01-1-002 | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 1 | 5.4 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
696 | 575120-03-1-001 | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP | 1 | 2.6 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
697 | 575120-03-1-002 | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP | 1 | 2.6 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
698 | 575150-01-2-001 | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP | 1 | 2.2 | 12 | 62.7 | Idle | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
699 | 575150-01-2-002 | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP | 1 | 2.2 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
700 | 575158-01-5-001 | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
701 | 575158-01-5-002 | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 |  |  | Not Started | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
702 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 1 | 4.7 |  |  | Not Started | 78-30
703 | 92339 | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION | 1 |  |  |  | Not Started | 53
704 | 92341 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 | 1 |  |  |  | Not Started | 53
705 | 31905379 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | RI |  | 2 | 37.8 | Idle | 32
706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 1 | 1.5 | 2 | 2.4 | Idle | 25
707 | 29904504 | EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A | C | 16 |  |  | Not Started | 21
708 | 29749798 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | C | 3 |  |  | Not Started | 23
709 | 20893203 | EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) | PJED | 9.2 |  |  | Not Started | 25
710 | 29715410 | EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO | CCHK | 6.2 |  |  | Not Started | 25
711 | 30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | AD | 0.5 |  |  | Not Started | 25
712 | 29411293 | EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | CCHK | 8.8 |  |  | Not Started | 27 | --, --, --, --, --, CLOSE-UP
713 | 29411377 | EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | CCHK | 8.8 |  |  | Not Started | 27 | --, --, --, --, --, CLOSE-UP
714 | 31889267 | EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. | 1 | 15.9 |  |  | Not Started | 27
715 | 30839449 | EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON | C | 48.5 |  |  | Not Started | 29 | --, JOB-SETUP, JOB-SETUP, JOB-SETUP, --, --, --, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, CLOSE-UP, CLOSE-UP
716 | 29500617 | EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | C | 6 |  |  | Not Started | 31
717 | 30482091 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | ACHK | 2 |  |  | Not Started | 31
718 | 30481965 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | ACHK | 4.9 |  |  | Not Started | 31
719 | 29155526 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | ACHK | 2.5 |  |  | Not Started | 31
720 | 29155624 | EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX | PJED | 2.5 |  |  | Not Started | 31
721 | 29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | PJED | 2.5 |  |  | Not Started | 31
722 | 29155864 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | PJED | 2 |  |  | Not Started | 31
723 | 23732996 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | PJED | 12.8 |  |  | Not Started | 32
724 | 23745496 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | PJED | 12.8 |  |  | Not Started | 32
725 | 31990073 | EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED | LINE | 54 |  |  | Not Started | 32
726 | 27685448 | EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS | CCHK | 16.2 |  |  | Not Started | 36
727 | 30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 1 | 471 |  |  | Not Started | 44
728 | 31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | PJED | 170 |  |  | Not Started | 44
729 | 29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | C | 23.2 |  |  | Not Started | 46
730 | 29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | C | 18 |  |  | Not Started | 46
731 | 29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | C | 18.5 |  |  | Not Started | 46
732 | 29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | C | 2.5 |  |  | Not Started | 46
733 | 29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | ACHK | 4 |  |  | Not Started | 46
734 | 29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | ACHK | 2.5 |  |  | Not Started | 46
735 | 15777417 | EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | PJED | 1.5 |  |  | Not Started | 53
736 | 15777631 | EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | PJED | 3 |  |  | Not Started | 53
737 | 16152729 | EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS | 1 | 8.3 |  |  | Not Started | 53
738 | 16152761 | EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS | 1 | 8.3 |  |  | Not Started | 53
739 | 17837147 | EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- | 1 | 25 |  |  | Not Started | 53
740 | 18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 1 | 62 |  |  | Not Started | 53
741 | 29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 1 | 33.8 |  |  | Not Started | 53
742 | 28479751 | EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 | 1 | 19.8 |  |  | Not Started | 53
743 | 31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | C | 42.2 |  |  | Not Started | 53
744 | 29399531 | EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI | CCHK | 28.2 |  |  | Not Started | 55
745 | 31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | ACHK | 1.7 |  |  | Not Started | 25
746 | 31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | ACHK | 1.7 |  |  | Not Started | 25
747 | 15969127 | EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. | 1 | 44.2 |  |  | Not Started | 53
748 | 10897096 | EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION | C | 12.7 |  |  | Not Started | 53
749 | 32362499 | S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION | ACHK | 6.5 |  |  | Not Started | 21-52 | --, --, --, CLOSE-UP
750 | 31662556 | S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH | ACHK | 2.7 |  |  | Not Started | 29
751 | 30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | CCHK | 22.5 |  |  | Not Started | 32-33 | --, --, --, --, --, --, --, --, --, --, OPS/LK, --, --, --, CLOSE-UP
752 | 30358131 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | RON | 2 |  |  | Not Started | 36
753 | 20038778 | S51-R10008/A320 FLEET // DENT AND BUCKLE CHART | HNGR | 33.5 | 1.3 | 89.8 | Idle | 51
754 | 31978429 | S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS | ACHK | 2.2 |  |  | Not Started | 52
755 | 31573583 | S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS | CCHK | 2.5 |  |  | Not Started | 53
756 | 32832482 | S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR | 1 |  | 1.3 | 68.8 | Idle | 71
757 | 29294848 | S73-D10063/ENGINE FUEL FILTER REPLACEMENT | ACHK | 4.3 |  |  | Not Started | 73
758 | 31958880 | REPLACE 3214-31/151653 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
759 | 31958882 | REPLACE 3214-31/151671 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
760 | 31958881 | REPLACE 3214-31/151674 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
761 | 31958879 | REPLACE 3214-31/151687 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
762 | 22959389 | REPLACE 47145-267/4527 (ACTUATOR-THS) | N | 6 |  |  | Not Started | 27
763 | 31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | N |  |  |  | Not Started | 20-00
764 | 26290429 | 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 |  |  | Not Started | 26-23
765 | 28781470 | 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 |  |  | Not Started | 26-23
766 | 28781472 | 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 |  |  | Not Started | 26-23
767 | 22574878 | 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 |  |  | Not Started | 26-23
768 | 23772081 | 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | CCHK | 2.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
769 | 23772080 | 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | CCHK | 2.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
770 | 31045000 | CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING | 1 | 4.8 |  |  | Not Started | 75
771 | 30304386 | CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 1 | 13.6 |  |  | Not Started | 72 | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP
772 | 80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | PANT |  | 16.2 | 6553.2 | Idle | 25
773 | 81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | N |  | 15 | 2045.8 | Idle | 25
774 | 94493475 | DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. | N |  | 2 | 967.8 | Idle | 11
775 | 94493476 | DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. | N |  | 2 | 967.8 | Idle | 11
776 | 94493487 | DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. | N |  | 1 | 919.5 | Idle | 11
777 | 94493488 | DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. | N |  | 1 | 919.4 | Idle | 11
778 | 94493489 | DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. | N |  | 1 | 919.2 | Idle | 11
779 | 94734250 | WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING | N | 1 | 1 | 1617 | Idle | 25
780 | 94740818 | BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN | N |  | 1 | 2060.3 | Idle | 25-00
781 | 94799712 | DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED | N |  | 1 | 1200.2 | Idle | 11-00
783 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | N | 1 |  |  | Not Started | 20 | ACFT RELEASE
784 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | N | 1 |  |  | Not Started | 20 | TC/P, TC/P
785 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | N | 5 |  |  | Not Started | 20 | ACFT RELEASE, ACFT RELEASE, --
786 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | N | 13 |  |  | Not Started | 20 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR
787 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | N | 22 |  |  | Not Started | 20 | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P
788 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | N | 2 |  |  | Not Started | 20 | TC/P
789 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | N | 3 |  |  | Not Started | 05-00 | FINAL INSP, FINAL INSP, FINAL INSP
790 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
791 | STJC-AREAS-FINAL-INSPECTION-03-GA-GO | AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
792 | STJC-AREAS-FINAL-INSPECTION-04-GA-GO | EMPENNAGE FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
793 | STJC-AREAS-FINAL-INSPECTION-05-GA-GO | AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
794 | STJC-AREAS-FINAL-INSPECTION-06-GA-GO | L/H AND R/H WINGS FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
795 | STJC-AREAS-FINAL-INSPECTION-07-GA-GO | LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) | N | 1 |  |  | Not Started | 05-00 | FINAL INSP
796 | STJC-AREAS-FINAL-INSPECTION-08-GA-GO | ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
797 | STJC-AREAS-FINAL-INSPECTION-09-GA-GO | APU FINAL INSPECTION | N | 1 |  |  | Not Started | 05-00 | FINAL INSP
798 | STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | N | 0.5 |  |  | Not Started | 05-11 | ACFT RELEASE
799 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | N | 7 |  |  | Not Started | 05-00 | FINAL INSP, FINAL INSP, FINAL INSP, FINAL INSP
800 | 32596938 | 22-70-00-01-0-A (03) / FMC DATA UPLOAD | 1 | 1 |  |  | Not Started | 22-70 | TC/P
801 | 242000-21-1-001 | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION | 1 | 2.1 |  |  | Not Started | 24-21 | --, TC/P, --
803 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 1 | 16 |  |  | Not Started | 38-10 | OPS/LK
804 | 32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 1 | 10 |  |  | Not Started | 25-00 | JOB-SETUP, TC/P, TC/P, TC/P, --, --, --, --, --
810 | 32913243 | CCC-32S (05) / A32S CABIN CRITICAL CHECK | 1 | 3.2 |  |  | Not Started | 25-00 | JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, --
811 | 94844878 | O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS | N | 24 |  |  | Not Started | 05-00
812 | 94844876 | L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 | N | 2 |  |  | Not Started | 32-00
813 | 32977683 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL | 1 | 3 |  |  | Not Started | 05-21
814 | 32977684 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE | 1 | 2 |  |  | Not Started | 05-21
815 | 32977685 | LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA | 1 | 4 |  |  | Not Started | 05-21
816 | 32977864 | PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. | 1 | 4 |  |  | Not Started | 05-21
817 | 32977871 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. | 1 | 4 |  |  | Not Started | 05-21
818 | 32977873 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. | 1 | 4 |  |  | Not Started | 05-21
819 | 32977874 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. | 1 | 4 |  |  | Not Started | 05-21
820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 1 | 2 |  |  | Not Started | 05-21
821 | 32977882 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. | 1 | 4 |  |  | Not Started | 05-21
822 | 32977883 | PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH | 1 |  | 5.2 | 75.6 | Idle | 05-21
823 | 32977884 | PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH | 1 |  | 18.5 | 75.4 | Idle | 05-21
825 | 32977905 | PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 1 | 8 |  |  | Not Started | 05-25
826 | 32977906 | PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 1 | 8 |  |  | Not Started | 05-25
827 | 32977907 | PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. | 1 | 2 | 0 | 3.2 | Idle | 05-25
828 | 32977908 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. | 1 | 4 |  |  | Not Started | 05-21
829 | 32977909 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. | 1 | 2 |  |  | Not Started | 05-25
830 | 32977910 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 1 | 4 |  |  | Not Started | 05-25
831 | 32977911 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 1 | 4 |  |  | Not Started | 05-25
832 | 32978070 | FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN | 1 |  |  |  | Not Started | 28-21
833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 1 | 4 | 4 | 26.6 | Idle | 05-21
834 | 32978238 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. | 1 | 2 |  |  | Not Started | 05-21
835 | 32978240 | NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. | 1 | 6 |  |  | Not Started | 05-21
836 | 32978243 | NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN | 1 | 2 |  |  | Not Started | 05-21
837 | 32978247 | NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. | 1 | 2 |  |  | Not Started | 05-21
838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 1 | 3 | 3 | 25.8 | Idle | 05-21
839 | 32978253 | LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. | 1 | 2 |  |  | Not Started | 05-25
840 | 32978254 | LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. | 1 | 8 |  |  | Not Started | 05-25
841 | 32978259 | LH MLG---PNT NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. | 1 | 2 |  |  | Not Started | 05-25
842 | 32978265 | LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
844 | 32978279 | RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. | 1 | 2 |  |  | Not Started | 05-25
845 | 32978280 | MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. | 1 | 2 |  |  | Not Started | 05-27
846 | 32978281 | RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
847 | 32978282 | RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" | 1 | 3 | 10.6 | 20.3 | Idle | 05-25
849 | 32978481 | RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. | 1 | 2 |  |  | Not Started | 32-30
850 | 32978506 | LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. | 1 | 2 |  |  | Not Started | 32-30
851 | 32978507 | FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. | 1 | 3 |  |  | Not Started | 25-50
852 | 32978509 | FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. | 1 | 6 |  |  | Not Started | 25-50
853 | 32978510 | FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. | 1 |  | 22.3 | 68.3 | Idle | 25-50
854 | 32978546 | FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. | 1 | 3 |  |  | Not Started | 25-50
855 | 32978563 | FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. | 1 | 4 |  |  | Not Started | 25-50
856 | 32978565 | FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED | 1 | 4 | 0.5 | 28.3 | Idle | 25-50
857 | 32978566 | FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. | 1 | 4 |  |  | Not Started | 25-50
858 | 32978568 | FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. | 1 | 2 |  |  | Not Started | 25-50
859 | 32978570 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY | 1 | 4 |  |  | Not Started | 05-28
861 | 32978585 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. | 1 |  |  |  | Not Started | 05-28
863 | 32978591 | FWD CARGO DOOR---PNT---NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. | 1 | 2 |  |  | Not Started | 05-28
864 | 32978593 | FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT | 1 | 4 |  |  | Not Started | 05-28
865 | 32978600 | FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. | 1 | 4 |  |  | Not Started | 05-28
866 | 32978626 | FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. | 1 | 4 |  |  | Not Started | 05-28
867 | 32978634 | AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" | 1 | 4 | 0.3 | 3.1 | Idle | 05-21
868 | 32978638 | AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" | 1 | 6 |  |  | Not Started | 05-21
869 | 32978643 | AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. | 1 | 6 |  |  | Not Started | 05-21
872 | 32978650 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY | 1 | 8 |  |  | Not Started | 05-28
873 | 32978651 | AFT CARGO DOOR---PNT---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. | 1 | 2 |  |  | Not Started | 05-28
876 | 32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 1 | 2 |  |  | Not Started | 25-21
877 | 32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 1 | 22 | 17.5 | 29.5 | Idle | 25-21
881 | 32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 1 | 12 | 6.5 | 29 | Idle | 25-21
882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 1 | 3 |  |  | Not Started | 25-21
886 | 32979256 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP KICK STRIP WITH CUT 0.5 IN. | 1 |  |  |  | Not Started | 05-25
887 | 32979285 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. | 1 |  |  |  | Not Started | 05-25
888 | 32979304 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
889 | 32979322 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.03 IN | 1 | 4 |  |  | Not Started | 05-25
890 | 32979401 | FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 1 | 12 | 0.5 | 36.3 | Idle | 05-24
891 | 32979406 | FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 1 | 8 | 5 | 36.3 | Idle | 05-24
892 | 32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 1 |  |  |  | Not Started | 25-65
893 | 32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 1 | 1 |  |  | Not Started | 25-65
894 | 32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 1 |  |  |  | Not Started | 35-30
895 | 32979731 | FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. | 1 |  |  |  | Not Started | 05-28
897 | 32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 1 | 24 | 22 | 51.9 | Idle | 25-21
899 | 32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 1 | 12 | 7 | 29.5 | Idle | 25-21
900 | 32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 1 | 6 |  |  | Not Started | 25-21
901 | 32391506 | 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
902 | 32439904 | 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
903 | 32163655 | 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
904 | 32163652 | 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
905 | 81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | N |  | 3.5 | 454.9 | Idle | 44-26-00
906 | 94844831 | DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN | N |  |  | 238.9 | Idle | 11
907 | 94844832 | DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED | N |  |  | 239 | Idle | 11
908 | 94844833 | DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED | N |  |  | 239 | Idle | 11
909 | 94844834 | DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN | N |  | 1 | 240.2 | Idle | 11
910 | 94844835 | DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN | N |  | 1 | 240.2 | Idle | 11
911 | 94844836 | RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED | N |  | 1 | 239.4 | Idle | 11
912 | 94844837 | DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN | N |  | 1 | 240.4 | Idle | 11
913 | 32345876 | EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 | ACHK | 2.5 |  |  | Not Started | 11
914 | 32850432 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | RON | 2 |  |  | Not Started | 21
915 | 15777708 | EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | C | 4.3 |  |  | Not Started | 53
916 | 15777769 | EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | C | 4.7 |  |  | Not Started | 53
917 | 28372303 | REPLACE DVE90-07/7369 (VALVE-SOLENOID) | N |  |  |  | Not Started | 35-00
918 | 28611923 | S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION | RON | 1.5 |  |  | Not Started | 25-30
919 | 32822269 | S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY | ACHK | 0.5 |  |  | Not Started | 26
920 | 32822529 | S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. | RON | 1 |  |  | Not Started | 31
921 | 30205720 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | ACHK | 1.5 |  |  | Not Started | 32 | INSPECTION
922 | 30262642 | S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL | ACHK | 1.7 |  |  | Not Started | 32
923 | 32800094 | S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK | CCHK | 31 |  |  | Not Started | 36
924 | 32872501 | S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS | LINE | 4 |  |  | Not Started | 36
926 | 32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 1 | 24 |  |  | Not Started | 25-21
928 | 32980047 | LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) | 1 | 8 | 8.5 | 16.8 | Idle | 24-92
929 | 32980064 | LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) | 1 | 8 | 5 | 20.3 | Idle | 24-92
930 | 32980065 | LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 | 1 |  |  |  | Not Started | 24-92
931 | 32980071 | LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) | 1 |  |  |  | Not Started | 24-92
932 | 32980080 | LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) | 1 |  |  |  | Not Started | 24-92
933 | 32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 1 | 6 |  |  | Not Started | 25-21
934 | 32980077 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. | 1 | 8 |  |  | Not Started | 05-25
935 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 1 | 0.2 |  |  | Not Started | 12-22 | TC/P
936 | 32980091 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. | 1 | 8 |  |  | Not Started | 05-25
937 | 32980104 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
938 | 32980083 | LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 | 1 |  |  |  | Not Started | 24-92
939 | 32980111 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE | 1 |  |  |  | Not Started | 05-25
941 | 32980118 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN | 1 | 8 |  |  | Not Started | 05-25
942 | 32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 1 | 16 | 16 | 51.8 | Idle | 25-21
943 | 44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 1 | 1.5 |  |  | Not Started | 44-21
944 | 32917899 | ISC/IN SERVCE CHECK_N | N |  |  |  | Not Started | 20-00
945 | 32420054 | W_N/WEEKLY CHECK | N |  |  |  | Not Started | 20-00
946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 1 | 2 |  |  | Not Started | 25-21
947 | ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | 1 | 2.8 |  |  | Not Started | 12 | TC/P, --, --, --
948 | WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | 1 | 5.9 |  |  | Not Started | 12 | TC/P, --, --, --, --, --, --, --
949 | 32980140 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
950 | 32980164 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
951 | 32980175 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP KICK STRIP WITH CUT DIM: L=1 IN | 1 | 8 |  |  | Not Started | 05-25
953 | 32980186 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
954 | 32980176 | REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) | 1 | 8 |  |  | Not Started | 05-28
955 | 32980920 | FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. | 1 | 8 |  |  | Not Started | 71
956 | 32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 1 |  |  |  | Not Started | 05-28
957 | 32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 1 | 3 |  |  | Not Started | 25-21
958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 1 | 2 |  |  | Not Started | 25-21
959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 1 | 6 |  |  | Not Started | 25-21
960 | 32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 1 | 6 |  |  | Not Started | 25-21
962 | 32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 1 | 2 |  |  | Not Started | 25-21
963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 1 | 2 |  |  | Not Started | 25-21
964 | 32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 1 | 15 | 7 | 29.5 | Idle | 25-21
966 | 32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 1 | 8 |  |  | Not Started | 25-30
968 | 32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 1 |  | 7.5 | 39.2 | Idle | 25-30
969 | 32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 1 |  |  |  | Not Started | 25-30
970 | 32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 1 |  | 9.5 | 64.4 | Idle | 25-30
971 | 32982199 | RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 1 |  | 1.5 | 62.1 | Idle | 25-40
972 | 32982200 | RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  | 2 | 62.3 | Idle | 25-40
973 | 32982202 | RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  |  |  | Not Started | 25-40
974 | 32982203 | RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 1 |  | 4 | 62.6 | Idle | 25-40
978 | 32983857 | PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. | 1 | 4 |  |  | Not Started | 05-24
979 | 32983861 | PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. | 1 | 8 |  |  | Not Started | 05-21
981 | 32983876 | PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. | 1 | 12 |  |  | Not Started | 05-21
982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 1 | 4 |  |  | Not Started | 05-21
983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 1 | 3 |  |  | Not Started | 05-21
984 | 32983896 | LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION | 1 | 8 |  |  | Not Started | 05-25
985 | 32983897 | PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. | 1 | 8 |  |  | Not Started | 05-21
986 | 32983910 | PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. | 1 |  |  |  | Not Started | 05-21
987 | 32983929 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. | 1 | 6 |  |  | Not Started | 05-21
988 | 32983937 | PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. | 1 | 8 | 0.5 | 39.8 | Idle | 05-21
989 | 32983944 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. | 1 | 6 |  |  | Not Started | 05-21
990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 1 | 4 |  |  | Not Started | 05-21
991 | 32983948 | OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS | 1 | 6 |  |  | Not Started | 05-25
992 | 32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 1 | 8.5 |  |  | Not Started | 25
993 | 32984016 | OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) | 1 | 3 |  |  | Not Started | 05-25
994 | 32984140 | AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED | 1 | 6 |  |  | Not Started | 71-13
995 | 32984158 | PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED | 1 | 3 | 3.5 | 16.4 | Idle | 71-13
996 | 32984174 | PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. | 1 |  |  |  | Not Started | 05-21
997 | 32984360 | FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 | 1 | 6 |  |  | Not Started | 05-25
999 | 32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 1 | 6 |  |  | Not Started | 25-21
1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 1 | 18 |  |  | Not Started | 05-25
1001 | 32984513 | R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION | 1 | 18 |  |  | Not Started | 05-25
1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 1 | 18 |  |  | Not Started | 05-25
1003 | 32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 1 | 12 | 7 | 29.6 | Idle | 25-21
1004 | 32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 3 |  |  | Not Started | 25
1005 | 32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1006 | 32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 1 | 2 |  |  | Not Started | 25
1007 | 32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1008 | 32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 1 |  |  |  | Not Started | 25
1009 | 32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 1 | 4 |  |  | Not Started | 25-10
1010 | 32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 1 |  |  |  | Not Started | 25
1011 | 32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1012 | 32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 1 |  |  |  | Not Started | 25-10
1013 | 32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 1 | 4 |  |  | Not Started | 25-10
1014 | 32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 1 | 6 | 6.5 | 27.3 | Idle | 38
1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 1 | 8 |  |  | Not Started | 05-25
1017 | 32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 1 | 3 |  |  | Not Started | 25-10
1018 | 32984975 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. | 1 | 6 |  |  | Not Started | 05-23
1019 | 32984986 | AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK | 1 | 8 |  |  | Not Started | 05-24
1020 | 32984983 | PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. | 1 | 8 |  |  | Not Started | 05-23
1021 | 32985000 | AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE | 1 | 8 |  |  | Not Started | 05-24
1022 | 32985009 | PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. | 1 |  |  |  | Not Started | 05-23
1023 | 32984981 | DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... | 1 | 4 | 0.3 | 2.8 | Idle | 51
1024 | 32985016 | PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. | 1 | 8 |  |  | Not Started | 05-23
1025 | 32985033 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. | 1 | 8 |  |  | Not Started | 05-23
1027 | 32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 1 | 2 |  |  | Not Started | 25
1028 | 32985066 | PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. | 1 |  |  |  | Not Started | 05-23
1029 | 32985072 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. | 1 | 2 |  |  | Not Started | 05-23
1030 | 32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1031 | 32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 1 | 8 |  |  | Not Started | 05-24
1034 | 32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 1 | 2 |  |  | Not Started | 25-61
1035 | 32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1036 | 32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1037 | 32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1038 | 32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 1 |  |  |  | Not Started | 25
1039 | 32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1040 | 32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 1 |  |  |  | Not Started | 25
1041 | 32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 1 |  |  |  | Not Started | 25
1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1044 | 32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1045 | 32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 1 |  |  |  | Not Started | 25
1046 | 32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 1 |  |  |  | Not Started | 25
1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1048 | 32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1049 | 32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 1 |  |  |  | Not Started | 25
1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1052 | 32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1053 | 32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  |  |  | Not Started | 25
1055 | 32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1056 | 32985503 | VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP | 1 | 10 |  |  | Not Started | 27-21
1061 | 32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 1 |  |  |  | Not Started | 35-23
1062 | 32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 1 |  |  |  | Not Started | 35-23
1063 | 32985836 | RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED | 1 | 6 |  |  | Not Started | 05-23
1064 | 32985860 | L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED | 1 | 8 |  |  | Not Started | 05-23
1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 1 | 10 |  |  | Not Started | 05-23
1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 1 | 8 |  |  | Not Started | 05-23
1067 | 32985872 | THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY | 1 | 8 |  |  | Not Started | 05-23
1068 | 32985870 | L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH | 1 |  |  |  | Not Started | 05-23
1069 | 32985875 | ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 1 | 8 |  |  | Not Started | 05-24
1070 | 32985877 | ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 1 | 8 |  |  | Not Started | 05-24
1072 | 32986985 | PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. | 1 |  |  |  | Not Started | 24-92
1073 | 32987001 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO#26`191`406 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE AT FLAP RIB STATION 4 WITH MULTIPL... | 1 |  | 0.3 | 2.5 | Idle | 51
1074 | 32987040 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO# 26191411 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS UPPER SKIN SURFACE 9 INCHES FROM THE TRAILING EDGE OF THE INBOARD FLAP AT... | 1 |  | 0.3 | 2.1 | Idle | 51
1075 | 32987066 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 1 | 6 |  |  | Not Started | 25-21
1076 | 32987146 | AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS | 1 | 16 |  |  | Not Started | 20-00
1077 | 32987097 | CABIN FLOOR PANELS - CAB -CALLBACK CABIN FLOOR PANEL NO: 241EF, 241KF, 241LF, 241MF, 242FF, 242KF, 242LF AND 242MF REQUIRES REMOVAL FOR ACCESS. | 1 |  |  |  | Not Started | 32-33
1078 | 32987238 | LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. | 1 |  |  |  | Not Started | 53-41
1079 | 32987295 | PRE---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW WEATHER SEAL UPPER AREA FOUND WITH MISSING MATERIAL/WORNOUT AND AFT LOWER AREA FOUND WITH OLD IMPROPER REPAIR. | 1 | 8 |  |  | Not Started | 56-10
1080 | 32987301 | DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. | 1 | 16 |  |  | Not Started | 56-10
1081 | 32987455 | PRE---F/O SLIDING WINDOW---RII---AP R/H SIDE F/O SLIDING WINDOW OUTER SURFACE AFT UPPER AND LOWER WEATHER SEAL FOUND DAMAGE. | 1 | 8 |  |  | Not Started | 56-10
1082 | 94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | N |  | 35 | 157.9 | Idle | 52
1083 | 32968390 | S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) | RON | 0.6 |  |  | Not Started | 25-60
1084 | 32913240 | S28-R10083/A320,321 REPETITIVE FUEL SUMP AND DRAIN - WATER REMOVAL | RON | 2 |  |  | Not Started | 28
1085 | 32984296 | S34-R10187/A320/A321 - T2CAS - UPDATE OF TERRAIN DATABASE INTO VERSION 227 | PJED | 1.3 |  |  | Not Started | 34
1086 | 32974165 | S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1 | 0.2 |  |  | Not Started | 53
1087 | 32974180 | S52-R10176/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1 | 0.5 |  |  | Not Started | 53
1088 | 32987715 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD OUTER SURFACE UPPER SURFACE WEATHER SEAL FOUND WITH IMPROPER REPAIR APPLICATION AND R/H SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR. | 1 | 8 |  |  | Not Started | 56-10
1089 | 32987725 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... | 1 | 16 |  |  | Not Started | 56-10
1091 | 32987890 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`424 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 1 |  | 0.3 | 1.8 | Idle | 51
1092 | 32987935 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`432 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 1 |  |  |  | Not Started | 51
1093 | 32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 1 |  |  |  | Not Started | 52-51
1094 | 32987951 | PRE---CPT SLIDING WINDOW---RII---AP L/H SIDE CPT SLIDING WINDOW OUTER SURFACE AFT AND LOWER SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR APPLICATION. | 1 | 8 |  |  | Not Started | 56-10
1095 | 32987959 | PRE---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW WEATHER SEAL AFT LOWER CORNER AREA FOUND DAMAGE. | 1 | 8 |  |  | Not Started | 56-10
1096 | 32987947 | DBC/DOCUMENT S51-R10008- LH WING--RII--SM REF TO WO#26191340 DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE BETWEEN FLAP RIB STATION 6 TO 7 WITH MULTIPLE SMALL DENTS LARGEST DIMENSIO... | 1 |  |  |  | Not Started | 51
1097 | 32987964 | DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. | 1 | 16 |  |  | Not Started | 56-10
1098 | 32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 1 |  |  |  | Not Started | 52-51
1099 | 32987973 | DBC/DOCUMENT S51-R10008- RH WING--RII--SM REF TO WO#26`191`414 DURING COMPLIANCE OF RH WING DBC SCANNING FOUND RH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE SECTION BETWEEN FLAP RIB STATION 4 TO 5 WITH MULTIPLE SMALL DENTS LARGES... | 1 |  |  |  | Not Started | 51
1100 | 32987976 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET IDENTIFICATION LABEL FOUND TORN AND NET STRIPS FOUND DETACHED. | 1 | 6 |  |  | Not Started | 25-50
1101 | 32987983 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET, IDENTIFICATION LABEL AND DIVIDER NET FOUND EXCESSIVE DIRTY WITH STAIN MARKS. | 1 | 6 |  |  | Not Started | 25-50
1102 | 32987979 | DBC/DOCUMENT S51-R10008-RH HORIZONTAL STABILIZER LE- RII--SM REF TO WO#26`191`479 DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND RH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN THS RIB STATION 9 WITH MULTIPLE SMALL DEN... | 1 |  |  |  | Not Started | 51
1103 | 32988009 | PRE---L/H WING FIXED L/E---NOCALLBACK---AP L/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 1 | 8 |  |  | Not Started | 05-25
1104 | 32988013 | PRE---R/H WING FIXED L/E---NOCALLBACK---AP R/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 1 | 8 |  |  | Not Started | 05-25
1105 | 32988015 | PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED | 1 | 8 |  |  | Not Started | 05-25
1106 | 32988202 | RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS | 1 | 16 |  |  | Not Started | 27-24
1107 | 32988329 | PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ | 1 | 2 |  |  | Not Started | 25-10
1108 | 32988444 | PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA | 1 | 4 |  |  | Not Started | 25-10
1109 | 32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 1 | 1.5 |  |  | Not Started | 25-10
1110 | 32988479 | CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ | 1 | 1.5 |  |  | Not Started | 25-10
1111 | 32988506 | CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED | 1 |  |  |  | Not Started | 25-10
1112 | 32988660 | PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS | 1 | 4 |  |  | Not Started | 25-10
1113 | 32988687 | CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ | 1 | 2 |  |  | Not Started | 25-10
1114 | 32988706 | CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED | 1 | 1 |  |  | Not Started | 25-10
1115 | 32988779 | CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA | 1 | 1.5 |  |  | Not Started | 25-10
1116 | 32988786 | PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA | 1 | 1 |  |  | Not Started | 25-10
1117 | 32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 1 | 2 |  |  | Not Started | 25-10
1118 | 32988998 | PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. | 1 | 8 |  |  | Not Started | 28-18
1119 | 32989018 | PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. | 1 |  |  |  | Not Started | 05-21
1120 | 32989039 | PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. | 1 |  |  |  | Not Started | 24-92
1121 | 32988850 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY SEVERAL AIR FLAP SEAL DETORIATED | 1 |  |  |  | Not Started | 25-10
1122 | 32989105 | PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. | 1 | 8 |  |  | Not Started | 24-92
1123 | 32989125 | PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. | 1 | 8 |  |  | Not Started | 24-92
1124 | 32989133 | CAB - NO CALL BACK - GLLY G2 GALLEY SEVERAL RUB STRIP FADED | 1 |  |  |  | Not Started | 25-10
1125 | 32989174 | BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY | 1 |  |  |  | Not Started | 57-56
1126 | 32989457 | CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. | 1 |  |  |  | Not Started | 25
1127 | 32989455 | CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP | 1 |  |  |  | Not Started | 25-00
1128 | 32989472 | CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING | 1 |  |  |  | Not Started | 25-00
1129 | 32989475 | AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. | 1 |  |  |  | Not Started | 25
1130 | 32989476 | CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE | 1 |  |  |  | Not Started | 25-00
1131 | 32989482 | CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT | 1 |  |  |  | Not Started | 25
1132 | 32989491 | CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. | 1 |  |  |  | Not Started | 25
1133 | 32989492 | CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT | 1 |  |  |  | Not Started | 25
1134 | 32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 1 |  |  |  | Not Started | 25
1135 | 32989529 | FWD GARGO COMPT=====FS=====NO CALL BACK FWD CARGO COMPARTMENT CEILING, SIDE WALL AND SLOPY AREA DIRTY WITH ACCUMULATED DUST | 1 | 30 |  |  | Not Started | 05-21
1136 | 32989545 | L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. | 1 | 6.5 |  |  | Not Started | 05-25
1137 | 32989556 | R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... | 1 | 30 |  |  | Not Started | 05-25
1138 | 32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1 | 4 |  |  | Not Started | 25
1139 | 32989577 | BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION | 1 | 20 |  |  | Not Started | 50-11-33
1140 | 32989579 | AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. | 1 | 15 |  |  | Not Started | 05-21
1141 | 32989728 | CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING | 1 |  |  |  | Not Started | 25
1142 | 32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 1 |  |  |  | Not Started | 25
1143 | 32989796 | CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY | 1 |  |  |  | Not Started | 25
1144 | 32989797 | S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE | 1 |  |  |  | Not Started | 25
1145 | 32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 1 |  |  |  | Not Started | 25
1146 | 32989825 | CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING | 1 |  |  |  | Not Started | 25
1147 | 32989853 | CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER | 1 |  |  |  | Not Started | 25
1148 | 32989854 | CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE | 1 |  |  |  | Not Started | 25
1149 | 32989860 | CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING | 1 |  |  |  | Not Started | 25
1150 | 32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 1 |  |  |  | Not Started | 25
1151 | 32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1 | 4 |  |  | Not Started | 25
1152 | 32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 1 |  |  |  | Not Started | 25-10
1153 | 32989942 | #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 1 | 8 |  |  | Not Started | 71-13
1154 | 32989943 | CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. | 1 |  |  |  | Not Started | 25-10
1155 | 32989944 | #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... | 1 | 8 |  |  | Not Started | 71-13
1156 | 32989952 | CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. | 1 |  |  |  | Not Started | 25-10
1157 | 32989954 | #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 1 | 2 |  |  | Not Started | 71-13
1158 | 32989962 | #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 1 |  |  |  | Not Started | 71-13
1159 | 32989953 | FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION | 1 | 30 |  |  | Not Started | 11-35
1160 | 32989963 | #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. | 1 | 3 |  |  | Not Started | 71-13
1161 | 32989964 | #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . | 1 | 6 |  |  | Not Started | 71-13
1162 | 32989965 | #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). | 1 | 3 |  |  | Not Started | 30-21
1163 | 32989966 | #2 ENG - FAN FR ASSY - HMU LINES CLAMPS - AP - RII #2 ENG FAN FRAME ASSEMBLY AT 06:00 O`CLOCK POSTION FOUND HYDROMECHANICAL UNIT (HMU) SOV FUEL LINES (ROD AND HEAD LINES) CLAMPS CORRODED . | 1 | 4 |  |  | Not Started | 24-92
1164 | 32989967 | #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. | 1 |  |  |  | Not Started | 24-92
1165 | 32989971 | #2 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #2 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. | 1 |  |  |  | Not Started | 05-24
1166 | 32989973 | #2 ENG - R/H T/REV - HCU - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FWD FACE FOUND HYDRAULIC CONTROL UNIT (HCU) LEAKING . | 1 | 4 |  |  | Not Started | 05-24
1167 | 32989975 | #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 1 | 4 |  |  | Not Started | 05-24
1168 | 32989976 | #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . | 1 | 4 |  |  | Not Started | 05-24
1169 | 32989982 | #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... | 1 |  |  |  | Not Started | 05-24
1170 | 32989993 | #2 ENG - L/H TREV - THERMAL BLANKET - SM - RII #2 ENG L/H THRUST REVERSER INNER SIDE FOUND THERMAL BLANKET TORN ( T/REV CHAFFING AGAINST T495 THERMOCOUPLE HARNESS AT 08:00 OCLOCK POSITION) DISTANCE TO NEAREST EDGE :- 2.5 INCH. DIM:- L= 2.31 INCH.... | 1 |  |  |  | Not Started | 05-24
1171 | 32989995 | RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. | 1 |  |  |  | Not Started | 25
1172 | 32989994 | #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... | 1 |  |  |  | Not Started | 05-24
1173 | 32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 1 |  |  |  | Not Started | 25-21
1174 | 32990008 | CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  |  |  | Not Started | 25-40
1175 | 32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO:33L,34JL,35K,37JL | 1 |  |  |  | Not Started | 25-21
1176 | 32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 1 |  |  |  | Not Started | 25-21
1177 | 32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 1 |  |  |  | Not Started | 25-21
1178 | 32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 1 |  |  |  | Not Started | 25-21
1179 | 32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 33B,C 32A,B,C AND 31A,B | 1 |  |  |  | Not Started | 25-21
1180 | 32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 1 |  |  |  | Not Started | 25-21
1181 | 32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 1 |  |  |  | Not Started | 25-21
1182 | 32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 1 |  |  |  | Not Started | 25-21
1183 | 32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 1 |  |  |  | Not Started | 25-21
1184 | 32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 1 |  |  |  | Not Started | 25-21
1185 | 32990036 | #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - NO CALL BACK #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 1 |  |  |  | Not Started | 71-13
1186 | 32990048 | #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... | 1 |  |  |  | Not Started | 71-13
1187 | 32990053 | #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... | 1 |  |  |  | Not Started | 71-13
1188 | 32990054 | #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... | 1 |  |  |  | Not Started | 71-13
1189 | 32990067 | #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 1 |  |  |  | Not Started | 71-13
1190 | 32990167 | #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 1 | 2 |  |  | Not Started | 71-13
1191 | 32990169 | #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. | 1 | 3 |  |  | Not Started | 71-13
1192 | 32990170 | #1 ENG - R/H FAN COWL - PRESS DR - AP - RII #1 ENG R/H FAN COWL INNER SIDE FOUND PRESSURE RELIEF DOOR UPPER AND LOWER SPRING LOADED ARMS HINGES RUSTED AND UPPER SPRING LOADED ARM LANYARD FWD END CHAFFED-OFF AND SPRING LOADED ARM END GOUGED. | 1 |  |  |  | Not Started | 71-13
1193 | 32990171 | #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... | 1 |  |  |  | Not Started | 71-13
1194 | 32990173 | #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. | 1 |  |  |  | Not Started | 24-92
1195 | 32990192 | #1 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #1 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (R/H T/REV TEFLON SEAL DETACHED FROM UPPER AND LOWER SIDE). | 1 |  |  |  | Not Started | 05-24
1196 | 32990196 | #1 ENG - L/H T/REV - LOWER BLOCKER DR - AP - NO CALL BACK #1 ENG L/H THRUST REVERSER FOUND LOWER BLOCKER DOOR ACTUATOR WITH HEAVY LEAK AT ROD END. | 1 | 3 |  |  | Not Started | 05-24
1197 | 32990203 | #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 1 |  |  |  | Not Started | 05-24
1198 | 32990219 | #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... | 1 |  |  |  | Not Started | 05-24
1199 | 32991206 | CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA | 1 |  |  |  | Not Started | 25-10
1200 | 32991276 | AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. | 1 |  |  |  | Not Started | 25
1201 | 32991499 | CAB - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. | 1 |  |  |  | Not Started | 25
1202 | 32991511 | CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | 1 |  |  |  | Not Started | 25
1203 | 32991517 | PNT - RII - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 1 |  |  |  | Not Started | 25
1204 | 32991518 | FINDING (NRC) TASKCARD ZL-531-02-1-001 (01) LH WING AP-- NO CALLBACK LH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT. | 1 |  |  |  | Not Started | 05-25
1205 | 32991527 | CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP | 1 |  |  |  | Not Started | 25
1206 | 32991534 | PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. | 1 |  |  |  | Not Started | 25
1207 | 32991563 | RH WING -- FT REFER TO TC # 572020-01-1-002, 572040-01-2-002, 572139-01-2-002, 572140-01-2-002 AND 572161-01-11-002 REQUIRE TO REMOVE RH WING FUEL TANK ACCESS PANELS - 640AB, 640BB , 640CB, 640DB, 640EB, 640FB, 640GB - 640HB, 640JB, 640KB, 640LB... | 1 |  |  |  | Not Started | 57
1208 | 32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 1 | 2 |  |  | Not Started | 25-21
1209 | 32991584 | LH WING -- FT REFER TO TC # 572020-01-1-001, 572040-01-2-001, 572139-01-2-001, 572140-01-2-001 AND 572161-01-11-001 REQUIRE TO REMOVE LH WING FUEL TANK ACCESS PANELS - 540AB, 540BB , 540CB, 540DB, 540EB, 540FB, 540GB - 540HB, 540JB, 540KB, 540LB... | 1 |  |  |  | Not Started | 57
5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 1 | 0.3 | 0.5 | 0.5 | Closed | 24-92 | INSPECTION
10 | 200125-05-1 | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP | 1 | 9.9 | 1 | 1 | Closed | 24-92 | INSPECTION
27 | 200315-01-1 | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP | 1 | 0.4 | 1 | 0.5 | Closed | 24-92 | INSPECTION
37 | 256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 1 | 0.4 | 12 | 2.8 | Closed | 25-61 | TC/P, TC/P, TC/P, TC/P, TC/P
38 | 262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 1 | 0.2 | 0.8 | 0.8 | Closed | 26-25 | INSPECTION
40 | 281800-02-1 | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION | 1 | 1.8 | 0.8 | 0.8 | Closed | 28-18 | INSPECTION
41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 1 | 0.2 | 4.5 | 2.8 | Closed | 28-18 | INSPECTION
103 | ZL-110-01-1 | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION | 1 | 0.2 | 1 | 1 | Closed | 05-21 | PRE INSP
107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | 1 | 38.3 | 5 | 12.2 | Closed | 05-21 | INSPECTION
110 | ZL-147-03-1 | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP | 1 | 0.9 | 0.8 | 0.8 | Closed | 05-21 | INSPECTION
116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | 1 | 2.2 | 2.5 | 1.9 | Closed | 05-21 | INSPECTION
118 | ZL-195-01-1 | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP | 1 | 0.9 | 0.7 | 0.7 | Closed | 05-21 | PRE INSP
119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | 1 | 1.3 | 5.5 | 2.8 | Closed | 05-21 | INSPECTION
120 | ZL-200-02-1 | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI | 1 | 18.5 | 2.3 | 2.4 | Closed | 05-21 | PRE INSP
123 | ZL-311-01-1 | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP | 1 | 0.4 | 0.8 | 0.8 | Closed | 05-23 | PRE INSP
124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | 1 | 0.2 | 15 | 9 | Closed | 05-23 | PRE INSP
125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | 1 | 0.2 | 7.8 | 7 | Closed | 05-23 | INSPECTION
127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | 1 | 1.8 | 1.8 | 1.6 | Closed | 05-23 | PRE INSP
128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | 1 | 0.9 | 8.3 | 4.1 | Closed | 05-24 | PRE INSP
129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | 1 | 0.9 | 0.8 | 0.6 | Closed | 05-24 | PRE INSP
130 | ZL-433-01-1-001 | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP | 1 | 1.3 | 0.5 | 0.5 | Closed | 05-24 | PRE INSP
131 | ZL-433-01-1-002 | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP | 1 | 1.3 | 0.5 | 0.5 | Closed | 05-24 | PRE INSP
132 | ZL-500-03-1-001 | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP | 1 | 1.4 | 1.8 | 2.3 | Closed | 05-25 | PRE INSP
133 | ZL-500-03-1-002 | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP | 1 | 1.4 | 1.8 | 2 | Closed | 05-25 | PRE INSP
134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | 1 | 0.9 | 1 | 0.8 | Closed | 05-25 | INSPECTION
136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | 1 | 0.9 | 3.8 | 25.5 | Closed | 05-25 | INSPECTION
137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | 1 | 0.9 | 3 | 2.9 | Closed | 05-25 | INSPECTION
140 | ZL-532-01-1-001 | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP | 1 | 0.5 | 1 | 1 | Closed | 05-25 | INSPECTION
142 | ZL-532-02-1-001 | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
144 | ZL-533-01-1-001 | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP | 1 | 0.5 | 1 | 1 | Closed | 05-25 | INSPECTION
146 | ZL-571-02-1-001 | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP | 1 | 0.9 | 0.5 | 0.5 | Closed | 05-25 | INSPECTION
147 | ZL-571-02-1-002 | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP | 1 | 0.9 | 0.5 | 0.5 | Closed | 05-25 | INSPECTION
152 | ZL-590-01-1-001 | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION | 1 | 0.4 | 1 | 1 | Closed | 05-25 | INSPECTION
153 | ZL-590-01-1-002 | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION | 1 | 0.4 | 1 | 1 | Closed | 05-25 | INSPECTION
155 | ZL-812-01-1 | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP | 1 | 0.4 | 1 | 1 | Closed | 05-28 | PRE INSP
156 | ZL-824-01-1 | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP | 1 | 0.2 | 1 | 1 | Closed | 05-28 | PRE INSP
162 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 1 | 0.4 | 2 | 1 | Closed | 21-23 | TC/P, TC/P
166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 1 | 0.2 | 4.5 | 2.8 | Closed | 24-28 | OPS/LK
179 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 1 | 2 | 1 | 1 | Closed | 25-60 | PRE INSP
180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 1 | 2 | 1 | 1 | Closed | 25-65 | PRE INSP
181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 1 | 1 | 1 | 1 | Closed | 25-65 | PRE INSP
184 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 1 | 1.3 | 0.2 | 0.2 | Closed | 25-50 | PRE INSP
203 | 282800-09-1 | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) | 1 | 0.3 | 0.2 | 0.2 | Closed | 28-28 | PRE INSP
210 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 1 | 0.1 | 1 | 1 | Closed | 32-30 | PRE INSP
211 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 1 | 0.1 | 0.2 | 0.2 | Closed | 32-30 | PRE INSP
212 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 1 | 0.1 | 0.5 | 0.5 | Closed | 32-30 | PRE INSP
215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 1 | 0.4 | 6.5 | 5.2 | Closed | 35-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
216 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 1 | 0.4 | 2.8 | 3.8 | Closed | 35-30 | PRE INSP, PRE INSP, PRE INSP
236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 1 | 0.7 | 15 | 17.3 | Closed | 24-92 | INSPECTION
238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 1 | 1.1 | 7 | 5.2 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
249 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 1 | 2.2 | 40 | 8.8 | Closed | 21-61 | PRE HGR
257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 1 | 8 | 4 | 2 | Closed | 23-73 | OPS/LK
258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 1 | 0.9 | 6 | 2.1 | Closed | 23-33 | OPS/LK
293 | 252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 1 | 0 | 0.8 | 0.8 | Closed | 25-22 | PRE INSP
294 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 1 | 3.3 | 0.8 | 0.8 | Closed | 25-40 | PRE INSP
303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 1 | 0.9 | 7 | 1.9 | Closed | 26-21 | TC/P, TC/P, TC/P
304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 1 | 0.9 | 7 | 1.9 | Closed | 26-21 | TC/P, TC/P, TC/P
306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 1 | 0.7 | 8.5 | 2.2 | Closed | 26-22 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
307 | 262200-04-1 | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE | 1 | 0.4 | 0.8 | 0.8 | Closed | 26-22 | INSPECTION
309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 1 | 0.7 | 4.5 | 2.8 | Closed | 26-22 | OPS/LK
310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 1 | 1.3 | 11 | 3.4 | Closed | 26-23 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
312 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 1 | 0.2 | 0.8 | 0.8 | Closed | 26-25 | INSPECTION
324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 1 | 2.2 | 39.6 | 7.4 | Closed | 27-24 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR
325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 1 | 5.5 | 36.8 | 9.2 | Closed | 27-34 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
327 | 274000-04-1 | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC | 1 | 0.2 | 20 | 8.8 | Closed | 27-96 | PRE HGR, PRE HGR, PRE HGR
333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 1 | 0.1 | 0.5 | 0.5 | Closed | 27-44 | PRE INSP
361 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 1 | 0.1 | 0.9 | 0.9 | Closed | 28-12 | PRE INSP
362 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 1 | 0.1 | 1 | 1 | Closed | 28-12 | PRE INSP
367 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 1 | 0.4 | 6 | 3.9 | Closed | 28-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
368 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 1 | 0.4 | 5 | 3.8 | Closed | 28-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
369 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 1 | 0.2 | 10 | 3 | Closed | 28-23 | PRE HGR, PRE HGR, JOB-CLOSEUP
387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 1 | 0.9 | 6.5 | 5.6 | Closed | 30-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 1 | 0.4 | 4.5 | 2.8 | Closed | 32-31 | OPS/LK
403 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 1 | 0.7 | 1 | 1 | Closed | 32-30 | PRE INSP
411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 1 | 0.2 | 8 | 3 | Closed | 32-42 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 1 | 0.2 | 9 | 3.1 | Closed | 33-51 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 1 | 1 | 6.5 | 2.6 | Closed | 34-55 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 1 | 0.2 | 4.5 | 1.4 | Closed | 34-22 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
426 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 1 | 0.6 | 10 | 4.4 | Closed | 35-12 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
429 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 1 | 2.2 | 3.5 | 1.6 | Closed | 25-64 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
430 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 1 | 0.4 | 3.5 | 3.3 | Closed | 35-30 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
436 | 361200-02-1 | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED | 1 | 4.4 | 42.7 | 22.3 | Closed | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
437 | 361200-03-1 | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK | 1 | 2.2 | 40.3 | 20.3 | Closed | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
445 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 1 | 0.2 | 0.5 | 0.5 | Closed | 49-81 | INSPECTION
473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 1 | 0.6 | 7.8 | 3.9 | Closed | 52-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 1 | 0.3 | 4.8 | 3 | Closed | 52-51 | OPS/LK
476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 1 | 0.1 | 4.5 | 3.1 | Closed | 52-51 | OPS/LK
487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 1 | 1.1 | 6 | 5.9 | Closed | 53-21 | PRE INSP, PRE INSP
514 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 1 | 0.2 | 0.5 | 0.5 | Closed | 71-10 | INSPECTION
515 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 1 | 0.2 | 0.5 | 0.5 | Closed | 71-10 | INSPECTION
517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 1 | 2 | 5.8 | 4.6 | Closed | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 1 | 1.8 | 1.5 | 3.5 | Closed | 71-13 | INSPECTION
523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 1 | 1.8 | 6.5 | 4.8 | Closed | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 1 | 0.5 | 1 | 1 | Closed | 71-13
531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 1 | 1.3 | 1 | 1 | Closed | 71-22 | PRE INSP
532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 1 | 1.3 | 1 | 1 | Closed | 71-22 | PRE INSP
539 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 1 | 2 | 9 | 4 | Closed | 72 | OPS/LK
540 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 1 | 2 | 9 | 4 | Closed | 72 | OPS/LK
546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 1 | 0.9 | 10.3 | 4.4 | Closed | 78-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
554 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | 1 | 12.5 | 1.3 | 1 | Closed | 05-21 | PRE INSP
555 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-21 | PRE INSP
556 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.2 | 0.2 | Closed | 05-21 | INSPECTION
557 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.2 | 0.2 | Closed | 05-21 | INSPECTION
558 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.1 | 0.1 | Closed | 05-21 | INSPECTION
560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | 1 | 1.1 | 9.3 | 17.1 | Closed | 05-21 | INSPECTION
561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | 1 | 0.4 | 8 | 49.7 | Closed | 05-23 | INSPECTION
562 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | 1 | 1.3 | 0.8 | 0.8 | Closed | 05-23 | INSPECTION
563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | 1 | 0.9 | 46.8 | 5.2 | Closed | 05-23 | INSPECTION
564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | 1 | 0.4 | 1.8 | 1 | Closed | 05-24 | INSPECTION
565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | 1 | 0.4 | 2 | 1.1 | Closed | 05-24 | INSPECTION
566 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
567 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | 1 | 0.9 | 12 | 50.6 | Closed | 05-24 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | 1 | 0.7 | 0.8 | 0.6 | Closed | 05-24 | INSPECTION
573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | 1 | 0.7 | 1.2 | 1 | Closed | 05-24 | INSPECTION
574 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
575 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
578 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | 1 | 0.4 | 0.5 | 0.5 | Closed | 05-27 | PRE INSP, PRE INSP
579 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | 1 | 0.2 | 0.2 | 0.2 | Closed | 05-28 | PRE INSP
580 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | 1 | 0.2 | 0.7 | 0.7 | Closed | 05-28 | PRE INSP
581 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | 1 | 0.4 | 0.1 | 0.1 | Closed | 05-28 | PRE INSP
601 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-21 | PRE INSP
602 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | 1 | 0.2 | 1 | 1 | Closed | 05-28 | PRE INSP, PRE INSP
622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 1 | 0.7 | 13.5 | 2.8 | Closed | 53-21 | PRE INSP, PRE INSP, PRE INSP
782 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | N | 9 | 1.7 | 12.4 | Closed | 20 | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP
802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 1 | 0 | 4.5 | 2.9 | Closed | 24-24 | OPS/LK
824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 1 | 4 | 8 | 4 | Closed | 05-25
843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 1 | 10 | 10 | 5 | Closed | 05-27
848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 1 | 3 | 3 | 1.5 | Closed | 05-25
860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 1 | 8 | 8 | 3.5 | Closed | 05-28
862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 1 | 8 | 8 | 2 | Closed | 05-28
870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 1 | 6 | 6 | 6 | Closed | 05-28
871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 1 | 6.5 | 6.5 | 6.5 | Closed | 05-28
874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 1 | 12 | 12 | 6 | Closed | 25-21
875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 1 | 120 | 120.5 | 53.3 | Closed | 25-21
878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 1 | 5 | 5 | 5 | Closed | 25-21
879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 1 | 3 | 3 | 1.5 | Closed | 25-21
880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 1 | 3 | 3 | 3 | Closed | 25-21
883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 1 | 3 | 4 | 4.1 | Closed | 05-25
884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 1 | 5 | 5 | 2 | Closed | 05-25
885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 1 | 2 | 2 | 2 | Closed | 25-21
896 | 32979723 | APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION | 1 | 4 | 13 | 8 | Closed | 36-12
898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 1 | 24 | 24 | 8 | Closed | 25-21
925 | 32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | RON | 2 | 4 | 4.4 | Closed | 38
927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 1 | 1 | 1 | 1 | Closed | 25-21
940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 1 | 3.5 | 3 | 1.5 | Closed | 25-21
952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 1 | 4 | 5 | 2 | Closed | 05-25
961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 1 | 5 | 5 | 3 | Closed | 25-21
965 | 32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 1 |  | 4.5 | 2.4 | Closed | 35-12
967 | 32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 1 |  | 6 | 2.2 | Closed | 25-30
975 | 32982253 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 66.5 | 18.9 | Closed | 27-84
976 | 32982260 | R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 68 | 19.5 | Closed | 27-84
977 | 32982263 | BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 15.9 | 9.3 | Closed | 53-41
980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 1 | 8 | 8 | 4 | Closed | 05-21
998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 1 | 4 | 4 | 2 | Closed | 05-25
1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 1 | 2 | 2 | 1 | Closed | 25-10
1026 | 32985022 | --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB | 1 | 4 | 3 | 1.5 | Closed | 53-79
1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 1 | 2 | 2 | 2 | Closed | 05-24
1057 | 32985575 | RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW | 1 |  | 19.1 | 7.5 | Closed | 05-23
1058 | 32985619 | ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 2.6 | 1.3 | Closed | 26-21 | OPEN-UP
1059 | 32985582 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 4 | 2.2 | Closed | 57-41 | OPEN-UP
1060 | 32985655 | BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 0.2 | 0.2 | Closed | 24-92
1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 28.8 | 16.3 | Closed | 53-41 | OPEN-UP
1090 | 32987776 | --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. | 1 |  | 29 | 23.5 | Closed | 11-21