## HZ-ASD Tracker
POOL CABIN ✈ HZ-ASD ✈ C2+6Y CHECK WORK PACKAGE TRACKER |  |  |  | DAY 14/38 |  |  | ✅ 105 / 409 Closed (26%)
LAST UPDATE: 30-Jul · 6 row(s) updated — filter column L for details | [6 empty] | AOG/Critical: 23
WO / Event Number | Task Description | Seq. No. | Category | Status | Priority | Specialty | PARTS REQ. | Remarks | Time EVAL? | AREA | Updated | Closed Date | Est MH | ATA | Booked MH | Actual Dur (h)
200145-01-1 | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING | 18 | ACFT GENERAL T/C | Open | Normal | JOINT |  | CABIN ACCESS |  | AFT
200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 24 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | FWD | 2026-07-22 | 2026-07-22 | 7.2 | 24-92 | 13.5 | 22.2
200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 25 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP / REMINE CLOSE UP | N/A | AFT |  |  | 3 | 24-92 | 11 | 209.5
200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 26 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP / REMINE CLOSE UP | N/A | AFT |  |  | 2.1 | 24-92 | 9.5 | 208.9
25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 32 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509031 CLOSED | N/A | FWD | 2026-07-19 |  | 2 | 25-11 | 6.5 | 16.7
25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 33 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509039 CLOSED | N/A | FWD | 2026-07-19 |  | 2 | 25-11
25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 34 | F/A SEAT | Open | AOG | CAB | Requested | P/S 4509037 (SOME PARTS S/D) | N/A | JOINT | 2026-07-19 |  | 4 | 25-22
253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 35 | GALLEY | Open | Normal | JOINT |  | CAB + INSP / REMINE CLOSE UP | N/A | JOINT |  |  | 0.5 | 25-30 | 44 | 265.1
254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 36 | LAVATORY | Open | Normal | JOINT |  | CAB + INSP / REMINE CLOSE UP | N/A | JOINT |  |  | 0.2 | 25-40 | 15 | 252.6
256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 37 | FLIGHT DECK | Closed | Normal | JOINT |  | C/W | N/A | FWD | 2026-07-20 | 2026-07-20 | 0.4 | 25-61 | 12 | 2.8
262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 38 | LAVATORY | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-20 | 2026-07-20 | 0.2 | 26-25 | 0.8 | 0.8
323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 44 | ACFT GENERAL T/C | Open | Normal |  | Requested | CABIN + COCKPIT ACCESS | N/A | FWD |  |  | 2.2 | 32-33
323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 45 | ACFT GENERAL T/C | Open | Normal |  |  | CABIN + COCKPIT ACCESS | N/A | FWD |  |  | 0.5 | 32-33 | 2 | 191.5
531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 51 | PAX DOORS | Closed | Normal |  |  | C/W | N/A | FWD | 2026-07-30 | 2026-07-29 | 0.7 | 53-11 | 2.5 | 74.5
531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 52 | ACFT GENERAL T/C | Open | Normal |  | Requested | A&P / REMINE CLOSE UP | N/A | FWD |  |  | 2 | 53-11 | 2.8 | 117.6
531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 53 | ACFT GENERAL T/C | Open | Normal |  | Requested | FWD DOORS GIRT FITTINGS / TO DO | N/A | FWD |  |  | 3.5 | 53-11
531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 55 | ACFT GENERAL T/C | Open | Normal | INSP | Requested | FWD GALLEY + LAV A + ALL B/C SEATS + COCKPIT DOOR + FLOOR PANELS REMOVAL | N/A | FWD | 2026-07-19 |  | 4.9 | 53-11
531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 56 | ACFT GENERAL T/C | Open | Normal | INSP | Requested | FWD GALLEY + LAV A + ALL B/C SEATS + COCKPIT DOOR + FLOOR PANELS REMOVAL | N/A | FWD | 2026-07-19 |  | 9.7 | 53-11 | 72 | 72.5
531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 57 | ACFT GENERAL T/C | Open | Normal | INSP | Requested | G2 GALLEY + ALL SEATS REMOVAL | N/A | FWD | 2026-07-19 |  | 39.8 | 53-11 | 10.5 | 166.6
534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 60 | PAX DOORS | Open | Normal | JOINT | Requested | C/W | N/A | AFT |  |  | 0.1 | 53-41 | 2.2 | 97.1
534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 61 | PAX DOORS | Open | Normal | JOINT | Requested | CAB + INSP / REMINE CLOSE UP | N/A | AFT |  |  | 3 | 53-41 | 24 | 48.5
534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 62 | ACFT GENERAL T/C | Open | Normal | CAB | Requested | REMOVE ALL GALLEYS AND LAVS + SOME ROWS OF G/C SEATS / REMINE CLOSE UP | N/A | JOINT |  |  | 50 | 53-41 | 104.5 | 192.6
534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 66 | ACFT GENERAL T/C | Open | Normal | CAB | Requested | AFT AREA / REMINE CLOSE UP | N/A | AFT |  |  | 4 | 53-41 | 22 | 64.3
562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 79 | GENERAL CABIN | Open | Normal | JOINT | Requested | CAB + INSP / INTERIOR C/W REMINE EXTERIR | N/A | JOINT | 2026-07-29 |  | 5.2 | 56-21 | 80 | 97.1
ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | 109 | ACFT GENERAL T/C | Open | Normal | CAB | Requested | CAB + INSP / FR 36 TO FR 46 / REMINE CLOSE UP | N/A | JOINT |  |  | 7 | 05-21 | 85.5 | 72.6
ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | 115 | ACFT GENERAL T/C | Closed | Normal | INSP |  | C/W | N/A | AFT | 2026-07-23 | 2026-07-23 | 77 | 05-21 | 2.5 | 47.7
ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | 122 | FLIGHT DECK | Closed | Normal | INSP |  | C/W | N/A | FWD | 2026-07-23 | 2026-07-23 | 0.4 | 05-22 | 21 | 30.4
31871161 | A_N (A_N09)/A_N-CHECK | 158 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 0 | 20-00
ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | 157 | PAX DOORS | Open | Normal | AP |  | AP | N/A | JOINT |  |  | 1 | 05-28 | 6 | 213.6
05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 159 | GENERAL CABIN | Open | Normal | CAB |  | ALL INFORMATIONS FILLED TO BE CLOSE BEFORE ACFT RELASE | N/A | JOINT |  |  | 2.2 | 05 | 8 | 232.6
11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 160 | GENERAL CABIN | Open | Normal | PAINT |  | PAINT | N/A | JOINT |  |  | 1 | 11-11
212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 162 | LAVATORY | Closed | Normal | CAB | Requested | C/W | N/A | JOINT | 2026-07-20 | 2026-07-20 | 0.4 | 21-23 | 2 | 1
25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 168 | FLIGHT DECK | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | FWD |  |  | 4.3 | 25-10 | 38 | 217.6
25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 169 | GENERAL CABIN | Open | Normal | JOINT | Requested | CAB + INSP / CHECK C/W | N/A | JOINT |  |  | 5.8 | 25-10 | 26.5 | 236.9
25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 170 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 2.3 | 25-10 | 7.5 | 213.7
25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 171 | PAX SEAT | Open | Normal | SEAT |  | STEP 8 (CAB POOL SPLTY) / TO DO AFTER SEAT INATALLAITON | N/A | JOINT |  |  | 1.5 | 25-10 | 6 | 213.9
25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 172 | F/A SEAT | Open | Normal | CAB |  | C/W | N/A | JOINT |  |  | 2.75 | 25-10 | 18 | 229.7
25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 173 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509045 CLOSED | N/A | JOINT | 2026-07-19 |  | 4 | 25-26
25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 174 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509318 CLOSED | N/A | JOINT | 2026-07-19 |  | 4 | 25-28
25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 175 | GALLEY | Open | Normal | AV |  | AV | N/A | JOINT |  |  | 2 | 25-30
25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 176 | GALLEY | Open | Normal | CAB |  | CAB ONLY / TO DO | N/A | JOINT |  |  | 0.5 | 25-30
25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 177 | GALLEY | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | JOINT |  |  | 6.9 | 25-10 | 28.5 | 265.6
25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 178 | LAVATORY | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | JOINT |  |  | 7.4 | 25-10 | 3.5 | 206.4
25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 179 | F/A SEAT | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-20 | 2026-07-20 | 2 | 25-60 | 1 | 1
25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 180 | GENERAL CABIN | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-21 | 2026-07-21 | 2 | 25-65 | 1 | 1
25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 181 | GENERAL CABIN | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-21 | 2026-07-21 | 1 | 25-65 | 1 | 1
253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 182 | GALLEY | Open | Normal | CAB | Requested | CAB / TO DO | N/A | JOINT |  |  | 0.3 | 20-00
253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 183 | GALLEY | Open | Normal | CAB | Requested | CAB / TO DO | N/A | JOINT |  |  | 0.4 | 25-34
256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 186 | PAX DOORS | Closed | Normal | CAB |  | C/W | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.9 | 25-62 | 10 | 5.3
261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 189 | LAVATORY | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-28 | 2026-07-28 | 0.5 | 24 | 6 | 1
31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 207 | FLIGHT DECK | Open | Normal | AV | Requested | AV | N/A | FWD |  |  | 2 | 31-63
353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 215 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | JOINT | 2026-07-21 | 2026-07-21 | 0.4 | 35-32 | 6.5 | 5.2
353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 216 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | JOINT | 2026-07-19 | 2026-07-19 | 0.4 | 35-30 | 2.8 | 3.8
383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 219 | LAVATORY | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 0.2 | 38-32
525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 223 | FLIGHT DECK | Open | Normal | JOINT |  | C/W | N/A | FWD |  |  | 0.9 | 52-51 | 7.8 | 237.6
527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 224 | PAX DOORS | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 0.3 | 12-22 | 2 | 26.1
561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 227 | FLIGHT DECK | Closed | Normal | AP |  | AP + INSP (ACCESS) | N/A | FWD | 2026-07-26 | 2026-07-26 | 3.5 | 56-10 | 15 | 134.1
05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 234 | ACFT GENERAL T/C | Open | Normal | INSP |  | SVTI | N/A | JOINT |  |  | 1 | 05-00
08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 235 | ACFT GENERAL T/C | Open | Normal | AP |  |  | N/A | JOINT |  |  | 65 | 08-10
212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 241 | FLIGHT DECK | Closed | Normal | AP |  | C/W | N/A | FWD | 2026-07-26 | 2026-07-26 | 0.4 | 21-21 | 1.5 | 5.7
23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 257 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 8 | 23-73 | 4 | 2
233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 258 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 0.9 | 23-33 | 6 | 2.1
235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 259 | FLIGHT DECK | Closed | Normal | AV |  | AV | N/A | FWD | 2026-07-23 | 2026-07-23 | 0.2 | 23-51 | 4 | 1
25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 272 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509325 / SEAT WILL BE REPLACED | N/A | FWD | 2026-07-19 |  | 0.5 | 25-11
25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 273 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509326 | N/A | FWD | 2026-07-19 |  | 1 | 25-11
25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 274 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509328 | N/A | FWD | 2026-07-19 |  | 4 | 25-11
25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 275 | FLIGHT DECK | Open | Normal | CAB | Requested | C/W | N/A | FWD | 2026-07-19 |  | 0.5 | 25-11
25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 276 | GENERAL CABIN | Open | Normal | CAB | Requested | P/S 4509334 | N/A | JOINT | 2026-07-19 |  | 48 | 25-28
25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 277 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509336 | N/A | FWD | 2026-07-19 |  | 6 | 25-28
25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 278 | FLIGHT DECK | Open | Normal | JOINT |  | CAB + INSP | N/A | FWD |  |  | 3.3 | 25 | 2 | 236.8
25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 279 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 11.7 | 25 | 3 | 237.2
25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 280 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 5.2 | 25 | 7 | 206.3
25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 281 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 3 | 25 | 9 | 182.2
25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 282 | PAX SEAT | Open | Normal | SEAT |  | STEP 6 (CAB POOL SPLTY) | N/A | JOINT |  |  | 1.8 | 25 | 14.5 | 220.3
25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 283 | GALLEY | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | JOINT |  |  | 2 | 25 | 11.5 | 209.2
25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 284 | LAVATORY | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | JOINT |  |  | 2 | 25 | 4.5 | 206.4
25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 285 | F/A SEAT | Open | Normal | CAB |  | CAB ONLY / CHECK C/W | N/A | JOINT |  |  | 3 | 25
25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 286 | PAX SEAT | Open | Normal | SEAT | Requested | SEAT SHOP | N/A | JOINT |  |  | 0.5 | 25
25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 287 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 0.5 | 25 | 152 | 75.2
252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 288 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 38 | 25-21 | 253.5 | 241.6
252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 289 | PAX SEAT | Open | Normal | CAB |  | REMAINING CLOSE UP | N/A | JOINT |  |  | 2 | 25-21 | 19.5 | 210
2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 290 | PAX SEAT | Open | Normal | SEAT |  | SEAT SHOP | N/A | JOINT |  |  | 3 | 25-21 | 2 | 215.5
2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 291 | PAX SEAT | Open | Normal | SEAT | Requested | SEAT SHOP | N/A | JOINT |  |  | 7 | 25-21 | 6 | 216.5
252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 292 | F/A SEAT | Open | Normal | JOINT |  | CAB + INSP / WITH INSTALLTION | N/A | JOINT |  |  | 0.7 | 25-22
252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 293 | F/A SEAT | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-20 | 2026-07-20 | 0 | 25-22 | 0.8 | 0.8
254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 294 | LAVATORY | Closed | Normal | INSP |  | C/W | N/A | JOINT | 2026-07-20 | 2026-07-20 | 3.3 | 25-40 | 0.8 | 0.8
256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 297 | GENERAL CABIN | Closed | Normal | AV |  | C/W | N/A | JOINT | 2026-07-22 | 2026-07-22 | 0.2 | 25-65 | 2 | 1
256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 299 | GENERAL CABIN | Open | Normal | JOINT |  | C/W REMAINING CLOSE UP | N/A | JOINT | 2026-07-19 |  | 0.5 | 25-11 | 46.5 | 265.1
262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 312 | LAVATORY | Closed | Normal | INSP |  | INSP | N/A | JOINT | 2026-07-20 | 2026-07-20 | 0.2 | 26-25 | 0.8 | 0.8
335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 413 | GENERAL CABIN | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-22 | 2026-07-22 | 0.2 | 33-51 | 9 | 3.1
351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 425 | FLIGHT DECK | Open | Normal | CAB |  |  | N/A | FWD |  |  | 0.2 | 35-12
351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 426 | FLIGHT DECK | Closed | Normal | JOINT |  |  | N/A | FWD | 2026-07-20 | 2026-07-20 | 0.6 | 35-12 | 10 | 4.4
352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 427 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 2 | 35-23 | 45 | 238.2
352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 428 | GENERAL CABIN | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 2.4 | 35-21 | 48.5 | 241.6
353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 429 | FLIGHT DECK | Closed | Normal | JOINT |  | C/W | N/A | FWD | 2026-07-20 | 2026-07-20 | 2.2 | 25-64 | 3.5 | 1.6
353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 430 | GENERAL CABIN | Closed | Normal | JOINT |  | C/W | N/A | JOINT | 2026-07-19 | 2026-07-19 | 0.4 | 35-30 | 3.5 | 3.3
383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 439 | LAVATORY | Open | Normal | AP | Requested | OPEN UP | N/A | JOINT |  |  | 10 | 38-31
384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 442 | ACFT GENERAL T/C | Open | Normal | AP | Requested | AP | N/A | JOINT |  |  | 0.7 | 38-42
521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 446 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | FWD |  |  | 1 | 52-10 | 22.5 | 43.1
521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 447 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | JOINT |  |  | 0.5 | 52-10 | 9 | 45.6
521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 448 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | FWD |  |  | 1 | 52-10 | 20.5 | 43.6
521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 449 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | AFT |  |  | 5 | 52-10
521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 450 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | FWD |  |  | 1 | 52-10 | 8.5 | 20.1
521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 451 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | FWD |  |  | 1 | 52-10 | 4.5 | 12.6
521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 452 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | AFT |  |  | 1 | 52-10 | 5.5 | 20.1
521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 453 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | AFT |  |  | 1 | 52-10 | 4.5 | 20.1
521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 454 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | AFT |  |  | 5 | 52-10
521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 455 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.9 | 52-10 | 7.5 | 2.5
521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 456 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 1.8 | 52-10 | 8.5 | 3.4
521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 457 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | FWD |  |  | 0.4 | 52-10 | 7.5 | 93.4
521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 458 | PAX DOORS | Open | Normal | CAB |  | CAB + INSP | N/A | AFT |  |  | 0.4 | 52-10 | 11.5 | 93.3
521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 459 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.9 | 52-10 | 11.5 | 3.9
521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 460 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.9 | 52-10 | 7.5 | 4.6
521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 461 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.4 | 52-10 | 8 | 5.4
521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 462 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | JOINT |  |  | 1.5 | 52-10
521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 463 | PAX DOORS | Closed | Normal | CAB | Requested | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.4 | 52-10 | 16 | 47
521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 464 | PAX DOORS | Closed | Normal | CAB |  | CAB + INSP | N/A | JOINT | 2026-07-26 | 2026-07-26 | 3.7 | 52-10 | 12.5 | 47.5
521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 465 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | JOINT |  |  | 0.9 | 12-22
522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 466 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 467 | PAX DOORS | Open | Normal | CAB | Requested | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 468 | PAX DOORS | Open | Normal | AP | Requested | AP + INSP | N/A | FWD |  |  | 3.5 | 52-21
522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 469 | PAX DOORS | Open | Normal | JOINT |  | CAB + INSP | N/A | JOINT |  |  | 3.5 | 52-21
525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 473 | FLIGHT DECK | Closed | Normal | JOINT |  | CAB + INSP | N/A | FWD | 2026-07-21 | 2026-07-21 | 0.6 | 52-51 | 7.8 | 3.9
525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 474 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-22 | 2026-07-22 | 0.3 | 52-51 | 4.8 | 3
525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 475 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-26 | 2026-07-26 | 0.4 | 52-51 | 4 | 2
525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 476 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-22 | 2026-07-22 | 0.1 | 52-51 | 4.5 | 3.1
525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 477 | FLIGHT DECK | Closed | Normal | AV |  | AV + INSP | N/A | FWD | 2026-07-26 | 2026-07-26 | 0.1 | 52-51 | 4 | 2
527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 478 | PAX DOORS | Closed | Normal | AV |  | AV | N/A | JOINT | 2026-07-26 | 2026-07-26 | 0.1 | 52-71 | 6 | 3
527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 479 | PAX DOORS | Open | Normal | AV |  | AV + INSP | N/A | JOINT |  |  | 0.2 | 52-73
527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 480 | PAX DOORS | Closed | Normal | AV |  | AV + INSP | N/A | JOINT | 2026-07-23 | 2026-07-23 | 0.2 | 52-73 | 10 | 4.2
531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 481 | PAX DOORS | Open | Normal | JOINT | Requested | C/W | N/A | JOINT |  |  | 0.2 | 53-11 | 2 | 97.1
531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 482 | FLIGHT DECK | Closed | Normal | AP |  | AP + INSP | N/A | FWD | 2026-07-26 | 2026-07-26 | 0.4 | 53-11 | 2.2 | 7.2
531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 483 | FLIGHT DECK | Open | Normal | AP | Requested | AP + INSP | N/A | FWD |  |  | 2.3 | 53-11 | 11 | 25.5
531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 484 | FLIGHT DECK | Open | Normal | CAB | Requested | CAB + INSP | N/A | FWD |  |  | 2.3 | 53-11
561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 509 | FLIGHT DECK | Open | Normal | CAB |  | P/S 4509339 | N/A | FWD |  |  | 0.4 | 12-22
38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 591 | ACFT GENERAL T/C | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 10 | 38-10
521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 594 | PAX DOORS | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 0.9 | 12-22
521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 595 | PAX DOORS | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 0.9 | 12-22
ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | 602 | PAX DOORS | Closed | Normal | CAB |  | INSP | N/A | AFT | 2026-07-20 | 2026-07-20 | 0.2 | 05-28 | 1 | 1
05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 603 | ACFT GENERAL T/C | Open | Normal | PLNG |  | PLNG | N/A | JOINT |  |  | 1 | 05-11
521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 609 | PAX DOORS | Closed | Normal | CAB |  | CAB | N/A | JOINT | 2026-07-27 | 2026-07-27 | 2.5 | 52-10 | 2.5 | 0.5
521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 610 | PAX DOORS | Open | Normal | JOINT | Requested | CAB + INSP | N/A | FWD |  |  | 1.8 | 25-62 | 34 | 89.6
521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 611 | PAX DOORS | Open | Normal | JOINT | Requested | CAB + INSP | N/A | AFT |  |  | 1.9 | 52-13 | 16 | 69
522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 612 | PAX DOORS | Open | Normal | AP | Requested | AP + INSP | N/A | JOINT |  |  | 10.1 | 52-21
531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 618 | PAX DOORS | Open | Normal | JOINT | Requested | C/W | N/A | FWD |  |  | 3 | 53-11 | 9.5 | 63
533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 626 | ACFT GENERAL T/C | Open | Normal | AP |  | AP + INSP | N/A | FWD |  |  | 2.1 | 53 | 6.2 | 21.3
534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 630 | ACFT GENERAL T/C | Open | Normal |  | Requested | ACCESS (AFT GALLEY/LAVS - AFT DOOR LININGS - BLANKETS) | N/A | AFT |  |  | 16.4 | 53-41
534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 631 | ACFT GENERAL T/C | Open | Normal |  |  | ACCESS (AFT GALLEY/LAVS - AFT DOOR LININGS - BLANKETS) | N/A | AFT |  |  | 0.7 | 57-21
534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 632 | ACFT GENERAL T/C | Open | Normal | JOINT | Requested | CAB + INSP | N/A | AFT |  |  | 1.6 | 53-41 | 9 | 63.1
534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 635 | ACFT GENERAL T/C | Open | Normal |  | Requested | ACCESS (AFT AREA) | N/A | AFT |  |  | 6.2 | 53-41
534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 636 | ACFT GENERAL T/C | Open | Normal |  | Requested | ACCESS (AFT AREA - GALLEY/LAVS) | N/A | AFT |  |  | 3.5 | 53-51
29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 706 | LAVATORY | Closed | Normal | INSP |  | INSP | N/A | JOINT | 2026-07-22 | 2026-07-22 | 1.5 | 25 | 5 | 3.6
30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | 711 | FLIGHT DECK | Open | Normal | CAB | Requested | P/S 4509340 | N/A | FWD | 2026-07-19 |  | 0.5 | 25
29155624 | EOD-320-31-00010-R00/FDIMU - TELEDYNE DMU SOFTWARE CAPABLE FOMAX | 720 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | JOINT |  |  | 2.5 | 31 | 18 | 43.2
29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | 721 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | JOINT |  |  | 2.5 | 31
29155864 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | 722 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | JOINT |  |  | 2 | 31
30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 727 | ACFT GENERAL T/C | Open | Normal | AV | Requested | REVIEW FOR ACCESS | N/A | JOINT |  |  | 471 | 44 | 29.1 | 51.7
31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | 728 | ACFT GENERAL T/C | Open | Normal | AV | Requested | REVIEW FOR ACCESS | N/A | JOINT |  |  | 170 | 44
29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | 729 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX (ACCESS COCKPIT) | N/A | JOINT |  |  | 23.2 | 46 | 2 | 89.2
29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | 730 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX (B/C BLANKETS REMOVAL) | N/A | JOINT |  |  | 18 | 46 | 25.7 | 90.6
29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | 731 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | FWD |  |  | 18.5 | 46 | 18 | 70.1
29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | 732 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | JOINT |  |  | 2.5 | 46
29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | 733 | ACFT GENERAL T/C | Open | Normal | AV | Requested | FOMAX | N/A | JOINT |  |  | 4 | 46
29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | 734 | ACFT GENERAL T/C | Open | Normal | AV |  | FOMAX | N/A | JOINT |  |  | 2.5 | 46
18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 740 | ACFT GENERAL T/C | Open | Normal |  | Requested | CABIN ACCESS | N/A |  |  |  | 62 | 53 | 2.2 | 2.7
29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 741 | ACFT GENERAL T/C | Open | Normal |  | Requested | AFT AREA / OPEN UP | N/A | AFT |  |  | 33.8 | 53 | 18.1 | 48.6
31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | 743 | ACFT GENERAL T/C | Open | Normal |  | Requested | SEATS REMOVAL | N/A | AFT |  |  | 42.2 | 53
31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 745 | PAX SEAT | Open | Normal | JOINT | Requested | CAB + INSP | N/A | JOINT |  |  | 1.7 | 25
31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | 746 | PAX SEAT | Open | Normal | JOINT | Requested | CAB + INSP | N/A | JOINT |  |  | 1.7 | 25
30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | 751 | ACFT GENERAL T/C | Open | Normal |  | Requested | ACCESS (FLOOR PANLES/SEATS) | N/A |  |  |  | 22.5 | 32-33 | 16.3 | 191.4
31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | 763 | FLIGHT DECK | Open | Normal | CAB | Requested | CAB | N/A | FWD |  |  | 0 | 20-00
80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | 772 | TEDLAR/SIDEWALL | Open | Normal | CAB | Requested | LOGBOOK CABIN | N/A | AFT |  |  | 0 | 25 | 16.2 | 6743.5
81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | 773 | GALLEY | Open | Normal | CAB | Requested | LOGBOOK CABIN | N/A | AFT |  |  | 0 | 25 | 15 | 2236.1
STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | 782 | ACFT GENERAL T/C | Closed | Normal |  |  |  | N/A | JOINT | 2026-07-20 | 2026-07-20 | 9 | 20 | 1.7 | 12.4
STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | 786 | ACFT GENERAL T/C | Open | Normal |  | Requested |  | N/A | JOINT |  |  | 13 | 20
STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | 787 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 22 | 20
STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | 788 | PAX DOORS | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 2 | 20
STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | 789 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 3 | 05-00
STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | 790 | ACFT GENERAL T/C | Open | Normal | CAB |  | CAB | N/A | FWD |  |  | 2 | 05-00
STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | 798 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 0.5 | 05-11
STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | 799 | ACFT GENERAL T/C | Open | Normal |  |  |  | N/A | JOINT |  |  | 7 | 05-00
381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 803 | ACFT GENERAL T/C | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 16 | 38-10
32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 804 | GENERAL CABIN | Open | Normal | CAB | Requested | CAB | N/A | JOINT |  |  | 10 | 25-00 | 97 | 25.8
CCC-32S | CCC-32S (05) / A32S CABIN CRITICAL CHECK | 810 | GENERAL CABIN | Open | Normal | CAB |  | CAB | N/A | JOINT |  |  | 3.2 | 25-00
32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 874 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-21 | 2026-07-21 | 12 |  | 12 | 6
32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 875 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-21 | 2026-07-21 | 120 |  | 120.5 | 53.3
32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 876 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 2
32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 877 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-26 | 2026-07-26 | 22 |  | 22 | 106.1
32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 878 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 5 |  | 5 | 5
32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 879 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 3 |  | 3 | 1.5
32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 880 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 3 |  | 3 | 3
32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 881 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-26 | 2026-07-26 | 13 |  | 13 | 105.7
32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 882 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-22 | 2026-07-22 | 3 |  | 3 | 3
32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 885 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 2 |  | 2 | 2
32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 892 | GENERAL CABIN | Closed | Normal | AV | Requested |  |  | AFT | 2026-07-26 | 2026-07-26 |  |  | 12.5 | 114.1
32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 893 | GENERAL CABIN | Open | Normal | CAB |  |  |  | AFT |  |  | 1
32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 894 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD
32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 897 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-26 | 2026-07-26 | 24 |  | 24 | 128.6
32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 898 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 24 |  | 24 | 8
32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 899 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-26 | 2026-07-26 | 47 |  | 47 | 56.1
32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 900 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 6.5 |  | 6.5 | 169.3
81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | 905 | GENERAL CABIN | Open | Normal | AV | Requested |  |  | N/A |  |  |  |  | 3.5 | 645.2
28611923 | S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION | 918 | GALLEY | Open | Normal | CAB |  |  |  | FWD |  |  | 1.5 |  | 0.4 | 69.6
32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | 925 | GENERAL CABIN | Closed | Normal | CAB |  |  |  | JOINT | 2026-07-19 | 2026-07-19 | 2 |  | 4 | 4.4
32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 926 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 24
32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 927 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 1 |  | 1 | 1
32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 933 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-26 | 2026-07-26 | 6.5 |  | 6.5 | 59.3
32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 940 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 3.5 |  | 3 | 1.5
32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 942 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-26 | 2026-07-26 | 29 |  | 29 | 128.6
44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 943 | GENERAL CABIN | Open | Normal | AV |  |  |  | N/A |  |  | 1.5
32917899 | ISC/IN SERVCE CHECK_N | 944 | ACFT GENERAL T/C | Open | Normal | AP |  |  |  | N/A
32420054 | W_N/WEEKLY CHECK | 945 | ACFT GENERAL T/C | Open | Normal | AP |  |  |  | N/A
32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 946 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-22 | 2 |  | 2 | 2
ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | 947 | ACFT GENERAL T/C | Open | Normal | AP |  |  |  | N/A |  |  | 2.8
WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | 948 | ACFT GENERAL T/C | Open | Normal | AP |  |  |  | N/A |  |  | 5.9
32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 956 | GENERAL CABIN | Open | Normal | CAB |  |  |  | AFT |  |  |  |  | 14 | 18.4
32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 957 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 3
32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 958 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-22 | 2026-07-22 | 2 |  | 2 | 2
32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 959 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-22 | 2026-07-22 | 6 |  | 6 | 6
32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 960 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 6
32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 961 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-21 | 2026-07-21 | 5 |  | 5 | 3
32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 962 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-26 | 2026-07-26 | 2 |  | 2 | 44.3
32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 963 | PAX SEAT | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-22 | 2026-07-22 | 2 |  | 2 | 2
32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 964 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 15 |  | 7 | 56
32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 965 | FLIGHT DECK | Closed | Normal | CAB | Requested |  |  | FWD | 2026-07-20 | 2026-07-20 |  |  | 4.5 | 2.4
32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 966 | GALLEY | Open | Normal | S/M |  |  |  | AFT |  |  | 8 |  | 0.5 | 68.8
32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 967 | GENERAL CABIN | Closed | Normal | S/M |  |  |  | AFT | 2026-07-20 | 2026-07-20 |  |  | 6 | 2.2
32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 968 | GENERAL CABIN | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 7.5 | 229.6
32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 969 | GENERAL CABIN | Open | Normal | CAB |  |  |  | AFT
32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 970 | GENERAL CABIN | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 9.5 | 254.7
32982199 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 971 | F/A SEAT | Open | AOG | CAB |  |  |  | FWD |  |  |  |  | 1.5 | 252.4
32982200 | SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 972 | F/A SEAT | Open | AOG | CAB | Requested |  |  | AFT |  |  |  |  | 2 | 252.6
32982202 | R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 973 | F/A SEAT | Open | AOG | CAB |  |  |  | AFT
32982203 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 974 | F/A SEAT | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 4 | 252.9
32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 992 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | JOINT |  |  | 8.5
32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 999 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 10 |  | 9.5 | 191.4
32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 1003 | PAX SEAT | Open | Normal | SEAT |  |  |  | N/A |  |  | 12 |  | 11.5 | 219.9
32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 1004 | GALLEY | Open | Normal | CAB | Requested |  |  | AFT |  |  | 3
32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 1005 | GALLEY | Open | Normal | CAB | Requested |  |  | AFT |  |  | 2
32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 1006 | GALLEY | Open | Normal | CAB | Requested |  |  | AFT |  |  | 2
32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1007 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD |  |  | 2
32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 1008 | GENERAL CABIN | Open | Normal | AV | Requested |  |  | N/A
32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 1009 | LAVATORY | Closed | Normal | PAINT |  |  |  | FWD | 2026-07-23 | 2026-07-23 | 4 |  | 4.5 | 4.5
32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 1010 | GENERAL CABIN | Open | Normal | AV | Requested |  |  | N/A
32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1011 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD |  |  | 2
32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 1012 | GALLEY | Open | AOG | S/M | Requested |  |  | FWD |  |  |  |  | 14.3 | 81.3
32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 1013 | LAVATORY | Closed | Normal | PAINT | Requested |  |  | FWD | 2026-07-26 | 2026-07-26 | 4 |  | 4 | 4
32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 1014 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | AFT |  |  | 6 |  | 6.5 | 217.6
32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 1015 | LAVATORY | Closed | Normal | PAINT |  |  |  | FWD | 2026-07-21 | 2026-07-21 | 2 |  | 2 | 1
32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 1017 | GALLEY | Closed | Normal | PAINT | Requested |  |  | FWD | 2026-07-28 | 2026-07-28 | 3 |  | 4 | 4
32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 1027 | GALLEY | Open | Normal | CAB |  |  |  | FWD |  |  | 2
32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1030 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD |  |  | 2
32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1031 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD |  |  | 2
32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 1034 | FLIGHT DECK | Open | Normal | CAB |  |  |  | FWD |  |  | 2
32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 1035 | F/A SEAT | Open | Normal | CAB | Requested |  |  | FWD
32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT | 1036 | F/A SEAT | Open | AOG | CAB | Requested |  |  | FWD | 2026-07-30
32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1037 | F/A SEAT | Open | Normal | CAB | Requested |  |  | FWD
32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 1038 | F/A SEAT | Open | AOG | CAB | Requested |  |  | FWD
32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1039 | F/A SEAT | Closed | Normal | PAINT | Requested |  |  | FWD | 2026-07-26 | 2026-07-26 | 4 |  | 5.8 | 2.1
32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 1040 | F/A SEAT | Closed | Normal | PAINT |  |  |  | FWD | 2026-07-26 | 2026-07-26 | 4 |  | 6.2 | 2.5
32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 1041 | F/A SEAT | Open | Normal | CAB | Requested | C/W |  | AFT | 2026-07-30
32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 1042 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-22 | 2026-07-22 |  |  | 3.5 | 3.5
32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 1043 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-22 | 2026-07-22 |  |  | 3 | 3
32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 1044 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-26 | 2026-07-26 | 4 |  | 4 | 2
32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 1045 | F/A SEAT | Open | AOG | CAB | Requested |  |  | FWD
32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 1046 | F/A SEAT | Open | Normal | CAB | Requested |  |  | FWD
32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1047 | F/A SEAT | Closed | Normal | PAINT |  |  |  | FWD | 2026-07-22 | 2026-07-22 |  |  | 3.5 | 3.5
32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1048 | F/A SEAT | Open | Normal | CAB | Requested |  |  | FWD
32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 1049 | F/A SEAT | Open | AOG | CAB | Requested |  |  | FWD
32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 1050 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-22 | 2026-07-22 |  |  | 3.5 | 3.5
32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1051 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-22 | 2026-07-22 |  |  | 3 | 3
32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1052 | F/A SEAT | Open | Normal | CAB | Requested |  |  | AFT
32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 1053 | F/A SEAT | Open | Normal | CAB | Requested |  |  | AFT
32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1054 | F/A SEAT | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-22 | 2026-07-22 |  |  | 3 | 3
32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1055 | F/A SEAT | Open | Normal | CAB | Requested | C/W |  | AFT
32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 1061 | GENERAL CABIN | Open | AOG | CAB | Requested |  |  | JOINT | 2026-07-21
32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 1062 | GENERAL CABIN | Open | AOG | CAB | Requested |  |  | JOINT | 2026-07-21
32987066 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 1075 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 6
32987097 | CABIN FLOOR PANELS - CAB -CALLBACK CABIN FLOOR PANEL NO: 241EF, 241KF, 241LF, 241MF, 242FF, 242KF, 242LF AND 242MF REQUIRES REMOVAL FOR ACCESS. | 1077 | GENERAL CABIN | Open | ACCESS | CAB | Requested |  |  | JOINT |  |  |  |  | 29.5 | 185.8
94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | 1082 | PAX DOORS | Open | Normal | CAB | Requested |  |  | AFT |  |  |  |  | 35 | 348.3
32974165 | S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1086 | PAX DOORS | Open | Normal | CAB |  |  |  | AFT |  |  | 0.2
32974180 | S52-R10176/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1087 | PAX DOORS | Open | Normal | CAB | Requested |  |  | AFT |  |  | 0.5
32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 1093 | FLIGHT DECK | Closed | Normal | CAB | Requested |  |  | FWD | 2026-07-23 | 2026-07-23 |  |  | 3.5 | 5.6
32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 1098 | FLIGHT DECK | Closed | Normal | CAB |  |  |  | FWD | 2026-07-23 | 2026-07-23 |  |  | 4 | 6
32988329 | PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ | 1107 | GENERAL CABIN | Open | Normal | PAINT |  |  |  | AFT |  |  | 2
32988444 | PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA | 1108 | GENERAL CABIN | Open | Normal | CAB |  |  |  | AFT |  |  | 4
32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 1109 | PAX DOORS | Closed | Normal | CAB |  |  |  | AFT | 2026-07-30 | 2026-07-29 | 1.5 |  | 11 | 3
32988479 | CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ | 1110 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | AFT |  |  | 1.5
32988506 | CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED | 1111 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD
32988660 | PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS | 1112 | GENERAL CABIN | Open | Normal | PAINT |  | REQ REMOVAL |  | AFT |  |  | 4
32988687 | CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ | 1113 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | AFT |  |  | 2
32988706 | CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED | 1114 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | FWD |  |  | 1
32988779 | CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA | 1115 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | FWD |  |  | 1.5
32988786 | PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA | 1116 | GENERAL CABIN | Open | Normal | PAINT |  | REQ REMOVAL |  | FWD |  |  | 1
32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 1117 | GENERAL CABIN | Closed | Normal | CAB | Requested |  |  | AFT | 2026-07-26 | 2026-07-26 | 2 |  | 2 | 2
32988850 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY SEVERAL AIR FLAP SEAL DETORIATED | 1121 | GALLEY | Open | AOG | CAB | Requested |  |  | FWD
32989457 | CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. | 1126 | FLIGHT DECK | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 2.5 | 169.1
32989455 | CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP | 1127 | GALLEY | Open | Normal | CAB | Requested |  |  | AFT
32989472 | CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING | 1128 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD
32989475 | AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. | 1129 | PAX SEAT | Open | ACCESS | CAB |  |  |  | AFT |  |  | 8 |  | 4 | 190
32989476 | CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE | 1130 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD
32989482 | CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT | 1131 | GALLEY | Open | Normal | CAB |  |  |  | FWD
32989491 | CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. | 1132 | GALLEY | Open | Normal | CAB |  |  |  | FWD
32989492 | CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT | 1133 | GALLEY | Open | Normal | CAB |  |  |  | FWD
32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 1134 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD
32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1138 | PAX DOORS | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-28 | 2026-07-28 | 4 |  | 4 | 2
32989728 | CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING | 1141 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 1142 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989796 | CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY | 1143 | LAVATORY | Open | Normal | CAB |  |  |  | JOINT
32989797 | S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE | 1144 | GENERAL CABIN | Open | Normal | S/M |  |  |  | FWD |  |  |  |  | 4.3 | 81.6
32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 1145 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989825 | CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING | 1146 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD
32989853 | CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER | 1147 | GALLEY | Open | Normal | CAB |  |  |  | FWD |  |  | 1 |  | 2 | 170.1
32989854 | CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE | 1148 | GALLEY | Open | Normal | CAB |  |  |  | FWD
32989860 | CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING | 1149 | LAVATORY | Open | Normal | CAB |  |  |  | FWD
32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 1150 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1151 | PAX DOORS | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-28 | 2026-07-28 | 4 |  | 4 | 2
32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 1152 | LAVATORY | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-23 | 2026-07-23 |  |  | 2 | 2
32989943 | CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. | 1154 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989952 | CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. | 1156 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32989995 | RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. | 1171 | PAX SEAT | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 35.5 | 193.9
32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 1173 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-22 | 1.5 |  | 1.5 | 1.7
32990008 | CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS | 1174 | F/A SEAT | Open | ACCESS | CAB | Requested |  |  | AFT
32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO:33L,34JL,35K,37JL | 1175 | PAX SEAT | Open | Normal | AV |  |  |  | N/A
32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 1176 | PAX SEAT | Open | Normal | AV |  |  |  | N/A
32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 1177 | PAX SEAT | Open | Normal | AV |  |  |  | N/A
32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 1178 | PAX SEAT | Open | Normal | AV |  |  |  | N/A
32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 33B,C 32A,B,C AND 31A,B | 1179 | PAX SEAT | Open | Normal | AV |  |  |  | N/A
32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 1180 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-22 | 2026-07-22 |  |  | 1.5 | 1.8
32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 1181 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-23 | 2026-07-23 |  |  | 2.1 | 30.8
32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 1182 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-23 | 2026-07-23 |  |  | 2.1 | 29.7
32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 1183 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-23 | 2026-07-23 |  |  | 2.1 | 30.7
32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 1184 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-23 | 2026-07-23 |  |  | 2.1 | 30.7
32991206 | CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA | 1199 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | JOINT
32991276 | AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. | 1200 | PAX SEAT | Open | ACCESS | AV |  |  |  | AFT |  |  |  |  | 4 | 190.1
32991499 | CAB - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. | 1201 | LAVATORY | Open | Normal | CAB |  |  |  | FWD
32991511 | CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | 1202 | LAVATORY | Open | AOG | CAB | Requested |  |  | AFT
32991517 | PNT - RII - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 1203 | LAVATORY | Closed | Normal | PAINT | Requested |  |  | AFT | 2026-07-28 | 2026-07-28 | 5 |  | 5 | 86.1
32991527 | CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP | 1205 | LAVATORY | Open | Normal | CAB | Requested |  |  | AFT
32991534 | PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. | 1206 | LAVATORY | Open | Normal | PAINT |  |  |  | AFT |  |  | 3
32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 1208 | GENERAL CABIN | Closed | Normal | SEAT | Requested |  |  | N/A | 2026-07-22 | 2026-07-22 | 2 |  | 2 | 2
32991646 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. | 1211 | PAX SEAT | Open | Normal | AV |  |  |  | AFT |  |  |  |  | 4 | 189.8
32991651 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. | 1212 | PAX SEAT | Open | Normal | AV |  |  |  | AFT |  |  |  |  | 4 | 189.8
32992461 | MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. | 1218 | GALLEY | Open | Normal | S/M |  |  |  | FWD |  |  |  |  | 6.7 | 170.1
32992488 | CAB - CALL BACK - AFT GLLY AFT GALLEY REQUIRE REMOVAL FOR ACCESS | 1219 | GALLEY | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 45.5 | 187.2
32992489 | CAB - CALLBACK - FWD GALLEY FORWARD GALLEY - G1 AND G2 UNITS - REQUIRE REMOVAL FOR ACCESS. | 1220 | GALLEY | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 10 | 178.8
32992493 | CAB - CALLBACK - LAV A "LAVATORY A" REQUIRE REMOVAL FOR ACCESS. | 1221 | LAVATORY | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 32 | 52.8
32992492 | CAB - CALL BACK - LAV E LAVATORY "E" REQUIRE REMOVAL FOR ACCESS | 1222 | LAVATORY | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 32.5 | 161.7
32992500 | CAB - CALL BACK - LAV D LAVATORY "D" REQUIRE REMOVAL FOR ACCESS | 1223 | LAVATORY | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 3 | 157.9
32992517 | CAB - CALLBACK - STOWAGE C1 "STOWAGE C1" REQUIRE REMOVAL FOR ACCESS. | 1224 | GENERAL CABIN | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 9.5 | 169.1
32992509 | CAB - CALL BACK- SEAT SEATS FROM 39LH TO 44 LH AND 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS | 1225 | PAX SEAT | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 26 | 185.7
32992699 | CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING | 1227 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992702 | CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING | 1228 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992708 | CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING | 1229 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992709 | CAB - NO CALLBACK - LAV D LAV D THRESHOLD SCREW MISSING | 1230 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992712 | CAB - NO CALLBACK - LAV D LAV D TOILET SHROUD NOT SECURED | 1231 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992717 | CAB - NO CALLBACK - LAV D LAV D TOILET SEAT COVER BROKEN | 1232 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992719 | CAB - NO CALLBACK - LAV D LAV D DOOR LOCK LABLE FADED | 1233 | LAVATORY | Open | Normal | CAB |  |  |  | AFT
32992731 | CAB - RII - SEAT REMOVAL FOR ACCESS SEAT 5JL REQUIRE REMOVAL FOR ACCESS | 1234 | F/A SEAT | Open | Normal | CAB |  |  |  | FWD |  |  |  |  | 5 | 166.6
32992738 | CAB - NO CALL BACK - COFFEE MAKER AFT GALLEY COFFEE MAKER NO.1 STENCIL | 1235 | GALLEY | Open | Normal | CAB |  |  |  | AFT
32994020 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS | 1247 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-26 | 2026-07-26 | 24 |  | 24 | 8
32994039 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS | 1248 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-26 | 2026-07-26 | 12 |  | 12 | 61.4
32994149 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOODTRAYS ARE NOT ADJUSTABLE. | 1250 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 6.5 |  | 8 | 25.7
32994746 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 1254 | PAX SEAT | Open | Normal | SEAT | Requested |  |  | N/A |  |  | 2 |  | 1.5 | 87.1
32996054 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--CAB RH EMERGENCY EXIT HATCH DOOR WITH DOOR SEAL WORN AT LOWER EDGE | 1261 | PAX DOORS | Open | Normal | AP |  |  |  | N/A
32996073 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--SM RH FWD EMERGENCY EXIT HATCH DOOR CUTOUT WITH ABRAISION AT LOWER EDGE L=80 MM W=10 MM | 1262 | PAX DOORS | Open | Normal | AP |  |  |  | N/A |  |  | 3 |  | 0.2 | 43.6
32996610 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. | 1264 | PAX SEAT | Closed | Normal | SEAT |  |  |  | N/A | 2026-07-26 | 2026-07-26 | 6.5 |  | 6.5 | 6.7
32998113 | GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . | 1271 | GALLEY | Open | Normal | PAINT |  |  |  | N/A |  |  | 13 |  | 13 | 147.7
33011258 | SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) | 1302 | FLIGHT DECK | Open | Normal | PAINT |  |  |  | N/A |  |  | 24
33015570 | CAB - RII - COCKPIT CAPTAIN SEAT INERTIA REEL WITH FAST RETRACTION. | 1316 | FLIGHT DECK | Open | Normal | CAB |  |  |  | FWD
33017436 | CAB - NO CALL BACK - CURTAIN RAIL FWD GALLEY CURTAIN RAIL DEFORMED | 1317 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33017645 | CAB - NO CALL BACK - GALLEY G2 GALLEY COMP. 204 2EA TURN CATCH FADED | 1318 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33018932 | CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) | 1320 | GENERAL CABIN | Open | ACCESS | CAB |  |  |  | JOINT
33019264 | ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 | 1321 | PAX DOORS | Open | AOG | CAB | Requested |  |  | FWD |  |  |  |  | 6 | 70.3
33019327 | ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 | 1323 | PAX DOORS | Open | AOG | CAB | Requested |  |  | FWD |  |  |  |  | 6 | 70.2
33019384 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 | 1324 | PAX DOORS | Open | AOG | CAB | Requested |  |  | AFT |  |  |  |  | 9 | 70
33019437 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE L/H RQE REMOVEVAL FOR ACCESS PN / D30665-709 SN/ M14410 | 1325 | PAX DOORS | Open | ACCESS | CAB |  |  |  | AFT |  |  |  |  | 9 | 70
33020601 | FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . | 1332 | PAX DOORS | Open | Normal | PAINT |  |  |  | FWD |  |  | 24 |  | 2 | 36.8
33020680 | AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. | 1333 | PAX DOORS | Open | Normal | PAINT |  |  |  | AFT |  |  | 24 |  | 6 | 38.8
33020727 | CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - CAB - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . | 1334 | GENERAL CABIN | Open | Critical | S/M |  |  |  | AFT
33020729 | CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... | 1336 | GENERAL CABIN | Open | Critical | S/M |  |  |  | AFT |  |  |  |  | 7.8 | 42
33020731 | CAB - FLOOR STRUC - SEAT TRACK (Y-765) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-765) FWD OF FR41 WITH GOUGE AT UPPER FLANGE OF SEAT TRACK . DIM:- L=0.78 INCH. ,W=0.15 INCH.... | 1337 | GENERAL CABIN | Open | Critical | S/M |  |  |  | AFT |  |  |  |  | 4 | 40.5
33020734 | CAB - UNDER FLOOR - CAB - CALL BACK CABIN FROM FR 43 TO FR46 FOUND UNDER FLOOR STRUCTURE WITH MISSING CIC APPLICATION AND FROM FR36 TO FR46 FOUND UNDER FLOOR STRUCTURE , AIR CONDITIONING DUCT , LINES DUSTY AND WITH EXCESSIVE LINT ACCUMULATION. | 1338 | GENERAL CABIN | Open | Critical | CAB |  |  |  | AFT
33021722 | MACHINEST - NO CALL BACK - OVEN G1 GALLEY OVEN COMP. 104 SCREWS FROZEN | 1339 | GALLEY | Open | Normal | S/M |  |  |  | FWD
33021799 | EMERGENCY EXIT HATCH - CABIN - NO CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL | 1340 | GENERAL CABIN | Open | Normal | CAB |  |  |  | FWD |  |  |  |  | 4 | 39.6
33021843 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP 207. LATCH INOP | 1341 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33022670 | CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING | 1342 | GALLEY | Open | Normal | CAB | Requested |  |  | FWD
33022800 | CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. | 1343 | GALLEY | Open | AOG | CAB | Requested |  |  | FWD
33022853 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP | 1344 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33022868 | CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. | 1345 | FLIGHT DECK | Open | Normal | CAB |  |  |  | FWD
33022953 | CAB - NO CALLBACK - COCKPIT CAPTAIN FOOTREST RUBBER MAT WORN-OUT. | 1347 | FLIGHT DECK | Open | Normal | CAB |  |  |  | FWD
33022966 | CAB - NO CALLBACK - COCKPIT FLIGHT DECK CAPTAIN AND FIRST OFFICER PEDAL RUBBER MAT DIRTY. | 1348 | LAVATORY | Open | Normal | CAB |  |  |  | FWD
33022983 | CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. | 1349 | LAVATORY | Open | Normal | CAB |  |  |  | FWD
33023575 | FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 1352 | PAX DOORS | Closed | Normal | PAINT |  |  |  | FWD | 2026-07-30 | 2026-07-29 | 9 |  | 10 | 5.2
33023666 | CAB - RII - COCKPIT FLIGHT DECK FIRST OFFICER SEAT HARNESS DETERIORATED. | 1353 | FLIGHT DECK | Open | Normal | CAB | Requested |  |  | FWD
33023735 | FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 1354 | PAX DOORS | Closed | Normal | PAINT |  |  |  | AFT | 2026-07-30 | 2026-07-29 | 7 |  | 8 | 5.1
33023745 | CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. | 1355 | FLIGHT DECK | Open | Normal | CAB |  |  |  | FWD
33023803 | CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. | 1356 | FLIGHT DECK | Open | AOG | CAB | Requested |  |  | FWD
33023820 | CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED | 1357 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33023837 | CAB - NO CALL BACK - GALLEY FWD GALLEY (G1,G2) SIDE TURN CATCH FADED | 1358 | GALLEY | Open | Normal | CAB |  |  |  | FWD
33025667 | CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE | 1360 | PAX DOORS | Open | AOG | CAB | Requested |  |  | FWD
33028166 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY AIR CHILLER COVER PANEL GRILLE DEFORMED. | 1373 | GALLEY | Open | Normal | CAB |  | TQ 844238 F/UP |  | FWD
33028214 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT RH DOOR CUTOUT AT FR 68 AREA CORRODED AROUND GIRT BAR FITTING AND AT THE DRAIN HOLE | 1374 | PAX DOORS | Open | Normal | S/M |  |  |  | AFT |  |  |  |  | 0.3 | 1.9
33028291 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT LH DOOR CUTOUT AT FR 68 AND FR 66 AREA CORRODED AT GIRT BAR FITTINGS RIVETS 2EA | 1375 | PAX DOORS | Open | Normal | S/M |  |  |  | AFT |  |  |  |  | 3 | 26.6
33028466 | CAB - CALLBACK - G2 GALLEY G2 GALLEY REQUIRE REMOVAL FOR ACCESS. | 1377 | GALLEY | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 19.5 | 25.6
33028471 | CAB - RII - B/C SEATS ALL B/C SEATS REQUIRE REMOVAL FOR ACCESS. | 1378 | PAX SEAT | Open | ACCESS | CAB |  |  |  | FWD |  |  |  |  | 26 | 25.6
33028546 | CAB - NO CALLBACK - G/C AREA G/C AREA 9 EA SIDEWALLS WINDOW FRAME FOUND BROKEN. | 1379 | GENERAL CABIN | Open | Normal | CAB | Requested |  |  | FWD
33028549 | PNT - NO CALL BACK - GALLEY FWD (G1) GALLEY PAINT PEELED OFF BETWEEN COMP. 104 AND 105. | 1380 | GALLEY | Open | Normal | PAINT |  |  |  | FWD
33029239 | FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... | 1385 | GALLEY | Open | Normal | S/M |  |  |  | FWD
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal
|  |  |  | Open | Normal

## DASHBOARD
📊 HZ-ASD C2+6Y — WORK PACKAGE DASHBOARD |  |  |  |  | DAY 14/38 |  | START → | 2026-07-18
⚠️ WARNING — Completed 26% vs Time 35% · Days Left: 24 · Pace needed: 12.6/day vs avg 8.1/day | [6 empty] | END → | 2026-08-24
TOTAL WOs | CLOSED | OPEN | HPC ⏳ | 🚨 AOG/CRIT | MH DONE ⏱ | DONE
408 | 105 | 303 | 0 | 23 | 24.96% | 25.74%
TIMELINE — linked to LAYOVER sheet
🛬 O.O.S 17-Jul 🛫 B.I.S 24-Aug GROUND TIME 38 days · DAY 14/38
📍 Now: PHASE 3 — Mod & Rectification
⏳ Findings window closes in: 1 day(s)
📅 Next: FINDINGS CUTOFF — 01-Aug (in 1d)
🔒 Close-up in 19 day(s) · 20 ACCESS still open
BY SOURCE
| Closed | Total | % | Window ⏱ | Left
ROUTINE TASKS (WP) | 45 | 164 | 27.44% | 35.14% | 119 | 0.27439
ENG ORDERS (EOD/AD/EO) | 1 | 23 | 4.348% | 42.86% | 22 | 0.043478
FINDINGS (AMOS) | 59 | 221 | 26.7% | 42.42% | 162 | 0.26697
BY CATEGORY
| Closed | Total | % | Share | Left
GENERAL CABIN | 15 | 66 | 22.73% | 16.18% | 51 | 0.22727
GALLEY | 1 | 47 | 2.128% | 11.52% | 46 | 0.021277
LAVATORY | 11 | 40 | 27.5% | 9.804% | 29 | 0.275
PAX DOORS | 18 | 62 | 29.03% | 15.2% | 44 | 0.29032
F/A SEAT | 11 | 33 | 33.33% | 8.088% | 22 | 0.33333
PAX SEAT | 31 | 67 | 46.27% | 16.42% | 36 | 0.46269
FLIGHT DECK | 16 | 42 | 38.1% | 10.29% | 26 | 0.38095
TEDLAR/SIDEWALL | 0 | 1 | 0% | 0.2451% | 1
ACCESS | 0 | 20 | 0% | 4.902% | 20
ACFT GENERAL T/C | 2 | 50 | 4% | 12.25% | 48 | 0.04
SPECIALTY
| Closed | Total | % | Share | Left
CAB | 17 | 192 | 8.854% | 47.06% | 175 | 0.088542
SEAT | 32 | 53 | 60.38% | 12.99% | 21 | 0.60377
AV | 13 | 39 | 33.33% | 9.559% | 26 | 0.33333
WALL | 0 | 0 | 0% | 0% | 0
S/M | 1 | 12 | 8.333% | 2.941% | 11 | 0.083333
PAINT | 19 | 29 | 65.52% | 7.108% | 10 | 0.65517
JOINT | 8 | 31 | 25.81% | 7.598% | 23 | 0.25806
INSP | 10 | 14 | 71.43% | 3.431% | 4 | 0.71429
AP | 3 | 17 | 17.65% | 4.167% | 14 | 0.17647
DAILY CLOSURES — last 10 days |  | Σ Closed | Left | Cum % | 📉 S-curve: -75 behind 🔴
2026-07-22 | 22 | 53 | 355 | 12.99% | 0.1299 | 22
2026-07-23 | 12 | 65 | 343 | 15.93% | 0.15931 | 12
2026-07-24 | 0 | 65 | 343 | 15.93% | 0.15931
2026-07-25 | 0 | 65 | 343 | 15.93% | 0.15931
2026-07-26 | 30 | 95 | 313 | 23.28% | 0.23284 | 30
2026-07-27 | 1 | 96 | 312 | 23.53% | 0.23529 | 1
2026-07-28 | 5 | 101 | 307 | 24.75% | 0.24755 | 5
2026-07-29 | 4 | 105 | 303 | 25.74% | 0.25735 | 4
2026-07-30 | 0 | 105 | 303 | 25.74% | 0.25735
2026-07-31 | 0 | 105 | 303 | 25.74% | 0.25735
OPEN UP / ACCESS — removed items status |  |  |  | close-up in 19 d · 20 open
🔴 Still Open | 20 | 20 | 100%
🟡 I/W + HPC | 0 | 20 | 0%
🟢 Closed | 0 | 20 | 0%
🟢 Re-Installed | 0 | 0 | 0%
🔧 PARTS — Requested: 176 · Pending EVAL: 0
⚙️ Deferred: 0 · On Hold: 0 · N/A: 0 🚨 AOG open: 19 · Critical open: 4 · 🔁 Reopened: 0
🕐 WORKLOAD — Est 2,325 MH · Booked 3,018 · Closed 581 · MH 25% vs cards 26% · cabin 38% of acft pkg
WORKLOAD BY SPECIALTY (Est MH) |  | Est MH | Booked | Share %
CAB |  | 320.55 | 1087.1 | 13.79% |  | 0.13785
SEAT |  | 538.8 | 894.4 | 23.17% |  | 0.23171
AV |  | 733.6 | 185.1 | 31.55% |  | 0.31548
WALL |  | 0 | 0 | 0%
S/M |  | 8 | 46.9 | 0.344% |  | 0.0034403
PAINT |  | 150 | 104 | 6.451% |  | 0.064506
JOINT |  | 69 | 495.1 | 2.967% |  | 0.029673
INSP |  | 143 | 117.2 | 6.15% |  | 0.061496
AP |  | 110.7 | 42.1 | 4.761% |  | 0.047606
✈️ AIRCRAFT PACKAGE — ALL TRADES (whole-aircraft AMOS data · separate from cabin stats above)
TOTAL | CLOSED | OPEN | DONE | TIME | EST MH | BOOKED
1378 | 523 | 855 | 37.95% | 36.84% | 6196.7 | 8378
⚖️ CARDS — Cabin: 26% · Non-cabin: 43% · Whole pkg: 38% · cabin share of pkg closures: 20%
⏱ MH CABIN — Est 2,325h · Booked 3,018h (130% of est)
⏱ MH PKG — Est 6,197h · Booked 8,378h (135%) · cabin est share 38%
📍 BY AREA — cards & man-hours
Area | Cards | Closed | Done % | Est MH | Booked
FWD | 131 | 26 | 19.85% | 219.6 | 601.8
AFT | 98 | 17 | 17.35% | 306.8 | 515.1
JOINT | 117 | 30 | 25.64% | 1188.25 | 1428.5
🐌 STALLED CARDS — longest open, least booked (refreshed each closing cycle)
WO / Task | Description |  |  | Dur h | Booked | Idle h
80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE |  |  | 6744 | 16 | 6727
81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 L |  |  | 2236 | 15 | 2221
81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY |  |  | 645 | 4 | 642
94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SE |  |  | 348 | 35 | 313
32982199 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT |  |  | 252 | 2 | 251
32982200 | SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS |  |  | 253 | 2 | 251
32982203 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT |  |  | 253 | 4 | 249
32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS |  |  | 255 | 10 | 245

## AOG
AOG / MATERIAL — CABIN · HZ-ASD C2+6Y
WO | Seq | Description | Part No. | Part Description | Qty | Unit | Availability | Transfer | Due Date | Delivery Date
32982200 | 972 | SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 3B9002-7P | KIT - INSTALLATION | 1.00 | EA | UNAVAILABLE | — | 19.Jul.2026 | —
32985332 | 1038 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 4115-1-131-8110 | RESTRNT-SYSTEM | 2.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | —
32985343 | 1045 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 4115-1-131-8110 | RESTRNT-SYSTEM | 2.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | —
32985832 | 1061 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING | E60614-00XXXX | LANYARD, GENERATOR RELEASE (GREEN) | 72.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | —
32985832 | 1061 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING | E61445-00 | RPOE TENSIONING | 18.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | —
32985833 | 1062 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING | E60614-00XXXX | LANYARD, GENERATOR RELEASE (GREEN) | 72.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | —
32988850 | 1121 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY 8 EA AIR FLAP SEAL DETERIORATED. | SP1395 | VALVE ASSY-FLAP | 6.00 | EA | UNAVAILABLE | — | 21.Jul.2026 | —
33019264 | 1321 | ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 | FE240-221-001 | DIAPHRAGM SEAL | 1.00 | EA | UNAVAILABLE | — | 27.Jul.2026 | —
33019327 | 1323 | ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 | FE240-221-001 | DIAPHRAGM SEAL | 1.00 | EA | UNAVAILABLE | — | 27.Jul.2026 | —
33019384 | 1324 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 | FE240-221-001 | DIAPHRAGM SEAL | 1.00 | EA | UNAVAILABLE | — | 27.Jul.2026 | —
33022670 | 1342 | CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING | 3212MU01SA41 | FOOTSTEP ASSY | 1.00 | EA | UNAVAILABLE | — | 28.Jul.2026 | —
33022800 | 1343 | CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. | 918J8028 | SEALANT GERFLOR FLOOR MAT | 4.00 | EA | UNAVAILABLE | — | 28.Jul.2026 | —
33025667 | 1360 | CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE | D5367680500300 | PANEL ASSY-FLOOR | 1.00 | EA | UNAVAILABLE | — | 28.Jul.2026 | —
32985833 | 1062 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING | E61445-00 | RPOE TENSIONING | 15.00 | EA | UNAVAILABLE | — | 20.Jul.2026 | 30.Jul.2026
33023803 | 1356 | CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. | 16800-01-00 | THIRD OCCUPANT SEAT ASSY | 1.00 | EA | UNAVAILABLE | TRANSFER_NEEDED | 28.Jul.2026 | —
32985350 | 1049 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 2E7002-11APX | COVER ASSY-BACK | 1.00 | EA | UNAVAILABLE |  | 20.Jul.2027 | —
32985304 | 1036 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 2E7002-11APX | COVER ASSY-BACK | 1.00 | EA | UNAVAILABLE |  | 20.Jul.2029 | —
32985304 | 1036 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 2E7003-1 | CUSHION-BACK | 1.00 | EA | UNAVAILABLE |  | 20.Jul.2030 | —
32982202 | 973 | R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 2E1135-0532 | WASHER | 8 | EA | UNAVAILABLE |  | 20.Jul.2031 | —
32982199 | 971 | L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 2E1135-0533 | WASHER | 12 | EA | UNAVAILABLE |  | 20.Jul.2032 | —
32991511 | 1202 | LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | A225400429-750 | DOOR ASSY-WASHBASIN | 1 | EA | UNAVAILABLE |  | 20.Jul.2033 | —
32984848 | 1012 | G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | SP0614 | STRIKER PLATE U/O PN 330SVA4RGA00 | 3 | EA | UNAVAILABLE |  | 20.Jul.2034 | —

## LAYOVER
|  |  | HZ-ASD C2+6Y-CHK + WIFI — LAYOVER SCHEDULE | [38 empty] | O.O.S 17-Jul B.I.S 24-Aug GROUND TIME 38 DAYS
TASK | Start | Finish | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Day 11 |  |  | Day 12 |  |  | Day 13 |  |  | Day 14 |  |  | Day 15 |  |  | Day 16 |  |  | Day 17 |  |  | Day 18 |  |  | Day 19 |  |  | Day 20 |  |  | Day 21 |  |  | Day 22 |  |  | Day 23 |  |  | Day 24 |  |  | Day 25 |  |  | Day 26 |  |  | Day 27 |  |  | Day 28 |  |  | Day 29 |  |  | Day 30 |  |  | Day 31 |  |  | Day 32 |  |  | Day 33 |  |  | Day 34 |  |  | Day 35 |  |  | Day 36 |  |  | Day 37 |  |  | Day 38
|  |  | 2026-07-18 |  |  | 2026-07-19 |  |  | 2026-07-20 |  |  | 2026-07-21 |  |  | 2026-07-22 |  |  | 2026-07-23 |  |  | 2026-07-24 |  |  | 2026-07-25 |  |  | 2026-07-26 |  |  | 2026-07-27 |  |  | 2026-07-28 |  |  | 2026-07-29 |  |  | 2026-07-30 |  |  | 2026-07-31 |  |  | 2026-08-01 |  |  | 2026-08-02 |  |  | 2026-08-03 |  |  | 2026-08-04 |  |  | 2026-08-05 |  |  | 2026-08-06 |  |  | 2026-08-07 |  |  | 2026-08-08 |  |  | 2026-08-09 |  |  | 2026-08-10 |  |  | 2026-08-11 |  |  | 2026-08-12 |  |  | 2026-08-13 |  |  | 2026-08-14 |  |  | 2026-08-15 |  |  | 2026-08-16 |  |  | 2026-08-17 |  |  | 2026-08-18 |  |  | 2026-08-19 |  |  | 2026-08-20 |  |  | 2026-08-21 |  |  | 2026-08-22 |  |  | 2026-08-23 |  |  | 2026-08-24
|  |  | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G | D | T | G
PHASE 1 (Pre Hangar)
Aircraft Arrival | 2026-07-18 23:00
Heavy Wash | 2026-07-19 06:00
Both ENG Preservation | 2026-07-18 14:00
Pre HGR | 2026-07-19 14:00 | 2026-07-21 | [9 empty] | 21-Jul
Pre Insp | 2026-07-19 14:00 | 2026-07-21 | [9 empty] | 21-Jul
Defuel | 2026-07-22 | [13 empty] | 22-Jul
PHASE 2 (Inspection)
Nose Jacking – Prox Sensor Check | 2026-07-23 | [16 empty] | 23-Jul
Open-Up | 2026-07-21 | 2026-07-26 | [24 empty] | 26-Jul
Joint Cards Insp | 2026-07-21 | 2026-08-03 | [48 empty] | 3-Aug
Jacking – Free Fall Func Chk & NLG | 2026-07-23 | 2026-07-23 | [15 empty] | 23-Jul
Power Off | 2026-07-26 | 2026-08-02 | [45 empty] | 2-Aug
FINDING CUT-OFF | 2026-08-01 | [43 empty] | ◆ 1-Aug
PHASE 3 (Modification & Rectification)
Findings & Rectification | 2026-07-17 | 2026-08-19 | [96 empty] | 19-Aug
Engineering Orders Doc (EOD's / ER's) | 2026-07-25 | 2026-08-08 | [63 empty] | 8-Aug
FOMAX & Eclipse Connectivity Mods | 2026-07-26 | 2026-08-05 | [54 empty] | 5-Aug
MATERIALS ARRIVAL CUT-OFF | 2026-08-10 | [70 empty] | ◆ 10-Aug
PHASE 4 (Close Up & Final Inspection)
Cabin Restoration
Areas Close Up | 2026-08-14 | 2026-08-19 | [96 empty] | 19-Aug
Cabin, Cargos & Cockpit
Fuselage, Empennage & Wings
Engines
OPS & Func Check (Power On) | 2026-08-17 | 2026-08-19 | [96 empty] | 19-Aug
W&B | 2026-08-20 | [100 empty] | 20-Aug
Refuel & Leak Checks | 2026-08-21 | [103 empty] | 21-Aug
Engine Run | 2026-08-22 | [106 empty] | 22-Aug
PHASE 5 (Release)
Final Product Quality Inspection (FPQI) | 2026-08-23 | 2026-08-24 | [111 empty] | 24-Aug
Aircraft Release | 2026-08-24 | [112 empty] | 24-Aug
MILESTONES — auto from the schedule above
FINDINGS CUTOFF | 2026-08-01 |  | 46235
FOMAX START | 2026-07-26 |  | 387420489
FOMAX END | 2026-08-05 |  | 46239
POWER OFF | 2026-07-26 |  | 387420489
POWER ON | 2026-08-02 |  | 46236
CABIN CLOSE-UP | 2026-08-19 |  | 46253
FINAL INSPECTION | 2026-08-23 |  | 46257
DE-HANGAR | 2026-08-24 |  | 46258

## Findings Draft
📋 FINDINGS DRAFT — Pre-AMOS
Findings sourced from ACFT Finding Report App · Review & assign P/N before raising on AMOS
# | By | Category | Sub-Category | Finding Description | Remarks | Photo URL | AMOS Status | WO No. | P/N Required | Qty
1 | 30001575 | FLIGHT DECK | STOWAGE | STOWAGE COMP DIRTY |  | https://i.ibb.co/V0S6MWKf/2c0f499aba84.jpg ¦ https://i.ibb.co/DHR2Xff9/e954f2fa6628.jpg ¦ https://i.ibb.co/ymNVHCr5/82edb4a173a1.jpg ¦ https://i.ibb.co/mC61CMhY/2c192cc49cbd.jpg | Not Raised
2 | 30001575 | FLIGHT DECK | DECALS | DECAL DAMAGES |  | https://i.ibb.co/7JSQz40y/121e4cb35567.jpg ¦ https://i.ibb.co/pStxDjx/5a7078625ab8.jpg ¦ https://i.ibb.co/4ZNPYDdT/bc71fabd91d4.jpg ¦ https://i.ibb.co/7N0t9b8b/c83b27d90ddf.jpg ¦ https://i.ibb.co/FLWyVfps/b7ea655f3e1d.jpg | Not Raised
3 | 30001575 | FLIGHT DECK | WASTE GATE | WASTE GATE SPRING STUCK AND EDGES CHIPPED |  | https://i.ibb.co/cKvnQbLQ/d8d90d2d32a4.jpg ¦ https://i.ibb.co/1j6tQkM/d4739312fa3b.jpg | Not Raised
4 | 30001575 | FLIGHT DECK | FIRE EX | PORT FIRE EX COMP EDGES CHIPPED AND DIRTY AND DECAL EDGES DAMAGE |  | https://i.ibb.co/LDKNs53R/60a738aab7c7.jpg ¦ https://i.ibb.co/Kxw7TX6x/cb59ff7813b0.jpg | Not Raised
5 | 30001575 | FLIGHT DECK | DISC STOWAGE | DISC STOWAGE DIRTY, PAINT PEELED |  | https://i.ibb.co/sdM1bx04/333df573f526.jpg ¦ https://i.ibb.co/PynFbg0/9f4695bb788c.jpg ¦ https://i.ibb.co/BHcr8tYx/4133ee94ebe8.jpg | Not Raised
6 | 30001575 | FLIGHT DECK | STOWAGE COMP | STOWAGE COMP DIRTY AND PAINT FADED |  | https://i.ibb.co/TdKwHcy/1ffabf0fe14f.jpg ¦ https://i.ibb.co/TDG7VKmF/171a79eb51db.jpg ¦ https://i.ibb.co/Q7WVmGz2/0c91afae6c65.jpg | Not Raised
7 | 30001575 | FLIGHT DECK | COMP | STOWAGE COMP EDGES DAMAGED AND PLASTIC PAINT PEELED |  | https://i.ibb.co/cc3kMLpK/53b04780be07.jpg ¦ https://i.ibb.co/ZRSZV7zx/23f87b95eb76.jpg | Not Raised
8 | 30001575 | FLIGHT DECK | FO | FO SLIDING TABLE PAINT CHIPPED |  | https://i.ibb.co/5WPqGk9Z/ff9771b3f85c.jpg ¦ https://i.ibb.co/Xx9XSkkW/a843df085b90.jpg ¦ https://i.ibb.co/gMsCZk8F/1fca9100cc60.jpg ¦ https://i.ibb.co/gbwZJgF0/cf72cec589c0.jpg ¦ https://i.ibb.co/b560yNCb/199686d84502.jpg | Not Raised
9 | 30001575 | FLIGHT DECK | CAP TABLE | CAP SLIDING TABLE END CAB CHIPPED PAINT, MIDDLE LATCH STIFF, MIDDLE TABLE SCRATCHED AND CHIPPED, PAPER CLIP CORRODED, BLACK-RUBBER MISSING, SLOW, STIFF AND NEEDS FORCE IN RETURNING MECHANISM |  | https://i.ibb.co/LDLC8ZqF/8cf77b6f5530.jpg ¦ https://i.ibb.co/ZRLNXrzt/4800d4fd2aa6.jpg ¦ https://i.ibb.co/xq9k1xMs/262fcf47083b.jpg ¦ https://i.ibb.co/JWDXJzWr/07cf1aaa8eb2.jpg ¦ https://i.ibb.co/Cpr2n0LQ/9d1b84c61530.jpg | Not Raised
10 | 30001575 | FLIGHT DECK | CAP TABLE | CAP SLIDING TABLE END CAB CHIPPED PAINT, MIDDLE LATCH STIFF, MIDDLE TABLE SCRATCHED AND CHIPPED, PAPER CLIP CORRODED, BLACK-RUBBER MISSING, SLOW, STIFF AND NEEDS FORCE IN RETURNING MECHANISM |  | https://i.ibb.co/1J82sxYH/922b22e2b347.jpg ¦ https://i.ibb.co/SDgWyTVT/871156f4c614.jpg ¦ https://i.ibb.co/vxQ7GXv3/6ebd6ef51764.jpg ¦ https://i.ibb.co/XrmVv1DK/2f46cc33c276.jpg ¦ https://i.ibb.co/bjvdTxyL/3123161a3e72.jpg | Not Raised
11 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEATBUILT FAILUR QUICK RETURN MECHANISM |  | https://i.ibb.co/Psk4g0Px/1cb054ea4f6a.jpg | Not Raised
12 | 30001575 | FLIGHT DECK | FO | FO R/ARM REST DISCOLORED EDGES, DIRTY AND PLASTIC CRACKED |  | https://i.ibb.co/WW3Ww89K/4b2a0d6496e6.jpg ¦ https://i.ibb.co/mFXLhmw9/ae9d4313e427.jpg ¦ https://i.ibb.co/ZPMHNRR/47d47cad66a4.jpg ¦ https://i.ibb.co/Rt7R2Wp/40cda1aa9e80.jpg | Not Raised
13 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT R/ARM REST CRACKED AND COVER DISCOLORED AND DIRTY |  | https://i.ibb.co/jptRYwZ/4b75071905d7.jpg | Not Raised
14 | 30001575 | FLIGHT DECK | ARM REST | CAP L/ARM REST ADJUSTMENT PLASITC COVER DIRTY |  | https://i.ibb.co/fdQJtVPD/6c5898afedb4.jpg | Not Raised
15 | 30001575 | FLIGHT DECK | ARM REST | CAP L/ARM REST BLACK-STAIN, SMALL CHIPPED AND CUT |  | https://i.ibb.co/Q7RmqyDf/fb4466e57942.jpg ¦ https://i.ibb.co/tMSsM8mG/f53be1cf7c3a.jpg ¦ https://i.ibb.co/ynK0c9RY/d0d17dcd9252.jpg ¦ https://i.ibb.co/7JmgMSjk/82bf315c451b.jpg ¦ https://i.ibb.co/qMP5DS22/2df5b79458e4.jpg | Not Raised
16 | 30001575 | FLIGHT DECK | FO | FO SEAT BLACK-AFT METAL CHIPPED PAINT |  | https://i.ibb.co/QvjZWqKG/59d01c63a2f6.jpg | Not Raised
17 | 30001575 | FLIGHT DECK | FO | FO BACK-LIFE-VEST SHROUD CUT DOWNWARD |  | https://i.ibb.co/m19rqHf/b2e4ad62c53d.jpg | Not Raised
18 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT LIFE-VEST SHROUD CUT |  | https://i.ibb.co/yn0yQ4x1/279f1f147658.jpg | Not Raised
19 | 30001575 | FLIGHT DECK | FO | FO SEAT LIFE-VEST DECAL BLACK- STAINS |  | https://i.ibb.co/2YCfrKVB/556a869cc13b.jpg | Not Raised
20 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT DOWNWARD BLACK-METAL CHIPPED PAINT |  | https://i.ibb.co/cS5D6Psm/243ecd294b1f.jpg | Not Raised
21 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT LIFE-VEST DECAL SMALL CHIPP |  | https://i.ibb.co/MxQpY4gN/12a5ddc7c3f2.jpg | Not Raised
22 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT LIFE-VEST INTERIOR STOWAGE SCRATCHED AND DIRTY |  | https://i.ibb.co/mVT1jb3q/cc4177051ecc.jpg | Not Raised
23 | 30001575 | FLIGHT DECK | 2ND OBSERVER | SECOND OBSERVER CHEST BUILT WHITE PAINT STAIN |  | https://i.ibb.co/CKNQ4z9d/e8e9d04a488b.jpg | Not Raised
24 | 30001575 | FLIGHT DECK | 2ND OBSERVER | SECOND OBSERVER BACK REST DISCONNECTED |  | https://i.ibb.co/Vc777w3c/b0b48c74575e.jpg ¦ https://i.ibb.co/N648M3vP/11c2306341dc.jpg | Not Raised
25 | 30001575 | FLIGHT DECK | 1ST OBSERVER | FIRST OBSERVER SEAT METAL CHIPPED PAINT |  | https://i.ibb.co/bq5YNVk/85adca2d030c.jpg ¦ https://i.ibb.co/YFfSdYCR/e6bcb06764ab.jpg | Not Raised
26 | 30001575 | FLIGHT DECK | 2ND OBSERVER | SECOND OBSERVER SEAT COVER DIRTY AND HAS PAINT |  | https://i.ibb.co/2zzR477/08f76236c977.jpg ¦ https://i.ibb.co/7x7wYdSR/131c64682066.jpg ¦ https://i.ibb.co/qMYS1513/84844b7670b5.jpg ¦ https://i.ibb.co/qY3RKBtm/6270fc2e42b8.jpg | Not Raised
27 | 30001575 | FLIGHT DECK | 2ND OBSERVER | SECOND OBSERVER BACK REST VELCRO AND BACK SHROUD DAMAGED |  | https://i.ibb.co/whnh6pLr/6ba11748fd70.jpg ¦ https://i.ibb.co/twRzwJN2/45656291e067.jpg ¦ https://i.ibb.co/SD0SB54n/ec34380d7077.jpg ¦ https://i.ibb.co/ZzK4tJ5X/5cd310c90a79.jpg | Not Raised
28 | 30001575 | FLIGHT DECK | 1ST OBSERVER | FIRST OBSERVER SEAT DOWNWARD LIFE-VEST VELCRO AND ITS SHROURD DAMAGED |  | https://i.ibb.co/0RrZqhPv/83cabfa26e93.jpg ¦ https://i.ibb.co/WW9zMtSJ/2366efe464e8.jpg ¦ https://i.ibb.co/MxcBVKt5/79dd79aa0263.jpg | Not Raised
29 | 30001575 | FLIGHT DECK | 1ST OBSERVER | FIRST OBSERVER SEAT CUSHION ASSY OUT OF POSITION |  | https://i.ibb.co/twwK46n6/a17d41102121.jpg | Not Raised
30 | 30001575 | FLIGHT DECK | 1ST OBSERVER | 1ST OBSERVER FRAYED BOTH CHEST SEAT BUILTS |  | https://i.ibb.co/BVDVySKF/2531c0f00e11.jpg | Not Raised
31 | 30001575 | FLIGHT DECK | 1ST OBSERVER | FIRST OBSERVER BACK REST CUSHION COVER STAINS |  | https://i.ibb.co/Lzt9XjGn/c5910b5f05df.jpg ¦ https://i.ibb.co/7JtVCDb1/781b1f4bca16.jpg | Not Raised
32 | 30001575 | FLIGHT DECK | 1ST OBSERVER | FIRST OBSERVER HEAD REST BACK SHROUD PAINT FADED AND CHIPPED |  | https://i.ibb.co/QvBqsVrB/62c63eda3c80.jpg ¦ https://i.ibb.co/JRYGm3CY/d71b42254f96.jpg | Not Raised
33 | 30001575 | FLIGHT DECK | FO | FO SEAT CHIPPED PAINT AND SCRATCHED |  | https://i.ibb.co/MkzHWMCN/b7b646fa0e2f.jpg | Not Raised
34 | 30001575 | FLIGHT DECK | CAP | CAP SEAT VELCRO DAMAGED |  | https://i.ibb.co/ch6mpQxv/cfc4cb910db7.jpg | Not Raised
35 | 30001575 | FLIGHT DECK | FO | FO SEAT VELCRO DAMAGED |  | https://i.ibb.co/99k4Dq5L/d46c0d84098c.jpg | Not Raised
36 | 30001575 | FLIGHT DECK | FO | FO BACK REST WOOL DAMAGED |  | https://i.ibb.co/bgfH9kgk/77a72493a2a9.jpg | Not Raised
37 | 30001575 | FLIGHT DECK | FO | FO HEAD REST WOOL DAMAGED |  | https://i.ibb.co/yBxP5Z23/e2a71d7eb3ba.jpg | Not Raised
38 | 30001575 | FLIGHT DECK | FO | FO HEAD REST COVER DIRTY |  | https://i.ibb.co/ynphm1Nj/2387e98568d7.jpg | Not Raised
39 | 30001575 | FLIGHT DECK | CO-PILOT | FO SEAT CUSHION COVER WRINKLED AND DIRTY AND OUT OF POSITION |  | https://i.ibb.co/DHn8F1T6/b6651423efea.jpg ¦ https://i.ibb.co/QFJfJ2KN/c02f7ffad194.jpg | Not Raised
40 | 30001575 | FLIGHT DECK | FO | CO-PILOT BACK REST COVER DIRTY |  | https://i.ibb.co/2727DJB1/3ae7e496ad10.jpg | Not Raised
41 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT WOOL DAMAGED |  | https://i.ibb.co/FL85fX9x/31b1b21ce9e1.jpg | Not Raised
42 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT METAL CHIPPED PAINT |  | https://i.ibb.co/j97YnJMw/b05e6fe61233.jpg | Not Raised
43 | 30001575 | FLIGHT DECK | CAP SEAT | CAP SEAT COVER WRINKELD AND DIRTY |  | https://i.ibb.co/NgbxRL2N/27e5367d796d.jpg | Not Raised
44 | 30001575 | FLIGHT DECK | CAP SEAT | CAP BACK REST CUSHION COVER STITCHES OUT |  | https://i.ibb.co/fGZNDCPk/92ca183952a3.jpg | Not Raised
45 | 30001575 | FLIGHT DECK | CAP SEAT | GREEN PAINT ON CAP BACK REST COVER |  | https://i.ibb.co/7HnFvQr/e70e3dd50d94.jpg | Not Raised
46 | 30001575 | FLIGHT DECK | CAP SEAT | PILOT HEAD REST COVER DIRTY |  | https://i.ibb.co/0pv4pkLZ/76b22a74ae65.jpg ¦ https://i.ibb.co/21CbSPSV/d84741ae1ef3.jpg | Not Raised
47 | 30004221 | PAINT | 5CA | WINDOW |  | https://i.ibb.co/84bDjHc0/d316030718c1.jpg | Not Raised
48 | 3004221 | PAINT | 41 CBA | WINDOW |  | https://i.ibb.co/Dgt4DpFw/4b7c6bdd70a4.jpg | Not Raised
49 | 30004221 | PAINT | L1 DOOR | PAINT |  | https://i.ibb.co/7NZ7NNxR/2857df8c6fa3.jpg ¦ https://i.ibb.co/8DJTWgNL/f95d061a7c01.jpg | Not Raised
50 | 30004221 | GENERAL CABIN | L2DOOR | ASSIST HAND LOOSE |  | https://i.ibb.co/5gk4tDhh/13efe7f780ea.jpg | Not Raised
51 | 30004221 | PAINT | SLIDRAFT L2 | PAINT |  | https://i.ibb.co/gHscmRs/fd9581d7dfe7.jpg ¦ https://i.ibb.co/nsR0bHvJ/335b2133a087.jpg ¦ https://i.ibb.co/JRWSZJ8s/01331eaab6af.jpg | Not Raised
52 | 30004221 | PAINT | SLIDRAFT R2 | PAINT BUSTLE |  | https://i.ibb.co/60GT35SB/a38a518fb250.jpg ¦ https://i.ibb.co/ynxLnqK2/de727618bf77.jpg | Not Raised
53 | 30004221 | GENERAL CABIN | OSB 44 LKJ | COVER HEAD STOWG CRACKED |  | https://i.ibb.co/WWd398s8/861ceceec6a6.jpg | Not Raised
54 | 30004221 | GENERAL CABIN | OSB 44 CBA | COVER HEAD STOWG CRACKED |  | https://i.ibb.co/TMKCr6Qj/75c05868109a.jpg ¦ https://i.ibb.co/nqTKt8Jt/447819849780.jpg ¦ https://i.ibb.co/jPsdRth0/f57ee83007c1.jpg ¦ https://i.ibb.co/XkzS6Vht/04d876ad9637.jpg | Not Raised
55 | 30004221 | GENERAL CABIN | OSB 42LKJ | MISSING BUMBER |  | https://i.ibb.co/KxFSKVX8/9bd40414853c.jpg | Not Raised
56 | 30004221 | GENERAL CABIN | OSB 42CBA | MISSING BUMBER |  | https://i.ibb.co/vxGt43t7/1459f5f65542.jpg | Not Raised
57 | 30004221 | GENERAL CABIN | OSB 41 LKJ | CRACKED AND MISSING BUMBER |  | https://i.ibb.co/pr9cnSM0/52e81f995e35.jpg ¦ https://i.ibb.co/jkx1RFmM/58d9c1af3583.jpg ¦ https://i.ibb.co/Z6fbrkNj/3f7e99b85707.jpg ¦ https://i.ibb.co/N27jvxkF/580608c09a1f.jpg | Not Raised
58 | 30004221 | GENERAL CABIN | OSB 41 CBA | MISSING BUMBER |  | https://i.ibb.co/s47XvNd/6cd9ef796bc1.jpg | Not Raised
59 | 30004221 | GENERAL CABIN | OVER HEAD 41 CBA | CEILING PANEL CRACKED |  | https://i.ibb.co/JFxHNzQs/89805b217683.jpg ¦ https://i.ibb.co/4nhpCV18/8cdef659b359.jpg | Not Raised
60 | 30004221 | PAINT | OSB 40 LKJ | PAINT , DENT |  | https://i.ibb.co/DfPjwzRN/496dbf06e75b.jpg ¦ https://i.ibb.co/0jB6qQzf/baab45f12c2c.jpg | Not Raised
61 | 30004221 | GENERAL CABIN | OSB40CBA | MISSING BUMBER AND SECRW |  | https://i.ibb.co/d4Fj3bGz/8e7891537bc9.jpg ¦ https://i.ibb.co/qLsSVB96/970630c19e27.jpg ¦ https://i.ibb.co/R4j5mGFJ/ee733396a77e.jpg | Not Raised
62 | 30004221 | PAINT | ISB LKJ | CRACKED |  | https://i.ibb.co/Z6vK4Dbz/66cda2b68d8b.jpg ¦ https://i.ibb.co/dJVL0w4T/72a2bfda9aa7.jpg | Not Raised
63 | 30004221 | GENERAL CABIN | OSB 39 CBA | MISSING BUMBER |  | https://i.ibb.co/G4bnFGC2/5206906f3b42.jpg | Not Raised
64 | 30004221 | PAINT | OVER HEAD 37CBA | PAINT |  | https://i.ibb.co/b5w020G9/b4f5572b1ed9.jpg | Not Raised
65 | 30004221 | GENERAL CABIN | OSB 36 LKJ | MISSING BUMBER |  | https://i.ibb.co/JFx8N73m/87766c057487.jpg | Not Raised
66 | 30004221 | GENERAL CABIN | OSB 33LKJ | MISSING BUMBER |  | https://i.ibb.co/XxrgzxPy/1a8cdc94caf7.jpg | Not Raised
67 | 30004221 | PAINT | OSB 33LKJ | PAINT |  | https://i.ibb.co/1YfKKW0z/f03ad0c350db.jpg | Not Raised
68 | 30004221 | GENERAL CABIN | OSB 32LKJ | MISSING BUMBER |  | https://i.ibb.co/MkR0wtkV/d5324666531f.jpg | Not Raised
69 | 30004221 | PAINT | OSB 32LKJ | OSB DIVIDER PAINT AND DAMAGE |  | https://i.ibb.co/LXHbBNCX/ffb1ff765db9.jpg ¦ https://i.ibb.co/tpsftxFz/1d02acd3f358.jpg | Not Raised
70 | 30004221 | PAINT | OSB 31LKJ | PAINT |  | https://i.ibb.co/k2SrBPM5/11211fd0389f.jpg | Not Raised
71 | 30004221 | GENERAL CABIN | OSB 32CBA | CRACKED AND MISSING BUMBER |  | https://i.ibb.co/zVBk1qwZ/60c33b536f0c.jpg ¦ https://i.ibb.co/mmcTs3N/10eb29f0da42.jpg ¦ https://i.ibb.co/qMdt52kF/47a022d4f459.jpg | Not Raised
72 | 30004221 | GENERAL CABIN | OSB 30LKJ | MISSING BUMBER |  | https://i.ibb.co/B5mscqGS/7e1bf118ed62.jpg ¦ https://i.ibb.co/jZ18LjZW/876650fc0f79.jpg | Not Raised
73 | 30004221 | PAINT | OVER HEAD 5LJ | CRACKED |  | https://i.ibb.co/1f9BYpkC/2e6bef2110c3.jpg ¦ https://i.ibb.co/s9z2nynG/9ec1af033762.jpg | Not Raised
74 | 30004221 | GENERAL CABIN | OSB 5LJ | MISSING BUMBER |  | https://i.ibb.co/jvyz6t53/fb9fb5fa0ec6.jpg | Not Raised
75 | 30004221 | GENERAL CABIN | OSB | MISSING INNER BUMBER |  | https://i.ibb.co/Mxd7vgYg/9d7c8aab30d2.jpg ¦ https://i.ibb.co/YFKgFHYf/f6c70b3f6822.jpg ¦ https://i.ibb.co/WNBbN3vS/7da76f22d2c1.jpg | Not Raised
76 | 30004221 | PAINT | OSB 4LJ | CRACKED |  | https://i.ibb.co/6cpzYdWQ/f762fb52f07b.jpg ¦ https://i.ibb.co/9m9CrCqY/f3a8d937fd34.jpg ¦ https://i.ibb.co/qMP99g1S/80fb132c4eab.jpg | Not Raised
77 | 30004221 | GENERAL CABIN | 4LJ | OSB MISSING BUMBER |  | https://i.ibb.co/DHQ7syLg/73bf486c6e76.jpg | Not Raised
78 | 30004221 | GENERAL CABIN | OSB 3CA | OSB LINIER BROKEN |  | https://i.ibb.co/zVHJnzrS/fad54d3429b0.jpg ¦ https://i.ibb.co/bTwrPnN/3037c7e7281d.jpg | Not Raised
79 | 30004221 | PAINT | OVER HEAD 2CA | PAINT |  | https://i.ibb.co/gMsyXPqk/34fb9778d954.jpg | Not Raised
80 | 30004221 | PAINT | OVER HEAD 1LJ | PINT, CRACKED |  | https://i.ibb.co/s9kX5qNn/17ebc1d5f32c.jpg ¦ https://i.ibb.co/ZRy3r3T4/b7413580da86.jpg ¦ https://i.ibb.co/YFfCwF3B/2aa619eef3ec.jpg | Not Raised
81 | 30004221 | GENERAL CABIN | OVER HEAD 1CA | COVER HEAD STOWG CRACKED |  | https://i.ibb.co/MysFvdJK/7cc994a38d21.jpg | Not Raised
82 | 30004221 | GENERAL CABIN | OVER HEAD 1CA | MISSING RUBBER BUMBER |  | https://i.ibb.co/Tx6nqyqM/d58074246362.jpg | Not Raised
83 | 30004221 | GENERAL CABIN | FWD GALLEY | EMERGENCY FRAME BROKEN |  | https://i.ibb.co/Z6n5bDy4/4f4da9bc0de9.jpg | Not Raised
84 | 30001351 | GALLEY | GALLY G1 | REQUIRES PAINT |  | https://i.ibb.co/99rtDHqr/38ed67902991.jpg | Not Raised
85 | SHAREEF | GENERAL CABIN | N/A | R/H CLOSET TEDLAR DIRTY |  | https://i.ibb.co/6cbTrRvm/54a21f4c79cc.jpg | Not Raised
86 | SHAREEF | GENERAL CABIN | N/A | L/H CLOSET SCREW MISSING WASHER |  | https://i.ibb.co/CsQ3bMwb/b65c494a5b4a.jpg | Not Raised
87 | SHAREEF | GENERAL CABIN | N/A | L/H CLOSET SMALL KNOB LOOSE |  | https://i.ibb.co/7tGh4dNy/4929a6514712.jpg | Not Raised
88 | SHAREEF | GENERAL CABIN | N/A | L/H TURN CATCHES PNT SCRATCHED |  |  | Not Raised
89 | SHAREEF | GENERAL CABIN | N/A | CLOSET L/H MISSING SEALANT |  | https://i.ibb.co/MyBC3Y11/aab966f5177d.jpg | Not Raised
90 | SHAREEF | GENERAL CABIN | N/A | CLOSET L/H DIRTY |  | https://i.ibb.co/whMYr764/9d52359ec6c4.jpg | Not Raised
91 | SHAREEF | GENERAL CABIN | N/A | CLOSET R/H DIRTY |  | https://i.ibb.co/N6shNgZC/1e25ef869dc1.jpg | Not Raised
92 | SHAREEF | GENERAL CABIN | N/A | REQ PNT. TEDLAR ALSO |  | https://i.ibb.co/DH3JhYzK/8f57d09b687c.jpg | Not Raised
93 | SHAREEF | GENERAL CABIN | N/A | 2 SCREWS MISSING CLOSET R/H |  | https://i.ibb.co/XfCX7R4G/6d09137f212b.jpg | Not Raised
94 | SHAREEF | GENERAL CABIN | N/A | STRIKER IS DAMAGED UPPER CLOSET L/H ( S301 |  | https://i.ibb.co/HpVx8KTH/f4db823cd1b0.jpg | Not Raised
95 | SHAREEF | GENERAL CABIN | N/A | MOUNT COVER MISSING CLOSET L/H |  | https://i.ibb.co/h1h3HCjZ/36bcd77b32c6.jpg | Not Raised
96 | SHAREEF | GENERAL CABIN | N/A | AFT CLOSET L/H |  | https://i.ibb.co/23QKr9Nb/a1508e34cfb2.jpg | Not Raised
97 | SHAREEF | GALLEY | FWD G2 | STRIKER MISSING FOR COMP. 205, AND 202 | ALSO, COMP 209 STRIKE IS DAMAGED. | https://i.ibb.co/Mk1Hp0w5/b982e9d22a76.jpg ¦ https://i.ibb.co/fd9GghBj/7a2685e0f0d4.jpg | Not Raised
98 | 30001461 | GENERAL CABIN | N/A | TEDLAR ABOVE WINDOW 3LJ, 5AC CHIPPED |  |  | Not Raised
99 | 30001461 | GENERAL CABIN | N/A | SPLINEFOR 1AC, 1LJ, 5LJ BROKEN |  | https://i.ibb.co/MyJ6PzQP/729b451d0af7.jpg ¦ https://i.ibb.co/yDBLBFv/6201a108f7f4.jpg ¦ https://i.ibb.co/yc95Kjfd/6e1bda0f3b78.jpg | Not Raised
100 | 30001461 | GENERAL CABIN | N/A | DOG HOUSE LH B/C REQ PAINT |  | https://i.ibb.co/21WbMzdG/2467fd140f9c.jpg | Not Raised
101 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE 4LJ BROKEN |  | https://i.ibb.co/VWN1MJ2T/2c7c4aaa5233.jpg | Not Raised
102 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE BROKEN 1LJ |  | https://i.ibb.co/8LR8MfdZ/eedf5881277d.jpg | Not Raised
103 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE DOOR FOUND DIRTY FWD OF 1LJ |  | https://i.ibb.co/2YkBJbkk/d692b05da1ae.jpg | Not Raised
104 | 30001461 | GENERAL CABIN | N/A | FWD STOWAGE SEALANT MISSINF |  | https://i.ibb.co/4R3DG9V4/d02d02819b94.jpg | Not Raised
105 | 30001461 | GENERAL CABIN | N/A | ALL OVERHEAD STOWAGE COMPARTMENTS DIRTY |  | https://i.ibb.co/fzxDQgq6/cebeb219bdfb.jpg | Not Raised
106 | 30001461 | GENERAL CABIN | N/A | SEVERAL WINDOWS MISSMATCH COLORS |  | https://i.ibb.co/YF7xJhxS/39481d412fba.jpg | Not Raised
107 | 30001461 | GENERAL CABIN | N/A | FWD STOWAGE TEDLAR CHIPPED |  | https://i.ibb.co/sJ5k78Ps/e4e20e5ece6a.jpg ¦ https://i.ibb.co/PsvR868L/4834a4a1a72f.jpg | Not Raised
108 | 30001461 | GENERAL CABIN | N/A | FWD TRIM REQ S/M |  | https://i.ibb.co/zVVsHN6Y/57687a50cb99.jpg ¦ https://i.ibb.co/0y76kqMn/fadc4c2fd699.jpg | Not Raised
109 | 30001461 | GENERAL CABIN | N/A | 3CA OVH STOWAGE TRIM BROKEN |  | https://i.ibb.co/xS0SyrLw/ae70d27393fb.jpg | Not Raised
110 | 30001461 | GENERAL CABIN | N/A | SEVERAL OVH STOWAGE NEED ADJUSTMENT |  |  | Not Raised
111 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE FRONT OF 1LJ REQ PAINT |  | https://i.ibb.co/jkG28k8W/21d6184cf99f.jpg | Not Raised
112 | 30001461 | GENERAL CABIN | N/A | 2CA, 6CA OVH STOWAGE BUMBER MISSING |  | https://i.ibb.co/n8D75xvm/095e05b24d33.jpg ¦ https://i.ibb.co/fYdpHzhJ/bb386e02592f.jpg | Not Raised
113 | 30001461 | GENERAL CABIN | N/A | CEILING PANEL FOUND BROKEN ABOVE 4LJ |  | https://i.ibb.co/8nNvFF5P/639a7fff4c28.jpg | Not Raised
114 | 30001461 | GENERAL CABIN | N/A | DIVIDER CURTAIN MISSING SLIDESAND HOOKS |  | https://i.ibb.co/CpqWvd47/af4e7cff70f5.jpg ¦ https://i.ibb.co/M5pPgBN6/28d7df91ad00.jpg | Not Raised
115 | 30001461 | GENERAL CABIN | N/A | PARTITION TEDLAR FOLDED |  | https://i.ibb.co/wFVKWxcS/cbf00f8f6445.jpg | Not Raised
116 | 30001461 | GENERAL CABIN | N/A | TEDLAR ABOVE WINDOW 3LJ, 5AC CHIPPED |  | https://i.ibb.co/60sfPVRr/60186075a704.jpg ¦ https://i.ibb.co/93cc1GF9/4dcdf9d5b99b.jpg | Not Raised
117 | 30001461 | GENERAL CABIN | N/A | SPLINEFOR 1AC, 1LJ, 5LJ BROKEN |  | https://i.ibb.co/MyJ6PzQP/729b451d0af7.jpg ¦ https://i.ibb.co/yDBLBFv/6201a108f7f4.jpg ¦ https://i.ibb.co/yc95Kjfd/6e1bda0f3b78.jpg | Not Raised
118 | 30001461 | GENERAL CABIN | N/A | DOG HOUSE LH B/C REQ PAINT |  | https://i.ibb.co/21WbMzdG/2467fd140f9c.jpg | Not Raised
119 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE 4LJ BROKEN |  | https://i.ibb.co/VWN1MJ2T/2c7c4aaa5233.jpg | Not Raised
120 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE BROKEN 1LJ |  | https://i.ibb.co/8LR8MfdZ/eedf5881277d.jpg | Not Raised
121 | 30001461 | GENERAL CABIN | N/A | OVH STOWAGE DOOR FOUND DIRTY FWD OF 1LJ |  | https://i.ibb.co/2YkBJbkk/d692b05da1ae.jpg | Not Raised
122 | 30001461 | GENERAL CABIN | N/A | FWD STOWAGE SEALANT MISSINF |  | https://i.ibb.co/4R3DG9V4/d02d02819b94.jpg | Not Raised
123 | 30001461 | GENERAL CABIN | N/A | ALL OVERHEAD STOWAGE COMPARTMENTS DIRTY |  | https://i.ibb.co/fzxDQgq6/cebeb219bdfb.jpg | Not Raised
124 | 30001351 | GALLEY | GALLY G2 | PAINT 201 202 205 206 209 210 |  | https://i.ibb.co/B5wGqg8b/05c759851e6a.jpg ¦ https://i.ibb.co/0SBcPxM/d0fe0c86cc73.jpg ¦ https://i.ibb.co/Zzh6tNqg/c8003db95f6b.jpg ¦ https://i.ibb.co/dJHTS5zW/02434c2a1a46.jpg ¦ https://i.ibb.co/1Gc8Vn6w/8445e1786a22.jpg | Not Raised
125 | 30001351 | GALLEY | GALLY G2 | REQUIRES SHEET METAL DOOR STRIKER 201 202 205 206 209 210 |  | https://i.ibb.co/wNcdVsC4/eaf4fc008274.jpg ¦ https://i.ibb.co/jBHpz63/4f483308f085.jpg ¦ https://i.ibb.co/bgTBjq7D/3f67223bdf6f.jpg ¦ https://i.ibb.co/KxJmHJFk/2598c7d8cf17.jpg ¦ https://i.ibb.co/9mVkHZnF/466e5f1dd050.jpg | Not Raised
126 | 30001351 | GALLEY | GALLY G2 | SLAM LATCH LOOSE 201 203 205 209 210 |  |  | Not Raised
127 | 30001351 | GALLEY | GALLY G1 | DISENGAGEMENT DEVICE 101 DEFORMED |  | https://i.ibb.co/4Lm1wtv/867c68c34f18.jpg | Not Raised
128 | 30001351 | GALLEY | GALLY G2 | SEALENT DEFORMED AND DIRTY |  | https://i.ibb.co/zT3vH0p4/e6d9f4d4ac11.jpg | Not Raised
129 | 30001351 | GALLEY | GALLY G1 AND G2 | SEALENT DEFORMED AND DIRTY 108 AND 109 AND 110 AND 111 AND 212 |  | https://i.ibb.co/nNJdmRCv/96dd1fa2af26.jpg ¦ https://i.ibb.co/21ytbYXr/5d8a753ea700.jpg ¦ https://i.ibb.co/rRKxF5JW/88e926d0f82d.jpg ¦ https://i.ibb.co/GQgYY3g5/1e0993637a03.jpg ¦ https://i.ibb.co/DDrsPRXQ/f31a7f3f7057.jpg | Not Raised
130 | 30001351 | GALLEY | GALLY G2 | REQUIRES SHEET METAL 209 AND 210 |  | https://i.ibb.co/fz71QBd6/ef70e2b30651.jpg ¦ https://i.ibb.co/LXknV59C/6c1f8758b8e1.jpg | Not Raised
131 | 30001351 | GALLEY | GALLY G2 | REQUIRES SHEET METAL 201 AND 202 AND 206 AND 205 MISSING RIVETS |  | https://i.ibb.co/tMx7gggm/abf525f29670.jpg ¦ https://i.ibb.co/tfjqc3R/7e658c95da4e.jpg ¦ https://i.ibb.co/3GLY3t0/2bd93c46a850.jpg ¦ https://i.ibb.co/zVS1yp8j/b4402a249439.jpg ¦ https://i.ibb.co/PZ7k18RS/dc899058dd70.jpg | Not Raised
132 | 30001351 | GALLEY | GALLY G1 | NEEDS SHEET METAL 101 AND 102 |  | https://i.ibb.co/v4xSmXy3/6399dadb5905.jpg ¦ https://i.ibb.co/rG61wPKd/653916e35dcf.jpg ¦ https://i.ibb.co/WvPQMy07/759f953cc713.jpg ¦ https://i.ibb.co/sJt0Phch/be223e78ac22.jpg | Not Raised
133 | 30001351 | GALLEY | GALLY G1 | PAINT NEXT TO OVEN 2 AND BETWEN OVEN 1 |  | https://i.ibb.co/YF2bZzqj/4edade705ac0.jpg ¦ https://i.ibb.co/HDGNGBBm/258684e06df6.jpg | Not Raised
134 | 30001351 | TEDLAR/SIDEWALL | G2 | 209 TEDLAR |  | https://i.ibb.co/r2KgdVC9/a159e8a627e7.jpg | Not Raised
135 | 30001351 | GALLEY | GALLY G1 AND G2 | WORN AND DAMAGED CART DIVIDER ON BOTH SIDES |  |  | Not Raised
136 | 30001351 | GALLEY | GALLY G2 | FOOT STEP SCRATCHED AND COLOUR FADED MISSING KNOB |  | https://i.ibb.co/sxBDvN6/f0394f506858.jpg | Not Raised
137 | 30001351 | GALLEY | GALLY G1 | FOOT STEP SCRATCHED AND COLOUR FADED |  | https://i.ibb.co/hJH4xjGC/61795342a129.jpg | Not Raised
138 | 30001351 | GALLEY | GALLY G2 | 207 WASTE CONTAINER LATCH LOOSE |  | https://i.ibb.co/Ng1Cj1Ry/a8df7cd5de9f.jpg | Not Raised
139 | 30001351 | GALLEY | GALLY G1 | MID LATCH LEVER LOOSE ON 109 AND 110 |  | https://i.ibb.co/DDrzbrxn/e9383d640838.jpg ¦ https://i.ibb.co/yF6wHgts/30dffb1e290b.jpg ¦ https://i.ibb.co/xqMc0PLj/66f858a056c9.jpg | Not Raised
140 | 30001351 | GALLEY | GALLY G2 | 208 DAMAGED AND DECALS FADED |  | https://i.ibb.co/9kWd0Ygd/414280c92f37.jpg | Not Raised
141 | 30001351 | GALLEY | GALLY G2 | 204 RED LATCH BOTH SCRATCHED |  | https://i.ibb.co/0ptc6SZs/17f4fd4318c8.jpg | Not Raised
142 | 30001351 | GALLEY | GALLY G2 | NEXT TOO AND ABOVE 204 BENT AND DAMGED |  | https://i.ibb.co/0RbHPHY1/7582b3829c13.jpg ¦ https://i.ibb.co/hJr7t9fs/ba3a38af79cf.jpg | Not Raised
143 | 3000135 | GALLEY | GALLY G2 | TURN CATCH DAMAGED AND SCRATCHED |  | https://i.ibb.co/VYCmtf9Z/6abe906e4af3.jpg ¦ https://i.ibb.co/2Y3KKpV1/59e5075d0501.jpg ¦ https://i.ibb.co/1J6k3yPk/d5840ebc21c2.jpg ¦ https://i.ibb.co/6Rw8RTfY/7762b24e04d3.jpg | Not Raised
144 | 3000135 | GALLEY | GALLY G1 | TURN CATCH DAMAGED AND SCRATCHED |  | https://i.ibb.co/KjzGJ0Xy/9b1b750da460.jpg ¦ https://i.ibb.co/MyM5vVmB/a852470e8dbb.jpg ¦ https://i.ibb.co/4ZgC3gmB/759abe156364.jpg | Not Raised
145 | 30001351 | GALLEY | N/A | L1 CEILING PANEL DIRTY AND SCRATCHED MIDDLE CEILING PANEL DAMAGED R1 CEILING PANEL LIGHT DIRTY |  | https://i.ibb.co/dw8GwPc9/df5693e0c7c3.jpg ¦ https://i.ibb.co/TB4X0Fx0/6d3a18877e78.jpg ¦ https://i.ibb.co/HyQZZNj/bcea8bc38464.jpg ¦ https://i.ibb.co/wZfWmNrz/1d5c4e475c3f.jpg | Not Raised
146 | 30001351 | GALLEY | GALLY G1 | CURTAIN BENT SCRATCHED MISSING CURTAIN STOPPER DECALS FADED |  | https://i.ibb.co/gbxGx10j/436326e8ca26.jpg ¦ https://i.ibb.co/Kcb49JWf/6224e9593a1f.jpg ¦ https://i.ibb.co/VWQFDgTW/ca59ccfde78b.jpg | Not Raised
147 | 30001351 | GALLEY | GALLY G1 | AIR CHILLER DAMAGED BETWEEN 110 AND 111 |  | https://i.ibb.co/gLQ6nDSd/b769ff1bfd36.jpg ¦ https://i.ibb.co/nNH1cJQ9/f7c769cbee80.jpg ¦ https://i.ibb.co/s9KYb1dr/00868dadc0c2.jpg ¦ https://i.ibb.co/ks0kZQLG/c57413dd5305.jpg | Not Raised
148 | 30001351 | GALLEY | GALLY G1 | AIR CHILLER DAMAGED BETWEEN 109 AND 108 |  | https://i.ibb.co/Lzm3TnJR/92658f6e75d4.jpg ¦ https://i.ibb.co/mCNXf5rp/a52a43397956.jpg ¦ https://i.ibb.co/gFB6M7h5/82a835276612.jpg ¦ https://i.ibb.co/XxVBz9Ld/48e7b76e0ef3.jpg | Not Raised
149 | 30001351 | GALLEY | GALLY G2 | SEALENT MISSING |  | https://i.ibb.co/cXZtVCQp/2c0239d571ea.jpg | Not Raised
150 | 30001351 | GALLEY | GALLY G1 | MISSING SEALENT |  | https://i.ibb.co/1f9hxr1D/6ca7a14531f6.jpg ¦ https://i.ibb.co/zV6ZZw5x/13d9824beea4.jpg | Not Raised
151 | 30001351 | GALLEY | GALLY G1 | AIR CHILLER GRILL BENT |  | https://i.ibb.co/1tZJf3W4/53e5a708a2d4.jpg | Not Raised
152 | 30001351 | GALLEY | GALLY G1 | NOT WORKING OVEN 1 OVEN 2 COFFEE 1 COFFEE 2 OVEN GRILL 1 LOOSE OVEN GRILL 2 SCRATCHED |  | https://i.ibb.co/4n4qYJGz/efd0e9731af2.jpg ¦ https://i.ibb.co/Q7Qjv1j8/ba52c090056a.jpg ¦ https://i.ibb.co/0RRgbJkW/212f35865743.jpg ¦ https://i.ibb.co/Txm9wRRW/95294becc7ab.jpg | Not Raised
153 | 30001351 | GALLEY | GALLY G2 | CART CATCHER SCRATCHED AND DAMAGED |  | https://i.ibb.co/mVLQTZT0/92cb65565712.jpg ¦ https://i.ibb.co/C3mjqcWV/d651d7657618.jpg ¦ https://i.ibb.co/LXtfJdQf/0ed730f0596f.jpg ¦ https://i.ibb.co/F4vkvcS4/b946e8aeca88.jpg | Not Raised
154 | 30001351 | GALLEY | GALLY G1 | TABLE SCREW STUCK TABLE HOLDER |  | https://i.ibb.co/nMfNwcdf/32b9036c5d18.jpg ¦ https://i.ibb.co/4wbG41pz/21026aa555dd.jpg ¦ https://i.ibb.co/tTGj99Bm/ba2454883359.jpg | Not Raised
155 | 30001351 | GALLEY | GALLY G1 | CART CATCHER SCRATCHED AND DAMAGED KNOB FADED COLOUR AND DAMGED |  | https://i.ibb.co/JRtKQfZd/9f91d5bfd497.jpg ¦ https://i.ibb.co/rqrBKg3/98ef4f1da09d.jpg ¦ https://i.ibb.co/zhBy211v/b9d94ee34eae.jpg ¦ https://i.ibb.co/4ZxTkFdC/31215b3b3112.jpg | Not Raised
156 | SHAREEF | LAVATORY | LAV A | DECAL DISCOLORATION |  | https://i.ibb.co/mrs7zTmp/c52f31d1f3b8.jpg | Not Raised
157 | 30001575 | TEDLAR/SIDEWALL | LAV E | DAMAGED TEDLAR |  | https://i.ibb.co/679pj7JW/032df7288717.jpg | Not Raised
158 | 30001575 | LAVATORY | LAV E | DAMAGED NO SMOKE DECAL |  | https://i.ibb.co/Ngv0bRVP/7b3a9bfc0229.jpg | Not Raised
159 | 30001575 | TEDLAR/SIDEWALL | LAV E | DAMAGED TEDLAR |  | https://i.ibb.co/VpQmpzcB/b17035e70c99.jpg | Not Raised
160 | 30001575 | TEDLAR/SIDEWALL | LAV E | DAMAGED TEDLAR |  | https://i.ibb.co/cXtMZ3RX/bf13822f1c96.jpg | Not Raised
161 | 30001575 | LAVATORY | LAV E | CHIPPED WRITINGS (VACANT/) |  | https://i.ibb.co/sdXx9HRK/d46f55f62cdf.jpg | Not Raised
162 | 30001575 | LAVATORY | LAV E | DAMAGED SMOKE OR ASHTRAY DECAL |  | https://i.ibb.co/QFtCs22P/85fa1d71ba6c.jpg | Not Raised
163 | 30001575 | LAVATORY | LAV E | DOWNWARD DIRT.LAV. DOOR |  | https://i.ibb.co/MyW3tbfZ/39e6f301685c.jpg | Not Raised
164 | FOUAD MOJALLY | LAVATORY | D | LAVATORY FILTER DIRTY |  | https://i.ibb.co/DPvbPskJ/a5eec72114b7.jpg | Not Raised
165 | 30001575 | LAVATORY | LAV E | STOWAGE DOOR DENT |  | https://i.ibb.co/QsTz3dx/b985995513df.jpg | Not Raised
166 | FOUAD MOJALLY | LAVATORY | D | WASHBASINE PAINT DAMAG |  | https://i.ibb.co/LzbTn4hV/ed28575c2735.jpg | Not Raised
167 | 30001575 | LAVATORY | LAV E | STUCK AND SCRATCHED ON THE PAD DRAWER |  | https://i.ibb.co/LDf8wRbn/a7f8059b557a.jpg | Not Raised
168 | FOUAD MOJALLY | LAVATORY | D | LAVATORY MIRROR FADED |  | https://i.ibb.co/7BNyFqw/36d1b037fee1.jpg | Not Raised
169 | 30001575 | LAVATORY | LAV E | TOILET PAPER CASE CHIPPED PAINT |  | https://i.ibb.co/MyJ6LXjg/4dfe707300d1.jpg | Not Raised
170 | FOUAD MOJALLY | LAVATORY | D | LAVATORY DOOR HINGE MISSING SCREW |  | https://i.ibb.co/JW2R228C/eba7ce9f76a5.jpg | Not Raised
171 | 30001575 | LAVATORY | LAV E | DISCOLORED AND DIRTY MIRROR DOWNWARD |  | https://i.ibb.co/8LwVd5wz/f68bc27804d8.jpg | Not Raised
172 | FOUAD MOJALLY | LAVATORY | D | LAVATORY THRESHOLD MISSING SCREW |  | https://i.ibb.co/C3MLn3P8/cff405cd4423.jpg | Not Raised
173 | 30001575 | LAVATORY | LAV E | MISSING SCREW ON THE TOILET SHROUD |  | https://i.ibb.co/tPD4wSSp/9f83d948f23d.jpg | Not Raised
174 | FOUAD MOJALLY | LAVATORY | D | LAVATORY STOWAGE METAL PLATE DAMAGED |  | https://i.ibb.co/M5knjvNc/9510cb84f122.jpg | Not Raised
175 | SHAREEF | GENERAL CABIN | N/A | THE TRIANGLE THING. IN B/C R/H MISSING |  | https://i.ibb.co/60Gz6k29/3328e69c9444.jpg ¦ https://i.ibb.co/0RGT38Jd/8765e338d62f.jpg | Not Raised
176 | FOUAD MOJALLY | LAVATORY | D | LAVATORY STOWAGE CABINIT RUBBER SEAL DAMAGED |  | https://i.ibb.co/dsws3TMg/38f1714bbc08.jpg | Not Raised
177 | 30001575 | LAVATORY | LAV E | DIRTY FILTER |  | https://i.ibb.co/ksmJKrn8/20c46daad85f.jpg | Not Raised
178 | 30001575 | LAVATORY | LAV E | MISSING SCREW ON DOOR HINGE |  | https://i.ibb.co/YHq4VzG/3293f90e6d4d.jpg | Not Raised
179 | 30004221 | GALLEY | AFT GALLEY | OVEN NEEDS PINT |  | https://i.ibb.co/kVWQcjfb/d5f59f11d7bc.jpg | Not Raised
180 | FOUAD MOJALLY | LAVATORY | D | LAVATORY STOWAGE CABINET MISSING SCREW |  | https://i.ibb.co/QvDBjJcn/175cf909d418.jpg | Not Raised
181 | 30004221 | GALLEY | AFT GALLEY | DOOR R2 |  | https://i.ibb.co/m59zvPN7/5e2f6f0140ed.jpg | Not Raised
182 | 30001575 | LAVATORY | LAV E | DISCONNECTED AND DAMAGED CABINET.COMP NEXT TO THE MIRROR AND MISSING RUBBER SEAL |  | https://i.ibb.co/fVwK5hpV/e62262d1273d.jpg | Not Raised
183 | 30004221 | GALLEY | AFT GALLEY | A/C |  | https://i.ibb.co/wZmDGvfR/24aebb6aa2a1.jpg | Not Raised
184 | 30004221 | GALLEY | AFT GALLEY | A/C |  | https://i.ibb.co/tpN2pRKR/b3f0ac5ce5ce.jpg | Not Raised
185 | SHAREEF | GENERAL CABIN | N/A | CLOSET S301 |  | https://i.ibb.co/twP6KBCh/e364faa0a05f.jpg | Not Raised
186 | 30001575 | LAVATORY | LAV E | BABY BASSINET DOWNWARD HOLE |  | https://i.ibb.co/TDnbYnNX/55f63537cf11.jpg | Not Raised
187 | 30004221 | GALLEY | AFT GALLEY | MISSING SCREW 3EA |  | https://i.ibb.co/c7Nny7d/db493548a3d4.jpg | Not Raised
188 | 30004221 | GALLEY | AFT GALLEY | RED LATCH INOP |  | https://i.ibb.co/d4L4K5zx/e8f6ff132221.jpg | Not Raised
189 | 30001575 | LAVATORY | LAV E | BABY BASSINET PROTECTIVE RUBBER MISSING |  | https://i.ibb.co/fGqg14yW/067d1d7809c1.jpg | Not Raised
190 | FOUAD MOJALLY | LAVATORY | D | LAVATORY DOOR HINGE MISSING SCREW + WASHER |  | https://i.ibb.co/HDDtdwV9/68a3f9245b5e.jpg | Not Raised
191 | 30004221 | GALLEY | AFT GALLEY | COVER MISSING |  | https://i.ibb.co/SLQWPjy/a14a98c66c53.jpg | Not Raised
192 | SHAREEF | GENERAL CABIN | N/A | B/C 4LJ |  | https://i.ibb.co/0V6GVQm8/066e0d014357.jpg | Not Raised
193 | 30004221 | GALLEY | AFT GALLEY | MISSING SEALANT |  | https://i.ibb.co/Kc9Fd35s/356548df3adc.jpg | Not Raised
194 | FADULS | LAVATORY | LAV E | BABY BASSINET PROTECTIVE RUBBER MISSING |  | https://i.ibb.co/DDqBgTvg/7b6ecc2d3bbf.jpg | Not Raised
195 | 30004221 | GALLEY | AFT GALLEY | MISSING SEALANT |  | https://i.ibb.co/mCTwHnj3/54624dc96a6d.jpg | Not Raised
196 | FOUAD MOJALLY | LAVATORY | D | SHROUD ASSEMBLY NOT SECURE |  | https://i.ibb.co/dsVD2ZZq/88efe0eccd42.jpg | Not Raised
197 | 30004221 | GALLEY | AFT GALLEY | HINGE BROKEN |  | https://i.ibb.co/k7G8DTb/c9d665999c4c.jpg | Not Raised
198 | 30004221 | GALLEY | AFT GALLEY | DOOR NOT SECURED |  | https://i.ibb.co/5xSg2Szm/6e6f30d0df12.jpg | Not Raised
199 | FOUAD MOJALLY | LAVATORY | D | BABY BASSINT DEEP SCRATCH |  | https://i.ibb.co/XfWwM0Mv/e2ba680f0a0e.jpg | Not Raised
200 | 30004221 | GALLEY | AFT GALLEY | DOOR NOT SECURED |  | https://i.ibb.co/SD7njffh/e529b0472fff.jpg | Not Raised
201 | SHAREEF | LAVATORY | LAV A | PNT | HAVE TO PERSONALLY CHECK. LOOSE AT THE LOWER HINGE. | https://i.ibb.co/Fk5cH7L1/4b758f3867dc.jpg | Not Raised
202 | SHAREEF | LAVATORY | LAV A | PNT |  | https://i.ibb.co/N6F8DCXC/d799e52cc3e6.jpg | Not Raised
203 | SHAREEF | LAVATORY | LAV A | PNT |  | https://i.ibb.co/PvKn3Ttp/de8fc32528dd.jpg | Not Raised
204 | 30004221 | GALLEY | AFT GALLEY | HINGE DAMAGE |  | https://i.ibb.co/0psLW56P/107710d6bcb3.jpg | Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised
Not Raised

## OPEN UP-ACCESS
OPEN UP / ACCESS LOG ✈ HZ-ASD ✈ C2+6Y CHECK |  |  |  |  | 🔧 0 / 0 Re-Installed (0%)
Track every removed item — who removed it, under which WO, and reinstallation status |  |  |  |  | ⚠️ Still Open: 0
Seq. No. | Item Removed (panel / seat / component) | AREA | Relevant WO No. | Removed By | Status | Date Removed | Re-Installed By | Date Re-Installed | Remarks

## DASHBOARD OLD (hidden)
📊 ASD C2+6Y-CHECK — WORK PACKAGE DASHBOARD | [6 empty] | DAY 14/38 | CHECK START → | 2026-07-18
⚠️ WARNING — Completed 26% vs Time 35% · Days Left: 24 · Pace needed: 12.6/day vs avg 8.1/day | [7 empty] | CHECK END → | 2026-08-24
STATUS OVERVIEW | [5 empty] | ⏳ Findings window closes in: 1 day(s)
| Total Items/WOs | 408 | Closed | 105 |  | Completion | 26%
| Open | 303 | In Work (I/W) | 0 |  | Deferred / Hold | 0
PRIORITY ALERTS | [5 empty] | 📅 no upcoming milestone set
| AOG | 19 | Critical | 4 |  | 🚨 AOG/CRIT — STILL OPEN | 23
BY SOURCE — ROUTINE · ENG ORDERS · FINDINGS |  |  |  |  | 📍 Now: PHASE 3 — Mod & Rectification
| ROUTINE TASKS (WP) | 45 / 164 | ENG ORDERS (EOD/AD/EO) | 1 / 23 |  | FINDINGS (AMOS WOs) | 59 / 221
| Completion: 27% |  | Completion: 4% · Window: 43% elapsed |  |  | Completion: 27% · Share: 54% · Window: 42% elapsed
OPEN UP / ACCESS — removed items |  |  |  |  | 🔒 Close-up in 19 day(s) · 0 still open
| ⚠️ STILL OPEN | 0 | PARTIALLY | 0 |  | RE-INSTALLED | 0
| of 0 recorded items |  | need completion before closing |  |  | -
BY CATEGORY
| ACFT GENERAL T/C | 2 / 50 | LAVATORY | 11 / 40 |  | GALLEY | 1 / 47
| Completion: 4% |  | Completion: 28% |  |  | Completion: 2%
| GENERAL CABIN | 15 / 66 | TEDLAR/SIDEWALL | 0 / 1 |  | PAX SEAT | 31 / 67
| Completion: 23% |  | Completion: 0% |  |  | Completion: 46%
| PAX DOORS | 18 / 62 | F/A SEAT | 11 / 33 |  | — | 0 / 0 | 0 | 0
| Completion: 29% |  | Completion: 33% |  |  | —
| FLIGHT DECK | 16 / 42 | ACCESS | 0 / 0
| Completion: 38% |  | -
SPECIALTY
| CABIN | 17 / 192 | SEAT SHOP | 32 / 53 |  | AV/FOMAX | 13 / 39
| Completion: 9% |  | Completion: 60% |  |  | Completion: 33%
| SIDEWALL | 0 / 0 | S/M | 1 / 12 |  | PAINT | 19 / 29
| - |  | Completion: 8% |  |  | Completion: 66%
| JOINT | 8 / 31 | INSP | 10 / 14 |  | A/P | 3 / 17
| Completion: 26% |  | Completion: 71% |  |  | Completion: 18%
PARTS REQUIREMENTS (count of WOs with each status)
| Requested | 176 | Requested – CR | 0 |  | Requested – R | 0
| Pending - Require Evaluation | 0 | N/R (not required) | 0 |  | N/A (Not available) | 0

## FULL PKG (hidden)
Seq | WO / Task | Title | Priority | Est MH | Booked MH | Dur (h) | Progress | ATA | Phase | Day | Plan Cum
1 | 32797253 | 6Y_N/6Y_N YEARS STRUCTURE | N |  |  |  | Not Started | 05 |  | 1 | 0.0396
6 | 200121-01-1 | 200121-01-1 (3) / FWD AVIONIC COMP. ELECTRICAL WIRING | 1 | 1.3 |  |  | Not Started | 24-92 | TC/P, TC/P | 2 | 0.0792
8 | 200121-04-1 | 200121-04-1 (03) / FWD AVIONICS COMPT WIRING DET INSP | 1 | 1.3 |  |  | Not Started | 24-92 | INSPECTION | 3 | 0.1188
9 | 200125-01-1 | 200125-01-1 (2) / LATERAL AVIONIC COMPARTMENT CLEANING | 1 | 1.4 |  |  | Not Started | 24-92 | CLEAN-UP | 4 | 0.1584
11 | 200125-06-1 | 200125-06-1 (2) / LATERAL AVIONICS COMPT INSP | 1 | 10.2 |  |  | Not Started | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP | 5 | 0.1584
12 | 200127-02-1 | 200127-02-1 (2) / REAR AVIONICS COMPT CLEANING | 1 | 1.3 |  |  | Not Started | 24-92 | CLEAN-UP | 6 | 0.198
15 | 200131-01-1 | 200131-01-1 (2) / FWD CARGO COMPARTMENT CLEANING | 1 | 3.3 | 35 | 207.1 | Idle | 24-92 | JOB-SETUP, CLEAN-UP, CLOSE-UP, CLOSE-UP | 7 | 0.2376
16 | 200133-01-1 | 200133-01-1 (2) / FWD CGO UNDER FLOOR BAY (EWIS) CLEAN | 1 | 8.3 | 10 | 205.1 | Idle | 24-92 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP | 8 | 0.2773
18 | 200145-01-1 | 200145-01-1 (2) / ZONE UNDER CABIN FLOOR CLEANING | 1 | 9.9 |  |  | Not Started | 24-92 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP | 9 | 0.3046
19 | 200151-01-1 | 200151-01-1 (01) / AFT CARGO COMPARTMENT EWIS CLEANING | 1 | 78.5 |  |  | Not Started | 24-92 | INSPECTION, INSPECTION, CLEAN-UP, JOB-SETUP, JOB-CLOSEUP, INSPECTION | 10 | 0.332
20 | 200151-03-1 | 200151-03-1 (02) / ACT (EWIS) WIRING CONNECTION INSP | 1 | 13.8 |  |  | Not Started | 24-92 | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP | 11 | 0.3594
22 | 200191-01-1 | 200191-01-1 (02) / AIR COND COMP AND FAIRING CLEANING | 1 | 0.7 |  |  | Not Started | 24-92 | PWR-OFF | 12 | 0.3868
23 | 200211-02-1 | 200211-02-1 (01) / COCKPIT WIRING CLEANING | 1 | 5.7 |  |  | Not Started | 24-92 | PWR-OFF | 13 | 0.4142
25 | 200241-04-1 | 200241-04-1 (2) / CENTER PASSENGER COMPARTMENT INSP | 1 | 3 | 11 | 209.5 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP | 14 | 0.4416
26 | 200251-03-1 | 200251-03-1 (2) / AFT PASSENGER COMPARTMENT INSPECTION | 1 | 2.1 | 9.5 | 208.9 | Idle | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP | 15 | 0.4416
30 | 212100-03-1 | 212100-03-1 (0) / AIR DISTRIBUTION AND RECIRCULATION | 1 | 1 |  |  | Not Started | 21 | --, INSPECTION, -- | 16 | 0.469
32 | 25-11-00-18-0-SVA-001 | 25-11-00-18-0-SVA-001 (04) / FOURTH OCCUPANT SEAT COVERS REPLCMNT | 1 |  | 6.5 | 16.7 | Idle | 25-11 | TC/P | 17 | 0.4863
33 | 25-11-00-18-0-SVA-002 | 25-11-00-18-0-SVA-002 (04) / THIRD OCCUPANT SEAT COVERS R/R | 1 | 2 |  |  | Not Started | 25-11 | TC/P | 18 | 0.5036
34 | 25-22-00-03-0-SVA-002 | 25-22-00-03-0-SVA-002 (02) / CABIN ATTENDANT SEAT COVERS R&R | 1 | 4 |  |  | Not Started | 25-22 | TC/P | 19 | 0.5209
35 | 253000-01-1 | 253000-01-1 (3) / GALLEY ATTACHMENT POINTS INSPECTION | 1 | 0.5 | 44 | 265.1 | Idle | 25-30 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP | 20 | 0.5383
36 | 254000-02-2 | 254000-02-2 (2) / LAVATORIE’S ATTACHMENT POINTS INSP | 1 | 0.2 | 15 | 252.6 | Idle | 25-40 | JOB-SETUP, INSPECTION, JOB-CLOSEUP | 21 | 0.5556
39 | 272100-13-1 | 272100-13-1 (0) / RUDDER MECHANICAL CONTROL | 1 |  |  |  | Not Started | 27 |  | 22 | 0.5729
42 | 282800-08-1 | 282800-08-1 (02) / ADDITIONAL CENTER TANK (ACT) OPC | 1 | 1.1 | 21 | 98.5 | Idle | 28-28 | JOB-SETUP, OPS/LK, JOB-CLOSEUP | 23 | 0.5902
43 | 282800-18-1 | 282800-18-1 (08) / VENT/TRANSFER PIPE SHROUDS FNC | 1 | 1.5 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP | 24 | 0.5902
44 | 323300-01-1 | 323300-01-1 (2) / LG FREE FALL EXTN MECH&CABLE INSP | 1 | 2.2 |  |  | Not Started | 32-33 | JOB-SETUP, JOB-SETUP, TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP | 25 | 0.6094
45 | 323300-04-1 | 323300-04-1 (3) / LG FREE FALL MECH CABLE TENTION CHK | 1 | 0.5 | 2 | 191.5 | Idle | 32-33 | JOB-SETUP, JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP | 26 | 0.6286
46 | 341300-13-1 | 341300-13-1 (6) / ADM ACCURACY FUNCTIONAL TEST | 1 | 0.8 |  |  | Not Started | 34-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP | 27 | 0.6478
50 | 530000-01-1 | 530000-01-1 (4) / FUSELAGE DRAIN VALVE INSP | 1 | 0.7 | 0.2 | 106.4 | Idle | 53-00 | JOB-SETUP, INSPECTION, JOB-CLOSEUP | 28 | 0.667
52 | 531164-01-1 | 531164-01-1 (02) / FUSELAGE FR 15-21 INSPECTION | 1 | 2 | 2.8 | 117.6 | Idle | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP | 29 | 0.6862
53 | 531166-01-2 | 531166-01-2 (2) / FUSELAGE FR 16-20 INSPECTION | 1 | 3.5 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP | 30 | 0.7054
54 | 531171-01-1 | 531171-01-1 (2) / NLG SECONDARY DOOR HINGE SUPPORTS | 1 | 0.6 | 0 | 137.3 | Idle | 53-11 | INSPECTION, INSPECTION | 31 | 0.7246
55 | 531181-01-1 | 531181-01-1 (3) / FUSELAGE INTERNL STRUCT FR15-21 INSP | 1 | 4.9 |  |  | Not Started | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP | 32 | 0.7705
56 | 531189-01-2 | 531189-01-2 (2) / CABIN FLOOR STRUCT FR12 & FR21 INSP | 1 | 9.7 | 72 | 72.5 | Idle | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP | 33 | 0.8164
57 | 531194-01-2 | 531194-01-2 (2) / FLOOR STRUCTURE FR21 TO FR24 INSP | 1 | 39.8 | 10.5 | 166.6 | Idle | 53-11 | JOB-SETUP, JOB-SETUP, INSPECTION, TC/P, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP | 34 | 0.8164
59 | 533136-01-1 | 533136-01-1 (3) / MLG BAY INCLUDING DOOR BAY INSP | 1 | 0.2 | 13.5 | 253 | Idle | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP | 35 | 0.8623
60 | 534132-02-1 | 534132-02-1 (2) / DETAILED INSP OF AFT PASS/CREW DOOR CUTOUT, UPPER CORNERS | 1 |  | 2.2 | 97.1 | Idle | 53-41 |  | 36 | 0.9082
61 | 534135-01-4 | 534135-01-4 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 1 | 3 | 24 | 48.5 | Idle | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP | 37 | 0.9541
62 | 534147-01-1 | 534147-01-1 (2) / CABIN FLOOR STRUC AROUND GALLEY&LAV | 1 | 50 | 104.5 | 192.6 | Idle | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP | 38 | 1
63 | 534148-01-1 | 534148-01-1 (2) / FUSELAGE UNDER BELLY FAIRING INSP | 1 | 6 | 5.3 | 106.6 | Idle | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
66 | 534195-01-2 | 534195-01-2 (01) / CABIN FLOOR STRUCT BELOW AFT ENTERAN | 1 | 4 | 22 | 64.3 | Idle | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
68 | 535101-01-1 | 535101-01-1 (2) / REAR PRESSURE BULKHEAD AFT FACE INSP | 1 | 3.1 | 4.5 | 143.3 | Idle | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
69 | 551020-01-1 | 551020-01-1 (3) / ELEVATOR HNG SUPPORTS AND FTNGS INSP | 1 | 1.6 | 4.7 | 143.6 | Idle | 55-16 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
70 | 552002-01-1 | 552002-01-1 (2) / ELEVATOR HNG SUPPORT & ACT FTG INSP | 1 | 1.6 | 2.7 | 142.6 | Idle | 55-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
71 | 553004-01-1 | 553004-01-1 (2) / VERT STABILIZER ATTACH FITTINGS INSP | 1 | 0.3 | 25 | 114.5 | Idle | 55-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
72 | 553005-01-1 | 553005-01-1 (2) / RUDDER HINGE ARMS AND ACTUATOR INSP | 1 | 0.2 | 2.5 | 161.1 | Idle | 55-30 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
73 | 553006-01-2 | 553006-01-2 (2) / RUDDER HINGE ARM 6 AND 7 INSPECTION | 1 | 0.2 | 2 | 160.1 | Idle | 55-30 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
74 | 554003-01-1 | 554003-01-1 (03) / RUDDER SIDE PANELS INSPECTION | 1 | 1 | 7.5 | 634.2 | Idle | 55-40 | JOB-SETUP, CLEAN-UP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
75 | 554005-01-1 | 554005-01-1 (2) / RUDDER FTNG, ACT. ATTACH FTNG INSP | 1 | 0.2 | 2 | 161.1 | Idle | 55-40 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
76 | 554006-01-1 | 554006-01-1 (2) / RUDDER ATTACH FITTING 6 AND 7 INSP | 1 | 0.2 | 3.5 | 160.1 | Idle | 55-40 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
77 | 554008-01-1 | 554008-01-1 (3) / RUDDER L/H AND R/H SIDE PANELS INSP | 1 | 2.5 | 7.5 | 202.2 | Idle | 55-40 | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
78 | 554009-01-1 | 554009-01-1 (3) / RUDDER SIDE PNL (ELCH TEST) NDT INSP | 1 | 5.5 | 20.5 | 202.2 | Idle | 55-40 | JOB-SETUP, JOB-SETUP, X-RAY / NDT, X-RAY / NDT, JOB-CLOSEUP
79 | 562101-01-1 | 562101-01-1 (3) / CABIN AND DOOR WINDOW PANES INSP | 1 | 5.2 | 80 | 97.1 | Idle | 56-21 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
80 | 571122-01-1 | 571122-01-1 (2) / CENTER WING BOX REAR SPAR INSPECTION | 1 | 2.1 | 9 | 73.2 | Idle | 57-10 | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
81 | 571157-01-1 | 571157-01-1 (3) / CENTER WING BOX UPPER SKIN INSP | 1 | 7.7 |  |  | Not Started | 57-10 | JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-SETUP
84 | 572065-01-1-001 | 572065-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 1 | 0.8 | 135 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
85 | 572065-01-1-002 | 572065-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 1 | 0.8 | 154.7 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
88 | 572161-01-11-001 | 572161-01-11-001 (04) / LH O/WING BTTM ACCSS (RIB13-27) INSP | 1 | 0.5 | 7 | 47.4 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
89 | 572161-01-11-002 | 572161-01-11-002 (04) / RH O/WING BTTM ACCSS (RIB13-27) INSP | 1 | 0.5 | 8.5 | 47.4 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
99 | 575151-03-1 | 575151-03-1 (0) / TRAILING EDGE | 1 | 0.5 | 1 | 135.9 | Idle | 57-51 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
100 | 575167-01-1-001 | 575167-01-1-001 (02) / L/H OUTER WING BTOM SKN PNL NO3 INSP | 1 | 0.2 | 2.5 | 134.5 | Idle | 57-51 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
101 | 575167-01-1-002 | 575167-01-1-002 (02) / R/H OUTER WING BTTM SKIN NO.3 INSP | 1 | 0.2 | 5.8 | 157.9 | Idle | 57-51 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
105 | ZL-125-02-1 | ZL-125-02-1 (4) / LATERAL AVIONIC COMPARTMENT INSP | 1 | 0.8 | 6.5 | 117.5 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
108 | ZL-133-01-1 | ZL-133-01-1 (2) / FWD CARGO COMPAR UNDERFLOOR BAY INSP | 1 | 3.3 | 1 | 134.8 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
109 | ZL-145-01-1 | ZL-145-01-1 (2) / ZONE UNDER CABIN FLOOR INSPECTION | 1 | 7 | 85.5 | 72.6 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
111 | ZL-151-02-3 | ZL-151-02-3 (2) / AFT CARGO COMPARTMENT ZONAL INSP | 1 | 20 | 12 | 72.8 | Idle | 28-11 | JOB-SETUP, INSPECTION, INSPECTION, CLOSE-UP, CLOSE-UP
112 | ZL-153-01-1 | ZL-153-01-1 (03) / AFT CARGO COMPTMENT UNDERFLOOR BAY | 1 | 6.8 | 17 | 227.8 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
114 | ZL-163-01-1 | ZL-163-01-1 (01) / BULK CARGO COMPART UNDERFLOOR INSP | 1 | 2.9 | 0.6 | 135.1 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
117 | ZL-193-01-1 | ZL-193-01-1 (03) / UPPER WING FAIRING SLIDE STOWAGE AREA | 1 | 0.9 | 6.5 | 121.2 | Idle | 05-21 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP
157 | ZL-833-02-1 | ZL-833-02-1 (04) / FWD AND AFT EMERGENCY EXITS INSP | 1 | 1 | 6 | 213.6 | Idle | 05-28 | PRE INSP, PRE INSP, PRE INSP, PRE INSP
158 | 31871161 | A_N (A_N09)/A_N-CHECK | N |  |  |  | Not Started | 20-00
159 | 05-SVA-01 | 05-SVA-01 (00) / EMERGENCY EQUIPMENTS EXPIRY CHECK | 1 | 2.2 | 8 | 232.6 | Idle | 05
160 | 11-11-00-01-0-SVA | 11-11-00-01-0-SVA (02) / INTERIOR PLACARDS CHECK | 1 | 1 |  |  | Not Started | 11-11 | PRE INSP
163 | 212600-11-1 | 212600-11-1 (4) / DEMISTER FLTER&FILTER CARTRIDGE R&R | 1 | 0.2 |  |  | Not Started | 21-26 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
165 | 242000-25-1 | 242000-25-1 (02) / AC GENERATION | 1 | 1 |  |  | Not Started | 53-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
168 | 25-10-00-00-SVA | 25-10-00-00-SVA (00) / COCKPIT CHECK | 1 | 4.3 | 38 | 217.6 | Idle | 25-10
169 | 25-20-00-00-SVA | 25-20-00-00-SVA (01) / GENERAL CABIN DEEP INSP | 1 | 5.8 | 26.5 | 236.9 | Idle | 25-10
170 | 25-21-00-00-SVA | 25-21-00-00-SVA (01) / B/C SEAT DEEP INSP | 1 | 2.3 | 7.5 | 213.7 | Idle | 25-10
171 | 25-21-01-00-SVA | 25-21-01-00-SVA (01) / G/C SEAT DEEP INSP | 1 | 1.5 | 6 | 213.9 | Idle | 25-10
172 | 25-22-00-00-SVA | 25-22-00-00-SVA (01) / CABIN CREW SEAT DEEP INSP | 1 |  | 18 | 229.7 | Idle | 25-10
173 | 25-26-00-08-0-SVA | 25-26-00-08-0-SVA (05) / PASSNGER COMPT CURTAINS REPLACEMENT | 1 | 4 |  |  | Not Started | 25-26 | TC/P
174 | 25-28-00-03-0-SVA-001 | 25-28-00-03-0-SVA-001 (07) / HZ-ASA TO ASG AISLE CARPETS R/R | 1 | 4 |  |  | Not Started | 25-28 | PRE INSP
175 | 25-30-00-03-0-SVA | 25-30-00-03-0-SVA (02) / GALLEY CTL PANELS ELECTRICAL INSP | 1 | 2 |  |  | Not Started | 25-30 | PRE HGR
176 | 25-30-00-13-0-SVA | 25-30-00-13-0-SVA (02) / GALLY & WATER AUTO DRAIN VALVES OPC | 1 | 0.5 |  |  | Not Started | 25-30 | PRE INSP
177 | 25-32-00-00-SVA | 25-32-00-00-SVA (01) / GALLEY CHECK | 1 | 6.9 | 28.5 | 265.6 | Idle | 25-10
178 | 25-40-00-00-SVA | 25-40-00-00-SVA (01) / LAV CHECK | 1 | 7.4 | 3.5 | 206.4 | Idle | 25-10
182 | 253400-01-1. | 253400-01-1. (03) / GALLEY COOLING CLEANING | 1 | 0.3 |  |  | Not Started | 20-00
183 | 253400-02-1 | 253400-02-1 (3) / AIRCHILLER CONDENSER AIR FLTR CLEANING | 1 | 0.4 |  |  | Not Started | 25-34 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, CLEAN-UP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
190 | 262200-02-1 | 262200-02-1 (4) / APU AUTO FIRE EXTINGUISHING OPS | 1 | 0.2 |  |  | Not Started | 26-22 | OPS/LK
191 | 274000-02-1 | 274000-02-1 (4) / THS ACT OPS CHK (CMR) | 1 | 0.2 |  |  | Not Started | 27-44 | OPS/LK
192 | 274451-01-1 | 274451-01-1 (2) / THS BALL SCREW NUT LUBRICATION | 1 | 0.2 |  |  | Not Started | 12-22 | TC/P
193 | 274451-10-1 | 274451-10-1 (5) / THSA LOWER ATTACHM FOR SECOND LOAD | 1 | 10.7 |  |  | Not Started | 27-44 | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
194 | 274451-11-1 | 274451-11-1 (5) / THS UPER ATTACH FOR SECOND LOAD INSP | 1 | 14 |  |  | Not Started | 27-44 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
195 | 275446-01-1-001 | 275446-01-1-001 (03) / L/H FLAP TRACKS LUBRICATION | 1 | 1.8 |  |  | Not Started | 12-22 | TC/P, TC/P
196 | 275446-01-1-002 | 275446-01-1-002 (03) / R/H FLAP TRACKS LUBRICATION | 1 | 1.8 |  |  | Not Started | 12-22 | TC/P, TC/P
197 | 278468-01-1-002 | 278468-01-1-002 (02) / R/H WING SLAT TRACK LUBRICATION | 1 | 2.2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, JOB-CLOSEUP
199 | 281100-05-1 | 281100-05-1 (1) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | 1 | 0.7 |  |  | Not Started | 28-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
200 | 281100-06-1 | 281100-06-1 (3) / OPERATIONAL CHECK OF WATER DRAIN VALVES | 1 | 0.7 |  |  | Not Started | 53-11 | JOB-SETUP, OPS/LK
201 | 282800-01-1 | 282800-01-1 (04) / ACT LEAK MONITOR OPERATIONAL CHECK | 1 | 1.1 |  |  | Not Started | 28-28 | OPS/LK, OPS/LK
202 | 282800-03-1 | 282800-03-1 (03) / ACT WATER DRAIN VALVES OPS CHK | 1 | 0.4 |  |  | Not Started | 12-32 | TC/P, TC/P
206 | 292251-02-1 | 292251-02-1 (2) / RAT ASSEMBLY AND DOOR INSP | 1 | 0.7 |  |  | Not Started | 29-22 | TC/P
207 | 31-63-00-01-SVA-001 | 31-63-00-01-SVA-001 (04) / COCKPIT AND AVIONICS COMPARTMENT AREA AND EQUIPMENT`S CLEANING. | 1 | 2 |  |  | Not Started | 31-63 | CLEAN-UP
209 | 313300-08-1 | 313300-08-1 (3) / DFDR SYSTEM INTERCONNECTION | 1 | 2.5 |  |  | Not Started | 31-33 | JOB-SETUP, TC/P, JOB-CLOSEUP
219 | 383200-01-1 | 383200-01-1 (3) / WASHBASIN FILTER ELEMENT CLEANING | 1 | 0.2 |  |  | Not Started | 38-32 | CLEAN-UP, CLEAN-UP, CLEAN-UP
221 | 52-31-00-01-0-SVA | 52-31-00-01-0-SVA (02) / FWD CARGO COMPARTMENT DOOR PROXIMITY (28WV & 30WV) SWITCH AND TARGET CLEANING | 1 | 1.7 |  |  | Not Started | 52-71-00 | JOB-SETUP, --, --, --
222 | 52-32-00-01-0-SVA | 52-32-00-01-0-SVA (01) / AFT CARGO COMPARTMENT DOOR PROXIMITY SWITCH AND TARGET CLEANING | 1 | 1.3 |  |  | Not Started | 52-71-00 | CLEAN-UP, TC/P, TC/P, --, JOB-CLOSEUP
223 | 525111-06-2 | 525111-06-2 (2) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AND LATCH MECHANISM | 1 |  | 7.8 | 237.6 | Idle | 52-51 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
224 | 527100-02-1 | 527100-02-1 (4) / MAIN ENTRY DR WARNING PRX SW ACTUAT | 1 | 0.3 | 2 | 26.1 | Idle | 12-22 | TC/P, TC/P, TC/P, TC/P, TC/P
225 | 533154-06-1-A | 533154-06-1-A (03) / MLG HINGE FITTING KEEL BEAM INSP | 1 | 17.5 | 4 | 251 | Idle | 53-31 | JOB-SETUP, JOB-SETUP, --, --, --, --, INSPECTION, --, INSPECTION, --, --, --
226 | 31675402 | EOD-320-53-00042-R00/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL BE | 1 | 30.3 |  |  | Not Started | 53
228 | 72-00-00-01-0-SVA-001 | 72-00-00-01-0-SVA-001 (01) / NO. 1 ENGINE COMPRESSOR WASH | 1 | 13 |  |  | Not Started | 72-00 | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
229 | 72-00-00-01-0-SVA-002 | 72-00-00-01-0-SVA-002 (01) / NO. 2 ENGINE COMPRESSOR WASH | 1 | 13 |  |  | Not Started | 72-00 | JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
230 | 801110-C3-1-001 | 801110-C3-1-001 (01) / NO.1 ENGINE STARTER REPLENISHMENT | 1 | 0.7 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, JOB-CLOSEUP
231 | 801110-C3-1-002 | 801110-C3-1-002 (01) / NO.2 ENGINE STARTER REPLENISHMENT | 1 | 0.7 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, JOB-CLOSEUP
233 | 31574335 | C_N (C_N02)/C-CHECK | N |  |  |  | Not Started | 20-00
234 | 05-00-00-05-SVA | 05-00-00-05-SVA (03) / FINAL PRODUCT QUALITY INSPECTION | 1 | 1 |  |  | Not Started | 05-00 | ACFT RELEASE, ACFT RELEASE
235 | 08-10-00-01-0-A | 08-10-00-01-0-A (02) / WIGHT & BALANCE | 1 | 65 |  |  | Not Started | 08-10 | WT&BAL
245 | 213100-01-1 | 213100-01-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.2 |  |  | Not Started | 21-31 | OPS/LK
246 | 213100-02-1 | 213100-02-1 (4) / CABIN PRESSURE SYS MANUAL MODE OPC | 1 | 0.2 |  |  | Not Started | 21-31 | OPS/LK
248 | 213100-04-1 | 213100-04-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
250 | 215000-08-1 | 215000-08-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 1 | 0.5 |  |  | Not Started | 21 | --, INSPECTION, --
252 | 215222-01-1 | 215222-01-1 (3) / AIR CYCLE MACHINE PLENUM INSP | 1 | 1.8 | 12.5 | 24.3 | Idle | 21-52 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
253 | 215500-01-1 | 215500-01-1 (3) / EMERGENCY RAM AIR INLET SYSTEM OPC | 1 | 0.2 |  |  | Not Started | 21-55 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
254 | 215500-02-1 | 215500-02-1 (4) / EMERGENCY RAM AIR INLET AND FLOW OPC | 1 | 0.2 |  |  | Not Started | 21-55 | OPS/LK
255 | 216242-01-1 | 216242-01-1 (5) / TRIM AIR CHECK VALVES FLAPPERS INSP | 1 | 2.6 |  |  | Not Started | 21-63 | JOB-SETUP, TC/P, TC/P, TC/P, OPS/LK
272 | 25-11-00-03-0-SVA-001 | 25-11-00-03-0-SVA-001 (02) / THIRD OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 1 | 0.5 |  |  | Not Started | 25-11
273 | 25-11-00-08-0-SVA | 25-11-00-08-0-SVA (03) / CAPTAIN AND F/O SEATS BOTTOM REPLACMENT | 1 | 1 |  |  | Not Started | 25-11 | INSPECTION, --
274 | 25-11-00-09-0-SVA | 25-11-00-09-0-SVA (04) / CAPTAIN & F/O SEATS COVERS REPLACMENT | 1 | 4 |  |  | Not Started | 25-11 | TC/P, TC/P
275 | 25-11-00-17-0-SVA-002 | 25-11-00-17-0-SVA-002 (03) / FOURTH OCCUPANT SEAT BOTTOM CUSHION REPLACMENT | 1 | 0.5 |  |  | Not Started | 25-11 | PRE INSP, --
276 | 25-28-00-04-0-SVA-001 | 25-28-00-04-0-SVA-001 (03) / A320(HZ-ASA TO ASG) CARPETS&MATS R/R | 1 | 48 |  |  | Not Started | 25-28 | TC/P, TC/P, TC/P, TC/P
277 | 25-28-00-04-0-SVA-002 | 25-28-00-04-0-SVA-002 (03) / COCKPIT COMPARTMENT CARPETS REPLCMNT | 1 | 6 |  |  | Not Started | 25-28 | TC/P
278 | 25-SVA-01 | 25-SVA-01 (01) / COCKPIT CHECK | 1 | 3.3 | 2 | 236.8 | Idle | 25
279 | 25-SVA-02 | 25-SVA-02 (01) / GENERAL CABIN ITEMS C-CHK | 1 | 11.7 | 3 | 237.2 | Idle | 25
280 | 25-SVA-03 | 25-SVA-03 (01) / B/C SEAT REFRESH | 1 | 5.2 | 7 | 206.3 | Idle | 25
281 | 25-SVA-04 | 25-SVA-04 (01) / B/C SEAT DEEP REFRESH | 1 | 3 | 9 | 182.2 | Idle | 25
282 | 25-SVA-05 | 25-SVA-05 (01) / G/C SEAT REFRESH | 1 | 1.8 | 14.5 | 220.3 | Idle | 25
283 | 25-SVA-06 | 25-SVA-06 (01) / GALLEY REFRESH | 1 | 2 | 11.5 | 209.2 | Idle | 25
284 | 25-SVA-07 | 25-SVA-07 (01) / LAV REFRESH | 1 | 2 | 4.5 | 206.4 | Idle | 25
285 | 25-SVA-08 | 25-SVA-08 (01) / CABIN CREW SEAT DEEP INSP | 1 | 3 |  |  | Not Started | 25
286 | 25-SVA-09 | 25-SVA-09 (01) / B/C PAX SEATS CUSHION R/R | 1 | 0.5 |  |  | Not Started | 25
287 | 25-SVA-10 | 25-SVA-10 (02) / G/C PAX SEATS CUSHION R/R | 1 | 0.5 | 152 | 75.2 | Idle | 25
288 | 252100-01-0-SVA-002 | 252100-01-0-SVA-002 (02) / A320 AIRCRAFT HZ-ASA THRU HZ-ASG PASSENGER SEATS COVERS R/R | 1 | 38 | 253.5 | 241.6 | Idle | 25-21 | TC/P, TC/P
289 | 252100-01-1 | 252100-01-1 (4) / PAX SEAT ATTACH TO FLOOR&STRUC INSP | 1 | 2 | 19.5 | 210 | Idle | 25-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
290 | 2521000103-001 | 2521000103-001 (05) / PASS COMPARTMENT SEAT BELTS CLEANING B/C | 1 | 3 | 2 | 215.5 | Idle | 25-21 | TC/P, TC/P
291 | 2521000103-002 | 2521000103-002 (06) / PASS COMPARTMENT SEAT BELTS CLEANING G/C | 1 | 7 | 6 | 216.5 | Idle | 25-21 | TC/P, TC/P, TC/P, TC/P
292 | 252200-01-1 | 252200-01-1 (4) / CABIN ATTED SEAT ATTACHMENTS INSP | 1 | 0.7 |  |  | Not Started | 25-22 | --, PRE INSP, --
295 | 255000-08-1 | 255000-08-1 (02) / AFT CGO XZ & YZ ENDSTOPS INSP | 1 | 38.5 | 4.5 | 14 | Idle | 25-50 | INSPECTION
296 | 255000-10-1 | 255000-10-1 (3) / LOWER DECK CARGO LOADING | 1 | 3.6 | 9.6 | 85.8 | Idle | 25-50 | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P
298 | 256535-04-1 | 256535-04-1 (00) / EXTERNAL FIX ELT ANTENNA INSPECTION | 1 | 0.2 | 10 | 152.7 | Idle | 25 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
299 | 256652-01-1-SVA | 256652-01-1-SVA (01) / LIFE VEST RESTORATION PERIODIC CHECK FOR EXPIRATION | 1 | 0.5 | 46.5 | 265.1 | Idle | 25-11 | JOB-SETUP, INSPECTION, --, JOB-CLOSEUP
300 | 261500-03-1 | 261500-03-1 (3) / AVIONICS COMPARTMENT SMOKE DETECTION CLEAN TUBES | 1 | 0.2 | 2 | 26.1 | Idle | 26-15 | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, JOB-CLOSEUP
305 | 262100-05-1 | 262100-05-1 (6) / ENG FIRE EXTINGUISHING FIRE CTL OPC | 1 | 1.1 |  |  | Not Started | 26-21 | OPS/LK
311 | 262300-03-1 | 262300-03-1 (05) / FIRE EXTINGUISHING LINES LEAKAGE CHK | 1 | 4.4 |  |  | Not Started | 26-23 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
316 | 271400-03-1-001 | 271400-03-1-001 (03) / L/H AILERON SERVO CONTROL FLUID CHK | 1 | 0.7 | 12.5 | 192.8 | Idle | 27-14 | PRE HGR, PRE HGR, PRE HGR
317 | 271400-03-1-002 | 271400-03-1-002 (03) / R/H AILERON SERVO CONTROL FLUID CHK | 1 | 0.7 | 16 | 193 | Idle | 27-14 | PRE HGR, PRE HGR, PRE HGR
318 | 272100-02-1 | 272100-02-1 (03) / RUDDER CONTROL CABLES INSP | 1 | 75.5 |  |  | Not Started | 27-21 | TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION
319 | 272100-04-1 | 272100-04-1 (02) / RUDDER MECHANICAL CONTROL CHK | 1 | 0.2 | 21 | 73.5 | Idle | 27-26 | JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP
320 | 272100-05-1 | 272100-05-1 (02) / RUDDER CENTERING SPRING-ROD | 1 | 0.9 | 16 | 280.6 | Idle | 27-21 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
322 | 272100-12-1 | 272100-12-1 (00) / LUBRICATION OF RUDDER CONTROL CABLES IN REAR PART (ZONE 310). | 1 | 1.3 |  |  | Not Started | 27-21 | JOB-SETUP, --, --
323 | 272145-01-1 | 272145-01-1 (02) / RUDDER CABLE TENTION REGULATOR CHECK | 1 | 0.7 |  |  | Not Started | 27-21 | TC/P
326 | 273400-03-1 | 273400-03-1 (3) / ELEVATOR SERVO CONTROL FLUID-RESERVE | 1 | 1 |  |  | Not Started | 27-34 | JOB-SETUP, TC/P, JOB-CLOSEUP
328 | 274000-24-1 | 274000-24-1 (1) / OPERATIONAL CHECK OF THS ACTUATOR OVERRIDE MECHANISM. | 1 | 0.5 |  |  | Not Started | 27-44 | TC/P
329 | 274142-01-1 | 274142-01-1 (3) / THS TRIM CTL TENSION REG CABLE CHK | 1 | 0.1 |  |  | Not Started | 27-41 | JOB-SETUP, TC/P, JOB-CLOSEUP
330 | 274400-03-1 | 274400-03-1 (3) / THS ACTUATOR NO-BACK DEVICE OPC | 1 | 0.7 |  |  | Not Started | 27-44 | OPS/LK, OPS/LK
331 | 274451-04-1 | 274451-04-1 (3) / THS ACT NUT, SCREW & CLAW STOPS | 1 | 0.3 |  |  | Not Started | 27-44 | INSPECTION, INSPECTION
332 | 274451-05-1 | 274451-05-1 (4) / THSA UPPER & LOWER ATTACHMENTS INSP | 1 | 0.3 |  |  | Not Started | 27-44 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
334 | 274451-08-1 | 274451-08-1 (3) / THS BALL SCREW SHAFT INTEGRITY FNC | 1 | 0.9 |  |  | Not Started | 27-44 | OPS/LK, OPS/LK
335 | 274451-09-1 | 274451-09-1 (4) / THS ACTUATOR GEARBOX SERVICING | 1 | 1.1 |  |  | Not Started | 27-44 | TC/P, TC/P
346 | 275446-02-1-001 | 275446-02-1-001 (03) / L/H FLAP TRACKS, ROLLERS BERNG INSP | 1 | 0.7 | 6.2 | 134.9 | Idle | 27-54 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
347 | 275446-02-1-002 | 275446-02-1-002 (03) / R/H FLAP TRACKS, ROLLERS BERNG INSP | 1 | 0.7 | 10.8 | 157.9 | Idle | 27-54 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
348 | 275449-06-1-001 | 275449-06-1-001 (03) / L/H FLAP ACTUATOR ASSEMBLIES SVS | 1 | 17.6 |  |  | Not Started | 12-13 | TC/P
349 | 275449-06-1-002 | 275449-06-1-002 (03) / R/H FLAP ACTUATOR ASSEMBLIES | 1 | 17.6 |  |  | Not Started | 12-13 | TC/P
350 | 275451-01-1 | 275451-01-1 (2) / FLAP PCU GEARBOX OIL REPLENISHMENT | 1 | 0.2 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
353 | 278100-03-1 | 278100-03-1 (3) / SLAT SYSTEM WING TIP BRAKE OPC | 1 | 0.4 |  |  | Not Started | 27-81 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
356 | 278400-01-1-001 | 278400-01-1-001 (02) / L/H WING SLAT TRACK INSPECTION | 1 | 1.4 | 1.5 | 134.3 | Idle | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
357 | 278400-01-1-002 | 278400-01-1-002 (02) / R/H WING SLAT TRACK INSPECTION | 1 | 1.4 | 1.3 | 135.6 | Idle | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
358 | 278451-01-1 | 278451-01-1 (2) / SLAT PCU GEARBOX OIL REPLENISHMENT | 1 | 0.2 |  |  | Not Started | 12-13 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
359 | 278468-02-1-001 | 278468-02-1-001 (05) / L/H SLAT TRACKS INSPECTION | 1 | 2 | 2.5 | 134.5 | Idle | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
360 | 278468-02-1-002 | 278468-02-1-002 (04) / R/H SLAT TRACKS INSPECTION | 1 | 2 | 3.6 | 135.5 | Idle | 27-84 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
363 | 281600-01-1-001 | 281600-01-1-001 (02) / NO.1 ENGINE FUEL RECIRC VLV OPS CHK | 1 | 0.2 | 16 | 277.7 | Idle | 28-16 | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP
364 | 281600-01-1-002 | 281600-01-1-002 (02) / NO.2 ENGINE FUEL RECIRC VLV OPS CHK | 1 | 0.2 | 16 | 277.7 | Idle | 28-16 | JOB-SETUP, OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP
365 | 281800-01-1 | 281800-01-1 (2) / CTR TANK VAPOR SEAL DRAIN SYS FNC CK | 1 | 4.4 |  |  | Not Started | 28-18 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
366 | 282100-02-1 | 282100-02-1 (03) / CTR TANK PUMP CANISTER VALVES OPC | 1 | 0.2 |  |  | Not Started | 28-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
372 | 282800-04-1 | 282800-04-1 (02) / INDIVIDUAL MOTR TRX VLV OPC | 1 | 1.3 |  |  | Not Started | 28-28 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
374 | 282800-06-1 | 282800-06-1 (02) / (ACT) AIR INLET FILTER REPLACEMENT | 1 | 0.6 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
375 | 282800-07-1 | 282800-07-1 (02) / ACT TRANSFER SYSTEM FNC | 1 | 0.5 |  |  | Not Started | 28-28 | JOB-SETUP, TC/P, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
376 | 291000-04-1 | 291000-04-1 (3) / MAIN HYDRAULIC POWER FUNCTIONAL CHK | 1 | 0.2 |  |  | Not Started | 29-23 | OPS/LK
379 | 291000-10-1 | 291000-10-1 (03) / HYDRAULIC FIRE SHUTOFF VALVES FUNCTIONAL CHECK | 1 | 0.5 |  |  | Not Started | 29-10 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
381 | 291000-20-1 | 291000-20-1 (2) / ENG DRIVEN PUMP (EDP) DE-PRESS OPS | 1 | 0.6 |  |  | Not Started | 29-10 | OPS/LK
382 | 291000-25-1 | 291000-25-1 (1) / MAIN AND AUXILIARY HYDRAULIC POWER | 1 | 0.6 |  |  | Not Started | 29 | OPS/LK
383 | 291000-26-1 | 291000-26-1 (01) / MAIN AND AUXILIARY HYDRAULIC POWER | 1 | 0.6 |  |  | Not Started | 29 | JOB-SETUP, --, JOB-CLOSEUP
384 | 291900-02-1 | 291900-02-1 (3) / INTERNAL LEAK RATE BLUE HYD FUN CHK | 1 | 0.7 |  |  | Not Started | 29-10 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
385 | 293400-01-1 | 293400-01-1 (2) / RESERVOIR PRESSURIZATION INDICATING | 1 | 0.2 |  |  | Not Started | 29-34 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
390 | 313300-07-1 | 313300-07-1 (02) / DFDR SYSTEM INTERCONNECTION | 1 | 1.3 |  |  | Not Started | 31-33 | OPS/LK
398 | 321127-01-1-001 | 321127-01-1-001 (04) / LH MLG TORQUE LINK EXCESIVE PLAY CHK | 1 | 38.7 |  |  | Not Started | 32-11 | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
399 | 321127-01-1-002 | 321127-01-1-002 (04) / RH MLG TORQUE LINK EXCESIVE PLAY CHK | 1 | 38.7 |  |  | Not Started | 32-11 | JOB-SETUP, TC/P, TC/P, TC/P, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
402 | 323100-04-1 | 323100-04-1 (4) / (LG) SAFETY VALVE CLOSING OPS CHK | 1 | 0.9 |  |  | Not Started | 32-31 | OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-SETUP, TC/P
404 | 323100-06-1 | 323100-06-1 (3) / GEAR NOT DOWN WARNINGS BITE CHK | 1 | 0.2 |  |  | Not Started | 32-61 | OPS/LK
405 | 323105-04-1 | 323105-04-1 (4) / NORMAL EXTENSION AND RETRACTION | 1 | 2.2 |  |  | Not Started | 32-31 | OPS/LK
406 | 323105-05-1 | 323105-05-1 (3) / NORMAL EXTENSION AND RETRACTION | 1 | 1.1 |  |  | Not Started | 32-31 | OPS/LK
407 | 323173-00-SVA | 323173-00-SVA (01) / MLG & NLG PROXIMITY SENS. CLN & NLG CLEARANCE CHK | 1 | 4 | 17 | 163.6 | Idle | 32-31 | JOB-SETUP, TC/P, TC/P, CLOSE-UP
408 | 324000-14-1 | 324000-14-1 (2) / NORML BRAKE MODE AUTO REACT FUN CHK | 1 | 10.1 |  |  | Not Started | 32-42 | OPS/LK
409 | 324000-17-1 | 324000-17-1 (5) / BRAKE ACCOMULATOR SYSTEM FUN CHK | 1 | 2.2 |  |  | Not Started | 32-41 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
410 | 324300-01-3 | 324300-01-3 (3) / ALTERNATE BRAKING SYS OPS CHK | 1 | 1.3 |  |  | Not Started | 32-43 | OPS/LK
425 | 351000-01-1 | 351000-01-1 (3) / FULL FACE/QUICK OXYGEN MASKS OPC | 1 | 0.2 |  |  | Not Started | 35-12 | OPS/LK
427 | 352000-02-1 | 352000-02-1 (3) / PAX OXYGEN SYSTEM MASK RELEASE FNC | 1 | 2 | 45 | 238.2 | Idle | 35-23 | JOB-SETUP, TC/P, TC/P, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
428 | 352142-01-1-SVA | 352142-01-1-SVA (01) / VALIDITY CHECK OF CHEMICAL OXYGEN GENERATORS | 1 | 2.4 | 48.5 | 241.6 | Idle | 35-21 | JOB-SETUP, --, --, JOB-CLOSEUP, --
431 | 361100-01-1-001 | 361100-01-1-001 (02) / NO. 1 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 1 | 0.4 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
432 | 361100-01-1-002 | 361100-01-1-002 (02) / NO. 2 ENGINE OVERPRESS VALVE FUNCTIONAL TEST | 1 | 0.4 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
433 | 361100-SVA-01 | 361100-SVA-01 (01) / ENGINE BLEED AIR SUPPLY SYSTEM - HEALTH CHECK TEST OF TEMPERATURE CONT | 1 | 14.2 |  |  | Not Started | 36 | JOB-SETUP, OPS/LK, OPS/LK, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
434 | 361148-01-1-001 | 361148-01-1-001 (04) / L/H WING APU BLEED AIR DUCT LEAK CHK | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
435 | 361148-01-1-002 | 361148-01-1-002 (04) / R/H WING APU BLEED AIR DUCT LEAK CHK | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
438 | 361251-01-3 | 361251-01-3 (03) / APU BLEED CHECK VALVE INSP | 1 | 0.7 | 2.8 | 155.3 | Idle | 36-12 | JOB-SETUP, JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, OPS/LK, JOB-CLOSEUP
439 | 383100-07-1 | 383100-07-1 (07) / VACUUM TOILET SYSTEM CLEANING | 1 | 10 |  |  | Not Started | 38-31 | CLEAN-UP
440 | 384142-01-1 | 384142-01-1 (3) / AIR FILTER CARTRIDGE REPLACEMENT | 1 | 0.4 |  |  | Not Started | 38-41 | JOB-SETUP, CLEAN-UP, TC/P, OPS/LK, OPS/LK, JOB-CLOSEUP
442 | 384242-01-1 | 384242-01-1 (01) / WATER COMPRESSOR AIR FILTER R&R | 1 | 0.7 |  |  | Not Started | 38-42 | TC/P, OPS/LK
446 | 521000-01-SVA | 521000-01-SVA (01) / FWD LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 1 | 22.5 | 43.1 | Idle | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
447 | 521000-02-1 | 521000-02-1 (3) / PASSENGER/CREW DOOR SUSPENSION CHK | 1 | 0.5 | 9 | 45.6 | Idle | 52-10 | JOB-SETUP, JOB-SETUP, INSPECTION, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
448 | 521000-02-SVA | 521000-02-SVA (01) / FWD RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 1 | 20.5 | 43.6 | Idle | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
449 | 521000-03-SVA | 521000-03-SVA (01) / AFT LH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
450 | 521000-04-1-001 | 521000-04-1-001 (03) / L/H FWD PAX/CREW DOOR INTEGRITY CHK | 1 | 1 | 8.5 | 20.1 | Idle | 52-10 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
451 | 521000-04-1-002 | 521000-04-1-002 (03) / R/H FWD PAX/CREW DOOR INTEGRITY CHK | 1 | 1 | 4.5 | 12.6 | Idle | 52-10 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
452 | 521000-04-1-003 | 521000-04-1-003 (03) / L/H AFT PAX/CREW DOOR INTEGRITY CHK | 1 | 1 | 5.5 | 20.1 | Idle | 52-10 | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
453 | 521000-04-1-004 | 521000-04-1-004 (03) / R/H AFT PAX/CREW DOOR INTEGRITY CHK | 1 | 1 | 4.5 | 20.1 | Idle | 52-10 | INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, INSPECTION, JOB-CLOSEUP
454 | 521000-04-SVA | 521000-04-SVA (01) / AFT RH PASSENGER/CREW DOOR DAMPER AND EMERGENCY OPERATION CYLINDER DIAPHRAGM REPLACEMENT | 1 | 5 |  |  | Not Started | 52-10 | JOB-SETUP, TC/P, INSPECTION, JOB-CLOSEUP
457 | 521000-07-1-001 | 521000-07-1-001 (4) / FWRD L/H&R/H PASS/CREW DOR AJAST CK | 1 | 0.4 | 7.5 | 93.4 | Idle | 52-10 | OPS/LK, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
458 | 521000-07-1-002 | 521000-07-1-002 (5) / AFT PASS/CREW DOORS ADJUSTMENT CHK | 1 | 0.4 | 11.5 | 93.3 | Idle | 52-10 | OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, OPS/LK, OPS/LK
462 | 521000-11-1 | 521000-11-1 (6) / PASS/CREW DOORS STRIKERS MECHNSM OP | 1 | 1.5 |  |  | Not Started | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK, OPS/LK
465 | 521121-02-1 | 521121-02-1 (4) / PASSENGER/CREW DOORS LUBRICATION | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P, TC/P, TC/P, TC/P
466 | 522100-01-1 | 522100-01-1 (02) / PAX EMER EXIT OPENING FROM INSIDE | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
467 | 522100-02-5 | 522100-02-5 (04) / PASSENGER COMP EMERGENCY EXIT FNC | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
468 | 522100-07-5 | 522100-07-5 (03) / EMERGENCY EXIT HATCH OPERATION | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
469 | 522100-08-1 | 522100-08-1 (02) / PASSENGER COMPT EMERGENCY EXIT OPC | 1 | 3.5 |  |  | Not Started | 52-21 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
470 | 523100-01-1 | 523100-01-1 (3) / FORWARD CARGO COMPARTMENT DOOR FNC | 1 | 0.4 |  |  | Not Started | 52-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
471 | 523200-01-1 | 523200-01-1 (3) / AFT CARGO COMPARTMENT DOOR FNC | 1 | 0.4 |  |  | Not Started | 52-32 | JOB-SETUP, OPS/LK, JOB-CLOSEUP, JOB-CLOSEUP
472 | 524100-02-1 | 524100-02-1 (2) / AVNICS COMPT DOORS HNDLE LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | TC/P
479 | 527300-01-1 | 527300-01-1 (04) / EMERGENCY ESCAPE SLIDE WARNING SYS | 1 | 0.2 |  |  | Not Started | 52-73 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
481 | 531151-02-1 | 531151-02-1 (1) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 16 AND FRAME 20, LH/RH. | 1 |  | 2 | 97.1 | Idle | 53-11
483 | 531178-02-1 | 531178-02-1 (3) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF RETAINERS. | 1 |  | 11 | 25.5 | Idle | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
484 | 531182-02-1 | 531182-02-1 (1) / DET INSP OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 & FR8 FRAMES, INTERNAL STR FROM FR4 TO FR8 LH/RH | 1 | 2.3 |  |  | Not Started | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
485 | 531900-03-1 | 531900-03-1 (2) / FUSLGE SHEL PSTN TYP DRAIN VLV OPC | 1 | 1.3 |  |  | Not Started | 53-19 | OPS/LK
490 | 533900-01-1 | 533900-01-1 (2) / RUBBER FLAP DRAIN VLV OPC | 1 | 0.2 |  |  | Not Started | 53-39 | OPS/LK
491 | 534134-02-1 | 534134-02-1 (1) / DETAILED INSP. OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME 66 AND 68, LH/RH. | 1 |  | 2.7 | 97.1 | Idle | 53-41
492 | 534144-01-1 | 534144-01-1 (02) / FUSELAG INTERNAL STRUCT FR65-70 INSP | 1 | 1.5 | 3 | 142.7 | Idle | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
495 | 535900-01-1 | 535900-01-1 (3) / FUSELAGE DRAINAGE | 1 | 0.1 |  |  | Not Started | 53-59 | OPS/LK
496 | 535900-02-1 | 535900-02-1 (2) / BULK CARGO COMPARTMENT DOOR RUBBER FLAP DRAIN VALVE OPC | 1 | 0.2 |  |  | Not Started | 53-59 | OPS/LK
501 | 545000-05-1-001 | 545000-05-1-001 (01) / L/H PYLON FIRE SEALS INSP | 1 | 1.6 | 4.5 | 206.3 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
502 | 545000-05-1-002 | 545000-05-1-002 (01) / R/H PYLON FIRE SEALS INSP | 1 | 1.6 | 5.3 | 206.9 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
507 | 552600-01-1 | 552600-01-1 (1) / FUNCTIONAL CHECK OF ELEVATOR HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE FREE PLAY AND CONDITION. | 1 | 1.2 | 84 | 99.6 | Idle | 20-00
508 | 553600-01-1 | 553600-01-1 (06) / FUNCTIONAL CHECK OF RUDDER HINGE LINE BEARINGS AND ATTACHMENTS FOR EXCESSIVE PLAY AND CONDITION | 1 | 5.8 |  |  | Not Started | 55-47 | TC/P
509 | 561200-02-1 | 561200-02-1 (2) / COCKPIT SLIDING WINDOW LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | TC/P
510 | 572178-01-1-001 | 572178-01-1-001 (03) / L/H OUTER WING, TOP SKIN INSP | 1 | 1 | 1.5 | 134.6 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
511 | 572178-01-1-002 | 572178-01-1-002 (03) / R/H OUTER WING, TOP SKIN INSP | 1 | 1 | 1.2 | 135.7 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
512 | 572179-01-1-001 | 572179-01-1-001 (03) / L/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 1 | 1 | 3 | 134.4 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
513 | 572179-01-1-002 | 572179-01-1-002 (03) / R/H OUTER WING TOP SKIN RIB 11 TO 27 INSP | 1 | 1 | 1.5 | 180.7 | Idle | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
525 | 711300-C1-1-001 | 711300-C1-1-001 (02) / NO. 1 ENGINE FAN COWL LATCH TENSION | 1 | 1.2 |  |  | Not Started | 71-13 | OPS/LK, OPS/LK
526 | 711300-C1-1-002 | 711300-C1-1-002 (02) / NO. 2 ENGINE FAN COWL LATCH TENSION | 1 | 1.2 |  |  | Not Started | 71-13 | OPS/LK, OPS/LK
537 | 712213-01-1-001 | 712213-01-1-001 (02) / NO. 1 ENGINE AFT MOUNT PINS INSP | 1 | 2.2 | 24 | 46.7 | Idle | 71-22 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
538 | 712213-01-1-002 | 712213-01-1-002 (02) / NO. 2 ENGINE AFT MOUNT PINS INSP | 1 | 2.2 | 24 | 61.6 | Idle | 71-22 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
541 | 72-00-00-27-0-SVA-001 | 72-00-00-27-0-SVA-001 (01) / DEPERSERVATION OF ENG# 1 POST C-CHK | 1 | 2 |  |  | Not Started | 72 | OPS/LK
542 | 72-00-00-27-0-SVA-002 | 72-00-00-27-0-SVA-002 (01) / DEPERSERVATION OF ENG# 2 POST C-CHK | 1 | 2 |  |  | Not Started | 72 | OPS/LK
543 | 783000-C2-1-001 | 783000-C2-1-001 (02) / NO.1 ENGINE BLOCKER DOOR SEALS INSP | 1 | 0.2 | 6.2 | 85.6 | Idle | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
544 | 783000-C2-1-002 | 783000-C2-1-002 (02) / NO.2 ENGINE BLOCKER DOOR SEALS INSP | 1 | 0.2 | 12.2 | 88 | Idle | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
549 | 783100-C7-1-001 | 783100-C7-1-001 (03) / NO.1 ENG PRIMARY LATCH MECHNISM INSP | 1 | 0.1 | 6.2 | 85.6 | Idle | 78-31 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
550 | 783100-C7-1-002 | 783100-C7-1-002 (03) / NO.2 ENG PRIMARY LATCH MECHNISM INSP | 1 | 0.1 | 13.2 | 85.5 | Idle | 78-31 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
551 | 783200-01-1-001 | 783200-01-1-001 (04) / NO. 1 ENG “C” DUCT HINGE FITTINGS INSP | 1 | 0.8 | 8 | 110.2 | Idle | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
552 | 783200-01-1-002 | 783200-01-1-002 (04) / NO. 2 ENG “C” DUCT HINGE FITTINGS INSP | 1 | 0.8 | 7.8 | 110.7 | Idle | 78-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
553 | 783209-01-1 | 783209-01-1 (02) / DETAILED INSPECTION OF THRUST REVERSER V-GROOVE ADAPTER RING. | 1 | 3 | 1 | 207.1 | Idle | 78-32
582 | 272100-08-1 | 272100-08-1 (02) / RUDDER MECHANICAL CNTROL LUBRICATION | 1 | 0.2 |  |  | Not Started | 27-21 | TC/P
583 | 274100-03-1 | 274100-03-1 (3) / THS MECHANICAL CONTROL LUBRICATION | 1 | 0.4 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, JOB-CLOSEUP
584 | 282200-04-1 | 282200-04-1 (1) / APU FUEL PUMP SYSTEM AND FUEL FEED LINE | 1 | 2.5 |  |  | Not Started | 28-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
585 | 282400-01-1-001 | 282400-01-1-001 (05) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC | 1 | 0.5 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP
586 | 282400-01-1-002 | 282400-01-1-002 (06) / NO.2 ENG LOW PRESS SHUT OFF VALVE OPC | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, OPS/LK, JOB-CLOSEUP
587 | 282400-02-1-001 | 282400-02-1-001 (04) / NO. 1 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, JOB-CLOSEUP
588 | 282400-02-1-002 | 282400-02-1-002 (04) / NO. 2 ENG LOW PRESS SHUT OFF VALVE OPC BY INDIVIDUAL MOTORS | 1 | 0.7 |  |  | Not Started | 28-24 | PRE HGR, PRE HGR, JOB-CLOSEUP
589 | 344200-02-2 | 344200-02-2 (01) / RADIO ALTIMETER | 1 | 6.2 | 1 | 12.3 | Idle | 34-42 | JOB-SETUP, TC/P, JOB-CLOSEUP, JOB-CLOSEUP
590 | 344200-04-1 | 344200-04-1 (01) / RADIO ALTIMETER | 1 | 10.2 |  |  | Not Started | 34-42 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
591 | 38-10-00-SVA | 38-10-00-SVA (01) / DECALCIFICATION OF THE POTABLE WATER TANK AND DISTRIBUTION SYSTEM | 1 | 10 |  |  | Not Started | 38-10 | JOB-SETUP, --, JOB-CLOSEUP
592 | 383100-02-1 | 383100-02-1 (3) / INSPECT WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT, AND CLEAN AS NECESSARY | 1 | 3.1 |  |  | Not Started | 38-31 | JOB-SETUP, TC/P, CLOSE-UP
594 | 521000-14-1 | 521000-14-1 (7) / FWD AND AFT PASS/CREW DOOR HINGE LUB | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P
595 | 521121-01-1 | 521121-01-1 (4) / FWD AND AFT PASS/CREW DOOR EXT LUB | 1 | 0.9 |  |  | Not Started | 12-22 | TC/P
597 | 533130-01-1 | 533130-01-1 (04) / ANTI COLLISION LIGHT SKN CUTOUT INSP | 1 | 0.2 | 12.5 | 73.6 | Idle | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
598 | 533131-01-1 | 533131-01-1 (05) / SKIN AROUND ADF1 ANTENNA CUTOUT INSP | 1 | 0.8 | 22 | 75.5 | Idle | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
599 | 534112-01-1 | 534112-01-1 (03) / VHF3 ANTENNA SKIN CUTOUT INSPECTION | 1 | 0.1 | 14 | 73.5 | Idle | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
603 | 05-00-00-01-0-A | 05-00-00-01-0-A (04) / AIRCRAFT C&D CHECKS DATA REVIEW | 1 | 1 |  |  | Not Started | 05-11 | TC/P
604 | 12-21-11-01-0-SVA | 12-21-11-01-0-SVA (03) / AIRCRAFT EXTERIOR APPEARANCE WASH | 1 | 9.8 | 12 | 298.6 | Idle | 12-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, TC/P, TC/P, TC/P, TC/P, TC/P, JOB-CLOSEUP
605 | 12-21-11-03-0-SVA | 12-21-11-03-0-SVA (03) / AIRCRAFT HEAVY WASH | 1 |  | 135 | 300.6 | Idle | 12-21 | WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH, WASH
606 | 32-10-00-01-0-SVA | 32-10-00-01-0-SVA (02) / MLG DR ACTUATOR EYE END BEARING LUB | 1 | 2 | 9 | 25.5 | Idle | 32-12 | JOB-SETUP, TC/P, TC/P
607 | 321000-01-1 | 321000-01-1 (5) / MLG AND DOORS LUBRICATION | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
608 | 322100-07-1 | 322100-07-1 (4) / NLG AIRFRAME ATTACHMENT FITTING INSP | 1 | 19 | 66 | 99.4 | Idle | 32-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
610 | 521104-01-1 | 521104-01-1 (02) / FWD PAX DOOR INTERNAL STRUCTURE INSP | 1 | 1.8 | 34 | 89.6 | Idle | 25-62 | JOB-SETUP, JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
611 | 521304-01-1 | 521304-01-1 (02) / AFT PAX DOOR INTERNAL STRUCTURE INSP | 1 | 1.9 | 16 | 69 | Idle | 52-13 | TC/P, TC/P, TC/P, TC/P, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION
612 | 522102-01-1 | 522102-01-1 (04) / EMERGENCY EXITS STRUCTURE INSPECTION | 1 | 10.1 |  |  | Not Started | 52-21 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
613 | 523103-01-1 | 523103-01-1 (02) / FWD CGO DOOR INTERNAL STRUCTURE INSP | 1 | 3.6 | 2 | 142.4 | Idle | 52-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
614 | 523109-01-1 | 523109-01-1 (02) / FWD CARGO DOOR LOCKING HOOKS INSP | 1 | 0.4 | 4 | 143.4 | Idle | 52-31 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
615 | 523113-01-1 | 523113-01-1 (02) / AFT CGO DOOR INTERNAL STRUCTURE INSP | 1 | 2.5 | 3.5 | 142.7 | Idle | 52-32 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
616 | 523119-01-2 | 523119-01-2 (03) / AFT CARGO DOOR LOCKING HOOKS INSP | 1 | 0.4 | 3.5 | 141.2 | Idle | 52-32 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
617 | 523303-01-1 | 523303-01-1 (02) / BULK CARGO DOOR INTERNAL STRUC INSP | 1 | 1 | 1.6 | 142.5 | Idle | 52-33 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
618 | 531163-01-1 | 531163-01-1 (03) / FWD PAX/CREW DOOR SURROUND INSP | 1 | 3 | 9.5 | 63 | Idle | 53-11 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
619 | 532130-09-1 | 532130-09-1 (02) / ANTI-CRASH ROD JUNCTION | 1 | 2.8 |  |  | Not Started | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
620 | 532130-29-1 | 532130-29-1 (01) / ANTI-CRASH ROD JUNCTION | 1 | 4.4 |  |  | Not Started | 53-21 | JOB-SETUP, JOB-SETUP, JOB-SETUP, JOB-SETUP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
621 | 532132-01-1 | 532132-01-1 (06) / FWD CARGO DOOR HINGE FITTING INSP | 1 | 1 | 2 | 143.9 | Idle | 53-21 | CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP
623 | 532175-01-1 | 532175-01-1 (03) / INTERNAL STRUC AROUND FWD CGO DOOR | 1 | 5 | 4 | 143.3 | Idle | 53-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
626 | 533129-07-1 | 533129-07-1 (0) / EMERGENCY EXIT CUTOUTS | 1 |  | 6.2 | 21.3 | Idle | 53
627 | 533139-02-1 | 533139-02-1 (01) / INSPECTION OF LONGITUDINAL BEAM FLANGE | 1 |  | 3 | 17.8 | Idle | 53-31 | JOB-SETUP, INSPECTION, --
628 | 533152-01-7 | 533152-01-7 (02) / PRESS BULKHEAD AT FR35 FWD FACE INSP | 1 | 5 | 1 | 111 | Idle | 53-31 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP
630 | 534123-01-3 | 534123-01-3 (06) / GUSSET PLATE FASTENER HOLE NDT INSP | 1 | 16.4 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, --
631 | 534135-02-1 | 534135-02-1 (0) / REAR FUSELAGE | 1 | 0.7 |  |  | Not Started | 57-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
632 | 534143-01-3 | 534143-01-3 (03) / AFT PASSENGER/CREW DOOR CUTOUT INSP | 1 | 1.6 | 9 | 63.1 | Idle | 53-41 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
633 | 534150-01-1 | 534150-01-1 (02) / AFT CARGO DOOR CUTOUT INSPECTION | 1 | 2.8 | 6 | 25.5 | Idle | 53-41 | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
634 | 534164-01-1 | 534164-01-1 (05) / BULK CGO DOOR CUTOUT INTERNAL STRUC | 1 | 1.1 | 5 | 142.9 | Idle | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
635 | 534195-01-1 | 534195-01-1 (0) / CABIN FLOOR STRUCTURE AFT ENTRANCE A | 1 | 6.2 |  |  | Not Started | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
636 | 534395-01-2 | 534395-01-2 (0) / LATERAL SHEAR PLATES BETWEEN FRAME 6 | 1 | 3.5 |  |  | Not Started | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
639 | 545134-09-6-001 | 545134-09-6-001 (03) / L/H PYLON UPR SPAR RIB 4 AND 10 INSP | 1 | 0.8 | 13.2 | 207.1 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
640 | 545134-09-6-002 | 545134-09-6-002 (02) / R/H PYLON UPR SPAR RIB 4 AND 10 INSP | 1 | 0.8 | 1.3 | 206.8 | Idle | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
641 | 571192-09-1 | 571192-09-1 (0) / CENTER WING BOX | 1 | 1.2 | 9 | 134.2 | Idle | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
642 | 571192-19-1 | 571192-19-1 (0) / CENTER WING BOX | 1 | 1.2 | 7.5 | 134.2 | Idle | 57 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
643 | 572001-01-1-001 | 572001-01-1-001 (02) / L/H WING FRONT SPAR FWD FACE INSP | 1 | 1 | 0.5 | 134.7 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
644 | 572001-01-1-002 | 572001-01-1-002 (02) / R/H WING FRONT SPAR FWD FACE INSP | 1 |  | 7.8 | 158.6 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
645 | 572007-01-2-001 | 572007-01-2-001 (03) / L-OUTER WING REAR SPAR AFT FACE INSP | 1 | 1 | 0.5 | 134.7 | Idle | 57-20 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
646 | 572007-01-2-002 | 572007-01-2-002 (03) / R-OUTER WING REAR SPAR AFT FACE INSP | 1 | 1 | 8.2 | 158.4 | Idle | 57-20 | JOB-SETUP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
647 | 572020-01-1-001 | 572020-01-1-001 (03) / L/H WING TOP SKIN RIB 1 AND 8 INSP | 1 | 6 | 3.5 | 44.2 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
648 | 572020-01-1-002 | 572020-01-1-002 (03) / R/H WING TOP SKIN RIB 1 AND 8 INSP | 1 | 2 | 5.8 | 44.3 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
649 | 572040-01-2-001 | 572040-01-2-001 (03) / L/H WING BOTTOM SKIN CUTOUTS INSP | 1 | 0.2 | 2.5 | 44.2 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
650 | 572040-01-2-002 | 572040-01-2-002 (03) / R/H WING BOTTOM SKIN CUTOUTS INSP | 1 | 0.1 | 6.8 | 44.5 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
655 | 572063-01-1-001 | 572063-01-1-001 (02) / L/H O/WNG BTOM SKN LWR SURFACE INSP | 1 | 1.6 | 1 | 132.2 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
656 | 572063-01-1-002 | 572063-01-1-002 (02) / R/H O/WING BTOM SKN LWR SURFACE INSP | 1 | 1.6 | 2.5 | 144.3 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
657 | 572066-01-1-001 | 572066-01-1-001 (03) / L/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 1 | 1.5 | 134.5 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
658 | 572066-01-1-002 | 572066-01-1-002 (03) / R/H OUTER WING TOP SKIN LOWER SURFACE INSP | 1 | 1 | 0.8 | 136.1 | Idle | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
664 | 572139-01-2-001 | 572139-01-2-001 (02) / L/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 1 | 0.5 | 6.5 | 142.2 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
665 | 572139-01-2-002 | 572139-01-2-002 (02) / R/H OUTR WING BOTOM SKIN RIB BAY CUTOUTS INSP | 1 | 0.5 | 7.5 | 142.2 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
666 | 32712996 | 572140-01-2-001 (03) / LH OUTER WNG BOTTOM SKN CUTOUTS INSP | 1 | 1.3 | 5 | 46.2 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
667 | 572140-01-2-002 | 572140-01-2-002 (03) / RH OUTER WNG BOTTOM SKN CUTOUTS INSP | 1 | 0.5 | 5.5 | 46.3 | Idle | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP, JOB-CLOSEUP
675 | 574202-01-2-002 | 574202-01-2-002 (02) / R/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 1 | 0.8 | 17 | 135.2 | Idle | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
696 | 575120-03-1-001 | 575120-03-1-001 (02) / TRALING EDGE AILERON HINGE PINS INSP | 1 | 1.8 | 1 | 21.3 | Idle | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
699 | 575150-01-2-002 | 575150-01-2-002 (03) / R/H OUTER WING MLG SUPPORT RIBS INSP | 1 |  | 7.3 | 23.4 | Idle | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
701 | 575158-01-5-002 | 575158-01-5-002 (02) / R/H WNG BOTTOM SKN LWR SURFACE INSP | 1 |  | 5 | 22.4 | Idle | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
702 | 783000-C9-1 | 783000-C9-1 (01) / DETAILED INSPECTION OF TRU STRUTS. | 1 | 4.7 |  |  | Not Started | 78-30
707 | 29904504 | EOD-320-21-00004-R00/A320 - AIR CONDITIONING -AVIONICS EQUIPMENT VENTILATION - INTRODUCE A | C | 16 |  |  | Not Started | 21
708 | 29749798 | EOD-320-23-00013-R00/COMMUNICATIONS- COCKPIT VOICE RECORDER-ACTIVATION OF DATALINK RECORDI | C | 3 | 6 | 61.2 | Idle | 23
709 | 20893203 | EOD-320-25-00032-R00/AD-SPECIAL DETAILED INSPECTION OF THE RACK 80VU (CEO) | PJED | 9.2 |  |  | Not Started | 25
710 | 29715410 | EOD-320-25-00050-R00/AD-EQUIPMENT/FURNISHINGS - LININGS AND FURNISHINGS/FORWARD CARGO | CCHK | 6.2 |  |  | Not Started | 25
711 | 30970374 | EOD-320-25-00052-R00/PAD-THIRD OCCUPANT SEAT – 168 SERIES BOTTOM EQUIPPED SCREW REPLACEMENT | AD | 0.5 |  |  | Not Started | 25
712 | 29411293 | EOD-320-27-00018-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | CCHK | 8.8 |  |  | Not Started | 27 | --, --, --, --, --, CLOSE-UP
713 | 29411377 | EOD-320-27-00019-R00/A320 - FLIGHT CONTROLS - LIFT AUGMENTING - INTRODUCE IMPROVED SLAT GEA | CCHK | 8.8 |  |  | Not Started | 27 | --, --, --, --, --, CLOSE-UP
714 | 31889267 | EOD-320-27-00026-R00/AD- A320 - FLIGHT CONTROLS- HIGH TIME THSA INSPECTION. | C | 15.9 |  |  | Not Started | 27
715 | 30839449 | EOD-320-29-00007-R00/HYDRAULIC POWER - PYLON - REPLACE BUSHING ON HP LINE ON SVA CFM PYLON | C | 48.5 | 51.3 | 62.2 | Idle | 29 | --, JOB-SETUP, JOB-SETUP, JOB-SETUP, --, --, --, --, --, --, --, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, JOB-CLOSEUP, CLOSE-UP, CLOSE-UP
716 | 29500617 | EOD-320-31-00005-R00/A320 - INDICATING/RECORDING SYSTEMS - SDAC - ACQUISITION/INTERFACE- MO | C | 6 | 4 | 44.7 | Idle | 31
718 | 30481965 | EOD-320-31-00007-R00/A320 –ELECTRONIC INSTRUMENT SYSTEM (EIS) - INTRODUCE EIS2 STANDARD S16 | ACHK | 4.9 |  |  | Not Started | 31
719 | 29155526 | EOD-320-31-00009-R00/INTRODUCE FDIMU H/W 2234320-02-02 FROM VENDOR TELEDYNE | ACHK | 2.5 | 16 | 67.8 | Idle | 31
721 | 29155749 | EOD-320-31-00011-R00/FDIMU - TELEDYNE ETHERNET AND ADC ACTIVATION FOR FOMAX | PJED | 2.5 |  |  | Not Started | 31
723 | 23732996 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | PJED | 12.8 |  |  | Not Started | 32
724 | 23745496 | EOD-320-32-00023-R00/A32S – LANDING GEAR - MLG - INSPECTION SLIDING TUBE / SLAVE LINK LUG C | PJED | 12.8 |  |  | Not Started | 32
725 | 31990073 | EOD-320-32-00025-R00/A32S - LANDING GEAR – NLG - INTRODUCE A NEW IMPROVED | LINE | 54 | 84.2 | 163.6 | Idle | 32
726 | 27685448 | EOD-320-36-00008-R00/A320 -PNEUMATIC - INSTALL DISCRETE SIGNAL WIRING BETWEEN BMC AND PACKS | CCHK | 16.2 | 77 | 46.8 | Idle | 36
727 | 30817926 | EOD-320-44-00014-R00/ECLIPSE CONNECTIVITY MODIFICATION | 1 | 471 | 29.1 | 51.7 | Idle | 44
728 | 31328631 | EOD-320-44-00028-R00/DE-MOD TAQNIA SYSTEM REMOVAL | PJED | 170 |  |  | Not Started | 44
729 | 29155915 | EOD-320-46-00004-R00/INSTALL FOMAX SYSTEM PROVISIONS | C | 23.2 | 2 | 89.2 | Idle | 46
730 | 29156039 | EOD-320-46-00005-R00/INSTALL INTERNAL GATELINK ANTENNA FOR FOMAX | C | 18 | 25.7 | 90.6 | Idle | 46
731 | 29156133 | EOD-320-46-00006-R00/INSTALL COCKPIT WIFI ANTENNA FOR FOMAX | C | 18.5 | 18 | 70.1 | Idle | 46
732 | 29156195 | EOD-320-46-00007-R00/CONNECT ETHERNET LINK BETWEEN FOMAX AND FDIMU | C | 2.5 |  |  | Not Started | 46
733 | 29157165 | EOD-320-46-00008-R00/FOMAX 4 ACTIVATION | ACHK | 4 |  |  | Not Started | 46
734 | 29156249 | EOD-320-46-00009-R00/ACTIVATE FOMAX OPTION 1 | ACHK | 2.5 |  |  | Not Started | 46
735 | 15777417 | EOD-320-53-00008-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | PJED | 1.5 |  |  | Not Started | 53
736 | 15777631 | EOD-320-53-00009-R00/AD-INSPECTION OF HORIZONTAL UPPER STIFFENER OF LATERAL WINDOW FRAME | PJED | 3 |  |  | Not Started | 53
737 | 16152729 | EOD-320-53-00014-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 LHS | 1 | 8.3 |  |  | Not Started | 53
738 | 16152761 | EOD-320-53-00015-R00/INSPECTION OF VERTICAL STIFFENER OF LATERAL WINDOW FRAME AT FR 4 RHS | 1 | 8.3 |  |  | Not Started | 53
739 | 17837147 | EOD-320-53-00022-R00/CENTER FUSELAGE -INSPECTION OF FRAME FOOT AT FR43 RH/LH- | 1 | 25 | 14.7 | 74.6 | Idle | 53
740 | 18607800 | EOD-320-53-00023-R00/CENTER FUSELAGE -MODIFY FASTENER HOLE OF FRAME FEET COUPLING | 1 | 62 | 2.2 | 2.7 | Idle | 53
741 | 29441536 | EOD-320-53-00026-R01/A320- FUSELAGE - REAR FUSELAGE - INSPECTION FOR CRACKS AT FR68 | 1 | 33.8 | 18.1 | 48.6 | Idle | 53
742 | 28479751 | EOD-320-53-00039-R00/FUSELAGE - CENTER FUSELAGE - KEEL BEAM BOTTOM PANEL INSPECTION AT FR46 | 1 | 19.8 | 32.4 | 50.6 | Idle | 53
743 | 31381248 | EOD-320-53-00047-R00/AD-REAR FUSELAGE - EXCHANGE NYLON BUSHES REF SB 53-1542 | C | 42.2 |  |  | Not Started | 53
744 | 29399531 | EOD-320-55-00001-R00/STABILIZERS - VERTICAL STABILIZER - INTRODUCE IMPROVED RUDDER HINGE LI | CCHK | 28.2 | 110.3 | 90.6 | Idle | 55
745 | 31053001 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | ACHK | 1.7 |  |  | Not Started | 25
746 | 31053051 | EOD-333-25-00024-R00/AD- A330/A320- INSPECT EACH BUCKLE SCREW FOR CRACKED,LOOSE | ACHK | 1.7 |  |  | Not Started | 25
747 | 15969127 | EOD-A32S-53-00003-R03/INSPECTION OF THE SIDE BOX BEAM FLANGE AT LHS/RHS IN FR43 AREA. | 1 | 44.2 | 45.1 | 98.6 | Idle | 53
748 | 10897096 | EOD-A32S-53-00019-R00/AD-A320/A321-FUSELAGE-DOOR STOP FITTING HOLES AT FR68-INSPECTION | C | 12.7 | 1 | 24.3 | Idle | 53
750 | 31662556 | S29-R10107/A320 - HYDRULIC SYSTEM - ENGINE-PUMP PRESSURE SWITCH | ACHK | 2.7 |  |  | Not Started | 29
751 | 30936889 | S32-R10370/A32S - LANDING GEAR - FLEET CAMPIAGN FOR FREE FALL MECHANISM | CCHK | 22.5 | 16.3 | 191.4 | Idle | 32-33 | --, --, --, --, --, --, --, --, --, --, OPS/LK, --, --, --, CLOSE-UP
752 | 30358131 | S36-R10080/A32S - PNUMATIC - MEASUREMENT OF THE CWR OF THE OHDS LOOPS | RON | 2 |  |  | Not Started | 36
753 | 20038778 | S51-R10008/A320 FLEET // DENT AND BUCKLE CHART | HNGR | 33.5 | 1.3 | 280.1 | Idle | 51
754 | 31978429 | S52-D10064/INSPECTION OF HINGES/LATCHES AND LOSS OF SERVICE DOORS 19(X) PANELS | ACHK | 2.2 |  |  | Not Started | 52
755 | 31573583 | S53-D10054/INSPECTION FOR MISSING/LOOSE/DAMAGED FASTENERS | CCHK | 2.5 |  |  | Not Started | 53
756 | 32832482 | S71-D10554/CMF56-5B BOTH ENGINES INLET COWLS LIP SKIN INSPECTION & REPAIR | 1 |  | 1.3 | 259.2 | Idle | 71
757 | 29294848 | S73-D10063/ENGINE FUEL FILTER REPLACEMENT | ACHK | 4.3 |  |  | Not Started | 73
758 | 31958880 | REPLACE 3214-31/151653 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
759 | 31958882 | REPLACE 3214-31/151671 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
760 | 31958881 | REPLACE 3214-31/151674 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
761 | 31958879 | REPLACE 3214-31/151687 (BATTERY, EMERGENCY) | N |  |  |  | Not Started | 20-00
762 | 22959389 | REPLACE 47145-267/4527 (ACTUATOR-THS) | N | 6 |  |  | Not Started | 27
763 | 31197928 | REPLACE MF20-534/B005068 (FULL FACE QUICK DONN MASK REGULATOR) | N |  |  |  | Not Started | 20-00
764 | 26290429 | 34100005-1/50325D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 | 2 | 58.9 | Idle | 26-23
765 | 28781470 | 34100005-1/67427D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 | 2 | 59 | Idle | 26-23
766 | 28781472 | 34100005-1/67765D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 |  |  | Not Started | 26-23
767 | 22574878 | 34100005-1/E1800D1 WC(WEIGHT CHECK) / WEIGHT CHECK | 1 | 1.8 | 2 | 58.9 | Idle | 26-23
768 | 23772081 | 9024-15704-03/10115418 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | CCHK | 2.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
769 | 23772080 | 9024-15704-03/10115442 FC(FUNCTIONAL CHECK) / VALVE-SAFETY FUNCTIONAL CHECK | CCHK | 2.1 |  |  | Not Started | 21-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
770 | 31045000 | CFM56-5B3/3/643323 IN(INSPECTION) / EO 751107 CFM56-5B VBV RE-GREASING | 1 | 4.8 |  |  | Not Started | 75
771 | 30304386 | CFM56-5B3/3/645205 IN(INSPECTION) / ENG FAN SECTION INSP & LUB | 1 | 13.6 | 125.5 | 61.8 | Idle | 72 | JOB-SETUP, JOB-SETUP, CLEAN-UP, INSPECTION, INSPECTION, JOB-SETUP, JOB-CLOSEUP
772 | 80944787 | PANEL 41C CEILING PANEL FOUND DAMAGE | PANT |  | 16.2 | 6743.5 | Idle | 25
773 | 81002632 | AFT GALLEY COMP COVERT ATTACHMENT FITTING S302 S303 S304 LOWER FLAP IS BROKEN AND DETACHED FROM FLOOR | N |  | 15 | 2236.1 | Idle | 25
774 | 94493475 | DECAL #1 ENGINE OUTBOARD PIVOTING DOOR & PIVOTING DOOR LOCKOUT PIN DECAL ARE TORN. | N |  | 2 | 1158.1 | Idle | 11
775 | 94493476 | DECAL #1 ENGINE OUTBOARD DEPLOY SWITCH ACCESS DOOR DECAL TORN. | N |  | 2 | 1158.1 | Idle | 11
776 | 94493487 | DECAL #2 ENGINE OUTBOARD NO PERSONEL & 15FT AWAY DECAL FADED. | N |  | 1 | 1109.8 | Idle | 11
777 | 94493488 | DECAL #2 ENGINE INBOARD 15FT AWAY & WARNING DECAL ARE FADED. | N |  | 1 | 1109.8 | Idle | 11
778 | 94493489 | DECAL LH MAIN LANDING GEAR INFLATE TYRES WITH NITROGEN DECAL FADED. | N |  | 1 | 1109.5 | Idle | 11
779 | 94734250 | WING DURING WALK ARR FOUND (R) WING JACKING POINT (C0VER) MISSING | N | 1 | 1 | 1807.3 | Idle | 25
780 | 94740818 | BLANKING CAP L2 DOOR HOIST POINT EA 01 BLANKING CAP FOUND TORN | N | 2 | 2 | 2250.7 | Idle | 25-00
781 | 94799712 | DECAL FWD CARGO DOOR SELECTOR PNL AUX OPS INSTRUCTIONS DECAL IS FADED | N | 1 | 1 | 1390.5 | Idle | 11-00
783 | STJC-20-00-00-03-GA-GO | TOOL ACCOUNTABILITY PRIOR TO ACFT RELEASE | N | 1 |  |  | Not Started | 20 | ACFT RELEASE
784 | STJC-20-00-00-04-GA-SV | AIRCRAFT MAINTENANCE AND CABIN LOGBOOKS AUDIT | N | 1 |  |  | Not Started | 20 | TC/P, TC/P
785 | STJC-20-00-00-05-GA-SV | AIRCRAFT MAINTENANCE PACKAGE ACCOUNTABILITY CHECK | N | 5 |  |  | Not Started | 20 | ACFT RELEASE, ACFT RELEASE, --
786 | STJC-20-00-00-06-A32S-SV | HEAVEY CHECK PRE-HANGAR PREPARATION | N |  |  |  | Idle | 20 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR
787 | STJC-20-00-00-07-A32S-SV | HEAVEY CHECK DE-HANGARING PREPARATION | N | 22 |  |  | Not Started | 20 | TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P
788 | STJC-20-00-00-08-A32S-SV | CABIN DOORS SAFETY PINS INSTALLATION/REMOVAL | N | 2 |  |  | Not Started | 20 | TC/P
789 | STJC-AREAS-FINAL-INSPECTION-01-GA-GO | AIRCRAFT FINAL INSPECTION | N | 3 |  |  | Not Started | 05-00 | FINAL INSP, FINAL INSP, FINAL INSP
790 | STJC-AREAS-FINAL-INSPECTION-02-GA-GO | COCKPIT AND PAX CABIN FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
791 | STJC-AREAS-FINAL-INSPECTION-03-GA-GO | AIRCRAFT UPPER/LOWER FUSELAGE FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
792 | STJC-AREAS-FINAL-INSPECTION-04-GA-GO | EMPENNAGE FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
793 | STJC-AREAS-FINAL-INSPECTION-05-GA-GO | AFT/BULK/FWD CARGO COMPARTMENT FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
794 | STJC-AREAS-FINAL-INSPECTION-06-GA-GO | L/H AND R/H WINGS FINAL INSPECTION | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
795 | STJC-AREAS-FINAL-INSPECTION-07-GA-GO | LDGS & WHEEL WEEL FINAL INSPECTION (MLG & NLG) | N | 1 |  |  | Not Started | 05-00 | FINAL INSP
796 | STJC-AREAS-FINAL-INSPECTION-08-GA-GO | ENGINE AND PYLON FINAL INSPECTION (L/H & R/H) | N | 2 |  |  | Not Started | 05-00 | FINAL INSP
797 | STJC-AREAS-FINAL-INSPECTION-09-GA-GO | APU FINAL INSPECTION | N | 1 |  |  | Not Started | 05-00 | FINAL INSP
798 | STJC-CRS-GA-SV | CERTIFICATE OF RELEASE TO SERVICE (CRS) | N | 0.5 |  |  | Not Started | 05-11 | ACFT RELEASE
799 | STJC-RTS-03-A32S-SV | AIRCRAFT RETURN TO SERVICE FOR HEAVEY CHECK | N | 7 |  |  | Not Started | 05-00 | FINAL INSP, FINAL INSP, FINAL INSP, FINAL INSP
800 | 32596938 | 22-70-00-01-0-A (03) / FMC DATA UPLOAD | 1 | 1 |  |  | Not Started | 22-70 | TC/P
801 | 242000-21-1-001 | 242000-21-1-001 (04) / NO. 1 ENGINE AC GENERATION | 1 | 2.1 |  |  | Not Started | 24-21 | --, TC/P, --
803 | 381000-01-1 | 381000-01-1 (3) / WATER TANK DISINFECTION | 1 | 16 |  |  | Not Started | 38-10 | OPS/LK
804 | 32840057 | DCC-32S (13) / DCC A32S DAILY CABIN CHECK | 1 | 10 | 97 | 25.8 | Idle | 25-00 | JOB-SETUP, TC/P, TC/P, TC/P, --, --, --, --, --
810 | 32913243 | CCC-32S (05) / A32S CABIN CRITICAL CHECK | 1 | 3.2 |  |  | Not Started | 25-00 | JOB-SETUP, TC/P, TC/P, TC/P, TC/P, TC/P, TC/P, --
811 | 94844878 | O.O.S AIRCRAFT TAKEN OUT OF SERVICE AT 23:59 Z DATE 17 JULY 2026 FOR C2 + 6 YEARS CHECK. SCHEDULE 38 DAYS | N | 24 |  |  | Not Started | 05-00
812 | 94844876 | L/G ALL L/G SAFETY PINS ARE INSTALLED. AS PER AMM 32-00-00-481-001-A REV.69 DATE.01 MAY 2026 | N | 2 |  |  | Not Started | 32-00
813 | 32977683 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS TORN 1. APU FUEL-DRAIN VENT 2. FUEL LEAK MONITOR 3. LH/RH CAUTION INLET SWINGS INWARDS DECAL 4. YELLOW HYD BAY DECAL 5. AFT CARGO SELECTOR DECAL | 1 | 3 | 4 | 119.1 | Idle | 05-21
815 | 32977685 | LOWER FUSELAGE---AVN---NO CALLBACK DURING INSP, FOUND TORN EROSION TAPE ON VHF 2 ANTENNA | 1 | 4 |  |  | Not Started | 05-21
816 | 32977864 | PRE---UPPER FUSELAGE---NOCALLBACK---AV UPPER FUSELAGE GPS 1 ANTENNA, FWD AREA PAINT FOUND ERODED. | 1 | 4 |  |  | Not Started | 05-21
817 | 32977871 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (1) ANTENNA, LEADING EDGE INSULATION PROTECTION FOUND TORN AND WORNOUT. | 1 | 4 |  |  | Not Started | 05-21
818 | 32977873 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE FWD SATCOM ANTENNA AFT AREA AROUND EDGE SEALANT FOUND WORNOUT AND MISSING. | 1 | 4 |  |  | Not Started | 05-21
819 | 32977874 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE TCAS 1 ANTENNA, CAP SEALANT AROUND FASTENERS AND EDGES FOUND WORNOUT AND TORN. | 1 | 4 |  |  | Not Started | 05-21
821 | 32977882 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN AFT FUSELAGE UPPER SURFACE SATCOM ANTENNA L/E EXCESSIVE PAINT WORNOUT. | 1 | 4 |  |  | Not Started | 05-21
822 | 32977883 | PRE---UPPER FUSELAGE---RII---SM R2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH MULTIPLE MINOR DENTS. MAX DIAMENTER= 0.2 INCH MAX DEPTH= 0.013 INCH | 1 |  | 52.4 | 265.9 | Idle | 05-21
823 | 32977884 | PRE---UPPER FUSELAGE---RII---SM L2 PASSENGER ENTRY DOOR, FLOOR SCUFF PALTE EDGE FOUND WITH 01 EA DENTS. L= 0.4 INCH W= 0.5 INCH D= 0.050 INCH | 1 |  | 60.2 | 265.8 | Idle | 05-21
825 | 32977905 | PRE---L/H WING---NOCALLBACK---AP L/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 1 | 8 |  |  | Not Started | 05-25
826 | 32977906 | PRE---R/H WING---NOCALLBACK---AP R/H WING ADJACENT TO SLAT NO#01 I/B SIDE FIXED LEADING EDGE, SEAL FOUND TORN AND WORNOUT. | 1 | 8 |  |  | Not Started | 05-25
827 | 32977907 | PRE---R/H WING---RII---SM R/H WING UPPER SURFACE FWD OF SPOILER NO# 02 I/B SIDE, FWD AREA 01 EA RIVET HEAD FOUND SHEARED. | 1 | 2 | 0.5 | 193.6 | Idle | 05-25
828 | 32977908 | PRE---UPPER FUSELAGE---NOCALLBACK---AVN UPPER FUSELAGE VHF (3) ANTENNA, LEADING EDGE PAINT FOUND WORNOUT. | 1 | 4 | 8 | 42.4 | Idle | 05-21
830 | 32977910 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT UPPER FWD FUSELAGE AROUND COCKPIT WINDOW RETAINERS AND SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 1 | 4 | 8.5 | 136 | Idle | 05-25
832 | 32978070 | FINDING (NRC) TASKCARD 282100-05-1-001 AP RII DURING GVI FUEL PIPE AT PYLON #1 FOUND 2 EA MINER DENT ON LH SIDE MAIN FUEL FEED PIPE UNDER PYLON PNL413 CL 1- DENT L = 0.02 IN D= 0.009 IN 2- DENT L= 0.03 IN D= 0.0010 IN | 1 |  |  |  | Not Started | 28-21
834 | 32978238 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RG AFT DOOR DATA PLATE DECAL TORN. | 1 | 2 |  |  | Not Started | 05-21
835 | 32978240 | NLG DOOR---AP---NO CALL BACK---- NLG RH AFT DOOR AFT UPPER CORNER RUBBER SEAL WRINKLED. | 1 | 6 |  |  | Not Started | 05-21
837 | 32978247 | NLG WHEEL----AP---NO CALL BACK--- BOTH NLG WHEEL TIRE TPIS MISSING. | 1 | 2 |  |  | Not Started | 05-21
840 | 32978254 | LH MLG----AP---NO CALL BACK--- LH MLG BETWEEN FIXED AND HINGE FAIRING BONDING WIRE FRAYED. | 1 | 8 |  |  | Not Started | 05-25
841 | 32978259 | LH MLG---PNT NO CALL BACK--- LH MLG FIXED FAIRING DATA PLATE DECAL MISSING. | 1 | 2 |  |  | Not Started | 05-25
842 | 32978265 | LH MLG BAY----AP---NO CALL BACK--- LH MLG BAY FWD SIDE FUSELAGE LWR SEAL TORN AND WRINGKLED AND UPPER SIDE CORNER WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
845 | 32978280 | MLG----AP NO CALL BACK--- ALL MLG WHEEL TIRE MISSING TPIS. | 1 | 2 |  |  | Not Started | 05-27
846 | 32978281 | RH MLG---AP---NO CALL BACK--- RH MLG BAY FWD FUSELAGE LWR RUBBER SEAL WRINGKLED AND TORN, AND UPPER CORNET WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
847 | 32978282 | RH MLG---SM---CALL BACK---- RH MLG DOOR ON AFT UPPER CORNER PNL148FB SHAVING WITH MISSING PIECE. L= 4" W= 0.187" | 1 | 3 | 10.6 | 210.6 | Idle | 05-25
851 | 32978507 | FWD CARGO COMP----SM---CALL BACK---- FWD CARGO COMP ENTRY DOOR AT AFT SIDE PLATE BENDED. | 1 | 3 | 0.3 | 168.6 | Idle | 25-50
852 | 32978509 | FWD CARGO COMP---AP---NO CALL BACK---- FWD CARGO COMP ENTRY DOOR FWD DOOR NET TORN. | 1 | 6 |  |  | Not Started | 25-50
853 | 32978510 | FWD CARGO COMP---SM---CALL BACK---- PNL 131CW LH DECOMPRESSION PNL COVER WITH SKIN SEPARATION WITH MISSING PIECE OF HONEY COMB AND RH WITH SKIN SEPARATION WITH CUT. | 1 |  | 28.8 | 258.6 | Idle | 25-50
854 | 32978546 | FWD CARGO COMP---SM---CALL BACK---- FWD CARGO COMP PNL 131DW LH AND RH DECOMPRESSION COVER PNL WITH SKIN SEPARATION. | 1 | 3 | 7.8 | 50.3 | Idle | 25-50
855 | 32978563 | FWD CARGO COMP---SM----CALL BACK---- PNL 131KFWITH PUNCTURED ON MID SIDE AND FWD LOW SIDE CORNER SKIN SEPARATION. | 1 | 4 | 37.2 | 75.6 | Idle | 25-50
856 | 32978565 | FWD CARGO COMP---SM---CALL BACK---- PNL 132GF FWD SIDE PUNCTURED | 1 | 4 | 18.1 | 218.6 | Idle | 25-50
857 | 32978566 | FWD CARGO COMP---SM---CALL BACK--- PNL 131EF WITH SEVERAL PUNCTURED. | 1 | 4 | 12.7 | 80.9 | Idle | 25-50
858 | 32978568 | FWD CARGO COMP---PNT---NO CALL BACK---- PNL 132PW ACCES DECAL TORN. | 1 | 2 |  |  | Not Started | 25-50
861 | 32978585 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SIGN OF HYD LEAK. | 1 | 4 |  |  | Not Started | 05-28
863 | 32978591 | FWD CARGO DOOR---PNT---NO CALL BACK---- FWD CARGO DOOR DATA PLATE TORN. | 1 | 2 |  |  | Not Started | 05-28
864 | 32978593 | FWD CARGO DOOR---AP---CALL BACK--- FWD CARGO DOOR AFT LWR SIDE RUBBER SEAL WITH CUT | 1 | 4 |  |  | Not Started | 05-28
865 | 32978600 | FWD CARGO DOOR---SM---CALL BACK--- FWD CARGO DOOR LINING CRACK ON LWR FWD SIDE. | 1 | 4 | 25.5 | 49.6 | Idle | 05-28
866 | 32978626 | FWD CARGO DOOR---PNT---NO ALL BACK--- FWD CARGO DOOR LINING SEVERAL PNT CRACK. | 1 | 4 |  |  | Not Started | 05-28
867 | 32978634 | AFT CARGO COMP----SM---CALL BACK---- AFT CARGO COMP AFT DOOR NET STANCHION TUBE WTIH DENT ON MID SIDE L=1" W=0.5" D=0.125" | 1 | 4 | 0.3 | 193.5 | Idle | 05-21
868 | 32978638 | AFT CARGO COMP---SM---CALL BACK---- AFT CARGO COMP CIELING PNL 151DC DAMAGE WITH MISSING HONEY COMB L=1" W=0.5" | 1 | 6 |  |  | Not Started | 05-21
869 | 32978643 | AFT CARGO COMP----AP---NO CALL BACK--- AFT CARGO COMP SEVERAL PNL WITH MISSING SCREW AND DETACHED GAP SEAL. | 1 | 6 |  |  | Not Started | 05-21
873 | 32978651 | AFT CARGO DOOR---PNT---NO CALL BACK---- AFT CARGO DOOR DATA PLATE TORN. | 1 | 2 |  |  | Not Started | 05-28
876 | 32978879 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT BELT DIRTY | 1 | 2 |  |  | Not Started | 25-21
886 | 32979256 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--RII RH WING FLAP LWR KICK SEAL WITH CUT 0.5 IN. | 1 |  |  |  | Not Started | 05-25
887 | 32979285 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING AP--NO CALLBACK RH WING FLAP MOV. TRACK NO#3 DRAINED WITH SIGN OF OIL LEAKAGE. | 1 |  |  |  | Not Started | 05-25
888 | 32979304 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) / RH WING AP-- CALLBACK RH WING FLAP TRACK NO#3 O/B AFT UPPER SEAL WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
889 | 32979322 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING SM--RII RH WING SLAT NO#2 MID SIDE WITH SCRACH DIM. L=1 IN W=0.12 IN D=0.003 IN | 1 | 4 | 2.5 | 180.6 | Idle | 05-25
890 | 32979401 | FINDING (NRC) TASKCARD ZL-433-01-1-002 (02) ENG#2 SM--RII ENG#2 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 1 | 12 | 14.5 | 226.6 | Idle | 05-24
891 | 32979406 | FINDING (NRC) TASKCARD ZL-433-01-1-001 (02) / ENG#1 SM--RII ENG#1 AIR INTAKE LIP WITH SURFACE CORROSION ALL AROUND. | 1 | 8 | 5 | 226.6 | Idle | 05-24
892 | 32979530 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA (02) / RII/AVN AFT MEGAPHONE P/N A12SA S/N 1142984 WILL EXPIRE 09 /10/ 2026 LESS THAN 80 DAYS | 1 |  | 12.5 | 114.1 | Idle | 25-65
893 | 32979557 | FINDING (NRC) TASKCARD 25-65-00-01-0-SVA-001 /RII/CABIN AFT BOTH FIRST AID KIT WILL EXPIRE ON 06/2026 LESS THAN 6 MONTH | 1 | 1 |  |  | Not Started | 25-65
894 | 32979661 | FINDING (NRC) TASKCARD 353000-07-1 /CABIN/ NO CALLBACK PORTABLE OXYGEN MASK BEHIND SEAT 5 J WILL EXPIRE ON 09/2026 | 1 |  |  |  | Not Started | 35-30
900 | 32980022 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 1 | 6.5 | 6.5 | 169.3 | Idle | 25-21
901 | 32391506 | 114122014/CH1016136 LB(LUBRICATION) / LUB OF MLG AND DOORS | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
902 | 32439904 | 114122015/CH1009957 LB(LUBRICATION) / LUB OF MLG AND DOORS | 1 | 2 |  |  | Not Started | 12-22 | JOB-SETUP, TC/P, TC/P
903 | 32163655 | 342B050000/06787 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
904 | 32163652 | 342B050000/10718 RS(RESTORATION) / CLN THERMOSTAT - FAN AIR VALVE CTRL | 1 | 2.2 |  |  | Not Started | 36-11 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
905 | 81172702 | IFE REMOTE CONTROL VHS REMOTE CONTROL FOR 1L IS BROKEN BY CREW: 11013005 | N |  | 3.5 | 645.2 | Idle | 44-26-00
906 | 94844831 | DECAL BELLY LH LANDING GEAR ON GROUND AND YELLOW HYD BAY DECAL FOUND WORN | N |  |  | 429.2 | Idle | 11
907 | 94844832 | DECAL AFT BELLY WATER DRAIN VALVE AND FUEL LEAK MONITOR DECAL FOUND FADED | N |  |  | 429.3 | Idle | 11
908 | 94844833 | DECAL BELLY AIR CONDITIONING AND GROUND HYD CONNECTION BLUE DECAL FOUND FADED | N |  |  | 429.4 | Idle | 11
909 | 94844834 | DECAL AFT CARGO SELECTOR PANEL AUX OPS INSTRUCTIONS DECAL FOUND WORN | N |  | 1 | 430.5 | Idle | 11
910 | 94844835 | DECAL AFT BELLY APU CTR AND FUEL-DRAIN VENT DECAL FOUND TORN | N |  | 1 | 430.6 | Idle | 11
911 | 94844836 | RADIO ALTIMETER AFT BELLY RADIO ALTIMETER MARKINGS FOUND FADED | N |  | 1 | 429.8 | Idle | 11
912 | 94844837 | DECAL AFT CARGO DOOR ARROW, PULL, PUSH AND WARNING DECAL FOUND WORN | N |  | 1 | 430.8 | Idle | 11
913 | 32345876 | EOD-320-11-00001-R00/ADD MARKING ON AVIONICS DOORS 811 AND 824 | ACHK | 2.5 |  |  | Not Started | 11
914 | 32850432 | EOD-320-21-00005-R00/A320 - AIR CONDITIONING - INTRODUCE NEW CONTACTOR FOR BLOWER AND EXTRA | RON | 2 |  |  | Not Started | 21
915 | 15777708 | EOD-320-53-00010-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | C | 4.3 | 5.1 | 22.9 | Idle | 53
916 | 15777769 | EOD-320-53-00011-R00/FUSELAGE - MAIN STRUCTURE - APPLY A CUT ON STIFFENER ON | C | 4.7 | 2.8 | 68.6 | Idle | 53
917 | 28372303 | REPLACE DVE90-07/7369 (VALVE-SOLENOID) | N |  |  |  | Not Started | 35-00
918 | 28611923 | S25-R10381/HZ-ASD - FWD GALLEY COMP 104 WORKDECK BULGING REPEAT INSPECTION | RON | 1.5 | 0.4 | 69.6 | Idle | 25-30
919 | 32822269 | S26-R10173/A320/A321 - FIRE PROTECTION - INSTALLATION OF PLACARD IN LAVATORY | ACHK | 0.5 |  |  | Not Started | 26
920 | 32822529 | S31-D10211/(REPETITIVE) A320/321: ACARS OUTPUT RULE SETTING CHANGE. | RON | 1 |  |  | Not Started | 31
922 | 30262642 | S32-R10324/A320 - LANDING GEAR - OPERATIONAL CHECK OF PBCV TO VERIFY ELECTRICAL | ACHK | 1.7 |  |  | Not Started | 32
923 | 32800094 | S36-R10202/EBAS ENHANCEMENT TASKS - BLEED HEALTH CHECK | CCHK | 31 |  |  | Not Started | 36
924 | 32872501 | S36-R10216/A32S - LEAK CHECK IN PACK BAY AREA COMPONENTS | LINE | 4 |  |  | Not Started | 36
926 | 32980026 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS FOODTRAY DIRTY | 1 | 24 |  |  | Not Started | 25-21
928 | 32980047 | LATERAL AVIO COMPT---STR---RII 2EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR16 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.47IN) | 1 | 8 | 8.5 | 207.1 | Idle | 24-92
929 | 32980064 | LATERAL AVIO COMPT---STR---RII 1EA CRACK ON BRACKET ATTACHED TO CLAMP ALONG FR17 OF TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812, DIMENSION (L= 0.45IN) | 1 | 8 | 5 | 210.6 | Idle | 24-92
930 | 32980065 | LATERAL AVIO COMPT---STR---RII 1EA BROKEN BRACKET WITH CLAMP ATTACHED ALONG FR19 OF TOILET PIPE ASSY ACCESS FROM AVN DOOR 812 | 1 |  |  |  | Not Started | 24-92
931 | 32980071 | LATERAL AVIO COMPT---AP---NO CALLBACK VALVE-BUTTERFLY,AIR (P/N:V2T152D) UPPER ATTACHMENT DETACHED (ACCESS FROM AVN DOOR 812) | 1 | 4 |  |  | Not Started | 24-92
932 | 32980080 | LATERAL AVIO COMPT---AP---NO CALLBACK 1EA BROKEN UPPER CLAMP ON TOILET PIPE ASSY (ACCESS FROM AVN DOOR 812) | 1 | 4 |  |  | Not Started | 24-92
934 | 32980077 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AV--CALLBACK LH WING NAVIGATION TIP LIGHT WITH MISSING SEAL. | 1 | 8 | 12.5 | 114.5 | Idle | 05-25
935 | 523300-01-1 | 523300-01-1 (4) / BULK CARGO DOOR HANDLE AND HINGE LUB | 1 | 0.2 |  |  | Not Started | 12-22 | TC/P
936 | 32980091 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING-- AP--CALLBACK LH WING AROUND NAVIGATION TIP LIGHT WITH MISSING SEALANT. | 1 | 8 |  |  | Not Started | 05-25
937 | 32980104 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--CALLBACK LH WING FLAP TRACK FAIRING NO#4 O/B AFT UPPER SEAL WITH CUT. | 1 | 8 |  |  | Not Started | 05-25
938 | 32980083 | LATERAL AVIO COMPT---AVN---NO CALLBACK MISSING LOCKWIRE BETWEEN THE KNURLED NUT AND THE ELECTRICAL CONNECTOR ON BAT2 | 1 |  |  |  | Not Started | 24-92
939 | 32980111 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING FT--RII LH WING FLAP FAIRING #4 DRAINED WITH FUEL LEAKAGE | 1 |  | 3 | 194.6 | Idle | 05-25
941 | 32980118 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--RII LH WING SLAT TRACK COVER NO#2 WITH CRACK DIM: L= 2 IN | 1 | 8 |  |  | Not Started | 05-25
943 | 44-SVA-01 | 44-SVA-01 (01) / PANASONIC LEVEL 1 CHECK | 1 | 1.5 |  |  | Not Started | 44-21
944 | 32917899 | ISC/IN SERVCE CHECK_N | N |  |  |  | Not Started | 20-00
945 | 32420054 | W_N/WEEKLY CHECK | N |  |  |  | Not Started | 20-00
947 | ISC-32S | ISC-32S (14) / 32S IN-SERVEICE-CHECK (ISC) | 1 | 2.8 |  |  | Not Started | 12 | TC/P, --, --, --
948 | WEEKLY-32S | WEEKLY-32S (05) / WEEKLY 32S CHECK | 1 | 5.9 |  |  | Not Started | 12 | TC/P, --, --, --, --, --, --, --
949 | 32980140 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING SLAT NO.#3 IN/B SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
950 | 32980164 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) / LH WING AP--NO CALLBACK LH WING FLAP TRACK NO.#3 SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
951 | 32980175 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--RII LH WING FLAP LWR KICK SEAL WITH CUT DIM: L=1 IN | 1 | 8 |  |  | Not Started | 05-25
953 | 32980186 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING AP--NO CALLBACK LH WING FLAP TRACK MOV. FAIRING WITH SIGN OF OIL LEAKAGE. | 1 | 6 |  |  | Not Started | 05-25
954 | 32980176 | REAR AVIONIC COMPARTMENT DOOR---AP---NO CALLBACK OLD CORROSION INHIBITING COMP (CIC) FLAKING ON REAR AVIONIC COMPARTMENT DOOR (AFT DOOR 824) | 1 | 8 |  |  | Not Started | 05-28
955 | 32980920 | FINDING S71-D10554 (INLET COWL LIP)---STR---RII DURING INSP, FOUND BOTH ENGINES INLET COWL LIP SKIN WITH ALL AROUND SURFARCE DISCOLORATION. | 1 | 8 | 0.3 | 168.9 | Idle | 71
956 | 32981647 | AFT R/H PAX/CREW DOOR---CAB---NO CALLBACK DURING INSP, FOUND AFT R/H PAX/CREW DOOR SEAL DUSTY | 1 |  | 14 | 18.4 | Idle | 05-28
957 | 32981683 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1A,L, AND 4A, SHROUD/VELCRO ASSEMBLY DAMAGED. | 1 | 3 |  |  | Not Started | 25-21
960 | 32981726 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J, 2J, 3C, 4A,C, 5A,C,J, LATCH - BACK MISSING | 1 | 6 |  |  | Not Started | 25-21
964 | 32981816 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1J, 2A,L, 4A, 5J, SHROUD - CONSOLE SIDE DAMAGED. | 1 | 15 |  |  | Not Started | 25-21
966 | 32982172 | AFT GALLY SM--CALL BACK AFT GALLEY LOWER ATTACHMENT POINTS FITTING WITH 3 EA PLAT RUSTY | 1 | 8 | 0.5 | 68.8 | Idle | 25-30
968 | 32982194 | CAB-CALLBACK L2 STOWAGE REMOVAL FOR ACCESS | 1 |  | 7.5 | 229.6 | Idle | 25-30
969 | 32982195 | S/M NO CALLBACK L2 STOWAGE RAMP ASSY FOUND ALL INSERTS REMOVED | 1 |  |  |  | Not Started | 25-30
970 | 32982197 | CAB-CALLBACK R2 STOWAGE REMOVED FOR ACCESS | 1 |  | 9.5 | 254.7 | Idle | 25-30
971 | 32982199 | RII-CAB-L1 INBOARD AND OUTBOARD L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 1 |  | 1.5 | 252.4 | Idle | 25-40
972 | 32982200 | RII-CAB-SWIVEL SWIVEL FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  | 2 | 252.6 | Idle | 25-40
973 | 32982202 | RII-CALLBACK-R2 DOUBLE WALL-MOUNTED R2 DOUBLE WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  |  |  | Not Started | 25-40
974 | 32982203 | RII-CALLBACK L1 INBOARD AND OUTBOARD WALL-MOUNTED FLIGHT ATTENDANT SEAT REQUIRE REMOVAL FOR ACCESS. | 1 |  | 4 | 252.9 | Idle | 25-40
978 | 32983857 | PRE---ENG NO#02---RII---SM ENG NO#02 R/H FAN COWL FWD SIDE NEAR IDG OIL LEVEL ACCESS DOOR, EDGE PROTECTOR FOUND DETACHED WITH SHEARED RIVETS. | 1 | 4 | 1 | 161.6 | Idle | 05-24
979 | 32983861 | PRE---R/H AIR COND---NOCALLBACK---AP R/H AIR CONDITION PACK COMPT AFT AREA EXHAUST ASSY, INSIDE COMPT, I/B UPPER ATTACHMENT NUT FOUND MISSING. | 1 | 8 |  |  | Not Started | 05-21
981 | 32983876 | PRE--MLG W/W---NOCALLBACK---FS L/H AND R/H MLG WHEEL WELL FWD CUTOUT EDGE SEAL FOUND WORNOUT, TORN WITH CUTS. | 1 | 12 |  |  | Not Started | 05-21
984 | 32983896 | LH WING INBORAD/OUTBOARD FIXED L/E---AP---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED LEADING EDGE STRUCTURE TO FACILITATE INSPECTION | 1 | 8 |  |  | Not Started | 05-25
985 | 32983897 | PRE---HYD COMPT---NOCALLBACK---AP L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE SEAL FOUND MISSING AND DETACHED WITH CUTS. | 1 | 8 |  |  | Not Started | 05-21
986 | 32983910 | PRE---HYD COMPT---NOCALLBACK---AVN L/H AND R/H HYD COMPT ACCESS THROUGH PANELS 195 BB AND 196 BB INNER AREA, 02 EA CEILING LIGHT LAMPS FOUND BUSTED. | 1 |  | 5 | 125.8 | Idle | 05-21
987 | 32983929 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE R/H HYD COMPT ACCESS THROUG PANEL 196 BB, YELLOW ELECTRIC PUMP LOWER AREA FOUND WITH SIGN OF HYD LEAK. | 1 | 6 |  |  | Not Started | 05-21
988 | 32983937 | PRE---HYD COMPT---RII---FT LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, WATER DRAIN VALVE FOUND WITH SIGN OF LEAK. | 1 | 8 | 0.5 | 230.1 | Idle | 05-21
989 | 32983944 | PRE---HYD COMPT---NOCALLBACK---AP LOWER FUSELAGE L/H HYD COMPT ACCESS THROUG PANEL 195 BB, FWD WALL R/H SIDE AIR COND PACK EXHAUST FITTING, 02 EA BOLTS FOUND LOOSE. | 1 | 6 |  |  | Not Started | 05-21
991 | 32983948 | OUTBOARD FIXED TRAILING EDGE STR---PNT---NO CALLBACK CHIPPED PAINT ON THE LOWER SURFACE OF ALL SPOILERS | 1 | 6 | 12.5 | 168.2 | Idle | 05-25
992 | 32983996 | CAB - NO CALLBACK - LIFE VESTS ALL LIFE VESTS WILL EXPIRE WITHIN 3 YEARS. | 1 | 8.5 |  |  | Not Started | 25
993 | 32984016 | OUTBOARD FIXED TRAILING EDGE STR---AP---NO CALLBACK 1EA BROKEN BONDING STRAP ON SPOILER 4 (INBOARD SIDE) | 1 | 3 | 3.3 | 45.6 | Idle | 05-25
994 | 32984140 | AP---CALLBACK---RH ENG RH ENG I/B FAN COWL FWD LATCH CENTERING PIN CHAFFED | 1 | 6 |  |  | Not Started | 71-13
996 | 32984174 | PRE---L/H WHEEL WELL---NOCALLBACK---AVN L/H MLG WHEEL WELL CEILING LIGHT 01 EA LAMP FOUND BUSTED. | 1 | 2 |  |  | Not Started | 05-21
997 | 32984360 | FLAP TRACK NO. 4 AND FAIRINGS---AP---NO CALLBACK 2EA AFT BONDING STRAP BROKEN ON FLAP TRACK NO. 4 | 1 | 6 |  |  | Not Started | 05-25
999 | 32984263 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOOTWELL ASSEMBLY REQUIRE REMOVE FOR ACCESS | 1 | 10 | 9.5 | 191.4 | Idle | 25-21
1001 | 32984513 | R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED L/E STRUCTURE TO FACILITATE INSPECTION | 1 | 18 | 18 | 18.6 | Idle | 05-25
1003 | 32984585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT PANEL ASSEMBLY - ACCESS REQUIRE REMOVE FOR ACCESS | 1 | 12 | 11.5 | 219.9 | Idle | 25-21
1004 | 32984729 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 3 |  |  | Not Started | 25
1005 | 32984742 | CAB - NO CALLBACK - AFT GALLEY AFT 7 EA LONG AND 7 EA SHORT CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1006 | 32984765 | CAB - NO CALLBACK - AFT GALLEY AFT GALLEY COMPT. 517 UPPER COVER IS MISSING. | 1 | 2 |  |  | Not Started | 25
1007 | 32984781 | CAB - NO CALLBACK - FWD GALLEY G1 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1008 | 32984766 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU LIGTH COVER NOT SECUERD ABOVE SEAT 32C,38L | 1 |  |  |  | Not Started | 25
1010 | 32984820 | CABIN AREA -AV -NO CALL BACK (NRC) TASKCARD 25-SVA-02 (01) / ITEM ONE PSU SEAT BELT LIGTH INOP AT ABOVE SEAT NO 43K | 1 |  |  |  | Not Started | 25
1011 | 32984829 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY 4 EA LONG AND 4 EA SMALL CART TURN CATCHES PAINT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1012 | 32984848 | SM - NO CALLBACK - GALLEY G2 G2 GALLEY COMP. 205, 202, AND 209 MISSING STRIKER. | 1 |  | 14.3 | 81.3 | Idle | 25-10
1014 | 32984906 | CAB - RII - OXYGEN GENERATORS OXYGEN GENERATORS AT ROW 30 LH AND 34 LH WILL EXPIRE ON 05/2027 ROW 30 LH PN: E63440-00 SN: BEDE-F012-020 ROW 34 LH PN: E63440-00 SN: BEDE-F019-109 | 1 | 6 | 6.5 | 217.6 | Idle | 38
1019 | 32984986 | AP---CALLBACK---ENG. 1 EGT THERMOCOUPLE CHAFFED AT ENG. 1 AT 12 O`CLOCK | 1 | 8 |  |  | Not Started | 05-24
1020 | 32984983 | PRE---APU COMPT---RII---AP APU COMPT, AFT WALL LOWER AREA, 02 EA POINTS FIRE SEAL FOUND WITH CUT AND PUNCTURE. | 1 | 8 |  |  | Not Started | 05-23
1021 | 32985000 | AP---CALLBACK---ENG. 1 HP DUCT PRESSURE SENSE LINE AT 12 O`CLOCK CHAFFED OVER EGT THERMOCOUPLE | 1 | 8 |  |  | Not Started | 05-24
1022 | 32985009 | PRE---APU COMPT---NOCALLBACK---AVN APU COMPT, FWD WALL ILLUMINATION LIGHT, 02 EA LAMPS FOUND BUSTED. | 1 |  | 4 | 124.8 | Idle | 05-23
1023 | 32984981 | DBC/DOCUMENT S51-R10008- RH WING --RII--SM REF TO WO#22`044`538 DURING DBC REVIEW FOUND THE FOLLOWING RH WING INBOARD T/EDGE FLAP ASSY T/EDGE WEDGE LOWER EXTERIOR SURFACE ZONE 2 WITH 5 EACH SMALL DENTS LOCATED BETWEEN FLAP RIB STATION 3 TO 6. DE... | 1 | 4 | 4.3 | 193.1 | Idle | 51
1025 | 32985033 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, R/H DOOR FWD INNER EDGE SEALANT FOUND DETACHED. | 1 | 8 |  |  | Not Started | 05-23
1027 | 32985067 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY WORK SLIDING TABLE STUCK. | 1 | 2 |  |  | Not Started | 25
1028 | 32985066 | PRE---TAIL SECTION---NOCALLBACK---AVN AFT FUSELAGE TAIL SECTION, STROBE LIGHT LENSE FOUND FOGGY AND DIRTY. | 1 | 4 | 9 | 151.2 | Idle | 05-23
1029 | 32985072 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE IDENTIFICATION DECAL FOUND FADED AND WORNOUT. | 1 | 2 | 2 | 119.6 | Idle | 05-23
1030 | 32985083 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1031 | 32985088 | CAB - NO CALLBACK - G2 GALLEY G2 GALLEY COUNTERTOP SEALANT DETERIORATED. | 1 | 2 |  |  | Not Started | 25
1034 | 32985127 | CAB - NO CALLBACK - DESCENT DEVICE FLIGHT DECK FIRST OFFICER EMERGENCY DESCENT DEVICE COVER DETACHED. | 1 | 2 |  |  | Not Started | 25-61
1035 | 32985290 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT UPPER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1036 | 32985304 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1037 | 32985321 | CAB - NO CALLBACK L1 DOOR INBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1038 | 32985332 | CAB - NO CALL BACK L1 DOOR INBOARD F/A SEAT BELT DIRTY | 1 |  |  |  | Not Started | 25
1041 | 32985337 | CAB - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1045 | 32985343 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BELT DIRTY | 1 |  |  |  | Not Started | 25
1046 | 32985344 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT UPPER BUMPER DAMAGED | 1 |  |  |  | Not Started | 25
1048 | 32985349 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1049 | 32985350 | CAB - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1052 | 32985353 | CAB - NO CALLBACK L2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1053 | 32985354 | CAB - NO CALLBACK L2 DOOR F/A SEAT LOWER BACK CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1055 | 32985357 | CAB - NO CALLBACK R2 DOOR F/A SEAT BOTTOM CUSHION WORN OUT | 1 |  |  |  | Not Started | 25
1061 | 32985832 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 1 AC,2AC ,4AC,5AC,30ABC,31ABC,32ABC,34ABC,35ABC,36ABC,37ABC,38ABC,40ABC,41ABC,42ABC,43ABC,44ABC, | 1 |  |  |  | Not Started | 35-23
1062 | 32985833 | CAB -RII DURING OXYGEN GENERATOR CHECK FOUND GREEN LANYARD MISSING AND BRIDLE ASSY AT SEAT# 2JL,4JL,30JKL,31JKL32JKL,34JKL,36JKL,37JKL,38JKL,39JKL,40JKL,41JKL,42JKL,43JKL,44JKL. | 1 |  |  |  | Not Started | 35-23
1063 | 32985836 | RH THS TRAILING EDGE---AP---NO CALL BACK R/H THS TRAILING EDGE HING FITTINGS/ ACTUATOR ATTACHMENT 06EA BOINGING JUMPER BROKEN/FRAYED | 1 | 6 | 2 | 67.4 | Idle | 05-23
1064 | 32985860 | L/H THS TRAILING EDGE---AP---NO CALL BACK L/H THS TRAILING EDGE HING FITTINGS/ ACT ATTACHMENT 05EA BONDING JUMPER BROKEN/FRAYED | 1 | 8 | 2 | 67.4 | Idle | 05-23
1068 | 32985870 | L/H THS ---SM--RII LH THS TRAILING EDGE HINGE FITTING NO 6, INBOARD SIDE WITH CHAFING MARKS DIMENSION L= 0.5 INCH W=0.3 INCH D= 0.1 INCH | 1 |  | 1 | 66.6 | Idle | 05-23
1072 | 32986985 | PRE---REAR AVIONICS COMPT---CALLBACK---AVN REAR AVIONICS COMPT 63VU, 80VU, 187 VU AND 188 VU ELECTRICAL CONNECTIONS AND LOWER ATTACHMETS REQ CLEANING TO FACILITATE THE INSPECTION. | 1 | 6 |  |  | Not Started | 24-92
1073 | 32987001 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO#26`191`406 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE AT FLAP RIB STATION 4 WITH MULTIPL... | 1 |  | 10.8 | 192.8 | Idle | 51
1074 | 32987040 | DBC/DOCUMENT S51-R10008- LH WING --RII--SM REF TO WO# 26191411 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS UPPER SKIN SURFACE 9 INCHES FROM THE TRAILING EDGE OF THE INBOARD FLAP AT... | 1 |  | 3.5 | 192.5 | Idle | 51
1075 | 32987066 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT BELT DIRTY | 1 | 6 |  |  | Not Started | 25-21
1077 | 32987097 | CABIN FLOOR PANELS - CAB -CALLBACK COCKPIT PANEL # 211FF AND CABIN FLOOR PANEL NO: 232WF, 241EF, 241KF, 241LF, 242FF, 242KF, AND 242LF REQUIRES REMOVAL FOR ACCESS. | 1 |  | 29.5 | 185.8 | Idle | 32-33
1078 | 32987238 | LOWER FUSELAGE PANELS - FS -NO CALLBACK LOWER FUSELAGE PANEL # 197BB, 198BB,198GB, 197GB, 192KB, 191KB, 191BB, 197AB, 191GB, 192FB, 192EB, 191HB AND 191AB REQUIRES CLEANING. | 1 |  | 1 | 156.7 | Idle | 53-41
1079 | 32987295 | PRE---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW WEATHER SEAL UPPER AREA FOUND WITH MISSING MATERIAL/WORNOUT AND AFT LOWER AREA FOUND WITH OLD IMPROPER REPAIR. | 1 | 8 | 1 | 165.3 | Idle | 56-10
1081 | 32987455 | PRE---F/O SLIDING WINDOW---RII---AP R/H SIDE F/O SLIDING WINDOW OUTER SURFACE AFT UPPER AND LOWER WEATHER SEAL FOUND DAMAGE. | 1 | 8 |  |  | Not Started | 56-10
1082 | 94844868 | L2 PAX DOOR REF. TO W/O: 94844866 LH-AFT PASSENGER DOOR SEAL RETAINER WITH DENT ON LOWER EDGE. L= 1.3"IN. W= 0.3"IN. D= 0.284"IN. | N |  | 35 | 348.3 | Idle | 52
1083 | 32968390 | S25-D10305/A320 - PORTABLE (ELT) UNIT AND PROGRAMMING DONGLE (AIM) | RON | 0.6 |  |  | Not Started | 25-60
1084 | 32913240 | S28-R10083/A320,321 REPETITIVE FUEL SUMP AND DRAIN - WATER REMOVAL | RON | 2 | 3.5 | 184.7 | Idle | 28
1085 | 32984296 | S34-R10187/A320/A321 - T2CAS - UPDATE OF TERRAIN DATABASE INTO VERSION 227 | PJED | 1.3 |  |  | Not Started | 34
1086 | 32974165 | S52-R10175/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1 | 0.2 |  |  | Not Started | 53
1088 | 32987715 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD OUTER SURFACE UPPER SURFACE WEATHER SEAL FOUND WITH IMPROPER REPAIR APPLICATION AND R/H SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR. | 1 | 8 |  |  | Not Started | 56-10
1091 | 32987890 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`424 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 1 |  | 1.3 | 192.1 | Idle | 51
1092 | 32987935 | DBC/DOCUMENT S51-R10008- LH HORIZONTAL STABILIZER LE --RII--SM REF TO WO#26`191`432 DURING DBC REVIEW FOUND THE FOLLOWING DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND LH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN T... | 1 |  | 1.2 | 169.1 | Idle | 51
1094 | 32987951 | PRE---CPT SLIDING WINDOW---RII---AP L/H SIDE CPT SLIDING WINDOW OUTER SURFACE AFT AND LOWER SIDE WEATHER SEAL FOUND WITH ROUGH REPAIR APPLICATION. | 1 | 8 |  |  | Not Started | 56-10
1095 | 32987959 | PRE---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW WEATHER SEAL AFT LOWER CORNER AREA FOUND DAMAGE. | 1 | 8 |  |  | Not Started | 56-10
1096 | 32987947 | DBC/DOCUMENT S51-R10008- LH WING--RII--SM REF TO WO#26191340 DURING COMPLIANCE OF LH WING DBC SCANNING FOUND LH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE BETWEEN FLAP RIB STATION 6 TO 7 WITH MULTIPLE SMALL DENTS LARGEST DIMENSIO... | 1 |  | 0.2 | 169.3 | Idle | 51
1099 | 32987973 | DBC/DOCUMENT S51-R10008- RH WING--RII--SM REF TO WO#26`191`414 DURING COMPLIANCE OF RH WING DBC SCANNING FOUND RH WING INBOARD FLAPS LOWER SKIN SURFACE AT THE TRAILING EDGE SECTION BETWEEN FLAP RIB STATION 4 TO 5 WITH MULTIPLE SMALL DENTS LARGES... | 1 |  | 5.2 | 169.4 | Idle | 51
1100 | 32987976 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET IDENTIFICATION LABEL FOUND TORN AND NET STRIPS FOUND DETACHED. | 1 | 6 |  |  | Not Started | 25-50
1101 | 32987983 | PRE---AFT CARGO---NOCALLBACK---AP AFT AND BULK CARGO COMPT DOOR NET, IDENTIFICATION LABEL AND DIVIDER NET FOUND EXCESSIVE DIRTY WITH STAIN MARKS. | 1 | 6 |  |  | Not Started | 25-50
1102 | 32987979 | DBC/DOCUMENT S51-R10008-RH HORIZONTAL STABILIZER LE- RII--SM REF TO WO#26`191`479 DURING COMPLIANCE OF EMPENNAGE DBC SCANNING FOUND RH HORIZONTAL STABILIZER LEADING EDGE LOWER SKIN SURFACE SECTION BETWEEN THS RIB STATION 9 WITH MULTIPLE SMALL DEN... | 1 |  | 0.2 | 169.6 | Idle | 51
1103 | 32988009 | PRE---L/H WING FIXED L/E---NOCALLBACK---AP L/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 1 | 8 |  |  | Not Started | 05-25
1104 | 32988013 | PRE---R/H WING FIXED L/E---NOCALLBACK---AP R/H WING FIXED LEADING EDGE (FROM ROOT TO TIP) INNER STRUCTURE, SURFACE PROTECTION FOUND CHIPPED AND MISSING. | 1 | 8 |  |  | Not Started | 05-25
1106 | 32988202 | RUDDER ACTUATOR-AP-RII DURING RUDDER SERVO CONTROL FUNCTIONAL CHECK FOUND YELLOW RUDDER SERVO ACTUATOR OUT OF LIMITS | 1 | 16 |  |  | Not Started | 27-24
1107 | 32988329 | PAINT - NO CALL BACK - CEILING PANEL CEILING PANEL FOUND DAMAGED ABOVE 4LJ | 1 | 2 |  |  | Not Started | 25-10
1108 | 32988444 | PAINT - NO CALL BACK - CEILING PANEL CHIPPED CEILING PANEL CRACKED/CHIPPED AT 41CBA | 1 | 4 |  |  | Not Started | 25-10
1110 | 32988479 | CAB - NO CALL BACK - OSB OSB UPPER TRIM BROKEN AT 44 LKJ | 1 | 1.5 |  |  | Not Started | 25-10
1111 | 32988506 | CAB - NO CALL BACK - GLLY SLIDING TABLE 2EA RETAINER FADED | 1 |  |  |  | Not Started | 25-10
1112 | 32988660 | PANT - NO CALL BACK - OSB OSB AT 44 CBA PAINT CHIPPED & INNER DENTS | 1 | 4 |  |  | Not Started | 25-10
1113 | 32988687 | CAB - NO CALL BACK - OSB OSB DEVIDER DAMAGED AT 32LKJ | 1 | 2 |  |  | Not Started | 25-10
1114 | 32988706 | CAB - NO CALL BACK - EMERGENCY CHART EMERGENCY CHART HOLDER FOUND DAMAGED | 1 | 1 |  |  | Not Started | 25-10
1115 | 32988779 | CAB - NO CALL BACK - OSB OSB UPPER LINER BROKEN AT 3 CA | 1 | 1.5 |  |  | Not Started | 25-10
1116 | 32988786 | PAINT - NO CALL BACK - OSB OSB PAINT FOUND CHIPPED AT 1 CA | 1 | 1 |  |  | Not Started | 25-10
1118 | 32988998 | PRE---FWD CARGO---NOCALLBACK---AP FWD CARGO COMPT CNTR TANK FWD BKHD INSULATION BLANKET FOUND DUSTY AND DIRTY. | 1 | 8 |  |  | Not Started | 28-18
1120 | 32989039 | PRE---VERTICAL STAB---NOCALLBACK---FS VERTICAL STAB TIP AREA ELEMENT FIT ON HARNES 4202VB AND 4204VB SURROUNDING AREA FOUND DUSTY AND DIRTY. | 1 |  | 11 | 130.4 | Idle | 24-92
1121 | 32988850 | CAB - NO CALLBACK - FWD GALLEY FWD GALLEY 8 EA AIR FLAP SEAL DETERIORATED. | 1 |  |  |  | Not Started | 25-10
1122 | 32989105 | PRE---L/H THS---NOCALLBACK---AP L/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 FB, 01 EA ), ( 334 DB, 02 EA ) AND ( 334 BB, 01 EA ) BONDING WIRES FOUND BROKEN. | 1 | 8 |  |  | Not Started | 24-92
1123 | 32989125 | PRE---R/H THS---NOCALLBACK---AP R/H HORIZONTAL STAB TRAILING EDGE ACCESS THROUGH PANELS ( 334 BB,334 CB AND 334 DB ) 05 EA BONDING WIRES FOUND BROKEN. | 1 | 8 |  |  | Not Started | 24-92
1124 | 32989133 | CAB - NO CALL BACK - GLLY G2 GALLEY SEVERAL RUB STRIP FADED | 1 |  |  |  | Not Started | 25-10
1126 | 32989457 | CABIN FLOOR PANELS - CAB - CALLBACK COCKPIT/CABIN FLOOR PANELS 211FF REQUIRE REMOVAL FOR ACCESS. | 1 |  | 2.5 | 169.1 | Idle | 25
1127 | 32989455 | CAB - NO CALL BACK - AFT GALLEY 502 AFT GALLEY COMPARTMENT 502 SLAM LATCH INOP | 1 |  |  |  | Not Started | 25-00
1128 | 32989472 | CAB - NO CALL BACK - B/C HOUSEKEEPING B/C 1A AND 2C REQUIRE HOUSEKEEPING | 1 |  |  |  | Not Started | 25-00
1129 | 32989475 | AV - RII SEATS AT 30ABC TO 34 ABC REQUIRED TO REMOVED ELECTRICAL WIRE FOR ACCESS. | 1 | 8 | 4 | 190 | Idle | 25
1130 | 32989476 | CAB - NO CALL BACK - B/C 4C SHELF GLUE RESIDUE B/C 4C SHELF GLUE RESIDUE | 1 |  |  |  | Not Started | 25-00
1131 | 32989482 | CAB - NO CALL BACK - COMPT. 108 FWD GALLEY COMPT. 108 CARTS COOLING RUBBER WORN OUT | 1 |  |  |  | Not Started | 25
1132 | 32989491 | CAB - NO CALL BACK - GALLEY COMPT. 108 BUMPERS GALLEY COMPT. 108 BUMPERS DEATTACHED. | 1 |  |  |  | Not Started | 25
1133 | 32989492 | CAB - NO CALL BACK - COMPT. 111 FWD GALLEY COMPT. 111 CARTS COOLING RUBBER WORN OUT | 1 |  |  |  | Not Started | 25
1134 | 32989497 | CAB - NO CALL BACK - GALLEY 201 DAMAGED FWD GALLEY COMPT. 201 DOOR TRIM DAMAGED | 1 |  |  |  | Not Started | 25
1135 | 32989529 | FWD GARGO COMPT=====FS=====NO CALL BACK FWD CARGO COMPARTMENT CEILING, SIDE WALL AND SLOPY AREA DIRTY WITH ACCUMULATED DUST | 1 | 30 |  |  | Not Started | 05-21
1136 | 32989545 | L/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-001, L/H FLAP TRACK NO2 AND FAIRINGS REQ CLEANING TO FACILITATE THE INSP. | 1 | 13 | 13.6 | 138.6 | Idle | 05-25
1137 | 32989556 | R/H WING--FS--CALL BACK REF TO TASK CARD NO :ZL-531-02-1-002, ZL-532-01-1-002, , ZL-532-02-1-002 AND , ZL-533-01-1-002 R/H FLAP TRACK AND FAIRINGS NO 2, R/H FLAP TRACK AND FAIRINGS NO 3 R/H FLAP TRACK AND FAIRINGS NO 4 REQ CLEANING TO FACILIT... | 1 | 30 | 31 | 162.6 | Idle | 05-25
1140 | 32989579 | AFT CAB UNDERFLOOR COMP--FS--CALL BACK REF TO TASK CARD NO: ZL-171-01-2 AFT CAB UNDER FLOOR COMPT REQ CLEANING TO FACILITATE THE INSPECTION. | 1 | 15 |  |  | Not Started | 05-21
1141 | 32989728 | CAB - NO CALLBACK - LAV E LAV E SHROUD SCREW MISSING | 1 |  |  |  | Not Started | 25
1142 | 32989743 | CAB - NO CALLBACK - LAV E LAV E BABY BASSINET LOWER STOPPER MISSING | 1 |  |  |  | Not Started | 25
1143 | 32989796 | CAB - NO CALL BACK - AIR VENTILATION ALL LAV AIR VENTILATION FILTERS DIRTY | 1 |  |  |  | Not Started | 25
1144 | 32989797 | S/M - NO CALL BACK - C101 STOWAGE FWD COMPARTMENT C101 FRAME DAMAGE | 1 |  | 4.3 | 81.6 | Idle | 25
1145 | 32989800 | CAB - NO CALLBACK - LAV E LAV E DOOR WASHBASIN SCREW MISSING | 1 |  |  |  | Not Started | 25
1146 | 32989825 | CAB - NO CALL BACK - KICK STRIP KICK STRIP IN FRONT OF 1LJ SEALANT MISSING | 1 |  |  |  | Not Started | 25
1147 | 32989853 | CAB - NO CALL BACK - ICE BOX FWD GALLEY COMPT. 208 ICE BOX FULL OF WATER | 1 | 1 | 2 | 170.1 | Idle | 25
1148 | 32989854 | CAB - NO CALL BACK - FWD GALLEY COMPT. 209 DOOR TEDLAR DAMAGE | 1 |  |  |  | Not Started | 25
1149 | 32989860 | CAB - NO CALL BACK - LAV A SEALANT LAV A ABOVE TOILET SEAT SEALANT MISSING | 1 |  |  |  | Not Started | 25
1150 | 32989874 | CAB - NO CALLBACK-LAV E LAV E PAN FLOOR STRIP SCREW MISSING | 1 |  |  |  | Not Started | 25
1154 | 32989943 | CAB-NO CALL BACK (LAV E) LAV E DOOR HINGE WITH MISSING SCREW 1EA. | 1 |  |  |  | Not Started | 25-10
1155 | 32989944 | #2 ENG - L/H FAN COWL - GUIDE PIN - AP - NO CALL BACK #2 ENG L/H FAN COWL FOUND FWD GUIDE PIN (AFT OF #1 LATCH) WITH DEEP CHAFFING . DISTANCE TO NEAREST EDGE :- 0 INCH. DIM:- L=0.46 INCH. ,W=0.25 INCH. ,D= 0.03... | 1 | 8 |  |  | Not Started | 71-13
1156 | 32989952 | CAB - NO CALLBACK - (LAV E) LAV E DOOR LOCK VACANT IS FADED. | 1 |  |  |  | Not Started | 25-10
1157 | 32989954 | #2 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #2 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 1 | 2 |  |  | Not Started | 71-13
1158 | 32989962 | #2 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #2 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 1 |  | 10 | 186.6 | Idle | 71-13
1160 | 32989963 | #2 ENG - L/H AND R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEELED-OFF. | 1 | 6 | 6 | 136.1 | Idle | 71-13
1162 | 32989965 | #2 ENG - FWD ANTI ICE DUCT - MUSCLE LINE - AP - NO CALL BACK #2 ENG FAN FRAME ASSEMBLY AT 04:00 O`CLOCK POSTION FOUND FWD ANTI-ICE DUCT MUSCLE LINE JAM NUT INSTALLED WRONG POSITION (JAM NUT SECURED AT HOSE END NOT ON BRACKET). | 1 | 3 |  |  | Not Started | 30-21
1163 | 32989966 | #2 ENG - FAN FR ASSY - HMU LINES CLAMPS - AP - RII #2 ENG FAN FRAME ASSEMBLY AT 06:00 O`CLOCK POSTION FOUND HYDROMECHANICAL UNIT (HMU) SOV FUEL LINES (ROD AND HEAD LINES) CLAMPS CORRODED . | 1 | 4 |  |  | Not Started | 24-92
1164 | 32989967 | #2 ENG - IDG FEEDER CABLES CONNECTOR - AVN - NO CALL BACK #2 ENG AT ELECTRICAL CONNECTION JUNCTION BOX FOUND IDG FEEDER CABLE CONNECTOR WITH MISSING SAFTEY WIRE. | 1 | 4 |  |  | Not Started | 24-92
1165 | 32989971 | #2 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #2 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. | 1 |  | 0.2 | 68.9 | Idle | 05-24
1166 | 32989973 | #2 ENG - R/H T/REV - HCU - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FWD FACE FOUND HYDRAULIC CONTROL UNIT (HCU) LEAKING . | 1 | 4 |  |  | Not Started | 05-24
1167 | 32989975 | #2 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #2 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 1 | 4 |  |  | Not Started | 05-24
1168 | 32989976 | #2 ENG - R/H T/REV - OPENING ACT - AP - NO CALL BACK #2 ENG R/H THRUST REVERSER FOUND THRUST REVERSER OPENING ACTUATOR WITH HEAVY LEAK . | 1 | 4 |  |  | Not Started | 05-24
1169 | 32989982 | #2 ENG - R/H T/REV - HEAT SHIELD - SM - RII #2 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 8 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 4 INCH. DIM... | 1 |  | 1.2 | 60.6 | Idle | 05-24
1170 | 32989993 | #2 ENG - L/H TREV - THERMAL BLANKET - SM - RII #2 ENG L/H THRUST REVERSER INNER SIDE FOUND THERMAL BLANKET TORN ( T/REV CHAFFING AGAINST T495 THERMOCOUPLE HARNESS AT 08:00 OCLOCK POSITION) DISTANCE TO NEAREST EDGE :- 2.5 INCH. DIM:- L= 2.31 INCH.... | 1 |  | 0.2 | 59.4 | Idle | 05-24
1171 | 32989995 | RII-CAB SEAT# 30ABC, 31ABC, 32ABC, 33ABC AND 30JKL,31JKL, 32JKL ,33JKL REQUIRE REMOVAL SEAT`S FOR ACCESS. | 1 |  | 35.5 | 193.9 | Idle | 25
1172 | 32989994 | #2 ENG - L/H T/REV - HEAT SHIELD - SM - RII #2 ENG L/H THRUST REVERSER INNER FWD SIDE FOUND HEAT SHIELD WITH 5 CHAFFING MARKS ( T/REV CHAFFING AGAINST DRIAN LINE AND CONNECTOR JUNCTION BOX). #1 CHAFFING DISTANCE TO NEAREST EDGE :- 0 INCH. (CHAFF... | 1 |  | 2 | 66.6 | Idle | 05-24
1174 | 32990008 | CAB RII - F/A L2 F/A SEAT REQUIRE REMOVAL FOR ACCESS | 1 |  |  |  | Not Started | 25-40
1175 | 32990007 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO:33L,34JL,35K,37JL | 1 |  |  |  | Not Started | 25-21
1176 | 32990011 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 38J,K 39J,K,L 40 J,K,L 41 J,K,L 42J,K 43 J,K,L | 1 |  |  |  | Not Started | 25-21
1177 | 32990012 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 43 A,C 42 B,C 40A,C 39A,C AND 38A,B,C | 1 |  |  |  | Not Started | 25-21
1178 | 32990013 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 37A,B,C 36A,B,C 35C 34A,B,C | 1 |  |  |  | Not Started | 25-21
1179 | 32990020 | PAX SEAT--- AV-- NO CALL BACK PAX SEAT , POWER SOCKET SHROUD BROKEN SEAT NO: 33B,C 32A,B,C AND 31A,B | 1 |  |  |  | Not Started | 25-21
1186 | 32990048 | #1 ENG - L/H FAN COWL - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH GOUGE BETWEEN #2 LATCH AND #3 LATCH (ZONE D1) DISTANCE TO NEAREST EDGE :- 3.97 INCH. DIM:- L=0.5 INCH. ,W=0.12 INCH.... | 1 | 8 | 3 | 72.6 | Idle | 71-13
1187 | 32990053 | #1 ENG - L/H FAN COWLS - DENT - SM - RII #1 ENG L/H FAN COWL INNER SURFACE FOUND WITH DENT AT THE MIDDLE (ZONE D3) DISTANCE TO NEAREST EDGE :- 5.75 INCH. DIM:- L=0.61 INCH. ,W=0.5 INCH. D=0... | 1 | 8 | 0.8 | 69.6 | Idle | 71-13
1188 | 32990054 | #1 ENG - L/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG L/H FAN COWL FOUND AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE DISTANCE TO NEARST EDGE :- 0 INCH . (CORROSION REACHED EDGE) AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST ED... | 1 |  | 10 | 186.6 | Idle | 71-13
1189 | 32990067 | #1 ENG - R/H FAN COWL - AFT EDGE PROTEC - SM - RII #1 ENG R/H FAN COWL FOUND AFT EDGE PROTECTOR AND LWER AFT EDGE PROTECTOR WITH PITTING CORROSION AT LOWER SIDE . AFT EDGE PROTECTOR CORROSION DISTANCE TO NEAREST EDGE :- 0 INCH . (CORROSION REACH... | 1 |  | 17.8 | 182.6 | Idle | 71-13
1190 | 32990167 | #1 ENG - R/H FAN COWL - CLEVIS DECAL - PNT - NO CALL BACK #1 ENG - R/H FAN COWL INNER SIDE FOUND " NEVER TURN CLEVIS" DECAL FADED AND EDGES PEELED-OFF . | 1 | 2 |  |  | Not Started | 71-13
1191 | 32990169 | #1 ENG - R/H FAN COWL - HAZARD DECAL - PNT - NO CALL BACK #1 ENG R/H FAN COWLS EXTIROIR SURFACE FOUND ALL "STAY CLEAR OF HAZARD AREA DURING ENGINE RUNNING" DECALS FADED AND EDGES PEALED-OFF. | 1 | 3 |  |  | Not Started | 71-13
1192 | 32990170 | #1 ENG - R/H FAN COWL - PRESS DR - AP - RII #1 ENG R/H FAN COWL INNER SIDE FOUND PRESSURE RELIEF DOOR UPPER AND LOWER SPRING LOADED ARMS HINGES RUSTED AND UPPER SPRING LOADED ARM LANYARD FWD END CHAFFED-OFF AND SPRING LOADED ARM END GOUGED. | 1 | 8 |  |  | Not Started | 71-13
1193 | 32990171 | #1 ENG - L/H FAN COWL - METAL STRIP - SM - RII #1 ENG L/H FAN COWL UPPER SIDE FOUND METAL STRIP (BEHIND FAN COWL HINGES) WITH GOUGE AT FWD SIDE DISTANCE TO NEAREST EDGE :- 0.12 INCH. DIM:- L= 5.5 INCH. ,W=0.25 INCH.... | 1 |  | 0.3 | 44.1 | Idle | 71-13
1194 | 32990173 | #1 ENG - FAN FR - ASSY - IDG QAD - AP - NO CALL BACK #1 ENG FAN FRAME ASSEMBLY AT 05:30 O`CLOCK POSITION FOUND IDG QUICK ATTACH/DETACH (QAD) BOLT WITH WRONG DIRECTION SAFETY WIRE. | 1 | 4 |  |  | Not Started | 24-92
1195 | 32990192 | #1 ENG - L/H AND R/H T/REV - TEFLON SEAL - SM - RII #1 ENG L/H AND R/H THRUST REVERSERS AT FWD SIDE FOUND FAN COWLS RUB TEFLON SEAL DETERIORATED AND DETACHED. (R/H T/REV TEFLON SEAL DETACHED FROM UPPER AND LOWER SIDE). | 1 |  | 0.3 | 69.1 | Idle | 05-24
1196 | 32990196 | #1 ENG - L/H T/REV - LOWER BLOCKER DR - AP - NO CALL BACK #1 ENG L/H THRUST REVERSER FOUND LOWER BLOCKER DOOR ACTUATOR WITH HEAVY LEAK AT ROD END. | 1 | 3 |  |  | Not Started | 05-24
1197 | 32990203 | #1 ENG - L/H AND R/H T/REV - COOLING HOSE - AP - NO CALL BACK #1 ENG L/H AND R/H THRUST REVERSERS INNER SIDE FOUND THRUST REVERSER OPENING ACTUATORS COOLING HOSES DETERIORATED . | 1 | 8 |  |  | Not Started | 05-24
1198 | 32990219 | #1 ENG - R/H T/REV - HEAT SHIELD - SM - RII #1 ENG R/H THRUST REVERSER AT INNER FWD SIDE FOUND HEAT SHILED WITH 4 CHAFFING MARKS (T/REV CHAFFING AGAINST ANI-ICE MUSCLE LINE AND ITS BRACKETS AND CONNECTION JUNCTION BOX). #1 CHAFFING DISTANCE TO N... | 1 |  | 2 | 62.6 | Idle | 05-24
1199 | 32991206 | CAB - NO CALL BACK - OSB OSB MISSING RUBBER BUMBER 20 EA | 1 |  |  |  | Not Started | 25-10
1200 | 32991276 | AV - NO CALLBACK - PAX SEATS ELECTRICAL CONNECTIONS AT SEATS 30RH TO 34RH REQUIRE REMOVAL FOR ACCESS. | 1 |  | 4 | 190.1 | Idle | 25
1201 | 32991499 | PNT - RII - LAV A LAV A ACCESS DOOR WASTE COMPARTMENT HAS SMALL SCRATCHES ON UPPER SIDE. | 1 |  |  |  | Not Started | 25
1202 | 32991511 | CAB - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SMALL CRACK NEXT TO LATCH. | 1 |  |  |  | Not Started | 25
1204 | 32991518 | FINDING (NRC) TASKCARD ZL-531-02-1-001 (01) LH WING AP-- NO CALLBACK LH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT. | 1 | 6 |  |  | Not Started | 05-25
1205 | 32991527 | CAB - RII - LAV E LAV E WASTE FLAP DAMPER INOP | 1 |  |  |  | Not Started | 25
1206 | 32991534 | PNT - RII - LAV E LAV E ACCESS DOOR WASTE COMPARTMENT WITH SCRATCHES FROM OUTSIDE. | 1 | 3 |  |  | Not Started | 25
1207 | 32991563 | RH WING -- FT REFER TO TC # 572020-01-1-002, 572040-01-2-002, 572139-01-2-002, 572140-01-2-002 AND 572161-01-11-002 REQUIRE TO REMOVE RH WING FUEL TANK ACCESS PANELS - 640AB, 640BB , 640CB, 640DB, 640EB, 640FB, 640GB - 640HB, 640JB, 640KB, 640LB... | 1 |  | 96 | 192.1 | Idle | 57
1209 | 32991584 | LH WING -- FT REFER TO TC # 572020-01-1-001, 572040-01-2-001, 572139-01-2-001, 572140-01-2-001 AND 572161-01-11-001 REQUIRE TO REMOVE LH WING FUEL TANK ACCESS PANELS - 540AB, 540BB , 540CB, 540DB, 540EB, 540FB, 540GB - 540HB, 540JB, 540KB, 540LB... | 1 |  | 81.8 | 191.3 | Idle | 57
1210 | 32991594 | FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--NO C/B RH WING FLAP TRACK NO#2 AFT BONDING WIRE WITH CUT . | 1 | 6 | 5 | 46.3 | Idle | 05-25
1211 | 32991646 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS. | 1 |  | 4 | 189.8 | Idle | 53-41
1212 | 32991651 | AVIO - N0 CALL BACK - SEAT CONNECTION ELECTRICAL CONNECTIONS AT SEATS 39LH TO 44LH REQUIRE REMOVAL FOR ACCESS. | 1 |  | 4 | 189.8 | Idle | 53-41
1213 | 32991622 | FINDING (NRC) TASKCARD ZL-531-02-1-002 (01) RH WING AP--CALLBACK FLAP TRACK NO#2 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 1 | 6 |  |  | Not Started | 05-25
1214 | 32991955 | FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP--NO CALLBACK RH WING FLAP TRACK NO#3 AFT BONDING WIRE WITH CUT . | 1 | 6 |  |  | Not Started | 05-25
1215 | 32991957 | FINDING (NRC) TASKCARD ZL-532-01-1-002 (04) RH WING AP-- CALLBACK FLAP TRACK NO#3 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 1 | 6 |  |  | Not Started | 05-25
1216 | 32991972 | FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK FLAP TRACK NO#4 IN/B FWD UPPER ACTUATOR SUPPORT LINK TEFLON COLLAR NOT SECURED. | 1 | 4 |  |  | Not Started | 05-25
1217 | 32991973 | FINDING (NRC) TASKCARD ZL-533-01-1-002 (04) RH WING AP--CALLBACK RH WING FLAP TRACK NO#4 AFT BONDING WIRE WITH CUT . | 1 | 6 |  |  | Not Started | 05-25
1218 | 32992461 | MACHINIST - NO CALLBACK - FWD GALLEY G2 FWD G2 GALLEY COMP. 209 HINGE SCREW THREAD FOUND WITH BROKEN SCREW. | 1 |  | 6.7 | 170.1 | Idle | 25
1219 | 32992488 | CAB - CALL BACK - AFT GLLY AFT GALLEY REQUIRE REMOVAL FOR ACCESS | 1 |  | 45.5 | 187.2 | Idle | 53-41
1220 | 32992489 | CAB - CALLBACK - G1 GALLEY G1 GALLEY REQUIRE REMOVAL FOR ACCESS. | 1 |  | 10 | 178.8 | Idle | 25
1221 | 32992493 | CAB - CALLBACK - LAV A "LAVATORY A" REQUIRE REMOVAL FOR ACCESS. | 1 |  | 32 | 52.8 | Idle | 25
1222 | 32992492 | CAB - CALL BACK - LAV E LAVATORY "E" REQUIRE REMOVAL FOR ACCESS | 1 |  | 32.5 | 161.7 | Idle | 53-41
1223 | 32992500 | CAB - CALL BACK - LAV D LAVATORY "D" REQUIRE REMOVAL FOR ACCESS | 1 |  | 3 | 157.9 | Idle | 53-41
1224 | 32992517 | CAB - CALLBACK - STOWAGE C1 "STOWAGE C1" REQUIRE REMOVAL FOR ACCESS. | 1 |  | 9.5 | 169.1 | Idle | 25
1225 | 32992509 | CAB - CALL BACK- SEAT SEATS FROM 39LH TO 44 LH AND 39RH TO 44RH REQUIRE REMOVAL FOR ACCESS | 1 |  | 26 | 185.7 | Idle | 53-41
1227 | 32992699 | CAB - NO CALLBACK - LAV D LAV D DOOR HINGE SCREW MISSING | 1 |  |  |  | Not Started | 25-10
1228 | 32992702 | CAB - NO CALLBACK - LAV D LAV D LOWER CABINET LATCH SCREW MISSING | 1 |  |  |  | Not Started | 25-10
1229 | 32992708 | CAB - NO CALLBACK - LAV D LAV D DOOR FRAME SCREW MISSING | 1 |  |  |  | Not Started | 25-10
1230 | 32992709 | CAB - NO CALLBACK - LAV D LAV D THRESHOLD SCREW MISSING | 1 |  |  |  | Not Started | 25-10
1231 | 32992712 | CAB - NO CALLBACK - LAV D LAV D TOILET SHROUD NOT SECURED | 1 |  |  |  | Not Started | 25-10
1232 | 32992717 | CAB - NO CALLBACK - LAV D LAV D TOILET SEAT COVER BROKEN | 1 |  |  |  | Not Started | 25-10
1233 | 32992719 | CAB - NO CALLBACK - LAV D LAV D DOOR LOCK LABLE FADED | 1 |  |  |  | Not Started | 25-10
1234 | 32992731 | CAB - RII - SEAT REMOVAL FOR ACCESS SEAT 5JL REQUIRE REMOVAL FOR ACCESS | 1 |  | 5 | 166.6 | Idle | 25
1235 | 32992738 | CAB - NO CALL BACK - COFFEE MAKER AFT GALLEY COFFEE MAKER NO.1 STENCIL | 1 |  |  |  | Not Started | 25
1236 | 32993162 | UPPER AFT FUSELAGE SKIN=====SM====RII ACCESS THRU VERTICAL STABILIZER LEADING EDGE PNL 321AL FUSELAGE SKIN AREA AROUND 02EA HARNESS CONNECTION (4202VB, 4204VB) FOUND WITH PITTING CORROSION AROUND THE WHOLE CIRCUMFERENCE MAXIMUM LENGTH = 0.9" | 1 |  | 38.2 | 157.1 | Idle | 24-92
1239 | 32993252 | ENGINE#2 PYLON DRAIN--AP--NO CALL BACK ENGINE #2 PYLON ALL 03EA DRAIN LINE GRIL ENTRY POINT AND ADJACENT AREA DIRTY WITH ACCUMULATED DIRT | 1 | 8 |  |  | Not Started | 54-50
1240 | 32993255 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #5 OUT BOARD HINGE BONDING JUMPER BROKEN. | 1 | 6 | 6.3 | 46.3 | Idle | 05-25
1241 | 32993268 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #4 IN BOARD HINGE BONDING JUMPER BROKEN. | 1 | 6 | 2.3 | 44.6 | Idle | 05-25
1245 | 32993287 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, FROM RIB 08 TO RIB 27 HYD TUBE LINE MULTIPLE AREA TIE WRAP BROKEN | 1 | 6 |  |  | Not Started | 05-25
1246 | 32993288 | R/H WING TRAILING EDGE---AP---- NO CALL BACK R/H WING TRAILING EDGE, NEAR SPOILER #4, 2EA HYD TUBE LINE TIE WRAP BROKEN. | 1 | 6 |  |  | Not Started | 05-25
1250 | 32994149 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT FOODTRAYS ARE NOT ADJUSTABLE. | 1 | 6.5 | 8 | 25.7 | Idle | 25-25
1254 | 32994746 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT HEADREST REQUIRE REMOVE FOR ACCESS | 1 | 2 | 1.5 | 87.1 | Idle | 25-21
1255 | 32994800 | AFT OF BLK CGO-----F/S---------NO CALL BACK BLK CGO AFT OF AFT PARTTION AREA DIRTY | 1 | 14.5 | 14.5 | 19 | Idle | 05-21
1258 | 32995553 | AP---CALLBACK---LH WING LH WING INTERCONNECT STRUT LOWER KINK SEAL WITH CUT | 1 | 8 |  |  | Not Started | 27-51
1261 | 32996054 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--CAB RH EMERGENCY EXIT HATCH DOOR WITH DOOR SEAL WORN AT LOWER EDGE | 1 |  |  |  | Not Started | 05-28
1262 | 32996073 | FINDING (NRC) TASKCARD ZL-833-02-1 (04) / ITEM-1 RII--SM RH FWD EMERGENCY EXIT HATCH DOOR CUTOUT WITH ABRAISION AT LOWER EDGE L=80 MM W=10 MM | 1 | 3 | 0.2 | 43.6 | Idle | 05-28
1263 | 32996598 | FINDING (NRC) TASKCARD ZL-171-02-1 (2) / ITEM-1 SM--RII FUSELAGE SKIN INNER SURFACE WITH SURFACE CORROSION LOCATED BETWEEN FR 65-66 AND STRG 43-42L (VISIBLE THROUGH BULK CARGO AFT PARTITION PANELS) | 1 |  | 37.8 | 97.4 | Idle | 05-21
1265 | 32996715 | FWD CGO COMPT====AP===NO CALL BACK FWD CARGO COMPT AFT SIDE PACK AIR RECIRCULATION FILTER ELEMENTS BOTH ACCUMULATED WITH DIRT. | 1 | 4 |  |  | Not Started | 21-52
1266 | 32996751 | L/H WING REFUEL DEFUEL COUPLING===AP==RII L/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING. | 1 | 8 |  |  | Not Started | 28-25
1267 | 32996759 | R/H WING REFUEL/DEFUEL COUPLING===AP====RII R/H WING REFUEL/DEFUEL COUPLING-CAP CHAIN ASSEMBLY IS MISSING | 1 | 8 |  |  | Not Started | 28-25
1269 | 32997085 | APU BLEED DUCT=====AP======CALL BACK APU BLEED DUCT CHECK VLV SPRING BROKEN | 1 | 6 |  |  | Not Started | 36-12
1270 | 32998086 | RUDDER-----------NO CALLBACK-------------AF RUDDER ATTACH FITTING NO. 6 FOUND BONDING LEAD BROKEN. | 1 | 6 |  |  | Not Started | 55-40
1271 | 32998113 | GALLEY - PAINT - NO CALL BACK FWD AND AFT GALLEY ALL OVEN DOORS PAINT CHIPPED OFF . | 1 | 13 | 13 | 147.7 | Idle | 25-20
1272 | 32998140 | ENG 02 PYLON - PAINT - NO CALL BACK ENG 02 PYLON PANEL 423AR AND 423CR PAINT PEELED OFF. | 1 | 7 | 6.5 | 147.6 | Idle | 51-75
1273 | 32998206 | FINDING (NRC) TASKCARD 532181-02-1 (0) / ITEM-1 REF TO SEQ 489 INSPECTION AREA BETWEEN FR 34-35 AND STRG 38LH-38RH REQUIRE OPEN UP AND CLEANING FOR INSPECTION | 1 | 8 | 3 | 97 | Idle | 53
1274 | 32998241 | FINDING (NRC) TASKCARD 532137-03-1 (1) / ITEM ONE SM--RII FWD CARGO DOOR CUTOUTS BOTH FWD AND AFT LOWER CUTOUTS AT FRAMES FR24A AND FR28 WITH BOTH FITTINGS MISSING FASTNERS (2EA PER FITTING) | 1 |  | 0.2 | 49.1 | Idle | 53-21
1277 | 32998934 | FINDING (NRC) TASKCARD ZL-127-02-2 (3) / ITEM-1 FS--CALLBACK REF TO SEQ 106 REAR AVIONICS COMPARTMENT ACCESSIBLE THROUGH DOOR 824 AFT AVIONICS COMPARTMENT DOOR AREA AROUND DOOR CUTOUT AND BELOW COMPARTMENT FLOOR PANELS WITH DIRT REQ CLEANING FOR I... | 1 | 100 | 2 | 22.6 | Idle | 05-21
1278 | 33000741 | FINDING WING - PNT-NO CALL BACK L/H AND R/H WING INBD LOWER SURFACE WATER DRAIN VALVE DECALS MISSING . | 1 | 2 | 2 | 119.4 | Idle | 11-00
1279 | 33000793 | AP---RII---APU DOOR APU RIGHT ACCESS DOOR FWD AND MID WALL FIRE SEAL DETACHED | 1 | 8 |  |  | Not Started | 49-13
1280 | 33000799 | AP---CALLBACK---AFT BULKHEAD REMOVE REAR PRESSURE BULKHEAD COVER FOR INSPECTION | 1 | 8 | 9 | 117.7 | Idle | 53-51
1281 | 33001011 | L/H WING PNT - NO CALLBACK LH MLG (FWD OF MLG ) LWR SURFACE SKIN REINFOREING PLATE PNT CHIPPED OFF | 1 | 9 | 9 | 117.2 | Idle | 51-75
1282 | 33001198 | AP---NO CALLBACK---RUDDER RUDDER BR6 BONDING JUMBER CUT | 1 | 3 |  |  | Not Started | 05-23
1283 | 33001199 | AP---NO CALLBACK---RUDDER ALL RUDDER AFT HOLES COVER ARE TORN | 1 | 6 |  |  | Not Started | 05-23
1284 | 33001270 | FS---CALLBACK---AVN COMP AVIONICS COMP. STRUCTURE AFTER INSULATION BLANKET REMOVAL NEED DEEP CLEANING | 1 |  | 2.6 | 22.5 | Idle | 05-21
1286 | 33002727 | AP---CALLBACK---RH WING SLAT 1 RH WING SLAT 1 OUTBOARD EDGE SEAL CUT OFF | 1 | 6 |  |  | Not Started | 57-42
1287 | 33002757 | S52-R10176/ASD // L2 PAX DOOR SEAL RETAINER WITH DENT & GOUGE | 1 | 0.5 |  |  | Not Started | 53
1289 | 33002784 | PNT - NO CALLBACK - OSBD SEVERAL B/C OSB DOORS REQ PAINT. | 1 | 24 | 3 | 51 | Idle | 25
1290 | 33002861 | AP---CALLBACK---RH WING SLAT 5 RH WING SLAT 5 OUTBOARD EDGE SEAL CUT OFF | 1 | 6 |  |  | Not Started | 57-46
1291 | 33003253 | FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 4 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 1 | 6 |  |  | Not Started | 57-45
1292 | 33003265 | FINDING (NRC) TASKCARD 574505-01-1-001 (02) / ITEM-1 AP--CALLBACK LH WING SLAT N.O 4 INNER RUBBER SEAL TORN 2 EA | 1 | 4 |  |  | Not Started | 57-45
1293 | 33003278 | AP---RII---RH WING SLAT 4 RH WING SLAT 4 INBOARD TRACK LOWER PLATE ATTACHMENT CRACKED | 1 | 6 |  |  | Not Started | 57-45
1294 | 33003279 | SM - BRACKET ABOVE COCKPIT DOOR BRACKET ABOVE COCKPIT DOOR REQUIRE REMOVAL FOR ACCESS | 1 |  | 10.7 | 74.6 | Idle | 53-11
1295 | 33003366 | FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 5 INNER RUBBER SEAL TORN 1 EA | 1 | 4 |  |  | Not Started | 57-46
1296 | 33003374 | FINDING (NRC) TASKCARD 574605-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 1 | 6 |  |  | Not Started | 57-46
1297 | 33007153 | FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 1 | 4 |  |  | Not Started | 57-42
1298 | 33007155 | FINDING (NRC) TASKCARD 574205-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 1 INNER RUBBER SEAL TORN 1 EA AT SLAT INNER INBOARD SIDE | 1 | 4 |  |  | Not Started | 57-42
1299 | 33007178 | FINDING (NRC) TASKCARD 574305-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 2 LOWER PLATE LOCATED AT SLAT ATTACHMENT FITTING CRACKED 1EA | 1 | 6 |  |  | Not Started | 57-43
1300 | 33007172 | EOD-320-31-00012-R00/FDIMU - INSTALL NEW ADC DMU SW FOR FOMAX | PJED | 2 |  |  | Not Started | 31
1301 | 33007347 | FINDING (NRC) TASKCARD 574405-01-1-001 (02) / ITEM-1 AP--RII LH WING SLAT N.O 3 INNER RUBBER SEAL TORN 1 EA | 1 | 4 |  |  | Not Started | 57-44
1302 | 33011258 | PNT - NO CALL BACK - COCKPIT PANELS SEVERAL COCKPIT ACCESS PANELS REQ. PAINT ( 211AW, 211BW, 211FW, 211LW, 211AZ, 212AW, 212BW, 212FW, 212AZ ) | 1 | 24 |  |  | Idle | 25
1304 | 33012238 | UPPER FUSELAGE=====SM====RII UPPER FUSELAGE UNDERNEATH LARGE SATCOM ANTENNA 04EA RIVETS HEAD WITH PITTING CORROSION LOCATION BETWEEN FRAME 29-32 ALONG STRINGER 01RH AND 01LH DIMENSION AS FOLLOWS ALONG STR 01LH LENGTH = 01CM WIDTH = 0... | 1 | 8 | 9 | 50.6 | Idle | 05-21
1305 | 33012374 | L/H WING --- A/P ---CALL BACK L/H WING T/EDGE BETWEEN RIB 5 TO RIB 8 WITH TPS MISSING | 1 | 6 |  |  | Not Started | 57-51
1306 | 33012961 | L/H WING ---AP--- RII L/H WING I/B SIDE BETWEEN RIB 5 TO RIB 8 TORQUE SHAFT SEVERAL BOLTS WITH RUSTY | 1 | 6 |  |  | Not Started | 57-21
1308 | 33013430 | L/H WING ---SM--- RII L/H WING TRAILING EDGE NEAR SPOILER NO 3 ON TOP SKIN 3EA RIVET LOOSE /BROKEN | 1 |  | 0 | 43.4 | Idle | 57-21
1309 | 33013444 | L/H WING--- AP-- NO CALL BACK L/H WING TRAILING EDGE SPOILER NO.4 I/B HINGE BONDING WIRE WITH BROKEN. | 1 | 4 | 3 | 10.8 | Idle | 53-41
1310 | 33013470 | L/H WING --- AP--- NO CALL BACK L/H WING FLAP TRACK MOV FAIRING NO 2 AND 3 BONDING WIRE WITH BROKEN. | 1 | 6 | 3 | 10.9 | Idle | 57-26
1311 | 33013486 | L/H WING--- S/M ---- RII L/H WING O/B ACCESS THROUGHT PANEL # 575LB STRIP METAL DETACHED | 1 |  | 0.2 | 49.3 | Idle | 57-21
1312 | 33013510 | AVIONICS COMPT=======AV======NO CALL BACK REAR AVIONICS COMPT 63, 80, 187VU AND 188VU WIRING INSTALLED DIRTY WITH ACCUMULATED DUST | 1 | 4 |  |  | Not Started | 24-92
1313 | 33013536 | VERTICAL STABILIZER ATTACH FITTING=====FS======CALL BACK REFER TO TASK CARD 553004-01-1 VERTICAL STABILIZER ATTACH FITTINGS INCLUDING THE LOAD INTRODUCTION AREA AT THE SKIN PANELS REQ CLEANING TO FASCILITATE INSPECTION | 1 |  |  |  | Not Started | 55-36
1314 | 33013562 | ENG NO#01=====SM=====RII ENG NO#01 LH THR/REV NEAR THE FWD MOST HINGE ADJACENT STRUCTURE WITH BULGE ASSOCIATED WITH DELAMINATION DIMENSION AS FOLLOWS LENGTH = 3.5" WIDTH = 3" | 1 |  | 0.2 | 43.8 | Idle | 78-32
1315 | 33014957 | RADIO ALTIMETER - CALLBACK REF TO TC 344200-02-2 SEQ 589 - DISCARD OF RA ANTENNAS AND COAX CABLES | 1 | 8 |  |  | Not Started | 34-42
1316 | 33015570 | CAB - RII - COCKPIT CAPTAIN SEAT INERTIA REEL FAILED TO RETRACT PROPERLY. | 1 |  |  |  | Not Started | 25
1317 | 33017436 | CAB - NO CALL BACK - CURTAIN RAIL FWD GALLEY CURTAIN RAIL DEFORMED | 1 |  |  |  | Not Started | 25
1318 | 33017645 | CAB - NO CALL BACK - GALLEY G2 GALLEY COMP. 204 2EA TURN CATCH FADED | 1 |  |  |  | Not Started | 25-10
1319 | 33017650 | FINDING TASKCARD 532181-02-1 (0) /FWD FUSELAGE---STR---RII FIXED PARTITION STRUCTURE, FR34, (Y-765, Y765) LOWER ATTACHMENT DETACHED | 1 |  |  |  | Not Started | 53
1320 | 33018932 | CTR WING BOX REAR SPAR---CAB--CALLBACK REQ REMOVAL OF THE APPLICABLE INSULATION BLANKETS TO GET ACCESS TO THE INSPECTION AREA (FR42) | 1 |  |  |  | Not Started | 57-10
1321 | 33019264 | ESCAPE SLIDE -RII FWD PAX DOOR L/H ESCAPE SLIDE RQE REMOVED FOR ACCESS P/N : D30664-709 S/N: M18949 | 1 |  | 6 | 70.3 | Idle | 25-62
1322 | 33019321 | SM---RII---NLG ERROSION FOUND ON RH NOSE GEAR SWIVEL BEARING BUSHING | 1 |  | 1 | 25.5 | Idle | 32-21
1323 | 33019327 | ESCAPE SLIDE RII FWD PAX DOOR ESCAPE SLIDE R/H RQE REMOVAL FOR ACCESS PN/: D30664-709 S/N : C0740 | 1 |  | 6 | 70.2 | Idle | 25-62
1324 | 33019384 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE R/H RQE REMOVED FOR ACCESS PN/ D30665-709 SN/ M8479 | 1 |  | 9 | 70 | Idle | 25-62
1325 | 33019437 | ESCAPE SLIDE RII AFT PAX DOOR ESCAPE SLIDE L/H RQE REMOVEVAL FOR ACCESS PN / D30665-709 SN/ M14410 | 1 |  | 9 | 70 | Idle | 25-62
1326 | 33019665 | FINDING TASKCARD 531164-01-1 / FUSELAGE FR15-21-FS--CALLBACK REQ CLEANING OF FUSELAGE FR20-21; STR28LH-STR28LH TO FACILITATE INSPECTION | 1 | 20 | 20 | 29 | Idle | 53-11
1327 | 33014938 | S71-R10396/HZ-ASD ENG.1 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 1 | 4.5 |  |  | Not Started | 71
1328 | 33014940 | S71-R10397/HZ-ASD ENG.2 REPLACEMENT OF RH FAN COWL FWD AND AFT EDGE PROTECTORS | 1 | 4.5 |  |  | Not Started | 71
1329 | 33014947 | S71-R10398/HZ-ASD ENG.1 REPLACEMENT OF LH FAN COWL AFT EDGE PROTECTORS | 1 | 6 |  |  | Not Started | 71
1330 | 33019887 | AFT CARGO - UNDERFLOOR - FS -CALLBACK AFT CARGO UNDERFLOOR REQ ZONAL CLEANING FROM FRAME 46 TO 51 | 1 | 19.5 | 33.8 | 66.4 | Idle | 53
1331 | 95001843 | ROB .. REF TO TQ. 832572 AEVC P/N.87292325V07 S/N.VL2062006144 ROBBED TO SVC HZ-ASP. AS PER A320 AMM 21-26-34-000-001-A REV.69 DATE.01 MAY 2026 | N | 4 | 3 | 63.6 | Idle | 21-00
1332 | 33020601 | FWD PAX DOORS PNT NO CALL BACK FWD PAX DOORS LINING AND FRAME LINIING WHILE REMOVING FOUND WITH PNT FADED . | 1 | 24 | 2 | 36.8 | Idle | 52-10
1333 | 33020680 | AFT PAX DOORS PANT FEDED NO CALL BACK AFT PAX DOORS LINING AND FRAME LINING FOUND WITH FADED PNT. | 1 | 24 | 6 | 38.8 | Idle | 52-10
1334 | 33020727 | CAB - UNDER FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN UNDER FLOOR STRUCTURE FOUND MOST R/H SEAT TRACK (Y-1292) FWD OF FR47 WITH EXCESSIVE PLAY AND AFT ATTACHMENT BOLT WITH MISSING NUT . | 1 |  |  |  | Not Started | 05-21
1335 | 33020728 | AFT CGO COMPT=====AP=====RII AFT CGO COMPT FWD LEFT HAND SIDE APU DUCT CLAMP INSTALLATION ADJACENT AREA INSULATION BLANKETS WITH BURN MARKS (SIGN OF LEAK) | 1 | 4 |  |  | Not Started | 28-11
1336 | 33020729 | CAB - FLOOR STRUC - SEAT TRACK (Y-1292) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-1292) FWD OF FR42 WITH GOUGE AT THE MIDDLE OF SEAT TRACK . DIM:- L=0.31 INCH. ,W=0.17 INCH.... | 1 |  | 7.8 | 42 | Idle | 05-21
1337 | 33020731 | CAB - FLOOR STRUC - SEAT TRACK (Y-765) - SM - RII CABIN FLOOR STRUCTURE FOUND SEAT TRACK (Y-765) FWD OF FR41 WITH GOUGE AT UPPER FLANGE OF SEAT TRACK . DIM:- L=0.78 INCH. ,W=0.15 INCH.... | 1 |  | 4 | 40.5 | Idle | 05-21
1338 | 33020734 | CAB - UNDER FLOOR - CAB - CALL BACK CABIN FROM FR 43 TO FR46 FOUND UNDER FLOOR STRUCTURE WITH MISSING CIC APPLICATION AND FROM FR36 TO FR46 FOUND UNDER FLOOR STRUCTURE , AIR CONDITIONING DUCT , LINES DUSTY AND WITH EXCESSIVE LINT ACCUMULATION. | 1 |  |  |  | Not Started | 05-21
1339 | 33021722 | MACHINEST - NO CALL BACK - OVEN G1 GALLEY OVEN COMP. 104 SCREWS FROZEN | 1 |  |  |  | Not Started | 25
1340 | 33021799 | EMERGENCY EXIT HATCH - CABIN - NO CALLBACK AROUND EMERGENCY EXIT HATCH PANEL AND INSULATION BLANKET REQ REMOVAL | 1 |  | 4 | 39.6 | Idle | 53-00-00
1341 | 33021843 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP 207. LATCH INOP | 1 |  |  |  | Not Started | 25
1342 | 33022670 | CAB - NO CALL BACK - GALLEY G2 GALLEY FOOT STEP LEVER MISSING | 1 |  |  |  | Not Started | 25
1343 | 33022800 | CAB - NO CALLBACK - FWD FLOOR MAT J/C ENTRY WAY AND FWD GALLEY FLOOR MAT REQUIRE REPLACEMENT. | 1 |  |  |  | Not Started | 25-28
1344 | 33022853 | CAB - NO CALL BACK - GALLEY G1 GALLEY COMP. 101 SLIDE EXTRACTOR INOP | 1 |  |  |  | Not Started | 25
1345 | 33022868 | CAB - NO CALLBACK - COCKPIT F/O SLIDING WINDOW BLIND ROLLER DETERIORATED. | 1 |  |  |  | Not Started | 25-10
1347 | 33022953 | CAB - NO CALLBACK - COCKPIT CAPTAIN FOOTREST RUBBER MAT WORN-OUT. | 1 |  |  |  | Not Started | 25
1348 | 33022966 | CAB - NO CALLBACK - COCKPIT FLIGHT DECK CAPTAIN AND FIRST OFFICER PEDAL RUBBER MAT DIRTY. | 1 |  |  |  | Not Started | 25-10
1349 | 33022983 | CAB - NO CALLBACK - LAV A LAV A SERVICE CABIINET HINGE LOOSE. | 1 |  |  |  | Not Started | 25
1353 | 33023666 | CAB - RII - COCKPIT FLIGHT DECK FIRST OFFICER SEAT HARNESS DETERIORATED. | 1 |  |  |  | Not Started | 25
1355 | 33023745 | CAB - RII - 4TH OCCUPANT FLIGHT DECK SEAT 4TH OCCUPANT HARNESS DETERIORATED. | 1 |  |  |  | Not Started | 25-10
1356 | 33023803 | CAB - RII - 3RD OCCUPANT FLIGHT DECK 3RD OCCUPANT LOWER SHROUD NEXT TO LIFE VEST COVER DEFORMED. | 1 |  |  |  | Not Started | 25-10
1357 | 33023820 | CAB - NO CALL BACK - GALLEY G1 GALLEY OVEN #1 UPPER GRILL DE ATTACHED | 1 |  |  |  | Not Started | 25-10
1358 | 33023837 | CAB - NO CALL BACK - GALLEY FWD GALLEY (G1,G2) SIDE TURN CATCH FADED | 1 |  |  |  | Not Started | 25
1359 | 33024557 | VERTICAL STABLIZER HINGE FITTING (EOD-320-55-00001-R00) AS PER (EOD-320-55-00001-R00) ALL HINGE FITTINGS REQUIRE NDT AFTER REMOVAL . | 1 |  | 4 | 37.6 | Idle | 55
1360 | 33025667 | CAB - RII - R2 DOOR PANEL ASSY-FLOOR L2 & R2 DOOR PANEL FLOOR ASSY WITH DAMAGE | 1 |  |  |  | Not Started | 25
1361 | 33025672 | ENG #1 AND #2 AFT MOUNT PINS RETAINING PINS RUSTY---NO CALLBACK--AP ENG 1 AND 2 AFT MOUNT PINS RETAINING PINS FOUND RUSTY NEEDS REPLACEMENT 10 TOTAL IN BOTH ENGINES IPC REF: 71-22-11 FIG. 71-22-11-03 ITEM 10 | 1 | 8 |  |  | Not Started | 71-22
1362 | 33025883 | RH WING FUEL TANK======PNT=====RII RH WING OUT BOARD FUEL TANK FROM RIB 13 TO 27 ACCESS PNL INNER SIDE PRIMER AND PNT CHIPPED OFF (EXCEPT PNL 640KB) | 1 |  | 3.8 | 20.9 | Idle | 57-21
1363 | 33025887 | RH WING FUEL TANK======PNT=====RII RH WING FUEL TANK FROM RIB 13 TO 27 FUEL TANK ACCESS PNL CUT-OUT PRIMER AND PNT CHIPPED OFF/ DETERIORATED (EXCEPT AREA UNDER ACCESS PNL 640KB) | 1 | 7 | 8.2 | 23.1 | Idle | 57-21
1364 | 33025881 | ENG #1 FWD MOUNT (RH FWD) RETEINER DENTED --CALLBACK--AP ENG #1 FORWARD MOUNT, RH FORWARD BOLT RETAINER FOUND DENTED, NEEDS REPLACEMENT. REF IPC: 71-21-11 FIG. 71-21-11-04 PYLON ATTACH HARDWARE, ITEM (90) DESC: RETAINER-RH SIDE PART NO. 23... | 1 |  |  |  | Not Started | 71-21
1365 | 33025894 | LH WING FUEL TANK=======FT=====RII LH WING OUTBOARD FUEL TANK INNER SIDE ALONG RIB 12 AND RIB 13 02EA BONDING JUMPER BROKEN | 1 |  | 7 | 25.2 | Idle | 57-21
1366 | 33025896 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK INNER SIDE FROM RIB 8-11 01EA FUEL PIPE PRIMER PNT CHIPPED OFF/ PEELING OFF | 1 | 3 | 3.2 | 21.6 | Idle | 57-21
1367 | 33025897 | LH WING FUEL TANK======PNT======RII LH WING FUEL TANK ACCESS PNL CUT-OUT FROM RIB 13-27 PRIMER AND PNT CHIPPED OFF | 1 | 8 | 9.2 | 22.7 | Idle | 57-21
1368 | 33027334 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 1 & 2 THERE IS 5 BONDING JUMBERS CUT | 1 |  |  |  | Not Started | 57-20
1369 | 33027336 | FT---RII---LH WING LH WING INSIDE FUEL TANK BETWEEN RIB 8 & 9 THERE IS ONE BONDING JUMBERS CUT AT RIB 9 AND TWO BONDING JUMBERS BETWEEN RIB 7 AND 8 | 1 |  |  |  | Not Started | 57-20
1370 | 33027335 | OSS - NO CALLBACK - WINDOWS ALL WINDOWS EXTERNAL SIDE REQUIRE CLEANING. | 1 | 30 |  |  | Not Started | 56-21
1372 | 33028124 | BROKEN PLENUM LH&RH-AP-N0-CALLBACK DURING INSPECTION FOUND LH & RH PACKS PLENUM CHAMBERS DELAMINATED OUT OF LIMITS | 1 | 2 | 2 | 21.1 | Idle | 21-52
1373 | 33028166 | CAB - NO CALLBACK - G1 GALLEY G1 GALLEY AIR CHILLER COVER PANEL GRILLE DEFORMED. | 1 |  |  |  | Not Started | 25
1374 | 33028214 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT RH DOOR CUTOUT AT FR 68 AREA CORRODED AROUND GIRT BAR FITTING AND AT THE DRAIN HOLE | 1 |  | 0.3 | 1.9 | Idle | 53-41
1375 | 33028291 | FINDING (NRC) TASKCARD 534143-01-3 (03) / ITEM-1 SM--RII AFT LH DOOR CUTOUT AT FR 68 AND FR 66 AREA CORRODED AT GIRT BAR FITTINGS RIVETS 2EA | 1 |  | 3 | 26.6 | Idle | 53-41
1376 | 33028349 | AP---CALLBACK---REAR AVN COMP REAR AVN COMPARTMENT UNDER INSULATION AND FLOOR AREA REQUIRE CIC | 1 |  |  |  | Not Started | 05-21
1377 | 33028466 | CAB - CALLBACK - G2 GALLEY G2 GALLEY REQUIRE REMOVAL FOR ACCESS. | 1 |  | 19.5 | 25.6 | Idle | 25
1378 | 33028471 | CAB - RII - B/C SEATS ALL B/C SEATS REQUIRE REMOVAL FOR ACCESS. | 1 |  | 26 | 25.6 | Idle | 25
1379 | 33028546 | CAB - NO CALLBACK - G/C AREA G/C AREA 9 EA SIDEWALLS WINDOW FRAME FOUND BROKEN. | 1 |  |  |  | Not Started | 25
1380 | 33028549 | PNT - NO CALL BACK - GALLEY FWD (G1) GALLEY PAINT PEELED OFF BETWEEN COMP. 104 AND 105. | 1 |  |  |  | Not Started | 25
1381 | 33028590 | FINDING (NRC) TASKCARD 575158-01-5-002 (02) / ITEM-1 PNT--NOCALLBACK RH WING LOWER SURFACE BOTTOM SKIN BETWEEN RIB 1 AND RIB 9 WITH PAINT CHIPPED OFF | 1 |  |  |  | Not Started | 57-51
1382 | 33028952 | NO.1 ENGINE ACOUSTICAL PANEL MISSING SCREW--CALL BACK--AP NO.1 ENGINE ACOUSTICAL PANEL FOUND WITH MISSING SCREW MARKED WITH GREEN TAPE | 1 | 0.5 |  |  | Not Started | 20-00
1383 | 33029195 | ENG NO#01=====AP=====CALL BACK REFER TO TASK CARD 712213-01-1-001 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP | 1 |  |  |  | Idle | 71-22
1384 | 33029199 | ENG NO#02======AP=====CALL BACK REFER TO TASK CARD 712213-01-1-002 ENGINE AFT MOUNT PINS INNER SIDE DIRTY WITH ANTI SEIZE COMPOUND DIRTY REQ CLEANING TO FASCILITATE THE INSP | 1 |  |  | 9.4 | Idle | 71-22
1385 | 33029239 | FWD CABIN=====SM=====RII FWD CABIN FLOOR STRUCTURE BESIDE R1 DOOR UNDER ACCESS PNL 222FF BETWEEN FR 16-20 , ALONG Y-1732 AND Y-1292 RAILS 04EA LOCATION WITH SURFACE CORROSION DIMENSION AS FOLLOWS ALONG Y-1292 1)LENGTH = 1.6", WIDTH 1.1" 2)LENGT... | 1 |  |  |  | Not Started | 53-11
1386 | 33029270 | RH WING MLG SUPPORT RIBS=====AP====NO CALL BACK RH WING MLG SUPPORT RIBS AND ADJACENT AREA MISSING CIC | 1 |  |  |  | Not Started | 57-51
2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 1 | 4.4 | 12.2 | 3.9 | Closed | 24-92 | OPS/LK, OPS/LK
3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 1 | 0.3 | 1.5 | 3 | Closed | 24-92 | INSPECTION
4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 1 | 0.3 | 1.5 | 3 | Closed | 24-92 | INSPECTION
5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 1 | 0.3 | 0.5 | 0.5 | Closed | 24-92 | INSPECTION
7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 1 | 2.2 | 3 | 1.5 | Closed | 24-92 | INSPECTION
10 | 200125-05-1 | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP | 1 | 9.9 | 1 | 1 | Closed | 24-92 | INSPECTION
13 | 200127-05-1 | 200127-05-1 (2) / REAR AVIONICS COMPT INSPECTION | 1 | 3.3 | 1 | 1 | Closed | 24-92 | TC/P
14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 1 | 8.3 | 1 | 1 | Closed | 24-92 | INSPECTION
17 | 200137-01-1 | 200137-01-1 (3) / BAY BEHIND FWD CGO COMPT CLEANING | 1 | 38.1 | 12 | 84 | Closed | 24-92 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
21 | 200161-01-1 | 200161-01-1 (01) / BULK CARGO COMPARTMENT CLEANING | 1 | 81.4 | 15 | 85.3 | Closed | 24-92 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 1 | 7.2 | 13.5 | 22.2 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
27 | 200315-01-1 | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP | 1 | 0.4 | 1 | 0.5 | Closed | 24-92 | INSPECTION
28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 1 | 1.1 | 5.8 | 39.3 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 1 | 1.1 | 2.3 | 39.9 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
31 | 212600-09-1 | 212600-09-1 (3) / AVIO EQUIP VENTILATION GRID CLEANING | 1 | 0.7 | 8 | 4 | Closed | 21-26 | CLEAN-UP
37 | 256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 1 | 0.4 | 12 | 2.8 | Closed | 25-61 | TC/P, TC/P, TC/P, TC/P, TC/P
38 | 262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 1 | 0.2 | 0.8 | 0.8 | Closed | 26-25 | INSPECTION
40 | 281800-02-1 | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION | 1 | 1.8 | 0.8 | 0.8 | Closed | 28-18 | INSPECTION
41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 1 | 0.2 | 4.5 | 2.8 | Closed | 28-18 | INSPECTION
47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 1 | 0.2 | 5 | 6.5 | Closed | 35-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 1 | 0.2 | 3 | 1.5 | Closed | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 1 | 0.4 | 2.7 | 22.4 | Closed | 52-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
51 | 531102-01-1 | 531102-01-1 (5) / LH/RH FORWARD PASSENGER DOORS INSP | 1 | 0.7 | 2.5 | 74.5 | Closed | 53-11 | CLEAN-UP, INSPECTION, INSPECTION
58 | 532137-03-1 | 532137-03-1 (1) / FWD CARGO DOOR CUTOUT PANELS DETAILED INSPECTION | 1 | 1.6 | 4.5 | 34.4 | Closed | 53-21 | JOB-SETUP, INSPECTION, CLOSE-UP
64 | 534159-02-1 | 534159-02-1 (1) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE. | 1 | 2.3 | 7.5 | 87.3 | Closed | 53-41
65 | 534171-02-1 | 534171-02-1 (1) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | 1 | 0.5 | 3.5 | 12.6 | Closed | 53-41
67 | 534301-01-1 | 534301-01-1 (0) / REAR FUSELAGE | 1 | 2 | 5.5 | 33 | Closed | 53-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 1 | 0.4 | 2 | 16.7 | Closed | 57-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 1 | 0.4 | 1.5 | 16.2 | Closed | 57-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 1 | 0.5 | 1.5 | 16.3 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 1 | 0.5 | 1.5 | 16.2 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
90 | 572651-01-2-001 | 572651-01-2-001 (02) / L/H OTR WING REAR SPAR JAK FTNG INSP | 1 | 0.4 | 1.8 | 29.1 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
91 | 572651-01-2-002 | 572651-01-2-002 (02) / R/H OUTR WING REAR SPAR JACK FITTING | 1 | 0.4 | 3.5 | 30.8 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
92 | 574206-01-1 | 574206-01-1 (1) / DETAILED INSPECTION OF SLAT 1, PINION AND RACK TEETH, LH/RH. | 1 | 2 | 1.3 | 44.7 | Closed | 57-46
93 | 574306-01-1-001 | 574306-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 2, PINION AND RACK TEETH. | 1 | 2.3 | 2.5 | 40.3 | Closed | 57-46
94 | 574306-01-1-002 | 574306-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 2, PINION AND RACK TEETH | 1 | 2.3 | 1.2 | 43.1 | Closed | 57-46
95 | 574406-01-1 | 574406-01-1 (1) / DETAILED INSPECTION OF SLAT 3, PINION AND RACK TEETH, LH/RH. | 1 | 2.5 | 3.6 | 45 | Closed | 57-46 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
96 | 574506-01-1-001 | 574506-01-1-001 (01) / DETAILED INSPECTION OF L/H SLAT 4, PINION AND RACK TEETH. | 1 | 2.3 | 3.5 | 40.3 | Closed | 57-46
97 | 574506-01-1-002 | 574506-01-1-002 (01) / DETAILED INSPECTION OF R/H SLAT 4, PINION AND RACK TEETH | 1 | 2.3 | 3.8 | 45.1 | Closed | 57-46
98 | 574606-01-1 | 574606-01-1 (1) / DETAILED INSPECTION OF SLAT 5, PINION AND RACK TEETH, LH/RH. | 1 | 2 | 0.6 | 44.3 | Closed | 57-46
102 | 783210-01-1 | 783210-01-1 (0) / THRUST REVERSER STRUCTURE | 1 | 1 | 3.5 | 40.4 | Closed | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
103 | ZL-110-01-1 | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION | 1 | 0.2 | 1 | 1 | Closed | 05-21 | PRE INSP
104 | ZL-121-02-1 | ZL-121-02-1 (3) / AVIONIC COMPARTMENT ZONAL INSP | 1 | 1.7 | 2 | 1 | Closed | 05-21 | INSPECTION
106 | ZL-127-02-2 | ZL-127-02-2 (3) / REAR AVIONIC COMPARTMENT ZONAL INSP | 1 | 1.7 | 5.5 | 92.8 | Closed | 05-21 | INSPECTION
107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | 1 | 38.3 | 4 | 12.2 | Closed | 05-21 | INSPECTION
110 | ZL-147-03-1 | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP | 1 | 0.9 | 0.8 | 0.8 | Closed | 05-21 | INSPECTION
113 | ZL-161-02-3 | ZL-161-02-3 (0) / BULK CARGO COMPARTMENT | 1 | 7.2 | 2 | 4 | Closed | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | 1 | 77 | 2.5 | 47.7 | Closed | 05-21 | INSPECTION
116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | 1 | 2.2 | 2.5 | 1.9 | Closed | 05-21 | INSPECTION
118 | ZL-195-01-1 | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP | 1 | 0.9 | 0.7 | 0.7 | Closed | 05-21 | PRE INSP
119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | 1 | 1.3 | 5.5 | 2.8 | Closed | 05-21 | INSPECTION
120 | ZL-200-02-1 | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI | 1 | 18.5 | 2.3 | 2.4 | Closed | 05-21 | PRE INSP
121 | ZL-200-04-1 | ZL-200-04-1 (0) / UPPER HALF OF FUSELAGE | 1 | 12.6 | 8.5 | 6.5 | Closed | 05-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | 1 | 0.4 | 21 | 30.4 | Closed | 05-22 | INSPECTION
123 | ZL-311-01-1 | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP | 1 | 0.4 | 0.8 | 0.8 | Closed | 05-23 | PRE INSP
124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | 1 | 0.2 | 15 | 9 | Closed | 05-23 | PRE INSP
125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | 1 | 0.2 | 7.8 | 7 | Closed | 05-23 | INSPECTION
126 | ZL-325-01-1 | ZL-325-01-1 (4) / VERT STAB TRAILING EDGE ZONAL INSP | 1 | 0.4 | 13 | 119.3 | Closed | 05-23 | PRE INSP
127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | 1 | 1.8 | 1.8 | 1.6 | Closed | 05-23 | PRE INSP
128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | 1 | 0.9 | 8.3 | 4.1 | Closed | 05-24 | PRE INSP
129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | 1 | 0.9 | 0.8 | 0.6 | Closed | 05-24 | PRE INSP
130 | ZL-433-01-1-001 | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP | 1 | 1.3 | 0.5 | 0.5 | Closed | 05-24 | PRE INSP
131 | ZL-433-01-1-002 | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP | 1 | 1.3 | 0.5 | 0.5 | Closed | 05-24 | PRE INSP
132 | ZL-500-03-1-001 | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP | 1 | 1.4 | 1.8 | 2.3 | Closed | 05-25 | PRE INSP
133 | ZL-500-03-1-002 | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP | 1 | 1.4 | 1.8 | 2 | Closed | 05-25 | PRE INSP
134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | 1 | 0.9 | 1 | 0.8 | Closed | 05-25 | INSPECTION
135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | 1 | 0.9 | 0.5 | 57.8 | Closed | 05-25 | INSPECTION
136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | 1 | 0.9 | 3.8 | 25.5 | Closed | 05-25 | INSPECTION
137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | 1 | 0.9 | 3 | 2.9 | Closed | 05-25 | INSPECTION
138 | ZL-531-02-1-001 | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP | 1 | 1.4 | 2 | 56.3 | Closed | 05-25 | INSPECTION
139 | ZL-531-02-1-002 | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING | 1 | 1.4 | 1.5 | 56.3 | Closed | 05-25 | INSPECTION
140 | ZL-532-01-1-001 | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP | 1 | 0.5 | 1 | 1 | Closed | 05-25 | INSPECTION
141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | 1 | 0.5 | 1 | 56.3 | Closed | 05-25 | INSPECTION
142 | ZL-532-02-1-001 | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | 1 | 1.4 | 1.5 | 56.3 | Closed | 05-25 | INSPECTION
144 | ZL-533-01-1-001 | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP | 1 | 0.5 | 1 | 1 | Closed | 05-25 | INSPECTION
145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | 1 | 0.5 | 1.5 | 56.2 | Closed | 05-25 | INSPECTION
146 | ZL-571-02-1-001 | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP | 1 | 0.9 | 0.5 | 0.5 | Closed | 05-25 | INSPECTION
147 | ZL-571-02-1-002 | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP | 1 | 0.9 | 0.5 | 0.5 | Closed | 05-25 | INSPECTION
148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | 1 | 0.5 | 1 | 1 | Closed | 05-25 | PRE INSP
149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | 1 | 0.5 | 1 | 58.4 | Closed | 05-25 | PRE INSP
150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | 1 | 3.1 | 13 | 16 | Closed | 05-25 | --, PRE INSP
151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | 1 | 3.1 | 13 | 16.5 | Closed | 05-25 | --, PRE INSP
152 | ZL-590-01-1-001 | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION | 1 | 0.4 | 1 | 1 | Closed | 05-25 | INSPECTION
153 | ZL-590-01-1-002 | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION | 1 | 0.4 | 1 | 1 | Closed | 05-25 | INSPECTION
154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | 1 | 0.2 | 1 | 1 | Closed | 05-28 | PRE INSP
155 | ZL-812-01-1 | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP | 1 | 0.4 | 1 | 1 | Closed | 05-28 | PRE INSP
156 | ZL-824-01-1 | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP | 1 | 0.2 | 1 | 1 | Closed | 05-28 | PRE INSP
161 | 21-SVA-01 | 21-SVA-01 (00) / AC-COMPRESSOR DISCHARGE TEMP. SENSOR (CDS) CLN | 1 | 3 | 18 | 6 | Closed | 21-61 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
162 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 1 | 0.4 | 2 | 1 | Closed | 21-23 | TC/P, TC/P
164 | 242000-01-1 | 242000-01-1 (3) / GAPCU OPERATIONAL TEST | 1 | 0.2 | 4 | 2 | Closed | 24-41 | OPS/LK
166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 1 | 0.2 | 4.5 | 2.8 | Closed | 24-28 | OPS/LK
167 | 243800-01-1 | 243800-01-1 (3) / BATT CHARGE LIMITER OPS CHECK | 1 | 0.2 | 4 | 2 | Closed | 24-38 | OPS/LK
179 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 1 | 2 | 1 | 1 | Closed | 25-60 | PRE INSP
180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 1 | 2 | 1 | 1 | Closed | 25-65 | PRE INSP
181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 1 | 1 | 1 | 1 | Closed | 25-65 | PRE INSP
184 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 1 | 1.3 | 0.2 | 0.2 | Closed | 25-50 | PRE INSP
185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 1 | 1.3 |  |  | Closed | 25-50 | PRE INSP
186 | 256241-05-1 | 256241-05-1 (5) / CABN DOORS GIRT BAR FITT STOP CLEAN | 1 | 0.9 | 10 | 5.3 | Closed | 25-62 | CLEAN-UP, CLEAN-UP, OPS/LK, OPS/LK
187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 1 | 0.2 | 4 | 2 | Closed | 26-12 | OPS/LK
188 | 261600-06-1 | 261600-06-1 (0) / CARGO COMPARTMENT SMOKE DETECTION | 1 | 0.5 | 6 | 1 | Closed | 24
189 | 261700-06-1 | 261700-06-1 (0) / LAVATORY SMOKE DETECTION | 1 | 0.5 | 6 | 1 | Closed | 24
198 | 281100-02-1 | 281100-02-1 (3) / TANKS WATER DRAIN | 1 | 0.1 | 3.5 | 3 | Closed | 28-11 | OPS/LK
203 | 282800-09-1 | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) | 1 | 0.3 | 0.2 | 0.2 | Closed | 28-28 | PRE INSP
204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 1 | 0.2 | 3 | 1.1 | Closed | 29-10 | TC/P
205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 1 | 0.7 | 6 | 4.2 | Closed | 29-27 | TC/P
208 | 313000-01-1 | 313000-01-1 (5) / CLASS 3 FAULTS READING CHECK | 1 | 0.2 | 4 | 2 | Closed | 31-30 | PRE HGR
210 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 1 | 0.1 | 1 | 1 | Closed | 32-30 | PRE INSP
211 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 1 | 0.1 | 0.2 | 0.2 | Closed | 32-30 | PRE INSP
212 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 1 | 0.1 | 0.5 | 0.5 | Closed | 32-30 | PRE INSP
213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 1 | 0.1 | 8 | 2 | Closed | 32-44 | TC/P
214 | 344200-03-1 | 344200-03-1 (5) / RADIO ALTIMETER & ANTENNA CLEANING | 1 | 1 | 4 | 2 | Closed | 34-42 | CLEAN-UP
215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 1 | 0.4 | 6.5 | 5.2 | Closed | 35-32 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
216 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 1 | 0.4 | 2.8 | 3.8 | Closed | 35-30 | PRE INSP, PRE INSP, PRE INSP
217 | 361100-08-2-001-SVA | 361100-08-2-001-SVA (07) / NO. 1 ENGINE HIGH PRESSURE DUCT INSPECTION | 1 | 7.2 | 20.8 | 144.1 | Closed | 36-11 | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP
218 | 361100-08-2-002-SVA | 361100-08-2-002-SVA (07) / NO. 2 ENGINE HIGH PRESSURE DUCT INSPECTION | 1 | 7.2 | 11.1 | 145.9 | Closed | 36-11 | JOB-SETUP, INSPECTION, --, --, --, INSPECTION, JOB-CLOSEUP
220 | 49-90-00-01-1-SVA | 49-90-00-01-1-SVA (00) / APU OIL COOLER CLEANING | 1 | 1.8 | 27 | 9.2 | Closed | 20-00 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
227 | 561000-01-1-SVA | 561000-01-1-SVA (04) / COCKPIT WINDOWS INSPECTION | 1 | 3.5 | 15 | 134.1 | Closed | 56-10 | PRE HGR, INSPECTION, INSPECTION, JOB-CLOSEUP
232 | FRSEO722061 | FRSEO722061 (02) / ACFT FAN FRAME ASSY-ON WING INSP | 1 | 5.7 | 21.1 | 7.1 | Closed | 20-00
236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 1 | 0.7 | 15 | 17.3 | Closed | 24-92 | INSPECTION
237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 1 | 1.1 | 2.5 | 16.2 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 1 | 1.1 | 7 | 5.2 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 1 | 1.1 | 3 | 40.1 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 1 | 0.5 | 3.5 | 41.2 | Closed | 24-92 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
241 | 212100-01-1 | 212100-01-1 (05) / COKPT AIR SUPPLY DUCT GRID CLEANING | 1 | 0.4 | 1.5 | 5.7 | Closed | 21-21 | TC/P
242 | 212600-03-1 | 212600-03-1 (3) / SMOKE CONFIGURATION CTL CIRCUIT OPC | 1 | 0.2 | 4 | 2 | Closed | 21-26 | OPS/LK
243 | 212600-04-1 | 212600-04-1 (3) / DITCHING CONFIGURATION CONTROL OPC | 1 | 0.2 | 6 | 1 | Closed | 21-26 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
244 | 212600-08-1 | 212600-08-1 (3) / AIR INLET CHECK VLV OPERATIONAL CHK | 1 | 0.2 | 0.2 | 0.2 | Closed | 21-26 | OPS/LK
247 | 213100-03-1 | 213100-03-1 (3) / PRESSURE CONTROL AND MONITORING OPC | 1 | 0.2 | 2 | 2 | Closed | 21-31 | OPS/LK
249 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 1 | 2.2 | 40 | 8.8 | Closed | 21-61 | PRE HGR
251 | 215000-09-1 | 215000-09-1 (0) / AIR COOLING AND TEMPERATURE CONTROL | 1 | 0.5 | 3.2 | 6 | Closed | 21 | --, INSPECTION, --
256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 1 | 0.6 | 4 | 2 | Closed | 22-10 | OPS/LK
257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 1 | 8 | 4 | 2 | Closed | 23-73 | OPS/LK
258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 1 | 0.9 | 6 | 2.1 | Closed | 23-33 | OPS/LK
259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 1 | 0.2 | 4 | 1 | Closed | 23-51 | OPS/LK, OPS/LK
260 | 237100-02-1 | 237100-02-1 (02) / COCKPIT VOICE RECORDER (CVR) OPC | 1 | 1.1 | 4 | 2 | Closed | 23-71 | OPS/LK
261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 1 | 0.3 | 9 | 2.4 | Closed | 23-71 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
262 | 242200-01-1 | 242200-01-1 (4) / ELECTRICAL TRANS INHIBITION OPC | 1 | 0.2 | 4 | 2 | Closed | 24-22 | OPS/LK
263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 1 | 0.2 | 4 | 2 | Closed | 24-24 | OPS/LK
264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 1 | 0.2 | 3 | 2 | Closed | 24-25 | OPS/LK
265 | 242600-02-1 | 242600-02-1 (3) / MANUAL/AUTO GALLEY & BUS SHEDING OPC | 1 | 0.2 | 4 | 2 | Closed | 24-26 | OPS/LK
266 | 243000-13-1 | 243000-13-1 (01) / DC GENERATION | 1 | 0.1 | 6 | 1 | Closed | 53-31 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
267 | 243000-14-1 | 243000-14-1 (01) / DC GENERATION | 1 | 0.1 | 6 | 1 | Closed | 24-30 | JOB-SETUP, CLEAN-UP, JOB-CLOSEUP
268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 1 | 0.3 | 3 | 1 | Closed | 24-32 | OPS/LK
269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 1 | 0.3 | 4 | 2 | Closed | 24-34 | OPS/LK
270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 1 | 0.7 | 4 | 2 | Closed | 24-51 | OPS/LK
271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 1 | 0.2 | 4 | 2 | Closed | 24-51 | OPS/LK
293 | 252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 1 | 0 | 0.8 | 0.8 | Closed | 25-22 | PRE INSP
294 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 1 | 3.3 | 0.8 | 0.8 | Closed | 25-40 | PRE INSP
297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 1 | 0.2 | 2 | 1 | Closed | 25-65 | OPS/LK
301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 1 | 0.4 | 5 | 2.9 | Closed | 26-21 | OPS/LK
302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 1 | 0.4 | 5 | 2.9 | Closed | 26-21 | OPS/LK
303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 1 | 0.9 | 7 | 1.9 | Closed | 26-21 | TC/P, TC/P, TC/P
304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 1 | 0.9 | 7 | 1.9 | Closed | 26-21 | TC/P, TC/P, TC/P
306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 1 | 0.7 | 8.5 | 2.2 | Closed | 26-22 | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP
307 | 262200-04-1 | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE | 1 | 0.4 | 0.8 | 0.8 | Closed | 26-22 | INSPECTION
308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 1 | 0.4 | 6.5 | 2.1 | Closed | 26-22 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 1 | 0.7 | 4.5 | 2.8 | Closed | 26-22 | OPS/LK
310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 1 | 1.3 | 11 | 3.4 | Closed | 26-23 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
312 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 1 | 0.2 | 0.8 | 0.8 | Closed | 26-25 | INSPECTION
313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 1 | 0.2 | 3 | 1.5 | Closed | 27-14 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
314 | 271400-02-2-001 | 271400-02-2-001 (04) / L/H AILERON SERVO EXCESSIVE PLAY CHK | 1 | 4.4 | 13.2 | 139.7 | Closed | 27-14 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
315 | 271400-02-2-002 | 271400-02-2-002 (04) / RH AIL SERVO EXCESSIVE PLAY CHK | 1 | 4.4 | 7.7 | 137.3 | Closed | 27-14 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
321 | 272100-07-1 | 272100-07-1 (02) / RUDDER MECHANICAL CONTROL LINKAGE | 1 | 0.2 | 37 | 148.4 | Closed | 27-21 | INSPECTION
324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 1 | 2.2 | 40.6 | 7.4 | Closed | 27-24 | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR
325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 1 | 5.5 | 36.8 | 9.2 | Closed | 27-34 | PRE HGR, PRE HGR, PRE HGR, PRE HGR
327 | 274000-04-1 | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC | 1 | 0.2 | 21 | 8.8 | Closed | 27-96 | PRE HGR, PRE HGR, PRE HGR
333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 1 | 0.1 | 0.5 | 0.5 | Closed | 27-44 | PRE INSP
336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 1 | 0.7 | 8 | 4.3 | Closed | 27-44 | OPS/LK
337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 1 | 0.7 | 9 | 4 | Closed | 27-51 | PRE HGR, PRE HGR, PRE HGR
338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 1 | 0.2 | 20 | 37.8 | Closed | 27-51 | PRE HGR, PRE HGR, PRE HGR
339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 1 | 0.2 | 14.8 | 37.8 | Closed | 27-51 | PRE HGR, PRE HGR, PRE HGR
340 | 275100-03-1-001 | 275100-03-1-001 (05) / L/H WING FLAP TRANSMISSION SYS CHK | 1 | 1.8 | 0.7 | 52.6 | Closed | 27-54 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
341 | 275100-03-1-002 | 275100-03-1-002 (05) / R/H WING FLAP TRANSMISSION SYS CHK | 1 | 1.8 | 0.6 | 42.8 | Closed | 27-54 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
342 | 275144-01-1-001 | 275144-01-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 1 | 1.4 | 11 | 37.7 | Closed | 27-51 | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP
343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 1 | 1.4 | 10.8 | 37.7 | Closed | 27-51 | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP
344 | 275400-01-1-001 | 275400-01-1-001 (02) / L/H FLAP TRANSMISSION ASSEMBLY INSP | 1 | 4.5 | 9 | 2.6 | Closed | 27-54 | INSPECTION
345 | 275400-01-1-002 | 275400-01-1-002 (02) / R/H FLAP TRANSMISSION ASSEMBLY INSP | 1 | 4.5 | 13 | 3.3 | Closed | 27-54 | INSPECTION
351 | 276400-02-1-001 | 276400-02-1-001 (05) / L/H SPOILER AND HYDRAULIC ACTUATION | 1 | 6.2 | 10.7 | 13.8 | Closed | 27-64 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
352 | 276400-02-1-002 | 276400-02-1-002 (05) / RH SPOILER AND HYDRAULIC ACTUATION | 1 | 6.2 | 8.7 | 13.7 | Closed | 27-64 | JOB-SETUP, INSPECTION, INSPECTION, INSPECTION, INSPECTION, INSPECTION, JOB-CLOSEUP
354 | 278100-04-1-001 | 278100-04-1-001 (03) / L/H SLAT XMISION INSPECTION | 1 | 0.4 | 3 | 42 | Closed | 27-84 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
355 | 278100-04-1-002 | 278100-04-1-002 (03) / R/H SLAT XMISION INSPECTION | 1 | 0.4 | 1.8 | 43.3 | Closed | 27-84 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
361 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 1 | 0.1 | 0.9 | 0.9 | Closed | 28-12 | PRE INSP
362 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 1 | 0.1 | 1 | 1 | Closed | 28-12 | PRE INSP
367 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 1 | 0.4 | 6 | 3.9 | Closed | 28-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
368 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 1 | 0.4 | 5 | 3.8 | Closed | 28-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
369 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 1 | 0.2 | 10 | 3 | Closed | 28-23 | PRE HGR, PRE HGR, JOB-CLOSEUP
370 | 282541-01-1-001 | 282541-01-1-001 (04) / L/H REFUEL DEFUEL COUPLING DET INSP | 1 | 0.4 | 2.5 | 8.2 | Closed | 28-25 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
371 | 282541-01-1-002 | 282541-01-1-002 (04) / R/H REFUEL DEFUEL COUPLING DET INSP | 1 | 0.4 | 4.2 | 8.2 | Closed | 28-25 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 1 | 0.9 | 6 | 3 | Closed | 28-28 | OPS/LK
377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 1 | 0.2 | 4 | 2 | Closed | 29-23 | OPS/LK
378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 1 | 0.4 | 4 | 2 | Closed | 29-10 | OPS/LK
380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 1 | 1.6 | 8 | 2 | Closed | 29-23 | OPS/LK, OPS/LK
386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 1 | 0.9 | 2.5 | 16.3 | Closed | 30-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 1 | 0.9 | 6.5 | 5.6 | Closed | 30-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 1 | 0.6 | 9 | 2.1 | Closed | 30-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 1 | 0.3 | 4 | 2 | Closed | 31-33 | OPS/LK
391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 1 | 0.4 | 4 | 2 | Closed | 31-50 | OPS/LK
392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 1 | 0.9 | 4 | 1 | Closed | 31-60 | JOB-SETUP, OPS/LK
393 | 315000-04-1 | 315000-04-1 (4) / DMC3 POWER SUPPLY TRASF OPS CHK | 1 | 0.4 | 4 | 1 | Closed | 31-60 | JOB-SETUP, OPS/LK
394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 1 | 13.6 | 4.5 | 1.5 | Closed | 12-12 | JOB-SETUP, TC/P, JOB-CLOSEUP
395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 1 | 13.6 | 5 | 72.7 | Closed | 12-12 | JOB-SETUP, TC/P, JOB-CLOSEUP
396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 1 | 1.8 | 13 | 8 | Closed | 12-14 | OPS/LK
397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 1 | 1.8 | 7 | 2 | Closed | 12-14 | OPS/LK
400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 1 | 0.9 | 3 | 1 | Closed | 12-12 | OPS/LK
401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 1 | 0.4 | 4.5 | 2.8 | Closed | 32-31 | OPS/LK
403 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 1 | 0.7 | 1 | 1 | Closed | 32-30 | PRE INSP
411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 1 | 0.2 | 8 | 3 | Closed | 32-42 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 1 | 1.8 | 10 | 3 | Closed | 32-45 | JOB-SETUP, OPS/LK
413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 1 | 0.2 | 9 | 3.1 | Closed | 33-51 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 1 | 1 | 6.5 | 2.6 | Closed | 34-55 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 1 | 0.4 | 8 | 1 | Closed | 34-13 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
416 | 341300-02-1 | 341300-02-1 (3) / AIR DATA SWITCHING FUNCTION OPC | 1 | 0.2 | 6 | 1 | Closed | 34-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
417 | 341300-03-1 | 341300-03-1 (3) / OVERSPEED WARNINGS (VFE/VLE) OPC | 1 | 0.4 | 8 | 1 | Closed | 34-13 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 1 | 0.4 | 4 | 2 | Closed | 34-13 | OPS/LK
419 | 341300-09-1 | 341300-09-1 (3) / BACK-UP SPEED & ALTTITUDE SCALES OPC | 1 | 0.4 | 4 | 2 | Closed | 34-13 | OPS/LK
420 | 342000-03-1 | 342000-03-1 (3) / (ISIS) DC HOT BUS SUPPLY OPS CHK | 1 | 0.7 | 4 | 2 | Closed | 34-20 | OPS/LK
421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 1 | 0.2 | 4.5 | 1.4 | Closed | 34-22 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 1 | 0.9 | 13 | 2.2 | Closed | 34-22 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 1 | 0.4 | 4 | 2 | Closed | 34-48 | TC/P
424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 1 | 0.2 | 8 | 1 | Closed | 34-52 | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP
426 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 1 | 0.6 | 10 | 4.4 | Closed | 35-12 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
429 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 1 | 2.2 | 3.5 | 1.6 | Closed | 25-64 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
430 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 1 | 0.4 | 3.5 | 3.3 | Closed | 35-30 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
436 | 361200-02-1 | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED | 1 | 4.4 | 42.7 | 22.3 | Closed | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
437 | 361200-03-1 | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK | 1 | 2.2 | 41.3 | 20.3 | Closed | 36-12 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
441 | 384241-01-1 | 384241-01-1 (4) / AIR SUPPLY COMPSSOR INLET FLTER INSP | 1 | 0.2 | 15 | 3 | Closed | 38-42 | JOB-SETUP, TC/P, JOB-CLOSEUP
443 | 491300-B1-1 | 491300-B1-1 (02) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS. | 1 | 3.1 | 3.5 | 36.7 | Closed | 49-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
444 | 491600-B1-1 | 491600-B1-1 (02) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | 1 | 0.3 | 6 | 34 | Closed | 49-16 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
445 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 1 | 0.2 | 0.5 | 0.5 | Closed | 49-81 | INSPECTION
455 | 521000-05-1 | 521000-05-1 (4) / PAX/CREW DOOR LOCKING MECHANISM CHK | 1 | 0.9 | 7.5 | 2.5 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
456 | 521000-06-1 | 521000-06-1 (4) / PASS/CRW DOOR EMER ESC SLIDE FUNCHK | 1 | 1.8 | 8.5 | 3.4 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
459 | 521000-08-1 | 521000-08-1 (5) / PASS/CREW DOORS INTRLK MECHANISM OPC | 1 | 0.9 | 11.5 | 3.9 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
460 | 521000-09-1 | 521000-09-1 (6) / PASS/CREW DOOR MECH LOCK IND FUN CHK | 1 | 0.9 | 7.5 | 4.6 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
461 | 521000-10-1 | 521000-10-1 (6) / PASS/CREW DOOR DAMPING FUNC CHECK | 1 | 0.4 | 8 | 5.4 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
463 | 521000-12-1 | 521000-12-1 (6) / PASS/CREW DOOR ESCAB SLIDE DIS OPC | 1 | 0.4 | 16 | 47 | Closed | 52-10 | OPS/LK, OPS/LK, OPS/LK, OPS/LK
464 | 521000-18-1 | 521000-18-1 (3) / FUNCTIONAL CHECK OF ESCAPE SLIDE DISARMING WHEN DOOR IS OPENED FROM OUTSIDE. | 1 | 3.7 | 12.5 | 47.5 | Closed | 52-10 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 1 | 0.6 | 7.8 | 3.9 | Closed | 52-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 1 | 0.3 | 4.8 | 3 | Closed | 52-51 | OPS/LK
475 | 525111-03-1 | 525111-03-1 (4) / COCKPIT DOOR MANUAL SWITCH OVER OPS | 1 | 0.4 | 4 | 2 | Closed | 52-51 | OPS/LK
476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 1 | 0.1 | 4.5 | 3.1 | Closed | 52-51 | OPS/LK
477 | 525111-05-1 | 525111-05-1 (3) / COCKPIT DOOR OPENING BY EMERG CODE | 1 | 0.1 | 4 | 2 | Closed | 52-51 | OPS/LK
478 | 527100-01-1 | 527100-01-1 (6) / DOOR WARNING SYSTEM OPERATIONAL TEST | 1 | 0.1 | 6 | 3 | Closed | 52-71 | OPS/LK
480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 1 | 0.2 | 10 | 4.2 | Closed | 52-73 | OPS/LK
482 | 531176-02-1 | 531176-02-1 (1) / GVI OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BETWEEN FR 4 AND FR 12, LH/RH. | 1 | 0.4 | 2.2 | 7.2 | Closed | 53-11 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
486 | 531900-10-1 | 531900-10-1 (1) / FUSELAGE DRAINAGE | 1 | 1.5 | 3 | 2.6 | Closed | 53 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 1 | 1.1 | 6 | 5.9 | Closed | 53-21 | PRE INSP, PRE INSP
488 | 532176-01-1 | 532176-01-1 (0) / FORWARD FUSELAGE | 1 | 4 | 2.5 | 34 | Closed | 53 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
489 | 532181-02-1 | 532181-02-1 (0) / FORWARD FUSELAGE | 1 | 3 | 5 | 77.1 | Closed | 53
493 | 534307-03-1 | 534307-03-1 (0) / REAR FUSELAGE | 1 | 1.5 | 3.5 | 12.3 | Closed | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
494 | 534308-02-1 | 534308-02-1 (0) / REAR FUSELAGE | 1 | 37.5 | 5 | 12.8 | Closed | 53-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 1 | 0.4 | 4.2 | 41.7 | Closed | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 1 | 0.4 | 3.2 | 40.6 | Closed | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 1 | 2.6 | 2.5 | 39.8 | Closed | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 1 | 2.6 | 3.5 | 40.8 | Closed | 54-50 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 1 | 1.1 | 5.6 | 39.9 | Closed | 05-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 1 | 1.1 | 2.3 | 40.5 | Closed | 05-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 1 | 0.9 | 6 | 40.1 | Closed | 54-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 1 | 0.9 | 3.8 | 41 | Closed | 54-51 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
514 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 1 | 0.2 | 0.5 | 0.5 | Closed | 71-10 | INSPECTION
515 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 1 | 0.2 | 0.5 | 0.5 | Closed | 71-10 | INSPECTION
516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 1 | 2 | 2 | 16 | Closed | 71-13 | OPEN-UP, INSPECTION, CLOSE-UP
517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 1 | 2 | 5.8 | 4.6 | Closed | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
518 | 711000-C5-1-001 | 711000-C5-1-001 (02) / NO. 1 ENG PRESSURE RELIEF DOOR FUC | 1 | 1.1 | 3 | 3 | Closed | 73-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
519 | 711000-C5-1-002 | 711000-C5-1-002 (02) / NO. 2 ENG PRESSURE RELIEF DOOR FUC | 1 | 1.1 | 3 | 3 | Closed | 73-13 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 1 | 1.8 | 3 | 16.3 | Closed | 71-13 | INSPECTION
521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 1 | 1.8 | 2 | 3.5 | Closed | 71-13 | INSPECTION
522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 1 | 1.8 | 1.8 | 16.1 | Closed | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 1 | 1.8 | 6.5 | 4.8 | Closed | 71-13 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 1 | 0.5 | 1 | 1 | Closed | 71-13
527 | 712111-05-4-001 | 712111-05-4-001 (03) / NO. 1 ENGINE FWD MOUNT PYLON BOLTS INSP | 1 | 2.5 | 13 | 4.3 | Closed | 71-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
528 | 712111-05-4-002 | 712111-05-4-002 (03) / NO.2 ENGINE FWD MOUNT PYLON BOLTS INSP | 1 | 2.5 | 17 | 4.8 | Closed | 71-21 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 1 | 2.4 | 1.2 | 41.2 | Closed | 71-21 | PRE INSP, PRE INSP, PRE INSP
530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 1 | 2.4 | 1.2 | 41.5 | Closed | 71-21 | PRE INSP, PRE INSP, PRE INSP
531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 1 | 1.3 | 1 | 1 | Closed | 71-22 | PRE INSP
532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 1 | 1.3 | 1 | 1 | Closed | 71-22 | PRE INSP
533 | 712211-05-1-001 | 712211-05-1-001 (02) / NO. 1 ENG AFT MOUNT PYLON BOLTS INSP | 1 | 2.2 | 13 | 4.3 | Closed | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
534 | 712211-05-1-002 | 712211-05-1-002 (02) / NO. 2 ENG AFT MOUNT PYLON BOLTS INSP | 1 | 2.2 | 21 | 4.8 | Closed | 71-22 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 1 | 2.8 | 1.4 | 40.9 | Closed | 71-22 | PRE INSP, PRE INSP, PRE INSP
536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 1 | 2.8 | 1.2 | 41.2 | Closed | 71-22 | PRE INSP, PRE INSP, PRE INSP
539 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 1 | 2 | 9 | 4 | Closed | 72 | OPS/LK
540 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 1 | 2 | 9 | 4 | Closed | 72 | OPS/LK
545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 1 | 0.9 | 4 | 16 | Closed | 78-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 1 | 0.9 | 10.3 | 4.4 | Closed | 78-36 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
547 | 783100-C6-1-001 | 783100-C6-1-001 (02) / NO.1 ENGINE ACTU SECONDARY LOCK INSP | 1 | 0.9 | 14.5 | 6 | Closed | 78-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
548 | 783100-C6-1-002 | 783100-C6-1-002 (02) / NO.2 ENGINE ACTU SECONDARY LOCK INSP | 1 | 0.9 | 14.5 | 6 | Closed | 78-31 | JOB-SETUP, OPS/LK, JOB-CLOSEUP
554 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | 1 | 12.5 | 1.3 | 1 | Closed | 05-21 | PRE INSP
555 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-21 | PRE INSP
556 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.2 | 0.2 | Closed | 05-21 | INSPECTION
557 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.2 | 0.2 | Closed | 05-21 | INSPECTION
558 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | 1 | 0.4 | 0.1 | 0.1 | Closed | 05-21 | INSPECTION
559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | 1 | 75.7 | 0.5 | 0.5 | Closed | 05-21 | INSPECTION
560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | 1 | 1.1 | 8.3 | 17.1 | Closed | 05-21 | INSPECTION
561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | 1 | 0.4 | 8 | 49.7 | Closed | 05-23 | INSPECTION
562 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | 1 | 1.3 | 0.8 | 0.8 | Closed | 05-23 | INSPECTION
563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | 1 | 0.9 | 46.8 | 5.2 | Closed | 05-23 | INSPECTION
564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | 1 | 0.4 | 1.8 | 1 | Closed | 05-24 | INSPECTION
565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | 1 | 0.4 | 2 | 1.1 | Closed | 05-24 | INSPECTION
566 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
567 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | 1 | 0.9 | 7.5 | 62.7 | Closed | 05-24 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | 1 | 0.9 | 12 | 50.6 | Closed | 05-24 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-24 | INSPECTION
572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | 1 | 0.7 | 0.8 | 0.6 | Closed | 05-24 | INSPECTION
573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | 1 | 0.7 | 1.2 | 1 | Closed | 05-24 | INSPECTION
574 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
575 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | 1 | 1.4 | 1 | 1 | Closed | 05-25 | INSPECTION
576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | 1 | 1.4 | 1.2 | 49.9 | Closed | 05-25 | INSPECTION
577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | 1 | 1.4 | 1.5 | 2.4 | Closed | 05-25 | INSPECTION
578 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | 1 | 0.4 | 0.5 | 0.5 | Closed | 05-27 | PRE INSP, PRE INSP
579 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | 1 | 0.2 | 0.2 | 0.2 | Closed | 05-28 | PRE INSP
580 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | 1 | 0.2 | 0.7 | 0.7 | Closed | 05-28 | PRE INSP
581 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | 1 | 0.4 | 0.1 | 0.1 | Closed | 05-28 | PRE INSP
593 | 494000-B2-1 | 494000-B2-1 (02) / DETAILED INSPECTION OF IGNITER PLUG | 1 | 0.5 | 3.5 | 32.8 | Closed | 49-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
596 | 532178-01-1 | 532178-01-1 (0) / FUSELAGE EXTERNAL SKIN COVERED BY LA | 1 | 0.1 | 7 | 5.4 | Closed | 53
600 | 572610-02-2 | 572610-02-2 (0) / OUTER WING | 1 | 2.5 | 0.5 | 53.3 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
601 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | 1 | 0.9 | 1 | 1 | Closed | 05-21 | PRE INSP
602 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | 1 | 0.2 | 1 | 1 | Closed | 05-28 | PRE INSP, PRE INSP
609 | 521000-20-1 | 521000-20-1 (1) / OPERATIONAL CHECK OF DOOR DAMPING. | 1 | 2.5 | 2.5 | 0.5 | Closed | 52-10
622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 1 | 0.7 | 13.5 | 2.8 | Closed | 53-21 | PRE INSP, PRE INSP, PRE INSP
624 | 532180-04-2 | 532180-04-2 (0) / FORWARD FUSELAGE | 1 | 3 | 3 | 33.5 | Closed | 53
625 | 533111-01-1 | 533111-01-1 (03) / PRESS DEK MEMBRANES LWR SURFACE INSP | 1 | 3.3 | 1 | 3.5 | Closed | 53-31 | CLEAN-UP, INSPECTION
629 | 534107-03-1 | 534107-03-1 (0) / REAR FUSELAGE | 1 | 0.6 | 2.8 | 18.3 | Closed | 53-41 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 1 | 1.2 | 7 | 40.3 | Closed | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 1 | 0.9 | 3.8 | 23.6 | Closed | 54-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
651 | 572044-01-2-001 | 572044-01-2-001 (01) / L/H WING BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 | 1.5 | 29.1 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
652 | 572044-01-2-002 | 572044-01-2-002 (02) / R/H WING BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 | 8.2 | 4.2 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-SETUP
653 | 572062-01-1-001 | 572062-01-1-001 (03) / L OUTER WING FIXED TRAING EDGE INSP | 1 | 0.9 | 2.8 | 52.9 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
654 | 572062-01-1-002 | 572062-01-1-002 (03) / R OUTER WING FIXED TRAIING EDGE INSP | 1 | 0.9 | 1.2 | 0.9 | Closed | 57-20 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
659 | 572111-01-1-001 | 572111-01-1-001 (03) / LH WING REAR SPAR AFT FACE INSP | 1 | 0.9 | 1.5 | 53 | Closed | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
660 | 572111-01-1-002 | 572111-01-1-002 (03) / RH WING REAR SPAR AFT FACE INSP | 1 | 0.9 | 1.2 | 1 | Closed | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
661 | 572111-02-1 | 572111-02-1 (0) / OUTER WING REAR SPAR AFT FACE RIB 8- | 1 | 0.4 | 0.9 | 53.9 | Closed | 57 | JOB-SETUP, INSPECTION, JOB-CLOSEUP
662 | 572112-01-1-001 | 572112-01-1-001 (01) / L/H OUTER WING REAR SPAR AFT FACE INSP | 1 | 3.3 | 2.2 | 53 | Closed | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
663 | 572112-01-1-002 | 572112-01-1-002 (01) / R/H OUTER WING REAR SPAR AFT FACE INSP | 1 | 3.3 | 1.2 | 43.1 | Closed | 57-21 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
668 | 572607-01-1-001 | 572607-01-1-001 (2) / L/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 1 | 1.3 | 3.9 | 52.8 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
669 | 572607-01-1-002 | 572607-01-1-002 (2) / R/FLAP TRACK BEAMS FWD SPIGOT ATTACH | 1 | 1.3 | 7.2 | 4.3 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
670 | 572610-02-1-001 | 572610-02-1-001 (03) / LH FLAP TRACK BEAMS INSP | 1 | 1.4 | 7 | 153.7 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
671 | 572610-02-1-002 | 572610-02-1-002 (03) / RH FLAP TRACK BEAMS INSP | 1 | 1.4 | 12.8 | 81.5 | Closed | 57-26 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
672 | 574101-01-3-001 | 574101-01-3-001 (03) / L/H FIXED LE ROLLER PIN HOLES INSP | 1 | 6.4 | 2 | 41.6 | Closed | 57-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
673 | 574101-01-3-002 | 574101-01-3-002 (03) / R/H FIXED LE ROLLER PIN HOLES INSP | 1 | 6.4 | 8.8 | 67.8 | Closed | 57-41 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
674 | 574202-01-2-001 | 574202-01-2-001 (02) / L/H SLAT 1 TRACKS 1-4 ATACHMNTS INSP | 1 | 0.9 | 5 | 13.1 | Closed | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
676 | 574205-01-1-001 | 574205-01-1-001 (02) / L/H SLAT 1 TRAILING EDGE INSP | 1 | 0.5 | 0.6 | 41 | Closed | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
677 | 574205-01-1-002 | 574205-01-1-002 (02) / R/H SLAT 1 TRAILING EDGE INSP | 1 | 0.5 | 1.3 | 42.6 | Closed | 57-42 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
678 | 574302-01-2-001 | 574302-01-2-001 (02) / L/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 1 | 0.5 | 1.5 | 1.9 | Closed | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
679 | 574302-01-2-002 | 574302-01-2-002 (02) / R/H SLAT 2 TRACK 5-6 ATTACHMNTS INSP | 1 | 0.5 | 4.3 | 77.4 | Closed | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
680 | 574305-01-1-001 | 574305-01-1-001 (02) / L/H SLAT 2 TRAILING EDGE INSP | 1 | 0.5 | 2.5 | 42.2 | Closed | 57-43 | JOB-SETUP, --, INSPECTION, JOB-CLOSEUP
681 | 574305-01-1-002 | 574305-01-1-002 (02) / R/H SLAT 2 TRAILING EDGE INSP | 1 | 0.5 | 1.1 | 42.9 | Closed | 57-43 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
682 | 574402-01-2-001 | 574402-01-2-001 (02) / L/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 1 | 0.5 | 1.5 | 2.1 | Closed | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
683 | 574402-01-2-002 | 574402-01-2-002 (02) / R/H SLAT 3 TRACK 7-8 ATTACHMENTS INSP | 1 | 0.5 | 5.3 | 43 | Closed | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
684 | 574405-01-1-001 | 574405-01-1-001 (02) / L/H SLAT 3 TRAILING EDGE INSPECTION | 1 | 0.5 | 3.5 | 42.4 | Closed | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
685 | 574405-01-1-002 | 574405-01-1-002 (02) / R/H SLAT 3 TRAILING EDGE INSPECTION | 1 | 0.5 | 2 | 43 | Closed | 57-44 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
686 | 574502-01-2-001 | 574502-01-2-001 (02) / L/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 1 | 0.5 | 0.7 | 3.3 | Closed | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
687 | 574502-01-2-002 | 574502-01-2-002 (02) / R/H SLAT 4 TRACK 9-10 ATTACHMENTS INSP | 1 | 0.5 | 5.1 | 42.6 | Closed | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
688 | 574505-01-1-001 | 574505-01-1-001 (02) / L/H SLAT 4 TRAILING EDGE INSPECTION | 1 | 0.5 | 3 | 42 | Closed | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
689 | 574505-01-1-002 | 574505-01-1-002 (02) / R/H SLAT 4 TRAILING EDGE INSPECTION | 1 | 0.5 | 1.1 | 43.5 | Closed | 57-45 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
690 | 574602-01-2-001 | 574602-01-2-001 (02) / L/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 1 | 0.5 | 2.2 | 3.3 | Closed | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
691 | 574602-01-2-002 | 574602-01-2-002 (02) / R/H SLAT 5 TRACK 11-12 ATTACHMENTS INSP | 1 | 0.5 | 0.6 | 44.7 | Closed | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
692 | 574605-01-1-001 | 574605-01-1-001 (02) / L/H SLAT 5 TRAILING EDGE INSPECTION | 1 | 0.7 | 3 | 42.1 | Closed | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
693 | 574605-01-1-002 | 574605-01-1-002 (02) / R/H SLAT 5 TRAILING EDGE INSPECTION | 1 | 0.7 | 2.1 | 45.4 | Closed | 57-46 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
694 | 575107-01-1-001 | 575107-01-1-001 (02) / L/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 1 | 5.4 | 25 | 26.5 | Closed | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
695 | 575107-01-1-002 | 575107-01-1-002 (02) / R/H TRALNG EDGE SPOILER 2-5 FITINGS INSP | 1 | 5.4 | 0.6 | 42.5 | Closed | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
697 | 575120-03-1-002 | 575120-03-1-002 (02) / TRALING EDGE AILERON HINGE PINS INSP | 1 | 2.6 | 1.6 | 30.2 | Closed | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
698 | 575150-01-2-001 | 575150-01-2-001 (03) / L/H OUTER WING MLG SUPPORT RIBS INSP | 1 | 2.2 | 14.7 | 166.6 | Closed | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
700 | 575158-01-5-001 | 575158-01-5-001 (02) / L/H WNG BOTTOM SKN LWR SURFACE INSP | 1 | 0.4 | 1.5 | 28.1 | Closed | 57-51 | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP
703 | 22586962 | 92339 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION | 1 |  | 0.2 | 0.2 | Closed | 53
704 | 23464908 | 92341 (0) / TOILET SERVICES PANEL REINFORCEMENTS DOUBLER WITH CORROSION2 | 1 |  | 0.2 | 0.2 | Closed | 53
705 | 31905379 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | RI | 0.5 | 3 | 72.6 | Closed | 32
706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 1 | 1.5 | 5 | 3.6 | Closed | 25
717 | 30482091 | EOD-320-31-00006-R00/ACTIVATE HIGHSPEED UPLOADING (ARINC 615A) - EIS2 | ACHK | 2 | 20 | 29.3 | Closed | 31
749 | 32362499 | S21-R10347/A320FAM - CEHCK THE TORQUE VALUES OF ACM <-> MHX DUCT CONNECTION | ACHK | 6.5 | 2.6 | 10.7 | Closed | 21-52 | --, --, --, CLOSE-UP
782 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | N | 9 | 1.7 | 12.4 | Closed | 20 | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP
802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 1 | 0 | 4.5 | 2.9 | Closed | 24-24 | OPS/LK
814 | 32977684 | LOWER FUSELAGE---PNT---NO CALLBACK DURING INSP, FOUND THE FF DECALS FADED 1. GROUND SUPPLY AIR CONDITIONG DECAL 2. GROUND HYD CONN BLUE | 1 | 2 | 4 | 2 | Closed | 05-21
820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 1 | 2 | 1 | 1 | Closed | 05-21
824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 1 | 4 | 8 | 4 | Closed | 05-25
829 | 32977909 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER OUTER SURFACE "GROUND HERE " DECAL FOUDN TORN WITH CRACKS. | 1 | 2 | 2 | 1 | Closed | 05-25
831 | 32977911 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING UPPER SURFACE MULTIPLE SCREW HEADS FOUND WITH PAINT CHIPPED OFF. | 1 | 4 | 4 | 4 | Closed | 05-25
833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 1 | 4 | 4 | 4 | Closed | 05-21
836 | 32978243 | NLG----PNT---- NO CALL BACK---- NLG LEG LWR DECAL SEVERAL TORN | 1 | 2 | 3 | 1.5 | Closed | 05-21
838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 1 | 3 | 3 | 3 | Closed | 05-21
839 | 32978253 | LH MLG---PNT---NO CALL BACK---- LH MLG LEG 2EA DECALS FADED. | 1 | 2 | 2 | 2 | Closed | 05-25
843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 1 | 10 | 10 | 5 | Closed | 05-27
844 | 32978279 | RH MLG---PNT---NO CALL BACK---- RH MLG LEG TIRE PRESSURE DECAL TORN. | 1 | 2 | 2 | 2 | Closed | 05-25
848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 1 | 3 | 3 | 1.5 | Closed | 05-25
849 | 32978481 | RH MLG---AP---CALL BACK---- RH MLG DOWN LOCK SPRING RUSTY. | 1 | 2 | 9.5 | 6.8 | Closed | 32-30
850 | 32978506 | LH MLG---AP---CALL BACK---- LH MLG DOWNLOCK SPRING RUSTY. | 1 | 2 | 1.2 | 1.1 | Closed | 32-30
859 | 32978570 | FWD CARGO DOOR---AP---CALL BACK---- FWD CARGO DOOR BOTH ACTUATOR SURFACE RUSTY | 1 | 4 | 16.2 | 4.2 | Closed | 05-28
860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 1 | 8 | 8 | 3.5 | Closed | 05-28
862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 1 | 8 | 8 | 2 | Closed | 05-28
870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 1 | 6 | 6 | 6 | Closed | 05-28
871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 1 | 6.5 | 6.5 | 6.5 | Closed | 05-28
872 | 32978650 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR LINING DIRTY | 1 | 8 | 12 | 6 | Closed | 05-28
874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 1 | 12 | 12 | 6 | Closed | 25-21
875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 1 | 120 | 120.5 | 53.3 | Closed | 25-21
877 | 32978900 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1A,C,J , 2J,L , 3A,C,L 4C , 5C,J,L FOOD TRAY DOOR - SHROUD ASSEMBLY DAMAGED | 1 | 22 | 22 | 106.1 | Closed | 25-21
878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 1 | 5 | 5 | 5 | Closed | 25-21
879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 1 | 3 | 3 | 1.5 | Closed | 25-21
880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 1 | 3 | 3 | 3 | Closed | 25-21
881 | 32979121 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT LANYARD AND PIN - DETENT MISSING | 1 | 13 | 13 | 105.7 | Closed | 25-21
882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 1 | 3 | 3 | 3 | Closed | 25-21
883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 1 | 3 | 4 | 4.1 | Closed | 05-25
884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 1 | 5 | 5 | 2 | Closed | 05-25
885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 1 | 2 | 2 | 2 | Closed | 25-21
895 | 32979731 | FWD AVIO COMP DOOR---AVIO---CALLBACK REQ CLEANING OF THE FWD AVIONIC COMPT AND DOOR (811) TO FACILITATE INSPECTION. | 1 | 4 | 5.5 | 2.9 | Closed | 05-28
896 | 32979723 | APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION | 1 | 4 | 13 | 8 | Closed | 36-12
897 | 32979981 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT MAGAZINE SPRING LOOSE | 1 | 24 | 24 | 128.6 | Closed | 25-21
898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 1 | 24 | 24 | 8 | Closed | 25-21
899 | 32980020 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT ARMREST LOOSE | 1 | 47 | 47 | 56.1 | Closed | 25-21
921 | 30205720 | S32-R10322/A320 - LANDING GEAR - NLG MAIN AND AFT DOOR INSPECTION | ACHK | 1.5 | 1.7 | 1 | Closed | 32 | INSPECTION
925 | 32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | RON | 2 | 4 | 4.4 | Closed | 38
927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 1 | 1 | 1 | 1 | Closed | 25-21
933 | 32980070 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS#30A,B,C,J,K,L FOOD TRAY DIRTEY | 1 | 6.5 | 6.5 | 59.3 | Closed | 25-21
940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 1 | 3.5 | 3 | 1.5 | Closed | 25-21
942 | 32980133 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEATS BACKREST LOOSE | 1 | 29 | 29 | 128.6 | Closed | 25-21
946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 1 | 2 | 2 | 2 | Closed | 25-21
952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 1 | 4 | 5 | 2 | Closed | 05-25
958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 1 | 2 | 2 | 2 | Closed | 25-21
959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 1 | 6 | 6 | 6 | Closed | 25-21
961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 1 | 5 | 5 | 3 | Closed | 25-21
962 | 32981772 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2A, 4J PANEL ASSEMBLY - ACCESS DAMAGED. | 1 | 2 | 2 | 44.3 | Closed | 25-21
963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 1 | 2 | 2 | 2 | Closed | 25-21
965 | 32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 1 |  | 4.5 | 2.4 | Closed | 35-12
967 | 32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 1 |  | 6 | 2.2 | Closed | 25-30
975 | 32982253 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 66.5 | 18.9 | Closed | 27-84
976 | 32982260 | R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 68 | 19.5 | Closed | 27-84
977 | 32982263 | BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 1 |  | 15.9 | 9.3 | Closed | 53-41
980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 1 | 8 | 8 | 4 | Closed | 05-21
982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 1 | 4 | 5.5 | 2.5 | Closed | 05-21
983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 1 | 3 | 3.5 | 3.5 | Closed | 05-21
990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 1 | 4 | 4 | 2 | Closed | 05-21
995 | 32984158 | PAINT---CALLBACK---LH ENG LH ENG FAN COWL RED LATCHES PAINT PEELED | 1 | 3 | 4.5 | 134.7 | Closed | 71-13
998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 1 | 4 | 4 | 2 | Closed | 05-25
1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 1 | 18 | 19 | 14.4 | Closed | 05-25
1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 1 | 18 | 19 | 14.5 | Closed | 05-25
1009 | 32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 1 | 4 | 4.5 | 4.5 | Closed | 25-10
1013 | 32984883 | PNT - NO CALLBACK - LAV A LAV A BABY NUSRING TABLE PAINT FADED. | 1 | 4 | 4 | 4 | Closed | 25-10
1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 1 | 2 | 2 | 1 | Closed | 25-10
1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 1 | 8 | 10.7 | 6.7 | Closed | 05-25
1017 | 32984945 | PNT - NO CALLBACK - GALLEY G2 GALLEY G2 COMP. 209 DOOR PAINT CHIPPED. | 1 | 3 | 4 | 4 | Closed | 25-10
1018 | 32984975 | PRE---APU COMPT---NOCALLBACK---AP APU COMPT, EXHAUST BELLOW AFT CLAMP FOUND LOOSE. | 1 | 6 | 2 | 2 | Closed | 05-23
1024 | 32985016 | PRE---APU COMPT---RII---AP APU COMPT, FWD L/H AND R/H APU MOUNT ISOLATER BOLT HEADS FOUND RUSTY. | 1 | 8 | 2.9 | 4.2 | Closed | 05-23
1026 | 32985022 | --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB | 1 | 4 | 3 | 1.5 | Closed | 53-79
1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 1 | 2 | 2 | 2 | Closed | 05-24
1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 1 | 8 | 3.5 | 1.8 | Closed | 05-24
1039 | 32985334 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 | 4 | 5.8 | 2.1 | Closed | 25
1040 | 32985336 | PNT - NO CALLBACK L1 DOOR INBOARD F/A SEAT LEFT SIDE PAINT FADED | 1 | 4 | 6.2 | 2.5 | Closed | 25
1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 1 |  | 3.5 | 3.5 | Closed | 25
1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 1 |  | 3 | 3 | Closed | 25
1044 | 32985342 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT DOWN CASE PAINT FADED | 1 | 4 | 4 | 2 | Closed | 25
1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  | 3.5 | 3.5 | Closed | 25
1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 1 |  | 3.5 | 3.5 | Closed | 25
1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  | 3 | 3 | Closed | 25
1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 1 |  | 3 | 3 | Closed | 25
1056 | 32985503 | VERTICAL STABILIZER======FS=====CALL BACK REF TO TASK CARD 272100-07-1, ZL-325-01-1, VERTICAL STABILIZER TRAILING EDGE EXCESSIVE DIRTY REQUIRE CLEANING TO FASCILITATE INSP | 1 | 10 | 12.5 | 48.7 | Closed | 27-21
1057 | 32985575 | RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW | 1 |  | 19.1 | 7.5 | Closed | 05-23
1058 | 32985619 | ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 2.6 | 1.3 | Closed | 26-21 | OPEN-UP
1059 | 32985582 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 4 | 2.2 | Closed | 57-41 | OPEN-UP
1060 | 32985655 | BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 0.2 | 0.2 | Closed | 24-92
1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 1 | 10 | 14 | 30 | Closed | 05-23
1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 1 | 8 | 9 | 12.6 | Closed | 05-23
1067 | 32985872 | THS TRAILING EDGE=======FS=====NO CALL BACK LH AND RH THS TRAILING EDGE 04EA SERVO CONTROL AND ADJACENT AREA DIRTY | 1 | 8 | 8 | 5 | Closed | 05-23
1069 | 32985875 | ENG #1 PRE COOLER SEAL --AP--RII ENG#1 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 1 | 8 | 16.1 | 3.9 | Closed | 05-24
1070 | 32985877 | ENG #2 PRE COOLER SEAL --AP--RII ENG#2 ,UPPER FWD PYLON PER COOLER UPPER SIDE SEAL TORN OFF. | 1 | 8 | 5 | 4.6 | Closed | 05-24
1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 1 |  | 28.8 | 16.3 | Closed | 53-41 | OPEN-UP
1076 | 32987146 | AP---RII---LH ELEV LH ELEVATOR HINGE NO. 6 FITTING WEARED WITH CHAFFING MARKS | 1 | 16 | 20 | 8.1 | Closed | 20-00
1080 | 32987301 | DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. | 1 | 16 | 2.7 | 98.4 | Closed | 56-10
1089 | 32987725 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... | 1 | 16 | 0.8 | 141.8 | Closed | 56-10
1090 | 32987776 | --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. | 1 |  | 29 | 23.5 | Closed | 11-21
1093 | 32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 1 |  | 3.5 | 5.6 | Closed | 52-51
1097 | 32987964 | DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. | 1 | 16 | 3.2 | 97 | Closed | 56-10
1098 | 32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 1 |  | 4 | 6 | Closed | 52-51
1105 | 32988015 | PRE---L/H WING FIXED L/E---RII---AP L/H WING I/B FIXED L/E ACCESS THROUGH PANEL 521 BB, LOWER FIRE LOOP PASS THROUGH TEFLON CONNECTOR FOUND DISPLACED AND DETACHED | 1 | 8 | 1.5 | 7.7 | Closed | 05-25
1109 | 32988470 | CAB - NO CALL BACK - L2 DOOR ASSIST HANDLE LOOSE AT L2 DOOR. | 1 | 1.5 | 11 | 3 | Closed | 25-10
1117 | 32988794 | PAINT - NO CALL BACK - WINDOW SHADE WINDOW SHADE PAINT CHIPPED AT 41 CBA | 1 | 2 | 2 | 2 | Closed | 25-10
1119 | 32989018 | PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. | 1 | 19.5 | 19.5 | 6.5 | Closed | 05-21
1125 | 32989174 | BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY | 1 | 19.5 | 19.5 | 6.5 | Closed | 57-56
1138 | 32989575 | PNT - NO CALL BACK - R2 DOOR R2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1 | 4 | 4 | 2 | Closed | 25
1139 | 32989577 | BULK CARGO UNDER FLOOR ----FS--- CALL BACK----- REQ CLEANING OF THE UNDER FLOOR IN THE BULK CARGO FRAME 59 TO 70 FOR INSPECTION | 1 | 20 | 22.4 | 81.8 | Closed | 50-11-33
1151 | 32989888 | PNT - NO CALL BACK - L2 DOOR DECORATIVE COVER L2 DOOR DECORATIVE COVER OF THE ESCAPE SLIDE/RAFT NEEDS PAINT | 1 | 4 | 4 | 2 | Closed | 25
1152 | 32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 1 |  | 2 | 2 | Closed | 25-10
1153 | 32989942 | #2 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #2 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 1 | 8 | 17.6 | 26.4 | Closed | 71-13
1159 | 32989953 | FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION | 1 | 30 | 29 | 6.5 | Closed | 11-35
1161 | 32989964 | #2 ENG - L/H AND R/H FAN COWLS - PRIMER - PNT - NO CALL BACK #2 ENG L/H AND R/H FAN COWLS INNER SURFACE FOUND WITH PRIMER CHIPPED-OFF AND WITH MISMATCHED PRIMER SPOTS ALL OVER FAN COWLS INNER SURFACES . | 1 | 6 | 6.5 | 2.5 | Closed | 71-13
1173 | 32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 1 | 1.5 | 1.5 | 1.7 | Closed | 25-21
1180 | 32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 1 |  | 1.5 | 1.8 | Closed | 25-21
1181 | 32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 1 |  | 2.1 | 30.8 | Closed | 25-21
1182 | 32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 1 |  | 2.1 | 29.7 | Closed | 25-21
1183 | 32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 1 |  | 2.1 | 30.7 | Closed | 25-21
1184 | 32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 1 |  | 2.1 | 30.7 | Closed | 25-21
1185 | 32990036 | #1 ENG - L/H AND R/H FAN COWLS - BULB SEAL - AP - RII #1 ENG L/H AND R/H FAN COWLS FOUND DRAIN MAST BULB SEAL DETERIORATED . | 1 | 8 | 24.1 | 99 | Closed | 71-13
1203 | 32991517 | PNT - NO CALLBACK - LAV D LAV D ACCESS DOOR WASTE COMPARTMENT INSIDE PAINT SCRATCHED. | 1 | 5 | 5 | 86.1 | Closed | 25
1208 | 32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 1 | 2 | 2 | 2 | Closed | 25-21
1226 | 32992522 | RH THS UPPER TRAILING EDGE PANEL -SM - NO CALLBACK RH THS UPPER TRAILING EDGE PANEL WITH FROZEN SCREW ON PANEL 344AT, 344 BT AND 344 CT | 1 |  | 62.8 | 96.2 | Closed | 55-10-00
1237 | 32993180 | FUEL TANK ACCESS PANELS WITH FROZEN SCREW--NO CALL BACK LH WING FUEL TANK ACCESS PANELS 540HB (5EA) , 540JB (2EA) , 540KB (3EA) AND 540QB (1EA) WITH FROZEN SCREW. | 1 |  | 6.8 | 61.3 | Closed | 57-21
1238 | 32993201 | L/H AND R/H WINGS KIDNEY PANELS DIRTY ---FS--- NO CALL BACK PANELS NUMBER: 574AB AND 574BB FOR LEFT WING, AND 674AB, 674BB FOR RIGHT WING, AREA INSIDE FOUND DIRTY REQ FS ACTION | 1 | 19 | 13 | 6.5 | Closed | 05-25
1242 | 32993275 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE UPPER SKIN/TOP SKIN, SPOILER #3 NEAR CENTER ATTACHMENT 03EA RIVET LOOSE/SHEARD. | 1 |  | 27.3 | 64.8 | Closed | 05-25
1243 | 32993277 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 NEAR CENTER HING TOP SKIN 1EA RIVET LOOSE AND 1EA IS MISSING. | 1 |  | 13.3 | 65.2 | Closed | 05-25
1244 | 32993284 | R/H WING TRAILING EDGE---SM---- NO CALL BACK R/H WING TRAILING EDGE, SPOILER #2 IN BOARD HINGE TOP SKIN 1EA RIVET LOOSE. | 1 |  | 12.3 | 65.5 | Closed | 05-25
1247 | 32994020 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT DIAPHRAGM - SEATPAN REQUIRE REMOVE FOR ACCESS | 1 | 24 | 24 | 8 | Closed | 25-21
1248 | 32994039 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT DIAPHRAGM – BOTTOM REQUIRE REMOVE FOR ACCESS | 1 | 12 | 12 | 61.4 | Closed | 25-21
1249 | 32994166 | FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 1 |  | 7 | 2.9 | Closed | 71-22
1251 | 32994173 | FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 1 |  | 5 | 8.4 | Closed | 71-21
1252 | 32994187 | FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 1 |  | 4.1 | 2.7 | Closed | 71-21
1253 | 32994193 | FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 1 |  | 4.1 | 2.4 | Closed | 71-22
1256 | 32995398 | NO CALL BACK FUSELAGE (FS) FWD AVIONIC COPMARTMENT ZONAL INSP FROM ZONES 121 TO 122 REQ CLEAINING | 1 | 9 | 9 | 3 | Closed | 05-21
1257 | 32995496 | L/H VERTICAL STAP-----SM-------NO CALL BACK L/H UPPER VERTICAL STAB PNLS (334AT,334CT,334DT) WITH ROUNDED SCREWS | 1 |  | 12.3 | 69.8 | Closed | 55-33
1259 | 32995625 | RH WING FUEL ACCESS PNLS #640KB WITH 1 FROZEN SCREW ,640LB WITH 2 FROZEN SCREW AND 640HB WITH 1 FROZEN SCREW ,REQ TO REMOVE | 1 |  | 7.2 | 63 | Closed | 57-21
1260 | 32995946 | FINDING (NRC) TASKCARD 25-21-00-00-SVA (01) / ITEM ONE B/C SEAT# 1AC CUSHION ASSY-LEGREST TORN. | 1 | 2 | 2 | 2.3 | Closed | 25-25
1264 | 32996610 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C FRONT ROW SEAT#30A,B,C,J,K,L, ESCUTCHEON – IAT WITH SCRATCH. | 1 | 6.5 | 6.5 | 6.7 | Closed | 25-21
1268 | 32996857 | CAPT FIXED WINDOW======AP=====RII CAPT SIDE FIXED WINDOW AFT LWR CORNER WITH BUBBLES DIMENSIONS AS FOLLOWS LENGTH =3" WIDTH= 1.1" | 1 | 8 | 2.8 | 2 | Closed | 56-10
1275 | 32998246 | FWD CGO DOOR.....FS....NO CALLBACK FWD CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 1 | 2 | 2 | 1 | Closed | 52-30-00
1276 | 32998252 | AFT CGO DOOR....FS....NO CALLBACK AFT CGO DOOR LATCHING MECHANISM INTERNAL STRUCTURE DIRTY | 1 | 2 | 2 | 1 | Closed | 52-30-00
1285 | 33001460 | LH OVER WING PNL ---SM--NO CALLBACK--- WING ROOT PNL 191ET WITH 3 EA WRON HEAD SCREWS | 1 |  | 17.8 | 12.2 | Closed | 53-41
1288 | 33002750 | PNT---NO CALLBACK---RH WING SLAT RH WING SLAT 1, 2, 3, 4 & 5 TRAILING EDGES WITH PAINT CHIPPED OFF | 1 | 16 | 13.5 | 6.6 | Closed | 57-42
1303 | 33011331 | FINDING (NRC) TASKCARD 572065-01-1-001 (03) / ITEM ONE PNT--NOCALLBACK LH WING TRAILING EDGE AREA AT WING LOWER SURFACE BETWEEN RIB 1-5 WITH PAINT CRACKING / CHIPPED OFF | 1 | 16 | 17 | 6.5 | Closed | 57-20
1307 | 33013426 | L/H WING ---AP--- NO CALL BACK L/H WING TRAILING EDGE TORQUE SHAFT FROM RIB 5 TO RIB 27 VERY DIRTY | 1 | 4 | 0.5 | 0.5 | Closed | 57-21
1346 | 33022924 | RH WING FUEL ACCESS PNL#640KB WITH 4EA FROZEN SCREW | 1 |  | 6 | 2 | Closed | 57-21
1350 | 33023367 | AP---NO CALLBACK---UNDER BELLY FAIRING AFT CARGO COMPARTMENT-HEATING PRESSURE-REGULATING VALVE FWD CLAMP NOT SECURED WITH BENDED SECURING BOLT UNDER PANEL 197BB | 1 | 6 | 7 | 1.8 | Closed | 53-41
1351 | 33023576 | AP---NO CALLBACK---UNDER PNL BELLY FAIRING PNUEMATIC DUCT UNDER THE OVERWING SLIDE LH SIDE ONE TIE CLAMP NOT SECURED | 1 | 6 | 7 | 1.6 | Closed | 53-41
1352 | 33023575 | FINDING (NRC) TASKCARD 531102-01-1 (5) / ITEM-1 PNT--NOCALLBACK BOTH FWD LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 1 | 9 | 10 | 5.2 | Closed | 53-11
1354 | 33023735 | FINDING (NRC) TASKCARD 534132-02-1 (2) / ITEM ONE PNT--NOCLLBACK BOTH AFT LH AND RH UPPER PASSENGER DOORS CUTOUT WITH PAINT CHAFING | 1 | 7 | 8 | 5.1 | Closed | 53-41
1371 | 33027363 | FT---NO CALLBACK---RH WING RH WING ACCESS DOOR 640AB PAINT CHIPPED OFF | 1 |  | 2 | 2 | Closed | 57-20