## Sheet1
Type | Seq. No. | Work Step / Event Number | Title | Revision | Event | Priority | Part Requests | EstMH | Planned Date | Planned Duration | Actual Start | Actual Duration | Live MH | Prod. Booked MH | Progress | Booked Tool MH | Panel State | ATA Chapter | Approval Step | MRO Measurements | Phase | Ext. W/O No. | Cust. Event No. | Remarks (Event or W/O) | Findings (closed / total) | Sign Off | Work steps (closed / total) | Staff Assigned | EWI Status | Position | Link/Barcode | Closed By | Closed Date | Closing Status
| 2 | 200001-02-1 | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18472 | 17.Jul.2026 22:00 | 0.10139 | 23.Jul.2026 15:22 | 0.16181 |  | 0.51042 | Closed | 0 | T: 6; O: 0; C: 6 | 24-92 |  | [] | OPS/LK, OPS/LK |  |  |  | 200001-02-1 (3) / HIRF/LIGHTNING PROTECTION-WING CHK (32712972) |  | 2 / 2 | [] |  |  | MET.32712972 | 13008286 | 2026-07-26 | Performed
| 3 | 200003-01-1 | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB | 200003-01-1 (2) / ELEM FITT ON HARN 4202VB AND 4204VB (32712946) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:45 | 0.12708 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712946 | 13008286 | 2026-07-23 | Performed
| 4 | 200003-02-1 | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 16:47 | 0.12569 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 200003-02-1 (3) / HIRF/LIGHTNING PROTECTION-VRT FIN (32712992) |  | 1 / 1 | [] |  |  | MET.32712992 | 13008286 | 2026-07-23 | Performed
| 5 | 200003-03-1 | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB | 200003-03-1 (2) / ELEM FIT ON HARNES 4202VB & 4204VB (32712973) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 21.Jul.2026 10:27 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712973 | 13003390 | 2026-07-21 | Performed
| 7 | 200121-03-1 | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 24.Jul.2026 07:52 | 0.0625 |  | 0.125 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 200121-03-1 (2) / FORWARD AVIONIC COMPARTMENT INSP (32712948) |  | 1 / 1 | [] |  |  | MET.32712948 | 13008286 | 2026-07-26 | Performed
| 10 | 200125-05-1 | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP | 200125-05-1 (2) / LATERAL AVIONIC COMPARTMENT INSP (32712921) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.4125 | 17.Jul.2026 22:00 | 0.4125 | 19.Jul.2026 07:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 3; O: 0; C: 3 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 6 |  | 1 / 1 | [] |  |  | MET.32712921 | 13008286 | 2026-07-20 | Performed
| 14 | 200127-07-1 | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.34792 | 17.Jul.2026 22:00 | 0.34792 | 22.Jul.2026 12:42 | 0.041667 |  | 0.041667 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | INSPECTION |  |  |  | 200127-07-1 (2) / REAR AVIONIC COMPARTMENT INSPECTION (32712935) |  | 1 / 1 | [] |  |  | MET.32712935 | 13008286 | 2026-07-23 | Performed
| 24 | 200231-03-1 | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.29792 | 17.Jul.2026 22:00 | 0.15486 | 21.Jul.2026 12:38 | 0.92361 |  | 0.5625 | Closed | 0 | T: 0; O: 0; C: 0 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200231-03-1 (2) / FORWARD PASSENGER COMPARTMENT INSP (32712990) |  | 3 / 3 | [] |  |  | MET.32712990 | 13003390 | 2026-07-22 | Performed
| 27 | 200315-01-1 | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 11:11 | 0.020833 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | INSPECTION |  |  |  | 200315-01-1 (3) / TAIL CONE&APU ACCESSORY ROUTES INSP (32712977) |  | 1 / 1 | [] |  |  | MET.32712977 | 13003390 | 2026-07-20 | Performed
| 28 | 200413-03-1-001 | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 15:27 | 1899-12-31 15:16 |  | 0.23958 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-001 (02) / NO.1 ENG PYLON UPR FWD (EWIS) INSP (25335922) |  | 3 / 3 | [] |  |  | MET.25335922 | 13009981 | 2026-07-23 | Performed
| 29 | 200413-03-1-002 | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:51 | 1899-12-31 15:54 |  | 0.097222 | Closed | 0 | T: 9; O: 0; C: 9 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200413-03-1-002 (02) / NO.2 ENG PYLON UPR FWD (EWIS) INSP (25336676) |  | 3 / 3 | [] |  |  | MET.25336676 | 13009981 | 2026-07-23 | Performed
| 37 | 256141-01-1 | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP | 256141-01-1 (3) / CAPT AND F/O EMERGENCY DEVICE INSP (32712971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.015278 | 20.Jul.2026 08:31 | 0.11597 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-61 |  | [] | TC/P, TC/P, TC/P, TC/P, TC/P |  |  |  | 0 / 1 |  | 5 / 5 | [] |  |  | MET.32712971 | 13003390 | 2026-07-20 | Performed
| 38 | 262541-01-1 | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:18 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-01-1 (3) / LAVATORIES FIRE EXTINGUISHERS INSP (32712927) |  | 1 / 1 | [] |  |  | MET.32712927 | 13008286 | 2026-07-20 | Performed
| 40 | 281800-02-1 | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 06:04 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 28-18 |  | [] | INSPECTION |  |  |  | 281800-02-1 (2) / CENTER TANK VAPOR SEAL INSPECTION (32712944) |  | 1 / 1 | [] |  |  | MET.32712944 | 13003390 | 2026-07-20 | Performed
| 41 | 281800-05-1 | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP | 281800-05-1 (3) / CNTR TANK FWD BKHD INSULATION INSP (32712932) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 08:02 | 0.11458 |  | 0.1875 | Closed | 0 | T: 3; O: 0; C: 3 | 28-18 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712932 | 13003390 | 2026-07-21 | Performed
| 47 | 351351-01-1 | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0069444 | 23.Jul.2026 13:22 | 0.27153 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 351351-01-1 (2) / CREW OXYGEN DISTRIBUTION FNC (32712942) |  | 3 / 3 | [] |  |  | MET.32712942 | 13008286 | 2026-07-26 | Performed
| 48 | 361200-01-1 | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 13:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-01-1 (2) / CROSSBLEED VALVE MANUAL MODE OPS CHK (32712978) |  | 3 / 3 | [] |  |  | MET.32712978 | 13003390 | 2026-07-23 | Performed
| 49 | 524100-01-1 | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 08:00 | 0.93194 |  | 0.11111 | Closed | 0 | T: 4; O: 0; C: 4 | 52-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 524100-01-1 (4) / AVIONICS COMP. DOORS SEALS INSP (32712931) |  | 3 / 3 | [] |  |  | MET.32712931 | 13009981 | 2026-07-23 | Performed
| 82 | 572049-01-3-001 | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 21.Jul.2026 17:28 | 0.69722 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-001 (02) / L/H O/WNG BOTOM SKN DRAIN HOLES INSP (25335733) |  | 3 / 3 | [] |  |  | MET.25335733 | 13009981 | 2026-07-23 | Performed
| 83 | 572049-01-3-002 | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.011806 | 21.Jul.2026 17:29 | 0.67431 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-41 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 572049-01-3-002 (02) / R/H O/WNG BOTOM SKN DRAIN HOLES INSP (25336621) |  | 3 / 3 | [] |  |  | MET.25336621 | 13009981 | 2026-07-23 | Performed
| 86 | 572153-01-1-001 | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 17:25 | 0.67847 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-001 (02) / L/H WING BOTTOM SKIN DRAIN HOLES INSP (32712633) |  | 4 / 4 | [] |  |  | MET.32712633 | 13009981 | 2026-07-23 | Performed
| 87 | 572153-01-1-002 | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 17:27 | 0.67639 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 57-20 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 572153-01-1-002 (02) / RH WING BOTTOM SKIN DRAIN HOLES INSP (32712611) |  | 4 / 4 | [] |  |  | MET.32712611 | 13009981 | 2026-07-23 | Performed
| 103 | ZL-110-01-1 | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 05:57 | 0.040972 |  | 0.040972 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | PRE INSP |  |  |  | ZL-110-01-1 (3) / RADOME ZONAL INSPECTION (32712939) |  | 1 / 1 | [] |  |  | MET.32712939 | 13003390 | 2026-07-20 | Performed
| 107 | ZL-131-02-1 | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION | ZL-131-02-1 (2) / FORWARD CARGO COMPARTMENT INSPECTION (28325941) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 14:18 | 17.Jul.2026 22:00 | 1899-12-31 14:18 | 21.Jul.2026 08:01 | 0.50694 |  | 0.16667 | Closed | 0 | T: 12; O: 0; C: 12 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.28325941 | 13008286 | 2026-07-22 | Performed
| 110 | ZL-147-03-1 | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP | ZL-147-03-1 (3) / MLG-WELL AND HYD COMPARTMENT INSP (32712657) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:27 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | INSPECTION |  |  |  | 2 / 3 |  | 1 / 1 | [] |  |  | MET.32712657 | 13003390 | 2026-07-20 | Performed
| 115 | ZL-171-02-1 | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP | ZL-171-02-1 (2) / AFT CABIN UNDERFLOOR COMPART INSP (28325987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 05:00 | 17.Jul.2026 22:00 | 1900-01-02 05:00 | 21.Jul.2026 13:54 | 1899-12-31 23:41 |  | 0.10417 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.28325987 | 13003390 | 2026-07-23 | Performed
| 116 | ZL-191-02-1 | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 18:22 | 0.077778 |  | 0.10417 | Closed | 0 | T: 23; O: 0; C: 23 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-191-02-1 (02) / AIR CONDITIONING COMPART & FRNG INSP (28325991) |  | 1 / 1 | [] |  |  | MET.28325991 | 13008286 | 2026-07-22 | Performed
| 118 | ZL-195-01-1 | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP | ZL-195-01-1 (4) / HYDRAULIC COMP & FAIRINGS ZONAL INSP (32712964) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 07:54 | 0.027778 |  | 0.027778 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 2 / 8 |  | 1 / 1 | [] |  |  | MET.32712964 | 13003390 | 2026-07-20 | Performed
| 119 | ZL-197-01-1 | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION | ZL-197-01-1 (01) / REAR FAIRING ZONAL INSPECTION (25336636) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 21.Jul.2026 08:02 | 0.11736 |  | 0.22917 | Closed | 0 | T: 6; O: 0; C: 6 | 05-21 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336636 | 13003390 | 2026-07-21 | Performed
| 120 | ZL-200-02-1 | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI | ZL-200-02-1 (04) / UPPER HALF OF FUSELAGE ZON GVI (32712963) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.76944 | 17.Jul.2026 22:00 | 0.76944 | 18.Jul.2026 15:30 | 0.10139 |  | 0.097222 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 1 / 9 |  | 1 / 1 | [] |  |  | MET.32712963 | 13008286 | 2026-07-20 | Performed
| 122 | ZL-211-01-1 | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 05:08 | 1899-12-31 06:23 |  | 0.875 | Closed | 0 | T: 15; O: 0; C: 15 | 05-22 |  | [] | INSPECTION |  |  |  | ZL-211-01-1 (03) / COCKPIT ZONAL INSPECTION (32712928) |  | 1 / 1 | [] |  |  | MET.32712928 | 13003390 | 2026-07-23 | Performed
| 123 | ZL-311-01-1 | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP | ZL-311-01-1 (04) / AFT FUSELAGE TAIL SECTION ZONAL INSP (32712943) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:41 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | PRE INSP |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712943 | 13003390 | 2026-07-20 | Performed
| 124 | ZL-313-01-1 | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP | ZL-313-01-1 (4) / TAIL CONE APU AIR INTAKE AREA INSP (32712980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:43 | 0.37639 |  | 0.625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712980 | 13008286 | 2026-07-21 | Performed
| 125 | ZL-317-01-1 | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP | ZL-317-01-1 (3) / TAIL CONE/APU EXHAUST AREA INSP (32712954) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 12:42 | 0.29375 |  | 0.32639 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712954 | 13008286 | 2026-07-21 | Performed
| 127 | ZL-334-02-1 | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-02-1 (2) / THS TRAILING EDGE ZONAL INSPECTION (32712645) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 20.Jul.2026 18:07 | 0.068056 |  | 0.076389 | Closed | 0 | T: 24; O: 0; C: 24 | 05-23 |  | [] | PRE INSP |  |  |  | 1 / 6 |  | 1 / 1 | [] |  |  | MET.32712645 | 13008286 | 2026-07-21 | Performed
| 128 | ZL-415-01-1-001 | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 15:39 | 0.17153 |  | 0.34722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-001 (03) / L/H ENGINE LOWER PYLON ZONAL INSP (28325802) |  | 1 / 1 | [] |  |  | MET.28325802 | 13008286 | 2026-07-21 | Performed
| 129 | ZL-415-01-1-002 | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 19:25 | 0.024306 |  | 0.034722 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | PRE INSP |  |  |  | ZL-415-01-1-002 (03) / R/H ENGINE LOWER PYLON ZONAL INSP (28325897) |  | 1 / 1 | [] |  |  | MET.28325897 | 13008286 | 2026-07-21 | Performed
| 130 | ZL-433-01-1-001 | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-001 (02) / NO. 1 ENGINE AIR INTAKE LIP INSP (32712604) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 06:37 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712604 | 13008286 | 2026-07-20 | Performed
| 131 | ZL-433-01-1-002 | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP | ZL-433-01-1-002 (02) / NO. 2 ENGINE AIR INTAKE LIP INSP (32712607) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 09:54 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712607 | 13008286 | 2026-07-20 | Performed
| 132 | ZL-500-03-1-001 | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-001 (03) / L/H WING UPPER SURFACE ZONAL INSP (32712936) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 15:50 | 0.095833 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 1 / 7 |  | 1 / 1 | [] |  |  | MET.32712936 | 13008286 | 2026-07-20 | Performed
| 133 | ZL-500-03-1-002 | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.060417 | 17.Jul.2026 22:00 | 0.060417 | 18.Jul.2026 16:10 | 0.082639 |  | 0.076389 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-500-03-1-002 (03) / R/H WING UPPER SURFACE ZONAL INSP (32712966) |  | 1 / 1 | [] |  |  | MET.32712966 | 13008286 | 2026-07-20 | Performed
| 134 | ZL-521-01-1-001 | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 08:06 | 0.035417 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-521-01-1-001 (03) / L/H INBOARD FIXED L/E STRUCTURE INSP (32712947) |  | 1 / 1 | [] |  |  | MET.32712947 | 13003390 | 2026-07-21 | Performed
| 135 | ZL-521-01-1-002 | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP | ZL-521-01-1-002 (03) / R/H INBOARD FIXED L/E STRUCTURE INSP (32712934) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:21 | 1900-01-01 09:48 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712934 | 13008286 | 2026-07-23 | Performed
| 136 | ZL-522-01-1-001 | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-001 (03) / L/H WING O/B FIXED LEADING EDGE INSP (28325993) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 20.Jul.2026 09:20 | 1899-12-31 01:32 |  | 0.15625 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 4 |  | 1 / 1 | [] |  |  | MET.28325993 | 13003390 | 2026-07-21 | Performed
| 137 | ZL-522-01-1-002 | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.038194 | 21.Jul.2026 07:59 | 0.12014 |  | 0.125 | Closed | 0 | T: 14; O: 0; C: 14 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-522-01-1-002 (03) / R WING O/B FIXED LEADING EDGE INSP (28325992) |  | 1 / 1 | [] |  |  | MET.28325992 | 13003390 | 2026-07-21 | Performed
| 138 | ZL-531-02-1-001 | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP | ZL-531-02-1-001 (01) / L/H FLAP TRACK NO 2 AND FAIRING INSP (25335895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:28 | 1900-01-01 08:16 |  | 0.083333 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.25335895 | 13008286 | 2026-07-23 | Performed
| 139 | ZL-531-02-1-002 | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING | ZL-531-02-1-002 (01) / R/H FLAP TRACK NO 2 AND FAIRING (25336980) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.05625 | 17.Jul.2026 22:00 | 0.05625 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.25336980 | 13008286 | 2026-07-23 | Performed
| 140 | ZL-532-01-1-001 | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 10:06 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-01-1-001 (04) / L/H FLAP TRACK NO 3 AND FAIRING INSP (32712924) |  | 1 / 1 | [] |  |  | MET.32712924 | 13003390 | 2026-07-20 | Performed
| 141 | ZL-532-01-1-002 | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP | ZL-532-01-1-002 (04) / R/H FLAP TRACK NO 3 AND FAIRING INSP (32712979) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:29 | 1900-01-01 08:18 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712979 | 13008286 | 2026-07-23 | Performed
| 142 | ZL-532-02-1-001 | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-001 (01) / L/H FLAP TRACK NO 3 AND FAIRING (25336005) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 10:05 | 0.041667 |  | 0.041667 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.25336005 | 13003390 | 2026-07-20 | Performed
| 143 | ZL-532-02-1-002 | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.056944 | 17.Jul.2026 22:00 | 0.056944 | 20.Jul.2026 11:29 | 1900-01-01 08:17 |  | 0.0625 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-532-02-1-002 (01) / R/H FLAP TRACK NO 3 AND FAIRING (25336989) |  | 1 / 1 | [] |  |  | MET.25336989 | 13008286 | 2026-07-23 | Performed
| 144 | ZL-533-01-1-001 | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-001 (04) / L/H FLAP TRACK NO 4 AND FAIRING INSP (32712922) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 08:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 2 |  | 1 / 1 | [] |  |  | MET.32712922 | 13008286 | 2026-07-20 | Performed
| 145 | ZL-533-01-1-002 | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP | ZL-533-01-1-002 (04) / R/H FLAP TRACK NO 4 AND FAIRING INSP (32712970) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020139 | 17.Jul.2026 22:00 | 0.020139 | 20.Jul.2026 11:30 | 1900-01-01 08:15 |  | 0.0625 | Closed | 0 | T: 1; O: 0; C: 1 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712970 | 13008286 | 2026-07-23 | Performed
| 146 | ZL-571-02-1-001 | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP | ZL-571-02-1-001 (03) / LEFT MLG BAY ZONAL INSP (32712933) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:22 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 5 |  | 1 / 1 | [] |  |  | MET.32712933 | 13008286 | 2026-07-20 | Performed
| 147 | ZL-571-02-1-002 | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP | ZL-571-02-1-002 (03) / RIGHT MLG BAY ZONAL INSP (32712988) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 22:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 4 |  | 1 / 1 | [] |  |  | MET.32712988 | 13008286 | 2026-07-20 | Performed
| 148 | ZL-573-01-1-001 | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 22.Jul.2026 08:38 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | ZL-573-01-1-001 (04) / L/H INBOARD FIXED T/E STRUCTURE INSP (32712940) |  | 1 / 1 | [] |  |  | MET.32712940 | 13003390 | 2026-07-22 | Performed
| 149 | ZL-573-01-1-002 | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP | ZL-573-01-1-002 (04) / R/H INBOARD FIXED T/E STRUCTURE INSP (32712969) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.021528 | 17.Jul.2026 22:00 | 0.021528 | 20.Jul.2026 09:20 | 1900-01-01 10:23 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | PRE INSP |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712969 | 13008286 | 2026-07-23 | Performed
| 150 | ZL-574-01-1-001 | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 15:21 | 0.66806 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | ZL-574-01-1-001 (04) / L/H WING FALSE SPAR BOX ZONAL INSP (32712956) |  | 2 / 2 | [] |  |  | MET.32712956 | 13009981 | 2026-07-23 | Performed
| 151 | ZL-574-01-1-002 | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP | ZL-574-01-1-002 (04) / R/H WING FALSE SPAR BOX ZONAL INSP (32712918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.12778 | 17.Jul.2026 22:00 | 0.12778 | 22.Jul.2026 14:54 | 0.68611 |  | 0.54167 | Closed | 0 | T: 7; O: 0; C: 7 | 05-25 |  | [] | --, PRE INSP |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.32712918 | 13009981 | 2026-07-23 | Performed
| 152 | ZL-590-01-1-001 | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:13 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-001 (03) / L/H WING AILERON INSPECTION (32712955) |  | 1 / 1 | [] |  |  | MET.32712955 | 13008286 | 2026-07-20 | Performed
| 153 | ZL-590-01-1-002 | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 06:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-25 |  | [] | INSPECTION |  |  |  | ZL-590-01-1-002 (03) / R/H WING AILERON INSPECTION (32712923) |  | 1 / 1 | [] |  |  | MET.32712923 | 13008286 | 2026-07-20 | Performed
| 154 | ZL-811-01-1 | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP | ZL-811-01-1 (03) / FWD AVIONICS COMP. DOOR ZONAL INSP (32712974) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:41 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712974 | 13008286 | 2026-07-23 | Performed
| 155 | ZL-812-01-1 | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-28 |  | [] | PRE INSP |  |  |  | ZL-812-01-1 (03) / LATERAL AVIONICS COMP. DOORS INSP (32712950) |  | 1 / 1 | [] |  |  | MET.32712950 | 13008286 | 2026-07-20 | Performed
| 156 | ZL-824-01-1 | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP | ZL-824-01-1 (03) / REAR AVIONICS COMPARTMENT DOOR INSP (32712976) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:55 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712976 | 13008286 | 2026-07-20 | Performed
| 162 | 212300-02-1 | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 08:56 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 21-23 |  | [] | TC/P, TC/P |  |  |  | 212300-02-1 (4) / LAVATORY AIR EXTRACTION FLTR R/R (32807066) |  | 2 / 2 | [] |  |  | MET.32807066 | 13008286 | 2026-07-20 | Performed
| 166 | 242800-01-2 | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 06:45 | 0.11597 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-28 |  | [] | OPS/LK |  |  |  | 242800-01-2 (4) / STATIC INVERTER OPERATIONAL CHECK (32807105) |  | 1 / 1 | [] |  |  | MET.32807105 | 13008286 | 2026-07-22 | Performed
| 179 | 25-60-00-03-0-SVA | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:19 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-60 |  | [] | PRE INSP |  |  |  | 25-60-00-03-0-SVA (01) / EMERGENCY EQUIPMENT IN C/A SEAT STOWAGE INSPECTION (29295194) |  | 1 / 1 | [] |  |  | MET.29295194 | 13008286 | 2026-07-20 | Performed
| 180 | 25-65-00-01-0-SVA | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP | 25-65-00-01-0-SVA (02) / EMERGENCY EQUIP VALIDITY INSP (29295141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:26 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.29295141 | 40000929 | 2026-07-21 | Performed
| 181 | 25-65-00-01-0-SVA-001 | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK | 25-65-00-01-0-SVA-001 (02) / FIRST AID MEDICAL SURVL KIT CHECK (32807056) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 19.Jul.2026 06:36 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | PRE INSP |  |  | As per requested by CONF ENGG in T/Q CONF ENGG 805450. | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807056 | 40000929 | 2026-07-21 | Performed
| 184 | 255000-16-1-001 | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP | 255000-16-1-001 (03) / FWD CARGO COMP DIVIDER NETS INSP (32807080) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 19.Jul.2026 01:14 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 0 / 8 |  | 1 / 1 | [] |  |  | MET.32807080 | 13008286 | 2026-07-20 | Performed
| 185 | 255000-16-1-002 | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP | 255000-16-1-002 (03) / AFT AND BULK CARGO COMP NETS INSP (32807093) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 |  | 0 |  | 0 | Closed | 0 | T: 0; O: 0; C: 0 | 25-50 |  | [] | PRE INSP |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32807093 | 13003390 | 2026-07-22 | Performed
| 187 | 261200-01-1 | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:36 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 26-12 |  | [] | OPS/LK |  |  |  | 261200-01-1 (4) / ENG FIRE & OVERHEAT DETECTION TEST (32807063) |  | 1 / 1 | [] |  |  | MET.32807063 | 13008286 | 2026-07-23 | Performed
| 203 | 282800-09-1 | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.014583 | 19.Jul.2026 01:45 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 28-28 |  | [] | PRE INSP |  |  |  | 282800-09-1 (03) / ADDITIONAL CENTER TANK TRANSFER SYSTEM (GVI) (29295144) |  | 1 / 1 | [] |  |  | MET.29295144 | 13008286 | 2026-07-20 | Performed
| 204 | 291000-01-1 | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 15:46 | 0.046528 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 29-10 |  | [] | TC/P |  |  |  | 291000-01-1 (3) / HYD RESERVOIRS FLUID LEVEL CHECK (32807081) |  | 1 / 1 | [] |  |  | MET.32807081 | 13008286 | 2026-07-23 | Performed
| 205 | 291000-18-1 | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 15:46 | 0.17639 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 29-27 |  | [] | TC/P |  |  |  | 291000-18-1 (2) / HYDRAULIC RECOVERY TANK DRAINAGE (32807098) |  | 1 / 1 | [] |  |  | MET.32807098 | 13008286 | 2026-07-23 | Performed
| 210 | 323000-01-1-001 | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 18.Jul.2026 21:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 323000-01-1-001 (4) / (NLG) DOWNLOCK SPRING & ATTACHMENT (32807092) |  | 1 / 1 | [] |  |  | MET.32807092 | 13008286 | 2026-07-20 | Performed
| 211 | 323000-01-1-002 | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-002 (4) / LH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807075) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 01:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807075 | 13008286 | 2026-07-20 | Performed
| 212 | 323000-01-1-003 | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT | 323000-01-1-003 (4) / RH(MLG)DOWINLOCK SPRING & ATTACHMENT (32807099) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0048611 | 19.Jul.2026 00:43 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 32-30 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807099 | 13008286 | 2026-07-20 | Performed
| 213 | 324411-01-2 | 324411-01-2 (3) / BRAKE ACCUMULATOR | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 23.Jul.2026 04:34 | 0.084028 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 32-44 |  | [] | TC/P |  |  |  | 324411-01-2 (3) / BRAKE ACCUMULATOR (32807113) |  | 1 / 1 | [] |  |  | MET.32807113 | 13009981 | 2026-07-23 | Performed
| 215 | 353000-01-1 | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015278 | 17.Jul.2026 22:00 | 0.015278 | 21.Jul.2026 05:00 | 0.21528 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 35-32 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 353000-01-1 (5) / PORTABLE OXYGEN CYLINDERS OPC (32796726) |  | 3 / 3 | [] |  |  | MET.32796726 | 13003390 | 2026-07-21 | Performed
| 216 | 353000-05-1 | 353000-05-1 (5) / CABIN PBE INSP | 353000-05-1 (5) / CABIN PBE INSP (32796732) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:54 | 0.15764 |  | 0.11458 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 353000-05-1 (5) / CABIN PBE INSP (32796732) |  | 3 / 3 | [] |  |  | MET.32796732 | 13003390 | 2026-07-19 | Performed
| 236 | 200002-01-1 | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP | 200002-01-1 (2) / THS ELECTRICAL BONDING LEADS INSP (32712874) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 17:47 | 0.72222 |  | 0.625 | Closed | 0 | T: 10; O: 0; C: 10 | 24-92 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.32712874 | 13003390 | 2026-07-21 | Performed
| 237 | 200435-01-1-001 | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP | 200435-01-1-001 (03) / NO.1 ENG FAN&ACCESORY G/B WIRNG INSP (28390064) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:59 | 0.67431 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.28390064 | 13003390 | 2026-07-22 | Performed
| 238 | 200435-01-1-002 | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP | 200435-01-1-002 (03) / NO.2 ENG FAN & ACCE G/B (EWIS) INSP (28349854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.0375 | 21.Jul.2026 13:41 | 0.21736 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 2 |  | 3 / 3 | [] |  |  | MET.28349854 | 13003390 | 2026-07-21 | Performed
| 239 | 200453-01-1-001 | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.047222 | 17.Jul.2026 22:00 | 0.030556 | 21.Jul.2026 14:57 | 1899-12-31 16:08 |  | 0.125 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-001 (05) / NO. 1 ENG HOT SECTION WIRING INSP (32712959) |  | 3 / 3 | [] |  |  | MET.32712959 | 13009981 | 2026-07-23 | Performed
| 240 | 200453-01-1-002 | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022222 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 13:45 | 1899-12-31 17:12 |  | 0.14583 | Closed | 0 | T: 4; O: 0; C: 4 | 24-92 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 200453-01-1-002 (05) / NO. 2 ENG HOT SECTION WIRING INSP (32712991) |  | 3 / 3 | [] |  |  | MET.32712991 | 13009981 | 2026-07-23 | Performed
| 249 | 215000-03-2 | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.045833 | 20.Jul.2026 02:40 | 0.36736 |  | 1899-12-31 16:00 | Closed | 0 | T: 0; O: 0; C: 0 | 21-61 |  | [] | PRE HGR |  |  |  | 215000-03-2 (3) / PACK RAM AIR INLET INSPECTION (32712787) |  | 1 / 1 | [] |  |  | MET.32712787 | 13003390 | 2026-07-20 | Performed
| 256 | 221000-01-1 | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 08:44 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 22-10 |  | [] | OPS/LK |  |  |  | 221000-01-1 (4) / AUTOPILOT (AP) DISENGAGEMENT OPC (32712839) |  | 1 / 1 | [] |  |  | MET.32712839 | 40000929 | 2026-07-23 | Performed
| 257 | 23-73-00-01-0-SVA | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 22:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 23-73 |  | [] | OPS/LK |  |  |  | 23-73-00-01-0-SVA (01) / CABIN SIGNS OPS CHK (19873618) |  | 1 / 1 | [] |  |  | MET.19873618 | 13008286 | 2026-07-22 | Performed
| 258 | 233300-02-1 | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 22:08 | 0.086111 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 23-33 |  | [] | OPS/LK |  |  |  | 233300-02-1 (4) / PASSENGER ENTERTAINMENT OPC (32712733) |  | 1 / 1 | [] |  |  | MET.32712733 | 13008286 | 2026-07-22 | Performed
| 259 | 235100-01-1 | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:14 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 23-51 |  | [] | OPS/LK, OPS/LK |  |  |  | 235100-01-1 (02) / CAPT AND F/O AUDIO CTL PANELS OPC (25336141) |  | 2 / 2 | [] |  |  | MET.25336141 | 13008286 | 2026-07-23 | Performed
| 261 | 237135-02-1 | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.014583 | 17.Jul.2026 22:00 | 0.011806 | 23.Jul.2026 13:29 | 0.1 |  | 0.375 | Closed | 0 | T: 1; O: 0; C: 1 | 23-71 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 237135-02-1 (05) / UNDERWATER LOCATOR BEACON OPC (32712774) |  | 3 / 3 | [] |  |  | MET.32712774 | 13003390 | 2026-07-23 | Performed
| 263 | 242400-02-1 | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:38 | 0.083333 |  | 0.16667 | Closed | 0 | T: 2; O: 0; C: 2 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-02-1 (3) / EMERGENCY GENERATOR CONTROL UNIT OPC (32712832) |  | 1 / 1 | [] |  |  | MET.32712832 | 13008286 | 2026-07-23 | Performed
| 264 | 242500-01-1 | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 08:36 | 0.083333 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 24-25 |  | [] | OPS/LK |  |  |  | 242500-01-1 (7) / AC ESSENTIAL GENRATION SWITCHING OPC (32712691) |  | 1 / 1 | [] |  |  | MET.32712691 | 13008286 | 2026-07-23 | Performed
| 268 | 243200-01-1 | 243200-01-1 (6) / DC GENERATION SWITCHING OPC | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 09:39 | 0.042361 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 24-32 |  | [] | OPS/LK |  |  |  | 243200-01-1 (6) / DC GENERATION SWITCHING OPC (32712840) |  | 1 / 1 | [] |  |  | MET.32712840 | 13008286 | 2026-07-23 | Performed
| 269 | 243400-01-1 | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 22.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 24-34 |  | [] | OPS/LK |  |  |  | 243400-01-1 (4) / DC EMERGY CONFIGURATION CAUTION OPC (32712850) |  | 1 / 1 | [] |  |  | MET.32712850 | 13008286 | 2026-07-23 | Performed
| 270 | 245100-01-1 | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 22.Jul.2026 08:31 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-01-1 (3) / GENERATOR LINE CONTACTOR OPENING OPC (32712666) |  | 1 / 1 | [] |  |  | MET.32712666 | 13008286 | 2026-07-23 | Performed
| 271 | 245100-02-1 | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 07:51 | 0.084028 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 24-51 |  | [] | OPS/LK |  |  |  | 245100-02-1 (3) / COMMERCIAL ELEC LOAD SHEDDING OPC (32712707) |  | 1 / 1 | [] |  |  | MET.32712707 | 13008286 | 2026-07-23 | Performed
| 293 | 252200-03-1 | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.00069444 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:56 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-22 |  | [] | PRE INSP |  |  |  | 252200-03-1 (4) / CABIN ATTENDANT SEATS BELTS INSP (32712731) |  | 1 / 1 | [] |  |  | MET.32712731 | 13008286 | 2026-07-20 | Performed
| 294 | 254000-04-2 | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.1375 | 17.Jul.2026 22:00 | 0.1375 | 19.Jul.2026 06:58 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-40 |  | [] | PRE INSP |  |  |  | 254000-04-2 (4) / LAVATORIES FLOOR PANELS INSPECTION (32712700) |  | 1 / 1 | [] |  |  | MET.32712700 | 13008286 | 2026-07-20 | Performed
| 297 | 256535-01-1 | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0055556 | 19.Jul.2026 07:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-65 |  | [] | OPS/LK |  |  |  | 256535-01-1 (02) / EMERGENCY LOCATOR TRANSMITTER OPC (31498183) |  | 1 / 1 | [] |  |  | MET.31498183 | 13003390 | 2026-07-22 | Performed
| 301 | 262100-02-1-001 | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:46 | 0.12222 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-001 (04) / NO. 1 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712831) |  | 1 / 1 | [] |  |  | MET.32712831 | 13008286 | 2026-07-23 | Performed
| 302 | 262100-02-1-002 | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 12:48 | 0.12153 |  | 0.20833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPS/LK |  |  |  | 262100-02-1-002 (04) / NO. 2 ENG FIRE EXT BOTTLE LOW PRESS INDICATING CIRCUIT OPS CHK (32712838) |  | 1 / 1 | [] |  |  | MET.32712838 | 13008286 | 2026-07-23 | Performed
| 303 | 262100-03-1-001 | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:11 | 0.079861 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-001 (04) / NO.1 ENG FIRE EXTIG CONTINUTY CHK (32712878) |  | 3 / 3 | [] |  |  | MET.32712878 | 13003390 | 2026-07-21 | Performed
| 304 | 262100-03-1-002 | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 21.Jul.2026 16:14 | 0.077083 |  | 0.29167 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | TC/P, TC/P, TC/P |  |  |  | 262100-03-1-002 (04) / NO.2 ENG FIRE EXTIG CONTINUTY CHK (32712803) |  | 3 / 3 | [] |  |  | MET.32712803 | 13003390 | 2026-07-21 | Performed
| 306 | 262200-03-1 | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.020139 | 21.Jul.2026 15:51 | 0.090972 |  | 0.35417 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, TC/P, TC/P, JOB-CLOSEUP |  |  |  | 262200-03-1 (4) / APU FIRE EXTINGUISHING FIRING CHK (32712698) |  | 4 / 4 | [] |  |  | MET.32712698 | 13003390 | 2026-07-21 | Performed
| 307 | 262200-04-1 | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 20.Jul.2026 10:52 | 0.034722 |  | 0.034722 | Closed | 0 | T: 2; O: 0; C: 2 | 26-22 |  | [] | INSPECTION |  |  |  | 262200-04-1 (4) / APU FIRE EXTINGUISHING DISTRIBUTION PIPING INSP & DISCHARGE NOZZLE (32712842) |  | 1 / 1 | [] |  |  | MET.32712842 | 13003390 | 2026-07-20 | Performed
| 308 | 262200-05-1 | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 22.Jul.2026 13:39 | 0.088889 |  | 0.27083 | Closed | 0 | T: 1; O: 0; C: 1 | 26-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 262200-05-1 (3) / APU FIRE EXTINGUISHING LOW PRESS OPC (32712744) |  | 3 / 3 | [] |  |  | MET.32712744 | 13008286 | 2026-07-23 | Performed
| 309 | 262200-06-1 | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 19.Jul.2026 06:46 | 0.11667 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 26-22 |  | [] | OPS/LK |  |  |  | 262200-06-1 (5) / APU FIRE PUSH BUTTON & LP FUEL VLV (32712716) |  | 1 / 1 | [] |  |  | MET.32712716 | 13008286 | 2026-07-22 | Performed
| 310 | 262300-02-1 | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.036806 | 21.Jul.2026 14:33 | 0.14306 |  | 0.45833 | Closed | 0 | T: 2; O: 0; C: 2 | 26-23 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 262300-02-1 (05) / CARGO COMP FIRNG CIRCT CONTU CHK (32712799) |  | 4 / 4 | [] |  |  | MET.32712799 | 13003390 | 2026-07-21 | Performed
| 312 | 262541-04-1 | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 06:59 | 0.03125 |  | 0.03125 | Closed | 0 | T: 0; O: 0; C: 0 | 26-25 |  | [] | INSPECTION |  |  |  | 262541-04-1 (3) / LAVATORY FIRE EXTG PRESS READING CHK (32712705) |  | 1 / 1 | [] |  |  | MET.32712705 | 13008286 | 2026-07-20 | Performed
| 313 | 271400-01-1 | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 23.Jul.2026 16:40 | 0.063194 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 27-14 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 271400-01-1 (3) / AILERON DAMPING MEASUREMENT OPS TEST (32712730) |  | 3 / 3 | [] |  |  | MET.32712730 | 13003390 | 2026-07-23 | Performed
| 324 | 272400-02-1 | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION | 272400-02-1 (04) / FUNCTIONAL CHK OF RUDDER HYDRAULIC ACTUATION (28325998) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.05 | 21.Jul.2026 04:00 | 0.30833 |  | 1899-12-31 15:35 | Closed | 0 | T: 4; O: 0; C: 4 | 27-24 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 0 / 1 |  | 8 / 8 | [] |  |  | MET.28325998 | 13003390 | 2026-07-21 | Performed
| 325 | 273400-02-1 | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.22917 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:10 | 0.38472 |  | 1899-12-31 12:45 | Closed | 0 | T: 9; O: 0; C: 9 | 27-34 |  | [] | PRE HGR, PRE HGR, PRE HGR, PRE HGR |  |  |  | 273400-02-1 (04) / FUNCTIONAL CHECK OF ELEV SERVO CONT & HINGE BEARING PLAY (31481303) |  | 4 / 4 | [] |  |  | MET.31481303 | 13003390 | 2026-07-21 | Performed
| 327 | 274000-04-1 | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 02:44 | 0.36458 |  | 0.83333 | Closed | 0 | T: 1; O: 0; C: 1 | 27-96 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 274000-04-1 (3) / THS ACTUATOR WITH ELECTRIC MOTOR OPC (32712668) |  | 3 / 3 | [] |  |  | MET.32712668 | 13003390 | 2026-07-20 | Performed
| 333 | 274451-06-1 | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0041667 | 17.Jul.2026 22:00 | 0.0041667 | 21.Jul.2026 10:23 | 0.020833 |  | 0.020833 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | PRE INSP |  |  |  | 274451-06-1 (3) / THS ACT THREADED NUT INSPECTION (32712769) |  | 1 / 1 | [] |  |  | MET.32712769 | 13003390 | 2026-07-21 | Performed
| 336 | 274451-14-1 | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.029861 | 17.Jul.2026 22:00 | 0.014583 | 22.Jul.2026 15:44 | 0.17986 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 27-44 |  | [] | OPS/LK |  |  |  | 274451-14-1 (4) / THS ACTUATOR ELECTRICAL LOAD OPC (32712861) |  | 1 / 1 | [] |  |  | MET.32712861 | 13008286 | 2026-07-23 | Performed
| 337 | 275100-01-2 | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.020833 | 22.Jul.2026 11:21 | 0.16875 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-01-2 (4) / FLAP SYSTEM WING TIP BRAKE OPC (32712713) |  | 3 / 3 | [] |  |  | MET.32712713 | 13008286 | 2026-07-23 | Performed
| 338 | 275100-02-1-001 | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-001 (03) / L/H WING FLAP INTERCONNECTING STRUT (32712880) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:04 | 1899-12-31 13:47 |  | 0.83333 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712880 | 13003390 | 2026-07-23 | Performed
| 339 | 275100-02-1-002 | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0041667 | 22.Jul.2026 00:00 | 1899-12-31 13:50 |  | 0.61458 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | PRE HGR, PRE HGR, PRE HGR |  |  |  | 275100-02-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712843) |  | 3 / 3 | [] |  |  | MET.32712843 | 13003390 | 2026-07-23 | Performed
| 343 | 275144-01-1-002 | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.038889 | 22.Jul.2026 00:08 | 1899-12-31 13:43 |  | 0.44792 | Closed | 0 | T: 0; O: 0; C: 0 | 27-51 |  | [] | JOB-SETUP, INSPECTION, OPS/LK, JOB-CLOSEUP |  |  |  | 275144-01-1-002 (03) / R/H WING FLAP INTERCONNECTING STRUT (32712877) |  | 4 / 4 | [] |  |  | MET.32712877 | 13003390 | 2026-07-23 | Performed
| 361 | 281247-01-1-001 | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:07 | 0.038194 |  | 0.038194 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-001 (02) / L/H NACA INTAKE FOR SIGN OF BLOCLAGE (32712890) |  | 1 / 1 | [] |  |  | MET.32712890 | 13008286 | 2026-07-20 | Performed
| 362 | 281247-01-1-002 | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0034722 | 17.Jul.2026 22:00 | 0.0034722 | 19.Jul.2026 05:03 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 28-12 |  | [] | PRE INSP |  |  |  | 281247-01-1-002 (02) / R/H NACA INTAKE FOR SIGN OF BLOCKAGE (32712804) |  | 1 / 1 | [] |  |  | MET.32712804 | 13008286 | 2026-07-20 | Performed
| 367 | 282100-05-1-001 | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-001 (03) / NO. 1 ENGINE PIPES, COUPLINGS INSP (32712865) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:15 | 0.16042 |  | 0.25 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712865 | 40000010 | 2026-07-19 | Performed
| 368 | 282100-05-1-002 | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0083333 | 18.Jul.2026 17:16 | 0.15972 |  | 0.20833 | Closed | 0 | T: 8; O: 0; C: 8 | 28-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 282100-05-1-002 (03) / NO. 2 ENGINE PIPES, COUPLINGS INSP (32712800) |  | 3 / 3 | [] |  |  | MET.32712800 | 40000010 | 2026-07-19 | Performed
| 369 | 282300-01-2 | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 17:07 | 0.125 |  | 0.41667 | Closed | 0 | T: 1; O: 0; C: 1 | 28-23 |  | [] | PRE HGR, PRE HGR, JOB-CLOSEUP |  |  |  | 282300-01-2 (04) / FUEL CROSSFEED VALVE OPERATIONAL (28325816) |  | 3 / 3 | [] |  |  | MET.28325816 | 40000010 | 2026-07-19 | Performed
| 373 | 282800-05-2 | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 06:58 | 0.12569 |  | 0.25 | Closed | 0 | T: 3; O: 0; C: 3 | 28-28 |  | [] | OPS/LK |  |  |  | 282800-05-2 (3) / ADD CTR TANK MANL TRX OPC (28325959) |  | 1 / 1 | [] |  |  | MET.28325959 | 13003390 | 2026-07-22 | Performed
| 377 | 291000-06-1 | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 18.Jul.2026 14:03 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-23 |  | [] | OPS/LK |  |  |  | 291000-06-1 (3) / PTU YELLOW TO GREEN FUNCTIONAL CHECK (32712779) |  | 1 / 1 | [] |  |  | MET.32712779 | 13003390 | 2026-07-22 | Performed
| 378 | 291000-09-1 | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 14:08 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 29-10 |  | [] | OPS/LK |  |  |  | 291000-09-1 (4) / HYDRAULIC FIRE SHUT OFF VALVES OPC (32712688) |  | 1 / 1 | [] |  |  | MET.32712688 | 13003390 | 2026-07-22 | Performed
| 380 | 291000-19-1 | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.06875 | 17.Jul.2026 22:00 | 0.034028 | 18.Jul.2026 14:06 | 0.084028 |  | 0.33333 | Closed | 0 | T: 3; O: 0; C: 3 | 29-23 |  | [] | OPS/LK, OPS/LK |  |  |  | 291000-19-1 (4) / PTU INHIBITION LOGIC OPERATION CHECK (32712867) |  | 2 / 2 | [] |  |  | MET.32712867 | 13003390 | 2026-07-22 | Performed
| 386 | 302149-C1-1-001 | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 14:55 | 0.67778 |  | 0.10417 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 302149-C1-1-001 (02) / NO.1 ENG INTAKE ANTI-ICE DUCT INSP (26225037) |  | 3 / 3 | [] |  |  | MET.26225037 | 13003390 | 2026-07-22 | Performed
| 387 | 302149-C1-1-002 | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP | 302149-C1-1-002 (02) / NO.2 ENG INTAKE ANTI-ICE DUCT INSP (26290689) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022222 | 21.Jul.2026 13:17 | 0.23403 |  | 0.27083 | Closed | 0 | T: 3; O: 0; C: 3 | 30-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.26290689 | 13003390 | 2026-07-21 | Performed
| 388 | 303100-01-1 | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.01875 | 23.Jul.2026 12:17 | 0.086111 |  | 0.375 | Closed | 0 | T: 2; O: 0; C: 2 | 30-31 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 303100-01-1 (3) / PITOT PROBE HETR INSULATION RES FNC (32712674) |  | 3 / 3 | [] |  |  | MET.32712674 | 13003390 | 2026-07-23 | Performed
| 389 | 313300-03-1 | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.013194 | 23.Jul.2026 13:26 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 31-33 |  | [] | OPS/LK |  |  |  | 313300-03-1 (05) / DFDR SYSTEM INTERCONNECTION OPC (32712808) |  | 1 / 1 | [] |  |  | MET.32712808 | 13003390 | 2026-07-23 | Performed
| 391 | 315000-01-1 | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 08:15 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-50 |  | [] | OPS/LK |  |  |  | 315000-01-1 (3) / PFD-ND AND ECAM-ND MANUAL TRANS OPC (32712854) |  | 1 / 1 | [] |  |  | MET.32712854 | 40000929 | 2026-07-23 | Performed
| 392 | 315000-02-1 | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 15:09 | 0.042361 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 31-60 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 315000-02-1 (4) / EFIS & ECAM DMC OPS CHK (32712781) |  | 2 / 2 | [] |  |  | MET.32712781 | 13003390 | 2026-07-22 | Performed
| 394 | 321113-03-1-001 | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 22.Jul.2026 18:15 | 0.063194 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-001 (03) / LH MLG SHOCK ABSORBER FLUID LEVL CHK (25336785) |  | 3 / 3 | [] |  |  | MET.25336785 | 13008286 | 2026-07-23 | Performed
| 395 | 321113-03-1-002 | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.56806 | 17.Jul.2026 22:00 | 0.28403 | 19.Jul.2026 19:10 | 1900-01-02 00:43 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 12-12 |  | [] | JOB-SETUP, TC/P, JOB-CLOSEUP |  |  |  | 321113-03-1-002 (03) / RH MLG SHOCK ABSORBER FLUID LEVL CHK (25336733) |  | 3 / 3 | [] |  |  | MET.25336733 | 13008286 | 2026-07-23 | Performed
| 396 | 321113-04-1-001 | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 12:02 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-001 (03) / L/H MLG SHOCK ABSORBER PRESS CHK (32712855) |  | 1 / 1 | [] |  |  | MET.32712855 | 13008286 | 2026-07-23 | Performed
| 397 | 321113-04-1-002 | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.036111 | 22.Jul.2026 18:01 | 0.083333 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 12-14 |  | [] | OPS/LK |  |  |  | 321113-04-1-002 (03) / R/H MLG SHOCK ABSORBER PRESS CHK (32712715) |  | 1 / 1 | [] |  |  | MET.32712715 | 13008286 | 2026-07-23 | Performed
| 400 | 322113-01-1 | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.018056 | 22.Jul.2026 18:26 | 0.043056 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 12-12 |  | [] | OPS/LK |  |  |  | 322113-01-1 (4) / NLG SHOCK ABSORBR CHARGE PRSS CHK (32712797) |  | 1 / 1 | [] |  |  | MET.32712797 | 13008286 | 2026-07-23 | Performed
| 401 | 323000-17-1 | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.0083333 | 19.Jul.2026 06:43 | 0.11667 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 32-31 |  | [] | OPS/LK |  |  |  | 323000-17-1 (5) / LGCIU POWER SUPPLY RELAYS FUNC CHK (32712851) |  | 1 / 1 | [] |  |  | MET.32712851 | 13008286 | 2026-07-22 | Performed
| 403 | 323100-05-1 | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 18.Jul.2026 21:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 32-30 |  | [] | PRE INSP |  |  |  | 323100-05-1 (2) / NLG DOOR OPERATING MECHANISM INSP (32712809) |  | 1 / 1 | [] |  |  | MET.32712809 | 13008286 | 2026-07-20 | Performed
| 411 | 324300-02-1 | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 07:49 | 0.125 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 32-42 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 324300-02-1 (5) / OPERATIONAL CHECK OF ANTISKID INHIBITION (32712725) |  | 3 / 3 | [] |  |  | MET.32712725 | 13008286 | 2026-07-22 | Performed
| 412 | 324500-01-2 | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.072917 | 23.Jul.2026 03:30 | 0.12569 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 32-45 |  | [] | JOB-SETUP, OPS/LK |  |  |  | 324500-01-2 (4) / PARKING BRAKE SYSTEM OPS CHK (32712873) |  | 2 / 2 | [] |  |  | MET.32712873 | 13009981 | 2026-07-23 | Performed
| 413 | 335100-11-1 | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 21.Jul.2026 21:07 | 0.12847 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 33-51 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 335100-11-1 (1) / CABIN EMERGENCY LIGHTING (32712675) |  | 3 / 3 | [] |  |  | MET.32712675 | 13008286 | 2026-07-22 | Performed
| 414 | 34-55-00-03-A | 34-55-00-03-A (04) / VOR SYSTEM TEST | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.03125 | 21.Jul.2026 15:25 | 0.10833 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 34-55 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 34-55-00-03-A (04) / VOR SYSTEM TEST (32712755) |  | 3 / 3 | [] |  |  | MET.32712755 | 13003390 | 2026-07-21 | Performed
| 415 | 341300-01-1 | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.014583 | 21.Jul.2026 09:45 | 0.042361 |  | 0.33333 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 341300-01-1 (3) / VMO/MMO OVERSPEED WARNING OPC (32712762) |  | 4 / 4 | [] |  |  | MET.32712762 | 40000929 | 2026-07-23 | Performed
| 418 | 341300-05-1 | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:37 | 0.083333 |  | 0.16667 | Closed | 0 | T: 1; O: 0; C: 1 | 34-13 |  | [] | OPS/LK |  |  |  | 341300-05-1 (4) / ADIRU 5-MINUTE TIME DELAY OPC (32712719) |  | 1 / 1 | [] |  |  | MET.32712719 | 40000929 | 2026-07-23 | Performed
| 421 | 342200-01-1 | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0076389 | 19.Jul.2026 08:08 | 0.056944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-01-1 (5) / STANDBY COMPASS OPS CHK & GVI (32712695) |  | 4 / 4 | [] |  |  | MET.32712695 | 13008286 | 2026-07-22 | Performed
| 422 | 342200-05-1 | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038194 | 17.Jul.2026 22:00 | 0.03125 | 23.Jul.2026 05:11 | 0.090278 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 34-22 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 342200-05-1 (3) / STBY PNEM CIRCUT LOW RANG LEAK TEST (32712749) |  | 3 / 3 | [] |  |  | MET.32712749 | 13009981 | 2026-07-23 | Performed
| 423 | 344800-03-1 | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 08:34 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 34-48 |  | [] | TC/P |  |  |  | 344800-03-1 (04) / TERRAIN AWARENESS WARNING SYSTEM RA OPC (28325742) |  | 1 / 1 | [] |  |  | MET.28325742 | 13008286 | 2026-07-23 | Performed
| 424 | 345200-02-1 | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.00625 | 21.Jul.2026 09:41 | 0.042361 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 34-52 |  | [] | JOB-SETUP, OPS/LK, OPS/LK, JOB-CLOSEUP |  |  |  | 345200-02-1 (3) / ATC ANTENNAS FUNCTIONAL CHECK (32712786) |  | 4 / 4 | [] |  |  | MET.32712786 | 13008286 | 2026-07-23 | Performed
| 426 | 351241-01-1 | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION | 351241-01-1 (3) / CREW OXYGEN MASKS INSPECTION (32712806) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:08 | 0.18194 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712806 | 40000930 | 2026-07-20 | Performed
| 429 | 353000-06-1-SVA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.09375 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 06:17 | 0.06875 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25-64 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  | as per MGR Mial ear @Jinoy Jose, Thanks for the email. As discussed further, the referenced task cards will be revised to change the replacement interval from 6 months to 02 months prior to expiry. Dear @Mohammed A Albukhari, Refer email below. As discussed, please revised the text for following tasks to change the replacement interval from 6 months to 2 month prior to expiry. Remaining instructions (2 & 3 ) will be deleted from the task as well. MP Task Number Title PBE replacement interval 333 353250-01-1-SVA CABIN ATTENDANTS PORTABLE BREATHING EQUIPMENT (PBE) PERIODIC CHECK FOR EXPIRATION 6 Months 773 25-180-00-SVA PROTECTIVE BREATHING EQUIPMENT (PBE) EXPIRATION DATE CHECK 6 Months 787 25-060-00-01-SVA SMOK HOODS PERIODIC CHECK FOR EXPIRATION 6 Months 32S 353000-06-1-SVA PROTECT. BREATHING EQPT (CKPT & CABIN) PERIODIC CHECK FOR EXPIRATION 6 Months Regards, Muhammad Noor Manager, Maintenance Program E-mail: MONOOR@saudia.com Office: +966126867409 Maintenance Program, JED, SA | 353000-06-1-SVA (03) / COCKPIT (PBE) INSPECTION (28326058) |  | 3 / 3 | [] |  |  | MET.28326058 | 13008286 | 2026-07-20 | Performed
| 430 | 353000-07-1 | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION | 353000-07-1 (4) / PORTABLE OXYGEN MASKS INSPECTION (32712894) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 07:27 | 0.13611 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 35-30 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.32712894 | 13003390 | 2026-07-19 | Performed
| 436 | 361200-02-1 | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED | 361200-02-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED (32712883) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.18333 | 17.Jul.2026 22:00 | 0.091667 | 18.Jul.2026 13:20 | 0.92778 |  | 1899-12-31 18:40 | Closed | 0 | T: 10; O: 0; C: 10 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712883 | 40000010 | 2026-07-19 | Performed
| 437 | 361200-03-1 | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.091667 | 17.Jul.2026 22:00 | 0.041667 | 18.Jul.2026 15:16 | 0.84722 |  | 1899-12-31 16:20 | Closed | 0 | T: 2; O: 0; C: 2 | 36-12 |  | [] | JOB-SETUP, OPS/LK, JOB-CLOSEUP |  |  |  | 361200-03-1 (3) / APU BLEED AIR SUPPLY & CROSSBLEED LEAK CHECK (32712718) |  | 3 / 3 | [] |  |  | MET.32712718 | 40000010 | 2026-07-19 | Performed
| 445 | 498000-B1-1 | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 20.Jul.2026 10:51 | 0.020833 |  | 0.020833 | Closed | 0 | T: 3; O: 0; C: 3 | 49-81 |  | [] | INSPECTION |  |  |  | 498000-B1-1 (02) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS (32712864) |  | 1 / 1 | [] |  |  | MET.32712864 | 13003390 | 2026-07-20 | Performed
| 473 | 525111-01-1 | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP | 525111-01-1 (3) / COCKPIT DOOR LOCKING SYS MECH PARTS INSP (32712736) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.022917 | 17.Jul.2026 22:00 | 0.022917 | 21.Jul.2026 04:30 | 0.16111 |  | 0.32292 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.32712736 | 13003390 | 2026-07-21 | Performed
| 474 | 525111-02-1 | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.013194 | 17.Jul.2026 22:00 | 0.0069444 | 21.Jul.2026 03:47 | 0.125 |  | 0.19792 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-02-1 (3) / COCKPIT DOOR PRESS SENSING CHANNELS (32712895) |  | 1 / 1 | [] |  |  | MET.32712895 | 13008286 | 2026-07-22 | Performed
| 476 | 525111-04-1 | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0048611 | 17.Jul.2026 22:00 | 0.0027778 | 21.Jul.2026 03:44 | 0.12917 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] | OPS/LK |  |  |  | 525111-04-1 (3) / COCKPIT DOOR OPENING WITH POWER OFF (32712771) |  | 1 / 1 | [] |  |  | MET.32712771 | 13008286 | 2026-07-22 | Performed
| 480 | 527300-02-1 | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0048611 | 23.Jul.2026 03:05 | 0.17639 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-73 |  | [] | OPS/LK |  |  |  | 527300-02-1 (3) / EMERGENCY ESCAPE SLIDE RELEASE AND OVERPRESSURE WARNING SYSTEMS (32712706) |  | 1 / 1 | [] |  |  | MET.32712706 | 13009981 | 2026-07-23 | Performed
| 487 | 532137-01-1 | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.034028 | 21.Jul.2026 14:20 | 0.24514 |  | 0.25 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP |  |  |  | 532137-01-1 (03) / FWD CARGO DOOR CUTOUT PANEL INSP (32712835) |  | 2 / 2 | [] |  |  | MET.32712835 | 13008286 | 2026-07-22 | Performed
| 497 | 545000-01-1-001 | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 15:11 | 1899-12-31 15:25 |  | 0.13194 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-01-1-001 (02) / NO. 1 ENGINE PYLON DRAIN SYS INSP (26224706) |  | 3 / 3 | [] |  |  | MET.26224706 | 13009981 | 2026-07-23 | Performed
| 498 | 545000-01-1-002 | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP | 545000-01-1-002 (02) / NO. 2 ENGINE PYLON DRAIN SYSTEM INSP (26224854) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.013889 | 21.Jul.2026 14:30 | 1899-12-31 16:39 |  | 0.13542 | Closed | 0 | T: 7; O: 0; C: 7 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 1 |  | 3 / 3 | [] |  |  | MET.26224854 | 13009981 | 2026-07-23 | Performed
| 499 | 545000-04-1-001 | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 15:24 | 1899-12-31 15:46 |  | 0.10417 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-001 (02) / NO.1 ENG PYLN COMPT DRAIN SYS INSP (26224971) |  | 3 / 3 | [] |  |  | MET.26224971 | 13009981 | 2026-07-23 | Performed
| 500 | 545000-04-1-002 | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10972 | 17.Jul.2026 22:00 | 0.095833 | 21.Jul.2026 14:26 | 1899-12-31 16:45 |  | 0.14583 | Closed | 0 | T: 2; O: 0; C: 2 | 54-50 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-04-1-002 (02) / NO.2 ENG PYLN COMPT DRAIN SYS INSP (26225034) |  | 3 / 3 | [] |  |  | MET.26225034 | 13009981 | 2026-07-23 | Performed
| 503 | 545000-06-1-001 | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 15:18 | 1899-12-31 15:56 |  | 0.23264 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-001 (01) / L/H PYLONS CAF 4 SEALANT INSP (19876877) |  | 3 / 3 | [] |  |  | MET.19876877 | 13009981 | 2026-07-23 | Performed
| 504 | 545000-06-1-002 | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 14:42 | 1899-12-31 16:33 |  | 0.097222 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545000-06-1-002 (01) / R/H PYLONS CAF 4 SEALANT INSP (19876887) |  | 3 / 3 | [] |  |  | MET.19876887 | 13009981 | 2026-07-23 | Performed
| 505 | 545103-01-2-001 | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:07 | 1899-12-31 16:09 |  | 0.25 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-001 (03) / NO. 1 ENG PYLON FWD MOUNT FTTNG INSP (25336918) |  | 3 / 3 | [] |  |  | MET.25336918 | 13009981 | 2026-07-23 | Performed
| 506 | 545103-01-2-002 | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:19 | 1899-12-31 16:59 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 545103-01-2-002 (03) / NO. 2 ENG PYLON FWD MOUNT FTTNG INSP (25335813) |  | 3 / 3 | [] |  |  | MET.25335813 | 13009981 | 2026-07-23 | Performed
| 514 | 711000-C1-1-001 | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:34 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-001 (03) / #1 ENG INTAKE COWL AFT BULKHEAD INSP (26290633) |  | 1 / 1 | [] |  |  | MET.26290633 | 13008286 | 2026-07-20 | Performed
| 515 | 711000-C1-1-002 | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 05:35 | 0.020833 |  | 0.020833 | Closed | 0 | T: 2; O: 0; C: 2 | 71-10 |  | [] | INSPECTION |  |  |  | 711000-C1-1-002 (03) / #2 ENG INTAKE COWL AFT BULKHEAD INSP (19875138) |  | 1 / 1 | [] |  |  | MET.19875138 | 13008286 | 2026-07-20 | Performed
| 516 | 711000-C4-2-001 | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-001 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325730) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 15:06 | 0.66806 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | OPEN-UP, INSPECTION, CLOSE-UP |  |  |  | 0 / 8 |  | 3 / 3 | [] |  |  | MET.28325730 | 13003390 | 2026-07-22 | Performed
| 517 | 711000-C4-2-002 | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS | 711000-C4-2-002 (03) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS (28325833) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.081944 | 17.Jul.2026 22:00 | 0.070833 | 21.Jul.2026 14:21 | 0.19167 |  | 0.24306 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 5 |  | 3 / 3 | [] |  |  | MET.28325833 | 13003390 | 2026-07-21 | Performed
| 520 | 711000-C6-1-001 | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-001 (03) / NO.1 ENG FAN COW LATCH & AJCNT INSP (28325843) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:50 | 0.67917 |  | 0.125 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.28325843 | 13003390 | 2026-07-22 | Performed
| 521 | 711000-C6-1-002 | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP | 711000-C6-1-002 (02) / NO.2 ENG FAN COW LATCH & AJCNT INSP (28325855) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.072917 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 14:04 | 0.14653 |  | 0.083333 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | INSPECTION |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.28325855 | 13003390 | 2026-07-21 | Performed
| 522 | 711000-C7-1-001 | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 15:02 | 0.67153 |  | 0.076389 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-001 (02) / NO.1 ENG FAN COWL DOOR FIRESEAL INSP (26224711) |  | 3 / 3 | [] |  |  | MET.26224711 | 13003390 | 2026-07-22 | Performed
| 523 | 711000-C7-1-002 | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.076389 | 17.Jul.2026 22:00 | 0.065278 | 21.Jul.2026 14:07 | 0.2 |  | 0.27083 | Closed | 0 | T: 2; O: 0; C: 2 | 71-13 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 711000-C7-1-002 (02) / NO.2 ENG FAN COWL DOOR FIRESEAL INSP (26224781) |  | 3 / 3 | [] |  |  | MET.26224781 | 13003390 | 2026-07-21 | Performed
| 524 | 711300-01-2 | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. | 711300-01-2 (00) / GENERAL VISUAL INSPECTION OF FAN COWL DOOR HINGE FITTINGS AND SURROUNDING STRUCTURE. (23627239) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 11:01 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-13 |  | [] |  |  |  |  | 0 / 2 |  | 1 / 1 | [] |  |  | MET.23627239 | 40000930 | 2026-07-21 | Performed
| 529 | 712112-01-1-001 | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-001 (03) / NO. 1 ENGINE FWD MOUNT LINK LUGS INSP (28326019) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:59 | 1899-12-31 17:11 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326019 | 13009981 | 2026-07-23 | Performed
| 530 | 712112-01-1-002 | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP | 712112-01-1-002 (03) / NO. 2 ENGINE FWD MOUNT LINK LUGS INSP (28326018) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.10069 | 17.Jul.2026 22:00 | 0.091667 | 21.Jul.2026 14:31 | 1899-12-31 17:32 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.28326018 | 13009981 | 2026-07-23 | Performed
| 531 | 712211-03-1-001 | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-001 (03) / NO.1 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326017) |  | 1 / 1 | [] |  |  | MET.28326017 | 40000930 | 2026-07-21 | Performed
| 532 | 712211-03-1-002 | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.054861 | 20.Jul.2026 10:14 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP |  |  |  | 712211-03-1-002 (03) / NO.2 AFT ENG MOUNT INSTALLATION INSP EXPOSED SURFACES (28326023) |  | 1 / 1 | [] |  |  | MET.28326023 | 40000930 | 2026-07-21 | Performed
| 535 | 712212-01-1-001 | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-001 (02) / NO. 1 ENG AFT MOUNT LINK LUGS INSP (26290680) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 15:17 | 1899-12-31 16:53 |  | 0.059028 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290680 | 13009981 | 2026-07-23 | Performed
| 536 | 712212-01-1-002 | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP | 712212-01-1-002 (02) / NO. 2 ENG AFT MOUNT LINK LUGS INSP (26290654) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.11528 | 17.Jul.2026 22:00 | 0.10556 | 21.Jul.2026 14:54 | 1899-12-31 17:10 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 71-22 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 1 / 1 |  | 3 / 3 | [] |  |  | MET.26290654 | 13009981 | 2026-07-23 | Performed
| 539 | 72-00-00-25-0-SVA-001 | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:00 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-001 (01) / PRE C-CHK PRESERVATION ON ENG#1 OIL (28326050) |  | 1 / 1 | [] |  |  | MET.28326050 | 40000010 | 2026-07-19 | Performed
| 540 | 72-00-00-25-0-SVA-002 | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) | Block Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 18.Jul.2026 17:01 | 0.16736 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 72 |  | [] | OPS/LK |  |  |  | 72-00-00-25-0-SVA-002 (01) / PRE C-CHK PRESERVATION ON ENG#2 OIL (28325746) |  | 1 / 1 | [] |  |  | MET.28325746 | 40000010 | 2026-07-19 | Performed
| 545 | 783000-C4-1-001 | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 15:04 | 0.66667 |  | 0.16667 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-001 (02) / NO.1 ENG T/R TENSION HOK&AJCNT INSP (26224712) |  | 3 / 3 | [] |  |  | MET.26224712 | 13003390 | 2026-07-22 | Performed
| 546 | 783000-C4-1-002 | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.029167 | 21.Jul.2026 14:35 | 0.18264 |  | 0.43056 | Closed | 0 | T: 4; O: 0; C: 4 | 78-36 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 783000-C4-1-002 (02) / NO.2 ENG T/R TENSSION HOK AJCNT INSP (26224783) |  | 3 / 3 | [] |  |  | MET.26224783 | 13003390 | 2026-07-21 | Performed
| 554 | ZL-100-02-1 | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP | ZL-100-02-1 (04) / LOWER HALF OF FUSELAGE ZONAL INSP (32712743) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.51944 | 17.Jul.2026 22:00 | 0.51944 | 18.Jul.2026 13:45 | 0.041667 |  | 0.055556 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] | PRE INSP |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.32712743 | 13008286 | 2026-07-20 | Performed
| 555 | ZL-123-02-1 | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP | ZL-123-02-1 (4) / NOSE LANDING GEAR WELL ZONAL INSP (32712816) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 18.Jul.2026 21:35 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-21 |  | [] | PRE INSP |  |  |  | 2 / 6 |  | 1 / 1 | [] |  |  | MET.32712816 | 13008286 | 2026-07-20 | Performed
| 556 | ZL-131-01-1 | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 01:26 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-131-01-1 (05) / FWD CARGO COMPARTMENT ZONAL INSP (32712791) |  | 1 / 1 | [] |  |  | MET.32712791 | 13008286 | 2026-07-20 | Performed
| 557 | ZL-151-01-1 | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP | ZL-151-01-1 (3) / AFT CARGO COMPARTMENT ZONAL INSP (32712684) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:00 | 0.010417 |  | 0.010417 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 3 |  | 1 / 1 | [] |  |  | MET.32712684 | 13008286 | 2026-07-20 | Performed
| 558 | ZL-161-01-1 | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:11 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 1; O: 0; C: 1 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-01-1 (3) / BULK CARGO COMPARTMENT ZONAL INSP (32712661) |  | 1 / 1 | [] |  |  | MET.32712661 | 13008286 | 2026-07-20 | Performed
| 559 | ZL-161-02-1 | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1900-01-02 03:43 | 17.Jul.2026 22:00 | 1900-01-02 03:43 | 23.Jul.2026 13:06 | 0.020833 |  | 0.020833 | Closed | 0 | T: 7; O: 0; C: 7 | 05-21 |  | [] | INSPECTION |  |  |  | ZL-161-02-1 (02) / BULK CARGO COMPARTMENT ZONAL INSP (31498481) |  | 1 / 1 | [] |  |  | MET.31498481 | 13003390 | 2026-07-23 | Performed
| 560 | ZL-171-01-2 | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP | ZL-171-01-2 (04) / AFT CAB UNDERFLOOR COMP. ZONAL INSP (28326031) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.045833 | 17.Jul.2026 22:00 | 0.045833 | 21.Jul.2026 08:02 | 0.71389 |  | 0.34722 | Closed | 0 | T: 5; O: 0; C: 5 | 05-21 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.28326031 | 13008286 | 2026-07-22 | Performed
| 561 | ZL-300-02-1 | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 05:47 | 1900-01-01 01:43 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-300-02-1 (05) / STABILIZERS&CONE/REAR FUSELAGE INSP (32712776) |  | 1 / 1 | [] |  |  | MET.32712776 | 40000930 | 2026-07-21 | Performed
| 562 | ZL-315-01-1 | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | ZL-315-01-1 (02) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) (32712792) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.054861 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 10:05 | 0.03125 |  | 0.03125 | Closed | 0 | T: 2; O: 0; C: 2 | 05-23 |  | [] | INSPECTION |  |  |  | 0 / 5 |  | 1 / 1 | [] |  |  | MET.32712792 | 13003390 | 2026-07-20 | Performed
| 563 | ZL-334-01-1 | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 14:55 | 0.21667 |  | 1899-12-31 22:50 | Closed | 0 | T: 8; O: 0; C: 8 | 05-23 |  | [] | INSPECTION |  |  |  | ZL-334-01-1 (4) / THS TRAILING EDGE ZONAL INSPECTION (32712826) |  | 1 / 1 | [] |  |  | MET.32712826 | 13008286 | 2026-07-21 | Performed
| 564 | ZL-411-01-3-001 | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-001 (05) / NO. 1 ENGINE UPPER FORWARD PYLON (32712836) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.042361 |  | 0.076389 | Closed | 0 | T: 9; O: 0; C: 9 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712836 | 13008286 | 2026-07-21 | Performed
| 565 | ZL-411-01-3-002 | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON | ZL-411-01-3-002 (05) / NO. 2 ENGINE UPPER FORWARD PYLON (32712703) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.015972 | 17.Jul.2026 22:00 | 0.015972 | 20.Jul.2026 18:56 | 0.044444 |  | 0.083333 | Closed | 0 | T: 16; O: 0; C: 16 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  | #1 | MET.32712703 | 13008286 | 2026-07-21 | Performed
| 566 | ZL-437-01-1-001 | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:10 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-437-01-1-001 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.1 ENGINE (32712987) |  | 1 / 1 | [] |  |  | MET.32712987 | 13008286 | 2026-07-20 | Performed
| 567 | ZL-437-01-1-002 | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE | ZL-437-01-1-002 (05) / GENERAL VISUAL INSPECTION OF FAN COWL NO.2 ENGINE (32712965) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 19.Jul.2026 05:11 | 0.041667 |  | 0.041667 | Closed | 0 | T: 2; O: 0; C: 2 | 05-24 |  | [] | INSPECTION |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32712965 | 13008286 | 2026-07-20 | Performed
| 568 | ZL-451-01-1-001 | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-001 (04) / NO. 1 ENGINE THRUST REVERSER COWLING (28325878) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.022917 | 19.Jul.2026 16:20 | 1900-01-01 14:44 |  | 0.3125 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 4 |  | 3 / 3 | [] |  |  | MET.28325878 | 40000929 | 2026-07-23 | Performed
| 569 | ZL-451-01-1-002 | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING | ZL-451-01-1-002 (04) / NO. 2 ENGINE THRUST REVERSER COWLING (28325791) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.030556 | 19.Jul.2026 16:20 | 1900-01-01 02:35 |  | 0.5 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | JOB-SETUP, INSPECTION, JOB-CLOSEUP |  |  |  | 0 / 7 |  | 3 / 3 | [] |  |  | MET.28325791 | 13003390 | 2026-07-21 | Performed
| 570 | ZL-453-01-1-001 | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-001 (05) / NO.1 ENGINE HOT SECTION ZONAL INSP (32712853) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:09 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | 2 / 4 |  | 1 / 1 | [] |  |  | MET.32712853 | 40000930 | 2026-07-21 | Performed
| 571 | ZL-453-01-1-002 | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 10:12 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-453-01-1-002 (05) / NO.2 ENGINE HOT SECTION ZONAL INSP (32712760) |  | 1 / 1 | [] |  |  | MET.32712760 | 40000930 | 2026-07-21 | Performed
| 572 | ZL-471-01-4-001 | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:24 | 0.025 |  | 0.034722 | Closed | 0 | T: 12; O: 0; C: 12 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-001 (04) / NO.1 ENG PYLON L/E AND LOWER FAIRING (32712742) |  | 1 / 1 | [] |  |  | MET.32712742 | 13008286 | 2026-07-21 | Performed
| 573 | ZL-471-01-4-002 | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.027083 | 20.Jul.2026 19:00 | 0.040972 |  | 0.048611 | Closed | 0 | T: 10; O: 0; C: 10 | 05-24 |  | [] | INSPECTION |  |  |  | ZL-471-01-4-002 (04) / NO.2 ENG PYLON L/E AND LOWER FAIRING (32712778) |  | 1 / 1 | [] |  |  | MET.32712778 | 13008286 | 2026-07-21 | Performed
| 574 | ZL-500-02-1-001 | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-001 (05) / L/H WING LOWER SURFACE ZONAL INSP (32712761) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:22 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 10 |  | 1 / 1 | [] |  |  | MET.32712761 | 13008286 | 2026-07-20 | Performed
| 575 | ZL-500-02-1-002 | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP | ZL-500-02-1-002 (05) / R/H WING LOWER SURFACE ZONAL INSP (32712690) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 19.Jul.2026 09:20 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] | INSPECTION |  |  |  | 2 / 6 |  | 1 / 1 | [] |  |  | MET.32712690 | 13008286 | 2026-07-20 | Performed
| 576 | ZL-575-01-1-001 | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-001 (04) / L/H OUTB FIXED TRAILING EDGE INSP (32712777) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 20.Jul.2026 07:31 | 1900-01-01 01:55 |  | 0.052083 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712777 | 13003390 | 2026-07-22 | Performed
| 577 | ZL-575-01-1-002 | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP | ZL-575-01-1-002 (04) / R/H OUTB FIXED TRAILING EDGE INSP (32712872) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.058333 | 17.Jul.2026 22:00 | 0.058333 | 22.Jul.2026 17:23 | 0.097917 |  | 0.0625 | Closed | 0 | T: 4; O: 0; C: 4 | 05-25 |  | [] | INSPECTION |  |  |  | 0 / 5 |  | 1 / 1 | [] |  |  | MET.32712872 | 13008286 | 2026-07-23 | Performed
| 578 | ZL-734-01-1 | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION | ZL-734-01-1 (3) / MLG MAIN DOOR ZONAL INSPECTION (32712687) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 18.Jul.2026 22:32 | 0.020833 |  | 0.020833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] | PRE INSP, PRE INSP |  |  |  | 1 / 2 |  | 2 / 2 | [] |  |  | MET.32712687 | 13008286 | 2026-07-20 | Performed
| 579 | ZL-825-01-1 | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP | ZL-825-01-1 (04) / FORWARD CARGO COMP. DOOR ZONAL INSP (32712925) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 01:46 | 0.010417 |  | 0.010417 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 2 / 8 |  | 1 / 1 | [] |  |  | MET.32712925 | 13008286 | 2026-07-20 | Performed
| 580 | ZL-826-01-1 | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP | ZL-826-01-1 (04) / AFT CARGO COMP. DOOR ZONAL INSP (32712945) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 02:21 | 0.027083 |  | 0.027083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 3 |  | 1 / 1 | [] |  |  | MET.32712945 | 13008286 | 2026-07-20 | Performed
| 581 | ZL-827-01-1 | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP | ZL-827-01-1 (06) / BULK CARGO COMP. DOOR ZONAL INSP (32712796) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.018056 | 17.Jul.2026 22:00 | 0.018056 | 19.Jul.2026 02:15 | 0.0034722 |  | 0.0034722 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP |  |  |  | 1 / 1 |  | 1 / 1 | [] |  |  | MET.32712796 | 13008286 | 2026-07-20 | Performed
| 601 | ZL-191-01-2 | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP | ZL-191-01-2 (9) / AIR CONDITION COMPARTMENT ZONAL INSP (32807084) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.036111 | 17.Jul.2026 22:00 | 0.036111 | 20.Jul.2026 06:02 | 0.041667 |  | 0.041667 | Closed | 0 | T: 4; O: 0; C: 4 | 05-21 |  | [] | PRE INSP |  |  |  | 0 / 1 |  | 1 / 1 | [] |  |  | MET.32807084 | 13003390 | 2026-07-20 | Performed
| 602 | ZL-831-01-1 | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR | ZL-831-01-1 (05) / AFT PASSENGER/CREW DOOR (32807085) | Block Taskcard | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0090278 | 17.Jul.2026 22:00 | 0.0090278 | 19.Jul.2026 11:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] | PRE INSP, PRE INSP |  |  |  | 0 / 1 |  | 2 / 2 | [] |  |  | MET.32807085 | 13008286 | 2026-07-20 | Performed
| 622 | 532170-01-1 | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.027083 | 17.Jul.2026 22:00 | 0.023611 | 21.Jul.2026 13:16 | 0.11458 |  | 0.5625 | Closed | 0 | T: 1; O: 0; C: 1 | 53-21 |  | [] | PRE INSP, PRE INSP, PRE INSP |  |  |  | 532170-01-1 (5) / FWD CARGO DOOR LOCK FITTINGS INSP (32712995) |  | 3 / 3 | [] |  |  | MET.32712995 | 13003390 | 2026-07-21 | Performed
| 637 | 545107-01-1-001 | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.050694 | 17.Jul.2026 22:00 | 0.047917 | 21.Jul.2026 15:00 | 1899-12-31 16:19 |  | 0.29167 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-001 (04) / NO. 1 ENGINE AFT ATTACH BEAM INSP (32713050) |  | 4 / 4 | [] |  |  | MET.32713050 | 13008286 | 2026-07-23 | Performed
| 638 | 545107-01-1-002 | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.038889 | 17.Jul.2026 22:00 | 0.036111 | 21.Jul.2026 14:53 | 0.98194 |  | 0.15972 | Closed | 0 | T: 4; O: 0; C: 4 | 54-51 |  | [] | JOB-SETUP, CLEAN-UP, INSPECTION, JOB-CLOSEUP |  |  |  | 545107-01-1-002 (04) / NO. 2 ENGINE AFT ATTACH BEAM INSP (32713048) |  | 4 / 4 | [] |  |  | MET.32713048 | 13008286 | 2026-07-23 | Performed
| 705 | 31905379 | TPIS DEACTIVATION (0) / TPIS DEACTIVATION | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) | Single Running Taskcard | RI | <html><span style="font-weight: normal;">No part requests</span></html> | 0.020833 | 17.Jul.2026 22:00 | 0.020833 | 20.Jul.2026 17:31 | 1900-01-02 00:35 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 32 |  | [] |  |  |  |  | 31905379 / TPIS DEACTIVATION (0) / TPIS DEACTIVATION (31905379) |  | 2 / 2 | [] |  |  | MET.31905379 | 13003390 | 2026-07-23 | Performed
| 706 | 29294847 | 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS | 29294847 / 252582/AD-A320/A321, INSPECTION OF ALL LAVATORY WASTE RECEPTACLE DOORS (29294847) | Document | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.041667 | 22.Jul.2026 04:55 | 0.14931 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 0 / 5 |  | 0 / 1 | [] |  |  | ME.29294847 | 13003390 | 2026-07-22 | Performed
| 782 | STJC-20-00-00-01-GA-GO | HEAVY CHK AIRCRAFT (PRE-INSP) | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) | Jobcard | N | <html><span style="font-weight: normal;">No part requests</span></html> | 0.375 | 17.Jul.2026 22:00 | 0.375 | 18.Jul.2026 13:46 | 0.51806 |  | 0.071528 | Closed | 0 | T: 0; O: 0; C: 0 | 20 |  | [] | PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP, PRE INSP |  |  |  | STJC-20-00-00-01-GA-GO / HEAVY CHK AIRCRAFT (PRE-INSP) (32924592) |  | 9 / 9 | [] |  |  | JCA.32924592 | 13008286 | 2026-07-20 | Performed
| 802 | 242400-01-2 | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) | Single Running Taskcard | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0013889 | 17.Jul.2026 22:00 | 0.00069444 | 19.Jul.2026 06:36 | 0.11944 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 24-24 |  | [] | OPS/LK |  |  |  | 242400-01-2 (2) / AC EMERGENCY GENERATION OPC (32608234) |  | 1 / 1 | [] |  |  | MET.32608234 | 13008286 | 2026-07-22 | Performed
| 820 | 32977881 | PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 23.Jul.2026 15:58 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32977881 / PRE---UPPER FUSELAGE---NOCALLBACK---PNT PASSENGER ENTRY DOORS EXTERNAL SURFACE HOIST POINT COVERS FOUND TORN AND PEELED OFF. (32977881) |  | 0 / 1 | [] |  |  | WO.32977881 | 13003390 | 2026-07-23 | Performed
| 824 | 32977904 | PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 12:12 | 0.16667 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32977904 / PRE---L/H AND R/H WING---NOCALLBACK---PNT L/H AND R/H WING ALL SLATS EXTERNAL SURFACE HOIST POINT COVERS FOUND MISSING, TORN AND WORNOUT. (32977904) |  | 0 / 1 | [] |  |  | WO.32977904 | 13003390 | 2026-07-21 | Performed
| 833 | 32978236 | NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 04:38 | 0.16667 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978236 / NLG DOOR---PNT---NO CALL BACK---- NLG LH AND RH AFT DOOR MOUNT HINGES WITH PNT CHIP-OFF. (32978236) |  | 0 / 1 | [] |  |  | WO.32978236 | 13003390 | 2026-07-22 | Performed
| 838 | 32978249 | NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 05:29 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32978249 / NLG----PNT---NO CALL BACK---- NLG HCU SURFACE WITH PNT CHIP-OFF. (32978249) |  | 0 / 1 | [] |  |  | WO.32978249 | 13003390 | 2026-07-22 | Performed
| 843 | 32978273 | MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 17:15 | 0.20903 |  | 0.41667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-27 |  | [] |  |  |  |  | 32978273 / MLG----FS---NO CALL BACK----- INSIDE MLG DOOR ON KELL BEAM AREA DIRTY AND FULL OF WATER. (32978273) |  | 0 / 1 | [] |  |  | WO.32978273 | 13008286 | 2026-07-22 | Performed
| 848 | 32978291 | RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:59 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32978291 / RH MLG DOOR---PNT---NO CALL BACK--- RH MLG DOOR ACTUATOR SURFACE WITH PNT CHIP-OFF. (32978291) |  | 0 / 1 | [] |  |  | WO.32978291 | 13008286 | 2026-07-21 | Performed
| 860 | 32978583 | FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 21:01 | 0.14653 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978583 / FWD CARGO DOOR----FS---NO CALL BACK--- FWD CARGO DOOR LINING DIRTY. (32978583) |  | 0 / 1 | [] |  |  | WO.32978583 | 13008286 | 2026-07-22 | Performed
| 862 | 32978590 | FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 21.Jul.2026 20:28 | 0.084722 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978590 / FWD CARGO DOOR---FS---NO CALL BACK---- FWD CARGO DOOR ALL LWR ATTACHEMENT ROLLER DIRTY. (32978590) |  | 0 / 1 | [] |  |  | WO.32978590 | 13008286 | 2026-07-22 | Performed
| 870 | 32978648 | BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 16:18 | 0.25 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978648 / BULK CARGO DOOR---FS---NO CALL BACK--- BULK CARGO DOOR AREA AND LINING DIRTY. (32978648) |  | 0 / 1 | [] |  |  | WO.32978648 | 13008286 | 2026-07-22 | Performed
| 871 | 32978649 | AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.27083 | 17.Jul.2026 22:00 | 0.27083 | 21.Jul.2026 15:51 | 0.27083 |  | 0.27083 | Closed | 0 | T: 0; O: 0; C: 0 | 05-28 |  | [] |  |  |  |  | 32978649 / AFT CARGO DOOR---FS---NO CALL BACK--- AFT CARGO DOOR ALL ATTACHMENT FITTING ROLLER DIRTY. (32978649) |  | 0 / 1 | [] |  |  | WO.32978649 | 13008286 | 2026-07-22 | Performed
| 874 | 32978848 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.5 | 17.Jul.2026 22:00 | 0.25 | 21.Jul.2026 10:40 | 0.25 |  | 0.5 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978848 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT STRUCTURE DIRTY (32978848) |  | 0 / 1 | [] |  |  | WO.32978848 | 40000010 | 2026-07-21 | Performed
| 875 | 32978869 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1900-01-04 | 17.Jul.2026 22:00 | 0.27778 | 19.Jul.2026 03:10 | 1900-01-01 05:17 |  | 1900-01-04 00:30 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978869 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE ALL B/C SEAT ARMCAP AISLE AND CTR DIRTY (32978869) |  | 0 / 1 | [] |  |  | WO.32978869 | 40000010 | 2026-07-21 | Performed
| 878 | 32978919 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:00 | 0.20833 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978919 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEATS OVERRIDE - MANUAL CABLE DAMAGED. RECLINE CABLE AT SEAT # 4L LEGREST CABLE AT SEATS# 2J,3L,5A,J (32978919) |  | 0 / 1 | [] |  |  | WO.32978919 | 40000930 | 2026-07-21 | Performed
| 879 | 32978925 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 15:11 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978925 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 2A , 4A ARMREST LOOSE (32978925) |  | 0 / 1 | [] |  |  | WO.32978925 | 40000010 | 2026-07-21 | Performed
| 880 | 32978965 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 02:38 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32978965 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1J,2J,3J RUBSTRIP - SHELL DAMAGED (32978965) |  | 0 / 1 | [] |  |  | WO.32978965 | 40000930 | 2026-07-21 | Performed
| 882 | 32979157 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 22.Jul.2026 14:02 | 0.12639 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979157 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1AC , 5AC SHROUD - CONSOLE, FRONT LOWER DAMAGED (32979157) |  | 0 / 1 | [] |  |  | WO.32979157 | 13003390 | 2026-07-22 | Performed
| 883 | 32979156 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 21.Jul.2026 06:23 | 0.17083 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979156 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT--NO CALLBACK RH WING AROUND LANDING LIGHT BLACK PAINT MISSING. (32979156) |  | 0 / 1 | [] |  |  | WO.32979156 | 13008286 | 2026-07-21 | Performed
| 884 | 32979222 | FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 06:43 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32979222 / FINDING (NRC) TASKCARD ZL-500-02-1-002 (05) RH WING PNT-- NO CALLBACK RH WING LWR SURFACE IN/B UPPER MLG FIX DOOR WITH PAINT CRACKS (32979222) |  | 0 / 1 | [] |  |  | WO.32979222 | 13008286 | 2026-07-21 | Performed
| 885 | 32979231 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 04:06 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32979231 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1C , 3J RUBSTRIP - FRONT DAMAGED (32979231) |  | 0 / 1 | [] |  |  | WO.32979231 | 40000930 | 2026-07-21 | Performed
| 896 | 32979723 | APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.083333 | 19.Jul.2026 03:35 | 0.33333 |  | 0.54167 | Closed | 0 | T: 0; O: 0; C: 0 | 36-12 |  | [] |  |  |  |  | 32979723 / APU BLEED DUCT CONNECTION--AP--CALLBACK LEAK FOUND ON MISALIGNED FWD CLAMP OF VALVE ASSY-PRESSURE REGULATION (32979723) |  | 0 / 1 | [] |  |  | WO.32979723 | 40000010 | 2026-07-19 | Performed
| 898 | 32980018 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 1899-12-31 | 17.Jul.2026 22:00 | 0.25 | 20.Jul.2026 03:26 | 0.33333 |  | 1899-12-31 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980018 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE ALL G/C SEAT STRUCTURE DIRTY (32980018) |  | 0 / 1 | [] |  |  | WO.32980018 | 40000010 | 2026-07-21 | Performed
| 925 | 32930830 | S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) | Document | RON | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.0625 | 19.Jul.2026 12:05 | 0.18403 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 38 |  | [] |  |  |  |  | 32930830 / S38-D10019/A320/21 - VERIFICATION OF WATER-HEATER; LAVATORY (32930830) |  | 0 / 1 | [] |  |  | ME.32930830 | 13003390 | 2026-07-19 | Performed
| 927 | 32980031 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.041667 | 17.Jul.2026 22:00 | 0.041667 | 21.Jul.2026 05:18 | 0.041667 |  | 0.041667 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980031 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS #30C LINER CRACKED (32980031) |  | 0 / 1 | [] |  |  | WO.32980031 | 40000930 | 2026-07-21 | Performed
| 940 | 32980087 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.14583 | 17.Jul.2026 22:00 | 0.14583 | 21.Jul.2026 15:12 | 0.0625 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980087 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEATS# 33J, 34C,J ,37C, 38C, 40C, 41J AISLE BUMBER DAMAGE (32980087) |  | 0 / 1 | [] |  |  | WO.32980087 | 40000010 | 2026-07-21 | Performed
| 946 | 32980135 | FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:11 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32980135 / FINDING (NRC) TASKCARD 25-SVA-05 (01) / ITEM ONE G/C SEAT#30L ARM MONITOR LOOSE (32980135) |  | 0 / 1 | [] |  |  | WO.32980135 | 13003390 | 2026-07-22 | Performed
| 952 | 32980177 | FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:37 | 0.083333 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32980177 / FINDING (NRC) TASKCARD ZL-500-02-1-001 (05) LH WING PNT--NO CALLBACK LH WING IN/B FLAP AFT MID WITH PAINT PEELED OFF. (32980177) |  | 0 / 1 | [] |  |  | WO.32980177 | 13008286 | 2026-07-21 | Performed
| 958 | 32981716 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:14 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981716 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#2L, 4L, COVER - ARM SHROUD MISSING. (32981716) |  | 0 / 1 | [] |  |  | WO.32981716 | 13003390 | 2026-07-22 | Performed
| 959 | 32981721 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.25 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 11:18 | 0.25069 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981721 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#1L, 2A,C, 3L, 4L, 5A, SEAT CLOSEOUT ASSEMBLY DAMAGED. (32981721) |  | 0 / 1 | [] |  |  | WO.32981721 | 13003390 | 2026-07-22 | Performed
| 961 | 32981754 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.20833 | 17.Jul.2026 22:00 | 0.20833 | 21.Jul.2026 03:25 | 0.125 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981754 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 1L, 3L, 4A, 5A,C LIFE VEST DOOR, DUAL PAWL ASSEMBLY - NON LOCKABLE DAMAGED. (32981754) |  | 0 / 1 | [] |  |  | WO.32981754 | 40000930 | 2026-07-21 | Performed
| 963 | 32981774 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:28 | 0.084028 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32981774 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT#3JL COCKTAIL TABLE ASSEMBLY WITH SCRATCH. (32981774) |  | 0 / 1 | [] |  |  | WO.32981774 | 13003390 | 2026-07-22 | Performed
| 965 | 32982133 | CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING | 32982133 / CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING (32982133) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 13:01 | 0.1 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 35-12 |  | [] |  |  |  |  | 32982133 / CAB RII - OXYGEN MASK F/O OXYGEN MASK VALVE DISK MISSING (32982133) |  | 0 / 1 | [] |  |  | WO.32982133 | 40000010 | 2026-07-20 | Performed
| 967 | 32982191 | S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 12:20 | 0.090278 |  | 0.25 | Closed | 0 | T: 0; O: 0; C: 0 | 25-30 |  | [] |  |  |  |  | 32982191 / S/M L2 STOWAGE LOWER DIVIDER PACKER WITH 4 EACH FROZEN SCREWS (32982191) |  | 0 / 1 | [] |  |  | WO.32982191 | 13003390 | 2026-07-20 | Performed
| 975 | 32982253 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:34 | 0.78889 |  | 1900-01-01 18:30 | Closed | 0 | T: 6; O: 0; C: 6 | 27-84 |  | [] |  |  |  |  | 32982253 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL LEFT HAND WING PANELS -(522KB, 522QB AND 522UB) -(575LB AND 575KB) -(522AT UPPER SURFACE) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982253) |  | 0 / 1 | [] |  |  | WO.32982253 | 13003390 | 2026-07-20 | Performed
| 976 | 32982260 | R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 19.Jul.2026 15:40 | 0.8125 |  | 1900-01-01 20:00 | Closed | 0 | T: 4; O: 0; C: 4 | 27-84 |  | [] |  |  |  |  | 32982260 / R/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALL RIGHT HAND WING PANELS -(621AB) -(622CB, 622HB AND 622JB) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982260) |  | 0 / 1 | [] |  |  | WO.32982260 | 13003390 | 2026-07-20 | Performed
| 977 | 32982263 | BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 03:00 | 0.38889 |  | 0.66319 | Closed | 0 | T: 2; O: 0; C: 2 | 53-41 |  | [] |  |  |  |  | 32982263 / BELLY FAIRING PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS -(192AB 1EA SCREW) -(192LB 1 EA SCREW) -( FWD PANEL STRIP 1 EA SCREW) HAVE MULTIPLE FROZEN SCREWS (MARKED WITH TAPE) REQ S/M ACTION (32982263) |  | 0 / 1 | [] |  |  | WO.32982263 | 13003390 | 2026-07-20 | Performed
| 980 | 32983866 | PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 18:11 | 0.16736 |  | 0.33333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983866 / PRE--MLG W/W---NOCALLBACK---FS MLG WHEELWELL KEEL BEAM AREA FOUND EXCESSIVE DIRTY WITH ACCUMULATED WATER. (32983866) |  | 0 / 1 | [] |  |  | WO.32983866 | 13008286 | 2026-07-22 | Performed
| 982 | 32983882 | PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:11 | 0.10417 |  | 0.22917 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983882 / PRE--MLG W/W---NOCALLBACK---PNT L/H AND R/H WHEEL WELL MULTIPLE RIVET HEADS FOUND WITH MISSING PAINT APPLICATION. (32983882) |  | 0 / 1 | [] |  |  | WO.32983882 | 13003390 | 2026-07-23 | Performed
| 983 | 32983893 | PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.125 | 17.Jul.2026 22:00 | 0.125 | 23.Jul.2026 13:45 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983893 / PRE---HYD COMPT---NOCALLBACK---PNT R/H HYD COMPT PANEL 196 BB OUTER AND INNER AREA DECALS FOUND MISSIN, TORN AND WORNOUT. (32983893) |  | 0 / 1 | [] |  |  | WO.32983893 | 13003390 | 2026-07-23 | Performed
| 990 | 32983950 | PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32983950 / PRE---HYD COMPT---NOCALLBACK---PNT LOWER FUSELAGE ACCESS THROUGH L/H AND R/H HYD COMPT PANELS 195 BB AND 196 BB INNER AREA EDGE AND CORNER FITTING FOUND WITH MISSING PAINT APPLICATION. (32983950) |  | 0 / 1 | [] |  |  | WO.32983950 | 13003390 | 2026-07-23 | Performed
| 998 | 32984375 | FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 21.Jul.2026 06:32 | 0.083333 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984375 / FLAP TRACK AND FAIRINGS---PNT---NO CALLBACK CHIPPED PAINT ON 533 AB, 532 AB PANEL (32984375) |  | 0 / 1 | [] |  |  | WO.32984375 | 13008286 | 2026-07-21 | Performed
| 1000 | 32984479 | INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:46 | 0.60208 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984479 / INBOARD/OUTBOARD FIXED TRAILING EDGE STR---FS---CALLBACK REQ CLEANING OF INBOARD/OUTBOARD FIXED TRAILING EDGE STRUCTURE TO FACILITATE INSPECTION (32984479) |  | 0 / 1 | [] |  |  | WO.32984479 | 13009981 | 2026-07-23 | Performed
| 1002 | 32984550 | R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.75 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 18:43 | 0.60347 |  | 0.79167 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984550 / R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE---FS---CALLBACK REQ CLEANING OF R/H INBOARD/OUTBOARD FIXED T/E STRUCTURE TO FACILITATE INSPECTION (32984550) |  | 0 / 1 | [] |  |  | WO.32984550 | 13009981 | 2026-07-23 | Performed
| 1009 | 32984823 | PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 11:06 | 0.1875 |  | 0.1875 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984823 / PNT - NO CALLBACK - LAV A LAV A WASHBASIN PANEL PAINT SCRATCHED. (32984823) |  | 0 / 1 | [] |  |  | WO.32984823 | 13003390 | 2026-07-23 | Performed
| 1015 | 32984905 | PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 15:49 | 0.041667 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32984905 / PNT - NO CALLBACK - LAV A LAV A DECAL "PLEASE LOCK THE DOOR" AND FINE DECAL DISCOLORED. (32984905) |  | 0 / 1 | [] |  |  | WO.32984905 | 13003390 | 2026-07-21 | Performed
| 1016 | 32984942 | FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 18:00 | 0.27847 |  | 0.44444 | Closed | 0 | T: 0; O: 0; C: 0 | 05-25 |  | [] |  |  |  |  | 32984942 / FLAP TRACK NO. 3 AND FAIRING---FS---NO CALLBACK DURING INSP, FOUND FLAP TRACK NO. 3 FAIRINGS UPPER SURFACE DIRTY (32984942) |  | 0 / 1 | [] |  |  | WO.32984942 | 13008286 | 2026-07-23 | Performed
| 1026 | 32985022 | --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.16667 | 17.Jul.2026 22:00 | 0.16667 | 20.Jul.2026 11:00 | 0.0625 |  | 0.125 | Closed | 0 | T: 1; O: 0; C: 1 | 53-79 |  | [] |  |  |  |  | 32985022 / --SM--NO CALL BACK FROZEN SCREWS REQUIRE REMOVAL FOUND ON PANELS, 192LB,191JB,191GB AND 192AB (32985022) |  | 0 / 1 | [] |  |  | WO.32985022 | 13003390 | 2026-07-20 | Performed
| 1032 | 32985081 | PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 21.Jul.2026 06:58 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985081 / PRE---TAIL SECTION---NOCALLBACK---PNT AFT FUSELAGE TAIL SECTION, TAIL CONE HOIST POINT COVERS FOUND MISSING AND WORNOUT. (32985081) |  | 0 / 1 | [] |  |  | WO.32985081 | 13008286 | 2026-07-21 | Performed
| 1033 | 32985124 | PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.16667 | 23.Jul.2026 15:15 | 0.076389 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 05-24 |  | [] |  |  |  |  | 32985124 / PRE---TAIL SECTION---RII---AP APU FIRE BOTTLE DISCHARGE DISK FOUND FADED AND WORNOUT. (32985124) |  | 0 / 1 | [] |  |  | WO.32985124 | 13003390 | 2026-07-23 | Performed
| 1042 | 32985338 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:56 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985338 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT BOTH SIDES PAINT FADED (32985338) |  | 0 / 1 | [] |  |  | WO.32985338 | 13003390 | 2026-07-22 | Performed
| 1043 | 32985341 | PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:05 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985341 / PNT - NO CALLBACK R2 DOOR F/A SWIVEL SEAT HEAD CASE PAINT FADED (32985341) |  | 0 / 1 | [] |  |  | WO.32985341 | 13003390 | 2026-07-22 | Performed
| 1047 | 32985347 | PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:04 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985347 / PNT - NO CALLBACK L1 DOOR OUTBOARD F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985347) |  | 0 / 1 | [] |  |  | WO.32985347 | 13003390 | 2026-07-22 | Performed
| 1050 | 32985351 | PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 13:47 | 0.14583 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985351 / PNT - NO CALLBACK L2 DOOR F/A SEAT LEFT SIDE PAINT FADED (32985351) |  | 0 / 1 | [] |  |  | WO.32985351 | 13003390 | 2026-07-22 | Performed
| 1051 | 32985352 | PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:40 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985352 / PNT - NO CALLBACK L2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985352) |  | 0 / 1 | [] |  |  | WO.32985352 | 13003390 | 2026-07-22 | Performed
| 1054 | 32985355 | PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 14:21 | 0.125 |  | 0.125 | Closed | 0 | T: 0; O: 0; C: 0 | 25 |  | [] |  |  |  |  | 32985355 / PNT - NO CALLBACK R2 DOOR F/A SEAT LOWER BOTTOM CASE PAINT FADED (32985355) |  | 0 / 1 | [] |  |  | WO.32985355 | 13003390 | 2026-07-22 | Performed
| 1057 | 32985575 | RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 11:00 | 0.3125 |  | 0.79514 | Closed | 0 | T: 1; O: 0; C: 1 | 05-23 |  | [] |  |  |  |  | 32985575 / RH HORIZONTAL STABILIZER--SM-- RH HORIZONTAL STABILIZER PNL 344GB WITH 1 EA WORN HEAD SCREW (32985575) |  | 0 / 1 | [] |  |  | WO.32985575 | 13003390 | 2026-07-20 | Performed
| 1058 | 32985619 | ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 15:20 | 0.055556 |  | 0.10764 | Closed | 0 | T: 2; O: 0; C: 2 | 26-21 |  | [] | OPEN-UP |  |  |  | 32985619 / ENG.1 AND ENG.2 PYLON PANELS FROZEN SCREWS ----SM-----NO CALLBACK ENG.1 AND ENG.2 PYLON PANELS FROZEN (413DT AND 423DT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985619) |  | 0 / 1 | [] |  |  | WO.32985619 | 13003390 | 2026-07-20 | Performed
| 1059 | 32985582 | L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 14:20 | 0.090278 |  | 0.16667 | Closed | 0 | T: 3; O: 0; C: 3 | 57-41 |  | [] | OPEN-UP |  |  |  | 32985582 / L/H WING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK LEFT HAND WING PANELS (522CB, 522NB AND 522AB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985582) |  | 0 / 1 | [] |  |  | WO.32985582 | 13003390 | 2026-07-20 | Performed
| 1060 | 32985655 | BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 16:35 | 0.0069444 |  | 0.0069444 | Closed | 0 | T: 2; O: 0; C: 2 | 24-92 |  | [] |  |  |  |  | 32985655 / BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK BELLY FAIRING PANELS (192LB AND 192MB) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985655) |  | 0 / 1 | [] |  |  | WO.32985655 | 13003390 | 2026-07-20 | Performed
| 1065 | 32985861 | THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.41667 | 17.Jul.2026 22:00 | 0.20833 | 22.Jul.2026 03:13 | 1899-12-31 06:00 |  | 0.58333 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985861 / THS COMPT======FS====CALL BACK FINAL REF TO TASK CARD ZL-313-01-1 THS COMPT ACCESS THR PNL 314AR FLOOR AREA AROUND APU INTAKE DIRTY REQ CLEANING TO FASCILITATE THE INSP (32985861) |  | 0 / 1 | [] |  |  | WO.32985861 | 13009981 | 2026-07-23 | Performed
| 1066 | 32985871 | APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.33333 | 17.Jul.2026 22:00 | 0.33333 | 22.Jul.2026 20:37 | 0.52431 |  | 0.375 | Closed | 0 | T: 0; O: 0; C: 0 | 05-23 |  | [] |  |  |  |  | 32985871 / APU EXHAUST AREA======FS=====CALL BACK REF TO TASK CARD ZL-317-01-1 TAIL CONE APU EXHAUST AREA ACCES THRU 317AL LWR SIDE DIRTY REQUIRE CLEANING TO FASCILITATE THE INSP (32985871) |  | 0 / 1 | [] |  |  | WO.32985871 | 13009981 | 2026-07-23 | Performed
| 1071 | 32985880 | R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 20.Jul.2026 19:30 | 0.68056 |  | 1899-12-31 04:50 | Closed | 0 | T: 1; O: 0; C: 1 | 53-41 |  | [] | OPEN-UP |  |  |  | 32985880 / R/H BELLY FAIRING MULTABLE PANELS FROZEN SCREWS ----SM-----NO CALLBACK R/H BELLY FAIRING PANEL (192BT) HAVE MULTIPLE FROZEN AND ROUNDED SCREWS (MARKED WITH GREEN TAPE) REQ S/M ACTION (32985880) |  | 0 / 1 | [] |  |  | WO.32985880 | 40000930 | 2026-07-22 | Performed
| 1080 | 32987301 | DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 07:06 | 0.15486 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987301 / DBC---F/O FIXED WINDOW---RII---AP R/H SIDE F/O FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 1 INCH FROM INNER EDGE. (32987301) |  | 0 / 1 | [] |  |  | WO.32987301 | 13003390 | 2026-07-23 | Performed
| 1089 | 32987725 | PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 06:51 | 0.16458 |  | 0.027778 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987725 / PRE---F/O WIND SHIELD---RII---AP R/H SIDE F/O WINDSHIELD FOUND WITH BUBBLES AROUND EDGES AS : UPPER EDGE L= 15 INCH W= 02 INCHES FROM INNER EDGE LOWER EDGE L= 13 INCH W= 0.5 INCHES FROM INNER EDGE L/H SIDE EDGE L= 11 INCH W= 1.8 INCHES FROM INN... (32987725) |  | 0 / 1 | [] |  |  | WO.32987725 | 13003390 | 2026-07-23 | Performed
| 1090 | 32987776 | --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 21.Jul.2026 03:00 | 0.97917 |  | 1899-12-31 05:00 | Closed | 0 | T: 1; O: 0; C: 1 | 11-21 |  | [] |  |  |  |  | 32987776 / --SM--NO CALLBACK PANEL (191AT) HAS FROZEN SCREWS REQUIRE REMOVAL. (32987776) |  | 0 / 1 | [] |  |  | WO.32987776 | 40000930 | 2026-07-22 | Performed
| 1093 | 32987952 | CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:56 | 0.23333 |  | 0.14583 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987952 / CAB---RII---CKCPT DR COCKPIT DOOR LATCH TENONS NEED ADJUSTMENT (32987952) |  | 0 / 1 | [] |  |  | WO.32987952 | 13008286 | 2026-07-23 | Performed
| 1097 | 32987964 | DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0.66667 | 17.Jul.2026 22:00 | 0.33333 | 23.Jul.2026 08:32 | 0.094444 |  | 0.048611 | Closed | 0 | T: 0; O: 0; C: 0 | 56-10 |  | [] |  |  |  |  | 32987964 / DBC---CAPT FIXED WINDOW---RII---AP L/H SIDE CAPT FIXED WINDOW AFT LOWER CORNER FOUND WITH MULTIPLE BUBBLES. L= 03 INCH W= 2 INCH FROM INNER EDGE. (32987964) |  | 0 / 1 | [] |  |  | WO.32987964 | 13003390 | 2026-07-23 | Performed
| 1098 | 32987966 | CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:29 | 0.25 |  | 0.16667 | Closed | 0 | T: 0; O: 0; C: 0 | 52-51 |  | [] |  |  |  |  | 32987966 / CAB---RII---CKCPT DR COCKPIT DOOR CLEARANCES A, C & P OUT OF LIMIT (32987966) |  | 0 / 1 | [] |  |  | WO.32987966 | 13008286 | 2026-07-23 | Performed
| 1119 | 32989018 | PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:24 | 0.27153 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 05-21 |  | [] |  |  |  |  | 32989018 / PRE---AFT LOWER FUSELAGE---NOCALLBACK---FS AFT LOWER FUSELAGE REAR FAIRING ATTACHMENTS FOUND DIRTY. (32989018) |  | 0 / 1 | [] |  |  | WO.32989018 | 13008286 | 2026-07-23 | Performed
| 1125 | 32989174 | BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.8125 | 17.Jul.2026 22:00 | 0.27083 | 22.Jul.2026 11:16 | 0.27083 |  | 0.8125 | Closed | 0 | T: 0; O: 0; C: 0 | 57-56 |  | [] |  |  |  |  | 32989174 / BOTH WINGS.....FS....NO CALLBACK L/H AND R/H WINGS ALL MOVABLE FAIRING DIRTY (32989174) |  | 0 / 1 | [] |  |  | WO.32989174 | 13008286 | 2026-07-23 | Performed
| 1152 | 32989938 | PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 14:41 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-10 |  | [] |  |  |  |  | 32989938 / PAINT-NO CALLBACK (LAV E) LAV E ASHTRAY DECAL IN DOOR AND OUTDOOR DISCOLORATION. (32989938) |  | 0 / 1 | [] |  |  | WO.32989938 | 13003390 | 2026-07-23 | Performed
| 1159 | 32989953 | FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 1899-12-31 06:00 | 17.Jul.2026 22:00 | 0.25 | 22.Jul.2026 02:56 | 0.27222 |  | 1899-12-31 05:00 | Closed | 0 | T: 0; O: 0; C: 0 | 11-35 |  | [] |  |  |  |  | 32989953 / FWD CARGO UNDER FLOOR ----FS--- NO CALL BACK----- REQ CLEANING OF THE UNDER FLOOR BAY IN THE FORWARD CARGO COMPARTMENT FRAME 24 TO FRAME 34 FOR INSPECTION (32989953) |  | 0 / 1 | [] |  | UNDER FLOOR | WO.32989953 | 13003390 | 2026-07-22 | Performed
| 1173 | 32990006 | CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.0625 | 17.Jul.2026 22:00 | 0.0625 | 22.Jul.2026 16:10 | 0.070139 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990006 / CAB PAX SEAT---SEAT SHOP-- NO CALL BACK SEAT NO 30 J,K,L BAGAGE ROD NUT MISSSING. (32990006) |  | 0 / 1 | [] |  |  | WO.32990006 | 13003390 | 2026-07-22 | Performed
| 1180 | 32990021 | CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 16:10 | 0.072917 |  | 0.0625 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990021 / CAB PAX SEAT--- SEAT SHOP-- NO CALL BACK PAX SEAT 43 J,K ACTUATOR NUT MISSING. (32990021) |  | 0 / 1 | [] |  |  | WO.32990021 | 13003390 | 2026-07-22 | Performed
| 1181 | 32990026 | CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 06:53 | 1899-12-31 06:50 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990026 / CAB--PAX SEAT--- RII CAB PAX SEAT 43C FWD BEAM WITH CRACK. (32990026) |  | 0 / 1 | [] |  |  | WO.32990026 | 13003390 | 2026-07-23 | Performed
| 1182 | 32990029 | CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 08:00 | 1899-12-31 05:44 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990029 / CAB--PAX SEAT--- RII CAB PAX SEAT 40C FWD BEAM WITH CRACK. (32990029) |  | 0 / 1 | [] |  |  | WO.32990029 | 13003390 | 2026-07-23 | Performed
| 1183 | 32990034 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:00 | 1899-12-31 06:42 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990034 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 35C FWD BEAM WITH CRACK. (32990034) |  | 0 / 1 | [] |  |  | WO.32990034 | 13003390 | 2026-07-23 | Performed
| 1184 | 32990037 | CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 22.Jul.2026 07:03 | 1899-12-31 06:41 |  | 0.086806 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32990037 / CAB--PAX SEAT--- RII CAB PAX SEAT NO 33C FWD BEAM WITH CRACK. (32990037) |  | 0 / 1 | [] |  |  | WO.32990037 | 13003390 | 2026-07-23 | Performed
| 1208 | 32991585 | FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) | Finding WO | 1 | <html><span style="font-weight: normal;">All part requests closed.</span></html> | 0.083333 | 17.Jul.2026 22:00 | 0.083333 | 22.Jul.2026 15:33 | 0.083333 |  | 0.083333 | Closed | 0 | T: 0; O: 0; C: 0 | 25-21 |  | [] |  |  |  |  | 32991585 / FINDING (NRC) TASKCARD 25-SVA-03 (01) / ITEM ONE B/C SEAT# 2C CLOSEOUT - VIDEO, AISLE LOOSE. (32991585) |  | 0 / 1 | [] |  |  | WO.32991585 | 13003390 | 2026-07-22 | Performed
| 1249 | 32994166 | FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:32 | 0.12153 |  | 0.29167 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994166 / FINDING (NRC) TASKCARD 712212-01-1-001 (02) / ENG#2 AP---CALL BACK ENG#2 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994166) |  | 0 / 1 | [] |  |  | WO.32994166 | 13003390 | 2026-07-23 | Performed
| 1251 | 32994173 | FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 02:00 | 0.35139 |  | 0.20833 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994173 / FINDING (NRC) TASKCARD 712112-01-1-002 (03) ENG#2 AP-- CALLBACK ENG#2 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994173) |  | 0 / 1 | [] |  |  | WO.32994173 | 13003390 | 2026-07-23 | Performed
| 1252 | 32994187 | FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:42 | 0.1125 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 71-21 |  | [] |  |  |  |  | 32994187 / FINDING (NRC) TASKCARD 712112-01-1-001 (03) ENG#1 AP---CALLBACK ENG#1 FWD MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994187) |  | 0 / 1 | [] |  |  | WO.32994187 | 13003390 | 2026-07-23 | Performed
| 1253 | 32994193 | FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) | Finding WO | 1 | <html><span style="font-weight: normal;">No part requests</span></html> | 0 | 17.Jul.2026 22:00 | 0 | 23.Jul.2026 07:58 | 0.10139 |  | 0.17014 | Closed | 0 | T: 0; O: 0; C: 0 | 71-22 |  | [] |  |  |  |  | 32994193 / FINDING (NRC) TASKCARD 712212-01-1-002 (02) ENG#1 AP--CALLBACK ENG#1 AFT MOUNT LINK LUGS REQ CLEANING TO FACILITATE THE INSPECTION (32994193) |  | 0 / 1 | [] |  |  | WO.32994193 | 13003390 | 2026-07-23 | Performed